## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : ANTICA - SH
Task Name : FINISHING WORK
Page 1 of 1
Total Records: 16 Records 1 to 16
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | GROUTING WORK | 10 | Started | Material | (M)722 MID BLACK FILLER POWDER 3.75KG LATICRETE | PKT | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 615.96 | 1231.92 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
2 | GROUTING WORK | 10 | Started | Material | (M)BRIGHT WHITE_EPOXY BASE_3.75 KG | PKT | 15 | 651.36 | 9770.4 | 15 | 651.36 | 9770.4 | 2 | 651.36 | 1302.72 | 15 | 650 | 9750.0495 | 0 | 0 | 0 | 13 | 15 | 8467.68 | 9770.4
3 | GROUTING WORK | 10 | Started | Material | (M)LATICRETE 325 (20 KG) | BAGS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 874.99 | 1749.98 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
4 | GROUTING WORK | 10 | Started | Material | (M)SP-100 LATAPOXI RESIN KIT | NOS | 20 | 1.18 | 23.6 | 20 | 1.18 | 23.6 | 2 | 1.18 | 2.36 | 20 | 2550 | 51000.08 | 0 | 0 | 0 | 18 | 20 | 21.24 | 23.6
5 | GROUTING WORK | 10 | Started | Labour | (L)LABOR FOR CEMENT BASE GROUT (SQFT) | SQFT | 993 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 993 | 4 | 3972 | 993 | 4 | 3972 | 894 | 0 | 0 | -3972
6 | GROUTING WORK | 10 | Started | Labour | (L)LABOR FOR EPOXY GROUT | SQFT | 450 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 450 | 6 | 2700 | 450 | 6 | 2700 | 405 | 0 | 0 | -2700
7 | FURNITURE WORK |  | Tentative | Material | (M)12MM_W/P PLY | SHEET | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 1 | 0 | 2 | 2190.08 | 4380.16 | 0 | 0 | 0 | 2 | 2 | 2 | 2
8 | FURNITURE WORK |  | Tentative | Material | (M)19MM_W/P PLY | SHEET | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 1 | 0 | 2 | 3209.6 | 6419.2 | 0 | 0 | 0 | 2 | 2 | 2 | 2
9 | FURNITURE WORK |  | Tentative | Material | (M)FEVICOL | KG | 10 | 1 | 10 | 5 | 1 | 5 | 0 | 1 | 0 | 5 | 241.9 | 1209.5 | 0 | 0 | 0 | 10 | 10 | 10 | 10
10 | FURNITURE WORK |  | Tentative | Material | (M)LIXO MASSAGE CHAIR LI17001 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 350000 | 350000 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
11 | FURNITURE WORK |  | Tentative | Material | (M)LOCK | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 354 | 354 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
12 | FURNITURE WORK |  | Tentative | Material | (M)MORTISE LOCK BODY 45X80 | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
13 | FURNITURE WORK |  | Tentative | Material | (M)SS CYLINDER 70 MM | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 850.04 | 850.035 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
14 | FURNITURE WORK |  | Tentative | Material | (M)TUNES MORTISE LOCK BODY GREY | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 850.04 | 850.035 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
15 | FURNITURE WORK |  | Tentative | Material | (M)VENEER | SHEET | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 1 | 0 | 2 | 3964.8 | 7929.6 | 0 | 0 | 0 | 2 | 2 | 2 | 2
16 | FURNITURE WORK |  | Tentative | Labour | (L)LABOR FOR FURNITURE WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 153400 | 153400 | 0 | 0 | 0 | 1 | 1 | 0 | 0