## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GREENWOODS AARANYA
Task Name : TOWER D 101 SH
Page 1 of 1
Total Records: 265 Records 1 to 265
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)150X150 TILES INSERT (39720) | NOS | 8 | 1.18 | 9.44 | 8 | 1.18 | 9.44 | 0 | 1.18 | 0 | 6 | 1162.56 | 6975.3528 | 0 | 0 | 0 | 8 | 8 | 9.44 | 9.44
2 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)2-HOLE SINGLE-LEVER BASIN MIXER WALL MOUNTED -20289001 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 7392.36 | 7392.36 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)2-HOLE SINGLE-LEVER BASIN MIXER WALL MOUNTED -20474001 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 8448 | 8448 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
4 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)24064AL1 LINEARE 2 WAY DIVERTER | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 22872 | 22872 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
5 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)310MM RAIN SHOWER WITH ARM - 26564AL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 49656 | 49655.9952 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
6 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)310MM RAIN SHOWER WITH ARM 26066AL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
7 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)AMROCK KITCHEN SINK - DIAMOND - 24"x18"x8" | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 4248 | 4248 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
8 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)ANGLE STOP - 22037AL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 5620.81 | 5620.8104 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
9 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)ANGLE VALVE - 22008001 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 922.06 | 922.055 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
10 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)ANGLE VALVE - 22009001 | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
11 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)ANGLE VALVE 1/2" X 1/2", COOL SUNRISE GLOSSY-22041GL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 2947.14 | 2947.1425 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
12 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Bath spout with diverter -13425001 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 2270.12 | 4540.23 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
13 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Bath Towel Bar 520 mm 40459000 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
14 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Cistern-38986000 | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 3254.4 | 13017.6 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
15 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Concealed part-23200000 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 10133.31 | 10133.308 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
16 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Concealed Body for 2-Hole Wall-Mount Basin Mixer-32635000 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 7012.8 | 7012.8 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
17 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Concealed part 23571000 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 10132.8 | 10132.8 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
18 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Essence 2-Hole, 1-Handle Wall-Mount Basin Mixer-19967GN1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 25329.6 | 25329.6032 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
19 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Eurocube 2 way diverter-24062AL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 23802.25 | 23802.2504 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
20 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Eurocube basin mixer 23444AL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 25992 | 25991.9984 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
21 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Eurocube bath spout -13303AL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 12239.05 | 12239.0456 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
22 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Flush plate-38732AL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 5040.26 | 5040.26 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
23 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Grohe - Waste Coupling Full Thread -124512 | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 3 | 203.34 | 610.0078 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
24 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Grohtherm SmartControl Thermostat Square, 3Control-29121GN0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 74236.8 | 74236.804 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
25 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Hand shower-2780310E | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 1963.1 | 3926.205 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
26 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Health faucet -27513AL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 6019.49 | 6019.492 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
27 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Integra Rim Ex Wall Hung Matt Taupe 7041B420H0075 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 13603.2 | 13603.2 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
28 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)Integra Soft Close Seat Cover Matt Taupe 110-020H019 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 5648.44 | 5648.441 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
29 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)KASTELLO SQUARE TOILET_BOWL -CCAS3131-3W20400F0 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 8241.6 | 16483.196 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
30 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)KASTELLO SQUARE WH TOILET SEAT COVER -CCASC131-U200410F0 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 3062.55 | 6125.108 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
31 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)LINEARE BATH SPOUT 13383AL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
32 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)NEW TEMPESTA-F TRIGGER SPRAY SET - 26352000 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 1406.08 | 2812.15 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
33 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)NTEMPESTA SHOWER ARM-27851000 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 1128.06 | 1128.06 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
34 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)QUARTZ KM-031/ CO-16 400X400X155 MM | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
35 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)RACK BOLT - WC | PAIR | 4 | 1 | 4 | 4 | 1 | 4 | 0 | 1 | 0 | 4 | 450 | 1800 | 0 | 0 | 0 | 4 | 4 | 4 | 4
36 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)RAINSHOWER COSMOPOLITAN 310 HEADSHOWER 9.5L,380MM- 26066GN0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
37 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)RAINSHOWER HANDSHOWER HOLDER -27074GN0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 2861.14 | 2861.1375 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
38 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)RAINSHOWER WALL UNION-27057GN0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 6005.3 | 6005.2975 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
39 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)RAPIDO SMART BOX-35600000 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 7161.6 | 14323.2 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
40 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)RSH SMARTACTIVE 130 HANDSHOWER - 26574GN0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 12307.62 | 12307.6225 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
41 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SEAT & COVER - CF070001-6DF00-N | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 1344.06 | 1344.06 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
42 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SHOWER HOSE 1750MM-28388GL0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 2126.11 | 2126.105 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
43 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SINGLE-LEVER BATH/SHOWER MIXER LOCKABLE DIVERTER-29062001 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 4118.4 | 4118.4 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
44 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SINGLE-LEVER BATH/SHOWER MIXER LOCKABLE DIVERTER-29063001 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 4224 | 4224 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
45 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SIPC. 900 MM CHANNEL DRAINER | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 4679.35 | 4679.3525 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
46 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SKATE COSMO, DUAL FLUSH- 38732000 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 1249.5 | 2499 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
47 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SKATE COSMOPOLITAN FLUSH PLATE, BRUSHED COOL-38732GN0 - | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 5544.01 | 5544.0072 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
48 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SPOUT 19408GN1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 19723.19 | 19723.1944 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
49 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)SUPER THIN 200MM SQUARE AIR-IN RAIN SHOWERFFASS032-006500BC0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 4488.01 | 4488.0104 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
50 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TEMPESTA 250MM HEAD SHOWER WITH ARM -26682000 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 8160.4 | 8160.4 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
51 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TEMPESTA TRIGGER SPRAY SET, COOL SUNRISE - GLOSSY-27513GL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 6456.01 | 6456.0088 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
52 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TOILET PAPER HOLDER 40367AL1 | ROLL | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
53 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TOILET PAPER HOLDER 40367GL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
54 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TOILET PAPER HOLDER 40457000 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
55 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TOWEL RAIL 600MM 40366AL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
56 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)TOWEL RAIL 600MM 40366GL1 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
57 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)WASHER SET | NOS | 4 | 1 | 4 | 4 | 1 | 4 | 0 | 1 | 0 | 2 | 200 | 400 | 0 | 0 | 0 | 4 | 4 | 4 | 4
58 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)WASTE TRAP BASIN 1 1/4"- 29058000 | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 1536.08 | 6144.32 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
59 | TOWER D 101 SH CP & SANITARY FITTINGS | 0 | Tentative | Material | (M)WINSTON 3/6LPF WALL HUNG TOILET BOWL-CCAS3130-3W20410A0 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 3843 | 3843 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
60 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/2"_CP NIPPLE | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 70.8 | 708 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
61 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/4" X 2"_UPVC REDUCER | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
62 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/4" X 3/4"_CPVC REDUCER TEE. | NOS | 20 | 1.18 | 23.6 | 20 | 1.18 | 23.6 | 0 | 1.18 | 0 | 20 | 137.64 | 2752.7 | 0 | 0 | 0 | 20 | 20 | 23.6 | 23.6
63 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/4" X 5MTR X SDR 11_CPVC PIPE | NOS | 6 | 1 | 6 | 6 | 1 | 6 | 0 | 1 | 0 | 6 | 1197.94 | 7187.6202 | 0 | 0 | 0 | 6 | 6 | 6 | 6
64 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/4"_CPVC END CAP | NOS | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 39.51 | 395.06 | 0 | 0 | 0 | 10 | 10 | 10 | 10
65 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/4"_UPVC BRASS FTA | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
66 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1 1/4"_UPVC PIPE_SCH-40_3 MTR. | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
67 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)1/2 X 1 CP NIPPLE | NOS | 20 | 1 | 20 | 20 | 1 | 20 | 0 | 1 | 0 | 20 | 47.2 | 944 | 0 | 0 | 0 | 20 | 20 | 20 | 20
68 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)110MM Silencio P Trap | NOS | 7 | 1.18 | 8.26 | 7 | 1.18 | 8.26 | 0 | 1.18 | 0 | 7 | 867.06 | 6069.4403 | 0 | 0 | 0 | 7 | 7 | 8.26 | 8.26
69 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)237ML_UPVC SOLVENT(SOLUTION) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
70 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)3/4"_CPVC END CAP | NOS | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 12.11 | 121.06 | 0 | 0 | 0 | 10 | 10 | 10 | 10
71 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)3/4"_CPVC ELBOW 90 DEG | NOS | 50 | 1 | 50 | 50 | 1 | 50 | 0 | 1 | 0 | 50 | 15.93 | 796.5 | 0 | 0 | 0 | 50 | 50 | 50 | 50
72 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)3/4"_CPVC TEE | NOS | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 26.13 | 261.26 | 0 | 0 | 0 | 10 | 10 | 10 | 10
73 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)3/4"X1/2" CPVC BRASS FTA 90 DEG | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 77.74 | 777.38 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
74 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)3/4"X1/2" CPVC BRASS MTA | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 109.6 | 1095.98 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
75 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)4"X3' _SILENCIO PIPE D/S | NOS | 13 | 1 | 13 | 13 | 1 | 13 | 0 | 1 | 0 | 13 | 704.17 | 9154.1502 | 0 | 0 | 0 | 13 | 13 | 13 | 13
76 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)50MM PVC Pipe 6 KGF /CM2 | RFT | 180 | 1 | 180 | 130 | 1 | 130 | 0 | 1 | 0 | 130 | 56 | 7280.364 | 0 | 0 | 0 | 180 | 180 | 180 | 180
77 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)50MM PVC BEND 45 DEGREE | NOS | 25 | 1.18 | 29.5 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 48.57 | 485.68 | 0 | 0 | 0 | 25 | 25 | 29.5 | 29.5
78 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)50MM_PVC COUPLER | NOS | 20 | 1 | 20 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 33.04 | 330.4 | 0 | 0 | 0 | 20 | 20 | 20 | 20
79 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)50MM_PVC ELBOW 90 DEG. (6 KGF/cm2 ) | NOS | 40 | 1 | 40 | 20 | 1 | 20 | 0 | 1 | 0 | 20 | 53.86 | 1077.1 | 0 | 0 | 0 | 40 | 40 | 40 | 40
80 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)50MM_PVC TEE | NOS | 4 | 1 | 4 | 4 | 1 | 4 | 0 | 1 | 0 | 4 | 74.67 | 298.68 | 0 | 0 | 0 | 4 | 4 | 4 | 4
81 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)6"x6" SS JALI (EN-SQ-HG6) | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 0 | 1.18 | 0 | 6 | 195.76 | 1174.572 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
82 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)JASTI KHILLA 2 1/2" | PKT | 2.5 | 1 | 2.5 | 2.5 | 1 | 2.5 | 0 | 1 | 0 | 2.5 | 201.34 | 503.3425 | 0 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5
83 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)PVC RUBBER LUBRICANT_500GM (PIPE JOINT LUBRICANT) | NOS | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4
84 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)PVC Solvent - 500 ML(IPS WELDON 473G PVC100 SOLVENT CEMENT) | TIN | 2 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 208.16 | 208.16 | 0 | 0 | 0 | 2 | 2 | 2 | 2
85 | TOWER D 101 SH PLUMBING WORK | 0 | Tentative | Material | (M)TAFLON TAP | NOS | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 23.6 | 236 | 0 | 0 | 0 | 10 | 10 | 10 | 10
86 | TOWER D 101 SH CONSULTANCY CHARGES | 10 | Started | Labour | (L)CHARGES FOR PROVIDING PROJECT MANAGEMENT CONSULTANCY (LS) | LUMSUM | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 236000 | 236000 | 0.5 | 236000 | 118000 | 1 | 0.5 | 0 | -118000
87 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR CEILING PUNNING WORK | SQFT | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 33.04 | 1652 | 0 | 0 | 0 | 50 | 50 | 0 | 0
88 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR DHAR POLISH (RFT) | RFT | 200 | 1 | 200 | 0 | 0 | 0 | 0 | 1 | 0 | 200 | 25.96 | 5192 | 0 | 0 | 0 | 200 | 200 | 200 | 200
89 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR GROOVE (RFT) | RFT | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 23.6 | 11800 | 0 | 0 | 0 | 500 | 500 | 0 | 0
90 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR GYPSUM CEILING (SQFT) | SQFT | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 64.9 | 129800 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0
91 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR GYPSUM VERTICAL (RFT) | RFT | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 61.36 | 30680 | 0 | 0 | 0 | 500 | 500 | 0 | 0
92 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR LIGHT CUT OUT | NOS | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 35.4 | 1770 | 0 | 0 | 0 | 50 | 50 | 0 | 0
93 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR MOLDING (RFT) | RFT | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 64.9 | 12980 | 0 | 0 | 0 | 200 | 200 | 0 | 0
94 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR PUNNING | SQFT | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 29.5 | 118000 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0
95 | TOWER D 101 SH PUNNING WORK | 0 | Tentative | Labour | (L)LABOR FOR WALL GROOVE | RFT | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 21.24 | 21240 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0
96 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)10 A DRIVER | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 590 | 590 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
97 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)12 A DRIVER | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 649 | 6490 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
98 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)12 V CONNECTOR WITH BOX | NOS | 6 | 1 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6
99 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)12 W SURFACE CYLINDRICAL CEILING LIGHT | NOS | 5 | 1 | 5 | 5 | 1 | 5 | 0 | 1 | 0 | 5 | 767 | 3835 | 0 | 0 | 0 | 5 | 5 | 5 | 5
100 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)12W SPOT BLADE NW | NOS | 8 | 1.18 | 9.44 | 8 | 1.18 | 9.44 | 0 | 1.18 | 0 | 8 | 1475 | 11800 | 0 | 0 | 0 | 8 | 8 | 9.44 | 9.44
101 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)12W TRACK SPOT NW | NOS | 18 | 1.18 | 21.24 | 18 | 1.18 | 21.24 | 0 | 1.18 | 0 | 18 | 1799.5 | 32391 | 0 | 0 | 0 | 18 | 18 | 21.24 | 21.24
102 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)16MM x 7MM SURFACE PROFILE | RMT | 26 | 1.18 | 30.68 | 26 | 1.18 | 30.68 | 0 | 1.18 | 0 | 26 | 118 | 3068 | 0 | 0 | 0 | 26 | 26 | 30.68 | 30.68
103 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)17MM CONSEALED PROFILE LIGHT CP-1707 BLACK BODY COLOUR | RMT | 78 | 1.18 | 92.04 | 78 | 1.18 | 92.04 | 0 | 1.18 | 0 | 78 | 118 | 9204 | 0 | 0 | 0 | 78 | 78 | 92.04 | 92.04
104 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)17MM x 7MM CONCEAL PROFILE | RMT | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 118 | 1180 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
105 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)17MM x 7MM SURFACE PROFILE | RMT | 30 | 1.18 | 35.4 | 30 | 1.18 | 35.4 | 0 | 1.18 | 0 | 30 | 118 | 3540 | 0 | 0 | 0 | 30 | 30 | 35.4 | 35.4
106 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)18 W DIFFUSED BLADE NW | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 0 | 1.18 | 0 | 6 | 1652 | 9912 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
107 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)2 A DRIVER | NOS | 15 | 1.18 | 17.7 | 15 | 1.18 | 17.7 | 0 | 1.18 | 0 | 15 | 218.3 | 3274.5 | 0 | 0 | 0 | 15 | 15 | 17.7 | 17.7
108 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)20 A DRIVER | NOS | 5 | 1.18 | 5.9 | 5 | 1.18 | 5.9 | 0 | 1.18 | 0 | 5 | 1003 | 5015 | 0 | 0 | 0 | 5 | 5 | 5.9 | 5.9
109 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)23MM CONSEALED PROFILE LIGHT CP-2323 BLACK BODY COLOUR | RMT | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 0 | 1.18 | 0 | 12 | 212.4 | 2548.8 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
110 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)2M FOOT LIGHT | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 826 | 3304 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
111 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)35MM CONSEALED PROFILE LIGHT CP-3512 WHITE BODY COLOUR | RMT | 8 | 1.18 | 9.44 | 8 | 1.18 | 9.44 | 0 | 1.18 | 0 | 8 | 767 | 6136 | 0 | 0 | 0 | 8 | 8 | 9.44 | 9.44
112 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)35MM CONSEALED PROFILE LIGHT CP-3535 WHITE BODY COLOUR | RMT | 22 | 1.18 | 25.96 | 22 | 1.18 | 25.96 | 0 | 1.18 | 0 | 22 | 767 | 16874 | 0 | 0 | 0 | 22 | 22 | 25.96 | 25.96
113 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)5 A DRIVER | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 472 | 4720 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
114 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)582027 PHILIPS WEBBER TYPE I CONNECTION | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 472 | 4720 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
115 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)582034 PHILIPS WEBBER TRIMLESS CORNER 90 | NOS | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 0 | 1.18 | 0 | 12 | 649 | 7788 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
116 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)582040 PHILIPS RECESSED TRIMLESSTRACK 1M | NOS | 30 | 1.18 | 35.4 | 30 | 1.18 | 35.4 | 0 | 1.18 | 0 | 30 | 1357 | 40710 | 0 | 0 | 0 | 30 | 30 | 35.4 | 35.4
117 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)5W LEDLUM BLACK BODY STRIKER | NOS | 17 | 1.18 | 20.06 | 17 | 1.18 | 20.06 | 0 | 1.18 | 0 | 17 | 531 | 9027 | 0 | 0 | 0 | 17 | 17 | 20.06 | 20.06
118 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)CEILING FAN | NOS | 7 | 1 | 7 | 7 | 1 | 7 | 0 | 1 | 0 | 7 | 4012 | 28084 | 0 | 0 | 0 | 7 | 7 | 7 | 7
119 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)DRIVER | NOS | 3 | 1.18 | 3.54 | 3 | 1.18 | 3.54 | 0 | 1.18 | 0 | 3 | 2360 | 7080 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54
120 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)EXHAUST FAN | NOS | 8 | 1 | 8 | 8 | 1 | 8 | 0 | 1 | 0 | 8 | 1994.2 | 15953.6 | 0 | 0 | 0 | 8 | 8 | 8 | 8
121 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)HANGING LIGHT | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 13605.4 | 54421.6 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
122 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)HYBEC 6W EB-9321 COB LIGHT | NOS | 6 | 1.12 | 6.72 | 6 | 1.12 | 6.72 | 0 | 1.12 | 0 | 6 | 676.14 | 4056.84 | 0 | 0 | 0 | 6 | 6 | 6.72 | 6.72
123 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)LED STRIP LIGHT | RMT | 155 | 1 | 155 | 155 | 1 | 155 | 0 | 1 | 0 | 155 | 257.32 | 39884 | 0 | 0 | 0 | 155 | 155 | 155 | 155
124 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)LED STRIP LIGHT PRO GLOW PHILIPS 4K 5MTR ROLL | NOS | 17 | 1.18 | 20.06 | 17 | 1.18 | 20.06 | 0 | 1.18 | 0 | 17 | 1917.5 | 32597.5 | 0 | 0 | 0 | 17 | 17 | 20.06 | 20.06
125 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)MAGNETIC CORNER 90 DEGREE CONNECTOR | NOS | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 0 | 1.18 | 0 | 12 | 507.4 | 6088.8 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
126 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)PHILIPS 12W COB ASTRA SPOT 4K WHITE IN BODY COLOUR | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 0 | 1.18 | 0 | 6 | 1121 | 6726 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
127 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)PHILIPS 7W COB ASTRA SPOT 4K WHITE IN BODY COLOUR | NOS | 46 | 1.18 | 54.28 | 46 | 1.18 | 54.28 | 0 | 1.18 | 0 | 46 | 826 | 37996 | 0 | 0 | 0 | 46 | 46 | 54.28 | 54.28
128 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)PHILIPS MARATHON INDIRECT ROPELIGHT 3000K | RMT | 100 | 1.12 | 112 | 100 | 1.12 | 112 | 0 | 1.12 | 0 | 100 | 135.7 | 13570 | 0 | 0 | 0 | 100 | 100 | 112 | 112
129 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)PHILIPS ROPELIGHT CONNECTOR | NOS | 15 | 1.12 | 16.8 | 15 | 1.12 | 16.8 | 0 | 1.12 | 0 | 15 | 218.3 | 3274.5 | 0 | 0 | 0 | 15 | 15 | 16.8 | 16.8
130 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Material | (M)WARDROBE SWITCH | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 0 | 1.18 | 0 | 6 | 88.5 | 531 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
131 | TOWER D 101 SH ELECTRIC WORK | 0 | Started | Labour | (L)LABOUR FOR ELECTRIC WORK (NOS) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 94152.2 | 94152.2 | 1 | 94152.2 | 94152.2 | 1 | 0 | 0 | -94152.2
132 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)1200x600 STAR WHITE CRYSTAL TILES | SQFT | 224 | 1.18 | 264.32 | 217 | 1.18 | 256.06 | 22 | 1.18 | 25.96 | 217 | 85 | 18445.9114 | 0 | 0 | 0 | 202 | 224 | 238.36 | 264.32
133 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)1200x600 STAR WHITE MATT TILES | SQFT | 112 | 1 | 112 | 109 | 1 | 109 | 11 | 1 | 11 | 109 | 83 | 9047.4578 | 0 | 0 | 0 | 101 | 112 | 101 | 112
134 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)1209 Black Imported 1200x600 | SQFT | 186 | 1.18 | 219.48 | 186 | 1.18 | 219.48 | 19 | 1.18 | 22.42 | 186 | 45.62 | 8485.7292 | 0 | 0 | 0 | 167 | 186 | 197.06 | 219.48
135 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)195X1200_LEZORA_PINEWOOD CHOCO | SQFT | 180 | 1 | 180 | 180 | 1 | 180 | 18 | 1 | 18 | 180 | 53.1 | 9558 | 0 | 0 | 0 | 162 | 180 | 162 | 180
136 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)21003 Highlighter imported 200x200 | SQFT | 60 | 1.18 | 70.8 | 60 | 1.18 | 70.8 | 6 | 1.18 | 7.08 | 60 | 205.28 | 12316.806 | 0 | 0 | 0 | 54 | 60 | 63.72 | 70.8
137 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)300X75 AVOCADO GREEN CERAMIC GLAZED TILES | SQFT | 58 | 1.18 | 68.44 | 58 | 1.18 | 68.44 | 6 | 1.18 | 7.08 | 58 | 280.01 | 16240.8178 | 0 | 0 | 0 | 52 | 58 | 61.36 | 68.44
138 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)BONDTITE SUPER STRENGTH | TIN | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 1050 | 2100 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
139 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)CEMENT PPC - BAGS | BAGS | 30 | 1 | 30 | 30 | 1 | 30 | 3 | 1 | 3 | 30 | 339.99 | 10199.799 | 0 | 0 | 0 | 27 | 30 | 27 | 30
140 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)GREEN MARBLE | SQFT | 200 | 1.18 | 236 | 200 | 1.18 | 236 | 20 | 1.18 | 23.6 | 200 | 77.88 | 15576 | 0 | 0 | 0 | 180 | 200 | 212.4 | 236
141 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)ITALIAN MARBLE_ DYNA WHITE | SQFT | 170 | 1.18 | 200.6 | 0 | 0 | 0 | 17 | 1.18 | 20.06 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 170 | 180.54 | 200.6
142 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)KOTA | SQFT | 60 | 1 | 60 | 56 | 1 | 56 | 6 | 1 | 6 | 56 | 59.57 | 3335.8604 | 0 | 0 | 0 | 54 | 60 | 54 | 60
143 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)Kota green full body 1200x600 | SQFT | 171 | 1.18 | 201.78 | 171 | 1.18 | 201.78 | 17 | 1.18 | 20.06 | 171 | 70.96 | 12134.7585 | 0 | 0 | 0 | 154 | 171 | 181.72 | 201.78
144 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)LOCK BODY SMART SERIES SS 60X85 MM | NOS | 5 | 1.18 | 5.9 | 0 | 0 | 0 | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 4.72 | 5.9
145 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)PROTECTION FILM | ROLL | 5 | 1 | 5 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 4 | 5
146 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)SPARTEK TILES SIZE 1'X1' | SQFT | 1400 | 1.18 | 1652 | 1400 | 1.18 | 1652 | 140 | 1.18 | 165.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1400 | 1486.8 | 1652
147 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)STEEL GREY GRANITE | SQFT | 100 | 1 | 100 | 0 | 0 | 0 | 10 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 100 | 90 | 100
148 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)SUPERFLEX ECO (KERAKOLL) - 4 KG | TIN | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 2039.04 | 4078.08 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
149 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)Terazzo white 1200x600 | SQFT | 202 | 1.18 | 238.36 | 202 | 1.18 | 238.36 | 20 | 1.18 | 23.6 | 202 | 96.33 | 19459.6296 | 0 | 0 | 0 | 182 | 202 | 214.76 | 238.36
150 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)TILE FIXO X'TRAPLUS -20 KG (WHITE) | BAGS | 75 | 1.18 | 88.5 | 75 | 1.18 | 88.5 | 8 | 1.18 | 9.44 | 75 | 739.86 | 55489.5 | 0 | 0 | 0 | 67 | 75 | 79.06 | 88.5
151 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)VIETNAM WHITE/PEARL WHITE MARBAL | SQFT | 1000 | 1.18 | 1180 | 1000 | 1.18 | 1180 | 100 | 1.18 | 118 | 1000 | 519.2 | 519200 | 0 | 0 | 0 | 900 | 1000 | 1062 | 1180
152 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)WHITE MARBLE | SQFT | 150 | 1 | 150 | 0 | 0 | 0 | 15 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 150 | 135 | 150
153 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Material | (M)WHITE QUARTZ STONE | SQFT | 150 | 200 | 30000 | 0 | 0 | 0 | 15 | 200 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 150 | 27000 | 30000
154 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)CHARGES FOR LAMINATE FLOORING (SQFT) | SQFT | 542.49 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 542.49 | 165.2 | 89619.34 | 542.49 | 165.2 | 89619.34 | 488.49 | 0 | 0 | -89619.34
155 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)CHARGES FOR REDUCER (RFT) | RFT | 24 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 24 | 100.3 | 2407.2 | 24 | 100.3 | 2407.2 | 22 | 0 | 0 | -2407.2
156 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)CHARGES FOR TILE PATTA CUTTING (SQFT) | SQFT | 226 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 226 | 10 | 2260 | 224.7 | 10 | 2247 | 203 | 1.3 | 0 | -2247
157 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)DEPART LABOR | NOS | 15 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 10 | 920 | 9200 | 3.184 | 1100 | 3502.4 | 13 | 11.816 | 0 | -3502.4
158 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)DEPART MASON | NOS | 17 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 17 | 1100 | 18700 | 11.91 | 1100 | 13101 | 15 | 5.09 | 0 | -13101
159 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR AUSTRALIAN MARBLE FITTING | SQFT | 956 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 956 | 65 | 62140 | 955.28 | 65 | 62093.2 | 860 | 0.72 | 0 | -62093.2
160 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR CHAMFER (RFT) | RFT | 1549.49 | 1 | 1549.49 | 0 | 0 | 0 | 155 | 1 | 155 | 1549.49 | 20 | 30989.8 | 1092.84 | 20 | 21856.8 | 1394.49 | 456.65 | 1394.49 | -20307.31
161 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR CHAMFER POLISH (RFT) | RFT | 29 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 29 | 0 | 0
162 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR CRACK FILLING (RFT) | RFT | 265 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 265 | 0 | 0
163 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR DHAR POLISH (RFT) | RFT | 1602 | 1 | 1602 | 0 | 0 | 0 | 160 | 1 | 160 | 1564.49 | 17 | 26596.33 | 1300.21 | 17 | 22103.57 | 1442 | 301.79 | 1442 | -20501.57
164 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR DOOR & WINDOW FRAME (SQFT) | SQFT | 650 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 650 | 40 | 26000 | 643.26 | 40 | 25730.4 | 585 | 6.74 | 0 | -25730.4
165 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR DOOR & WINDOW SILL | SQFT | 220 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 220 | 40 | 8800 | 119.8 | 40 | 4792 | 198 | 100.2 | 0 | -4792
166 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR HOLE (NOS) | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 500 | 1500 | 0 | 0 | 0 | 3 | 3 | 0 | 0
167 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR HOLE 1" DIA (NOS) | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 100 | 400 | 4 | 100 | 400 | 4 | 0 | 0 | -400
168 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR ITALIAN DEDO (SQFT) | SQFT | 353 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 353 | 60 | 21180 | 351.28 | 60 | 21076.8 | 318 | 1.72 | 0 | -21076.8
169 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR ITALIAN MARBLE PLATFORM | SQFT | 82 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 82 | 45 | 3690 | 81.33 | 45 | 3659.85 | 74 | 0.67 | 0 | -3659.85
170 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR KOTA PLATFORM | SQFT | 77 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 77 | 35 | 2695 | 76.75 | 35 | 2686.25 | 69 | 0.25 | 0 | -2686.25
171 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR NOSE ROUND (RFT) | RFT | 42 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 42 | 0 | 0
172 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR SINK HOLE IN GRANITE | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 600 | 1800 | 3 | 600 | 1800 | 3 | 0 | 0 | -1800
173 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR SKIRTING (RFT) | RFT | 128 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 128 | 100.3 | 12838.4 | 128 | 100.3 | 12838.4 | 115 | 0 | 0 | -12838.4
174 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR SPARTEK TILES DEDO (1'X1') | SQFT | 196 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 196 | 17 | 3332 | 195.03 | 17 | 3315.51 | 176 | 0.97 | 0 | -3315.51
175 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR SPARTEK TILES FLOORING (1'X1') | SQFT | 143 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 143 | 15 | 2145 | 141.52 | 15 | 2122.8 | 129 | 1.48 | 0 | -2122.8
176 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR SUNK FILLING WITH SCREED (CMT) | CMT | 13 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 13 | 2000 | 26000 | 13 | 2000 | 26000 | 12 | 0 | 0 | -26000
177 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR VITRIFIED TILES DEDO (1200X600) | SQFT | 649 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 649 | 28 | 18172 | 646.71 | 28 | 18107.88 | 584 | 2.29 | 0 | -18107.88
178 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR VITRIFIED TILES DEDO (600X600) | SQFT | 214 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 214 | 17 | 3638 | 213.5 | 17 | 3629.5 | 193 | 0.5 | 0 | -3629.5
179 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR VITRIFIED TILES FLOORING (1200X600) | SQFT | 1455 | 0 | 0 | 0 | 0 | 0 | 146 | 0 | 0 | 1455 | 22 | 32010 | 1451.72 | 22 | 31937.84 | 1309 | 3.28 | 0 | -31937.84
180 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR VITRIFIED TILES FLOORING (300X300) | SQFT | 160 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 160 | 15 | 2400 | 150.54 | 15 | 2258.1 | 144 | 9.46 | 0 | -2258.1
181 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR WHITE MARBLE POLISH (SQFT) | SQFT | 995 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895 | 995 | 0 | 0
182 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOR FOR WOODEN PLANK (1200X200) | RFT | 283 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 283 | 10 | 2830 | 283 | 10 | 2830 | 255 | 0 | 0 | -2830
183 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR COUNTER TOP (SQFT) | SQFT | 67 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 67 | 40 | 2680 | 66.3 | 40 | 2652 | 60 | 0.7 | 0 | -2652
184 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR DOOR BIDDING PATTI (RFT) | RFT | 56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 56 | 70.8 | 3964.8 | 56 | 70.8 | 3964.8 | 50 | 0 | 0 | -3964.8
185 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR GRANITE PATTA (RFT) | RFT | 145.93 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 145.93 | 40 | 5837.2 | 0 | 0 | 0 | 130.93 | 145.93 | 0 | 0
186 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR ITALIAN DEDO MIRROR POLISH (SQFT) | SQFT | 146 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 146 | 0 | 0
187 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR ITALIAN LOOSE MIRROR POLISH (SQFT) | SQFT | 265 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 265 | 0 | 0
188 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR ITALIAN MARBLE FLOORING WITH CUTTING (SQFT) | SQFT | 42 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 42 | 50 | 2100 | 41.25 | 50 | 2062.5 | 38 | 0.75 | 0 | -2062.5
189 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)LABOUR FOR VITRIFIED FLOORING - 45° (RFT) | RFT | 117 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 117 | 25 | 2925 | 116.46 | 25 | 2911.5 | 105 | 0.54 | 0 | -2911.5
190 | TOWER D 101 SH FLOORING & DEDO WORK | 10 | Started | Labour | (L)PROVIDING & FIXING 3MM SPACER WITH REQUIRED TOOLS & TACKLES | SQFT | 415 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 415 | 2 | 830 | 413.5 | 2 | 827 | 373 | 1.5 | 0 | -827
191 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)1.5 SQMM 2 CORE SHIELDED CONTROL CABLE | RMT | 100 | 1.18 | 118 | 100 | 1.18 | 118 | 10 | 1.18 | 11.8 | 100 | 236 | 23600 | 0 | 0 | 0 | 90 | 100 | 106.2 | 118
192 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)25 MM UPVC DRAIN PIPE | RMT | 50 | 1.18 | 59 | 50 | 1.18 | 59 | 5 | 1.18 | 5.9 | 50 | 259.6 | 12980 | 0 | 0 | 0 | 45 | 50 | 53.1 | 59
193 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)DUCTABLE INDOOR UNIT 1.65 TONN | NOS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 31008 | 31008 | 0 | 0 | 0 | 1 | 1 | 1 | 1
194 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)DUCTABLE INDOOR UNIT 2.0 TONN | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 33331.2 | 133324.8 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
195 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)DUCTING | LOT | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 19597.44 | 19597.44 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
196 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)FIRE RETARDENT REXIN | SET | 5 | 1.18 | 5.9 | 5 | 1.18 | 5.9 | 1 | 1.18 | 1.18 | 5 | 2360 | 11800 | 0 | 0 | 0 | 4 | 5 | 4.72 | 5.9
197 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)G.I PERFORATED CABLE TRAY 300 X 300 X 50 | RMT | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 1298 | 7788 | 0 | 0 | 0 | 5 | 6 | 5.9 | 7.08
198 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)GI PERFORATED TRAY | RMT | 80 | 1.18 | 94.4 | 80 | 1.18 | 94.4 | 8 | 1.18 | 9.44 | 80 | 1298 | 103840 | 0 | 0 | 0 | 72 | 80 | 84.96 | 94.4
199 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)M.S. STRUCTURAL WORK (KG) | KG | 30 | 1.18 | 35.4 | 30 | 1.18 | 35.4 | 3 | 1.18 | 3.54 | 30 | 129.8 | 3894 | 0 | 0 | 0 | 27 | 30 | 31.86 | 35.4
200 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)ONE WAY CORNER TYPE UNIT 1.65 TONN | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 53684.48 | 53684.48 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
201 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)OUTDOOR UNIT | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 196715.52 | 196715.52 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
202 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)REFNETS | PAIR | 5 | 1 | 5 | 5 | 1 | 5 | 1 | 1 | 1 | 5 | 2545.92 | 12729.6 | 0 | 0 | 0 | 4 | 5 | 4 | 5
203 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)REMOTE CONTROL SYSTEM | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 5042.69 | 30256.1202 | 0 | 0 | 0 | 5 | 6 | 5.9 | 7.08
204 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)VOLUME CONTROL DAMPER | SQMT | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 7473.33 | 44840 | 0 | 0 | 0 | 5 | 6 | 5.9 | 7.08
205 | TOWER D 101 SH HVAC WORK | 10 | Started | Material | (M)VRF - VARIABLE REFRIGERANT FLOW | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 12980 | 12980 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
206 | TOWER D 101 SH HVAC WORK | 10 | Started | Labour | (L)CHARGES FOR 300 x 50 GI PERFORATED CABLE TRAY (RMT) | RMT | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6 | 177 | 1062 | 0 | 0 | 0 | 5 | 6 | 0 | 0
207 | TOWER D 101 SH HVAC WORK | 10 | Started | Labour | (L)CHARGES FOR M.S. STRUCTURAL WORK (KG) | KG | 30 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 30 | 29.5 | 885 | 0 | 0 | 0 | 27 | 30 | 0 | 0
208 | TOWER D 101 SH HVAC WORK | 10 | Started | Labour | (L)LABOR FOR 1.5 SQMM 2 CORE SHIELDED CONTROL CABLE | RMT | 100 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 100 | 59 | 5900 | 82 | 59 | 4838 | 90 | 18 | 0 | -4838
209 | TOWER D 101 SH HVAC WORK | 10 | Started | Labour | (L)LABOR FOR AC DRAIN PIPE (RMT) | RMT | 50 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 50 | 76.7 | 3835 | 34 | 76.7 | 2607.8 | 45 | 16 | 0 | -2607.8
210 | TOWER D 101 SH HVAC WORK | 10 | Started | Labour | (L)LABOR FOR GI PERFORATED CABLE TRAY | RMT | 80 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 80 | 177 | 14160 | 52 | 177 | 9204 | 72 | 28 | 0 | -9204
211 | TOWER D 101 SH HVAC WORK | 10 | Started | Labour | (L)LABOR FOR VRF SYSTEM (NOS) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 0 | 0
212 | TOWER D 101 SH COMMON MISC WORK | 10 | Started | Material | (M)HOLLOW CONCRETE BLOCK -16"X8"X8" | NOS | 80 | 1.18 | 94.4 | 80 | 1.18 | 94.4 | 8 | 1.18 | 9.44 | 80 | 44.84 | 3587.2 | 0 | 0 | 0 | 72 | 80 | 84.96 | 94.4
213 | TOWER D 101 SH FURNITURE WORK | 0 | Started | Labour | (L)LABOR FOR WOODEN CEILING WORK | SQFT | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 554.6 | 152515 | 264 | 554.6 | 146414.4 | 275 | 11 | 0 | -146414.4
214 | TOWER D 101 SH FURNITURE WORK | 0 | Started | Labour | (L)LABOUR FOR CARPENTRY WORK (NOS) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2635177.18 | 2635177.18 | 0.7 | 2635177.2 | 1844624.04 | 1 | 0.3 | 0 | -1844624.04
215 | TOWER D 101 SH FURNITURE WORK | 0 | Started | Labour | (L)LABOUR FOR CEMENT SHEET (SQFT) | SQFT | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 354 | 97350 | 0 | 0 | 0 | 275 | 275 | 0 | 0
216 | TOWER D 101 SH FURNITURE WORK | 0 | Started | Labour | (L)LABOUR FOR PALMET | SQFT | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 383.5 | 65195 | 170 | 383.5 | 65195 | 170 | 0 | 0 | -65195
217 | TOWER D 101 SH DRILLING WORK | 10 | Started | Labour | (L)LABOR FOR 30 MM DIA DRILLING (230 MM DEPTH) | NOS | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 7 | 106.2 | 743.4 | 0 | 0 | 0 | 6 | 7 | 0 | 0
218 | TOWER D 101 SH WATERPROOFING WORK | 10 | Started | Labour | (L)LABOUR FOR WATERPROOFING (SQFT) | SQFT | 1930 | 0 | 0 | 0 | 0 | 0 | 193 | 0 | 0 | 1573 | 54.28 | 85382.44 | 1573 | 54.28 | 85382.44 | 1737 | 357 | 0 | -85382.44
219 | TOWER D 101 SH AUTOMATION WORK | 0 | Tentative | Labour | (L)CHARGES FOR SUPPLY & INSTALLATION OF AUTOMATION | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 243939.04 | 243939.04 | 0 | 0 | 0 | 1 | 1 | 0 | 0
220 | TOWER D 101 SH AUTOMATION WORK | 0 | Tentative | Labour | (L)CHARGES FOR WIFI TOUCH PANEL (NOS) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 19956.16 | 19956.16 | 0 | 0 | 0 | 1 | 1 | 0 | 0
221 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)DEPART LABOR | NOS | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 826 | 12390 | 0 | 0 | 0 | 15 | 15 | 0 | 0
222 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR MONOCOAT POLISH WORK (RFT) | RFT | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 106.2 | 53100 | 0 | 0 | 0 | 500 | 500 | 0 | 0
223 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR MONOCOAT POLISH WORK (SQFT) | SQFT | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 212.4 | 148680 | 0 | 0 | 0 | 700 | 700 | 0 | 0
224 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR OIL PAINT (RFT) | RFT | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 9.44 | 1888 | 0 | 0 | 0 | 200 | 200 | 0 | 0
225 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR OIL PAINT (SQFT) | SQFT | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 13.57 | 2714 | 0 | 0 | 0 | 200 | 200 | 0 | 0
226 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR P U PALLATE COLOR WORK (RFT) | RFT | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0
227 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR P U PALLATE COLOR WORK (SQFT) | SQFT | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0
228 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)LABOR FOR PUTTY & PRIMER (SQFT) | SQFT | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 8.85 | 39825 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0
229 | TOWER D 101 SH PAINT WORK | 0 | Tentative | Labour | (L)PROVIDING & APPLYING ROYALE MATT | SQFT | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 21.24 | 95580 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0
230 | TOWER D 101 SH TEXTURE WORK | 0 | Tentative | Material | (M)BGB White Brick | SQFT | 130 | 1.18 | 153.4 | 130 | 1.18 | 153.4 | 0 | 1.18 | 0 | 130 | 271.4 | 35282 | 0 | 0 | 0 | 130 | 130 | 153.4 | 153.4
231 | TOWER D 101 SH TEXTURE WORK | 0 | Tentative | Material | (M)Demontized Brick Red | SQFT | 78 | 1.18 | 92.04 | 78 | 1.18 | 92.04 | 0 | 1.18 | 0 | 78 | 271.4 | 21169.2 | 0 | 0 | 0 | 78 | 78 | 92.04 | 92.04
232 | TOWER D 101 SH TEXTURE WORK | 0 | Tentative | Material | (M)Scrooves | SQFT | 71.1 | 1.18 | 83.9 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.1 | 71.1 | 83.898 | 83.898
233 | TOWER D 101 SH TEXTURE WORK | 0 | Tentative | Labour | (L)CHARGES FOR WALL TEXTURE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
234 | TOWER D 101 SH TEXTURE WORK | 0 | Tentative | Labour | (L)LABOR FOR TRY STONE TEXTURE | SQFT | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 0 | 0
235 | TOWER D 101 SH ALUMINIUM WORK | 10 | Started | Labour | (L)LABOR FOR ALUMINUM WINDOW (SQFT) | SQFT | 540 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 540 | 659.41 | 356080.1 | 540 | 659.41 | 356080.1 | 486 | 0 | 0 | -356080.1
236 | TOWER D 101 SH KITCHEN APPLIANCES | 0 | Tentative | Material | (M)CHIMNEY | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 21815 | 21815 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
237 | TOWER D 101 SH KITCHEN APPLIANCES | 0 | Tentative | Material | (M)DISHWASHER | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 49183 | 49183 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
238 | TOWER D 101 SH KITCHEN APPLIANCES | 0 | Tentative | Material | (M)HOB | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 12100 | 12100 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
239 | TOWER D 101 SH KITCHEN APPLIANCES | 0 | Tentative | Material | (M)MICROWAVE | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 22125 | 22125 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
240 | TOWER D 101 SH KITCHEN APPLIANCES | 0 | Tentative | Material | (M)OVEN | NOS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 23125 | 23125 | 0 | 0 | 0 | 1 | 1 | 1 | 1
241 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)CARTING CHARGES (NOS) | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 737.5 | 1475 | 1 | 767 | 767 | 2 | 1 | 0 | -767
242 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)CHARGES FOR 5MM MIRROR GLASS | SQFT | 55.75 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 55.75 | 123.9 | 6907.43 | 0 | 0 | 0 | 49.75 | 55.75 | 0 | 0
243 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)CHARGES FOR HOLE IN GLASS | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 12 | 53.1 | 637.2 | 12 | 53.1 | 637.2 | 11 | 0 | 0 | -637.2
244 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)CHARGES FOR MAGNETEIC SEAL (NOS) | NOS | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 8 | 171.1 | 1368.8 | 8 | 171.1 | 1368.8 | 7 | 0 | 0 | -1368.8
245 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)CHARGES FOR SILICON | NOS | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 9 | 210.04 | 1890.36 | 3 | 210.04 | 630.12 | 8 | 6 | 0 | -630.12
246 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)LABOR FOR 10 MM TUFFEN GLASS (SQFT) | SQFT | 100.25 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 100.25 | 182.9 | 18335.73 | 100.25 | 182.9 | 18335.73 | 90.25 | 0 | 0 | -18335.73
247 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)LABOR FOR BIG CUT (NOS) | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 531 | 1593 | 3 | 531 | 1593 | 3 | 0 | 0 | -1593
248 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)LABOR FOR GLASS FIXING (SQFT) | SQFT | 156 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 156 | 55.21 | 8612.53 | 100.25 | 53.1 | 5323.27 | 140 | 55.75 | 0 | -5323.27
249 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)LABOR FOR MIRROR MOUNTED TAPE | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 454.3 | 1362.9 | 0 | 0 | 0 | 3 | 3 | 0 | 0
250 | TOWER D 101 SH GLASS WORK | 10 | Started | Labour | (L)LABOR FOR MS BRACKET (NOS) | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 12 | 615.96 | 7391.52 | 12 | 615.96 | 7391.52 | 11 | 0 | 0 | -7391.52
251 | TOWER D 101 SH CIVIL WORK | 10 | Started | Labour | (L)DEPART LABOR | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1400 | 5600 | 4 | 1400 | 5600 | 4 | 0 | 0 | -5600
252 | TOWER D 101 SH CIVIL WORK | 10 | Started | Labour | (L)DEPART MASON | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1400 | 5600 | 4 | 1400 | 5600 | 4 | 0 | 0 | -5600
253 | TOWER D 101 SH CIVIL WORK | 10 | Started | Labour | (L)LABOR FOR NANO TOPPING OVER PLASTER WORK | SQFT | 438.75 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 438.75 | 70 | 30712.5 | 323.16 | 70 | 22621.2 | 394.75 | 115.59 | 0 | -22621.2
254 | TOWER D 101 SH PLANTATION WORK | 10 | Started | Labour | (L)CHARGES FOR PLANTATION WORK | LUMSUM | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 32940 | 32940 | 1 | 32940 | 32940 | 1 | 0 | 0 | -32940
255 | TOWER D 101 SH ANTI TERMITE TREATMENT | 0 | Tentative | Labour | (L)ANTI TERMITE TREATMENT (SQFT) | SQFT | 1960 | 3 | 5880 | 0 | 0 | 0 | 0 | 3 | 0 | 1960 | 6.2 | 12142.2 | 0 | 0 | 0 | 1960 | 1960 | 5880 | 5880
256 | TOWER D 101 SH RAILING WORK | 10 | Started | Labour | (L)LABOR FOR BALCONY RAILING (RFT) | RFT | 92 | 160 | 14720 | 0 | 0 | 0 | 9 | 160 | 1440 | 92 | 1427.8 | 131357.6 | 51.3 | 1427.8 | 73246.14 | 83 | 40.7 | 13280 | -58526.14
257 | TOWER D 101 SH FABRICATION WORK | 0 | Tentative | Labour | (L)LABOR FOR ANCHOR FASTNER 12MM | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 120 | 1440 | 0 | 0 | 0 | 12 | 12 | 0 | 0
258 | TOWER D 101 SH FABRICATION WORK | 0 | Tentative | Labour | (L)LABOR FOR ANCHOR FASTNERS M 12 (NOS) | NOS | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 120 | 4800 | 0 | 0 | 0 | 52 | 52 | 0 | 0
259 | TOWER D 101 SH FABRICATION WORK | 0 | Tentative | Labour | (L)LABOR FOR FABRICATED DUCT PLATFORM | KG | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 135 | 47520 | 0 | 0 | 0 | 352 | 352 | 0 | 0
260 | TOWER D 101 SH CURTAIN & MATTRESSES | 0 | Tentative | Material | (M)BED MATTRESS | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 16946.49 | 67785.96 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
261 | TOWER D 101 SH CURTAIN & MATTRESSES | 0 | Tentative | Material | (M)CURTAIN FABRIC (SHEER) | RMT | 126.5 | 1.06 | 134.09 | 126.5 | 1.06 | 134.09 | 0 | 1.06 | 0 | 126.5 | 597.77 | 75617.399 | 0 | 0 | 0 | 126.5 | 126.5 | 134.09 | 134.09
262 | TOWER D 101 SH CURTAIN & MATTRESSES | 0 | Tentative | Material | (M)ROMAN | SQFT | 97.75 | 1.18 | 115.35 | 97.75 | 1.18 | 115.35 | 0 | 1.18 | 0 | 97.75 | 152.19 | 14876.5725 | 0 | 0 | 0 | 97.75 | 97.75 | 115.345 | 115.345
263 | TOWER D 101 SH CURTAIN & MATTRESSES | 0 | Tentative | Material | (M)ROMAN LINING | RMT | 11 | 1.18 | 12.98 | 11 | 1.18 | 12.98 | 0 | 1.18 | 0 | 11 | 151.18 | 1662.98 | 0 | 0 | 0 | 11 | 11 | 12.98 | 12.98
264 | TOWER D 101 SH CURTAIN & MATTRESSES | 0 | Tentative | Material | (M)TRACK AND BRACKET | RFT | 54 | 1.18 | 63.72 | 54 | 1.18 | 63.72 | 0 | 1.18 | 0 | 54 | 253.65 | 13697.1 | 0 | 0 | 0 | 54 | 54 | 63.72 | 63.72
265 | TOWER D 101 SH CURTAIN & MATTRESSES | 0 | Tentative | Labour | (L)CHARGES FOR ARABIAN PATTERN STITCHING | PART | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 350 | 11550 | 0 | 0 | 0 | 33 | 33 | 0 | 0