## Task Details638476707871705389_
Task Details
Project Name : GREENWOODS AARANYA
Task Name : TOWER D
Total Records: 1054 Records 1 to 1054
Page 1 of 1
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
TOWER D | 0 |  | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D BASEMENT | 0 |  | 17 Mar 2020 |  | 07 Jul 2021 |  | 0 | 0 | 477 | 0
TOWER D BASEMENT CIVIL WORK | 0 |  | 17 Mar 2020 |  | 16 Jul 2021 |  | 0 | 0 | 486 | 0
TOWER D BASEMENT RCC WORK | 0 |  | 17 Mar 2020 |  | 16 Jul 2021 |  | 0 | 0 | 486 | 0
TOWER D BASEMENT RCC WORK FOR SLAB | 16052.019 | SQFT | 17 Mar 2020 |  | 20 Oct 2021 |  | 0 | 0 | 582 | 0
TOWER D BASEMENT THREADING WORK | 1 | NOS |  |  | 16 Jul 2021 |  | 0 | 0 | 44391 | 0
TOWER D BASEMENT RCC WORK REBARING WORK | 1 | NOS | 17 Mar 2020 |  | 26 Mar 2022 |  | 0 | 0 | 739 | 0
TOWER D BASEMENT PLASTER WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT PLASTER WORK | 16052.019 | SQFT | 17 Mar 2020 |  | 23 Feb 2024 |  | 0 | 0 | 1438 | 0
TOWER D BASEMENT CIVIL WORK REBARING WORK | 0 |  | 17 Mar 2020 |  | 13 Sep 2021 |  | 0 | 0 | 545 | 0
TOWER D BASEMENT CIVIL WORK REBARING WORK | 1 | NOS | 17 Mar 2020 |  | 13 Sep 2021 |  | 0 | 0 | 545 | 0
TOWER D BASEMENT MASONRY WORK | 0 |  | 17 Mar 2020 |  | 31 May 2023 |  | 0 | 0 | 1170 | 0
TOWER D BASEMENT MASONRY WORK | 1 | SQFT | 17 Mar 2020 |  | 31 May 2023 |  | 0 | 0 | 1170 | 0
TOWER D BASEMENT FINISHING WORK | 0 |  |  |  | 07 Jul 2021 |  | 0 | 0 | 44382 | 0
TOWER D BASEMENT WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  | 07 Jul 2021 |  | 0 | 0 | 477 | 0
TOWER D BASEMENT WATERPROOFING WORK | 9500 | SQFT |  |  | 07 Jul 2021 |  | 0 | 0 | 44382 | 0
TOWER D BASEMENT PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT FLOOR PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT FLOOR HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT COMMON WORK | 0 |  | 17 Mar 2020 |  | 06 Sep 2021 |  | 0 | 0 | 538 | 0
TOWER D BASEMENT COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D BASEMENT COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 06 Sep 2021 |  | 0 | 0 | 538 | 0
TOWER D BASEMENT COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 06 Sep 2021 |  | 0 | 0 | 538 | 0
TOWER D GROUND FLOOR | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D GROUND FLOOR CIVIL WORK | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D GROUND FLOOR RCC WORK | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D GROUND FLOOR RCC WORK FOR SLAB | 5771.78 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR RCC WORK THREADING WORK | 1 | NOS | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR MASONRY WORK | 5771.78 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR PLASTER WORK | 0 |  |  |  | 09 Feb 2023 |  | 0 | 0 | 44964 | 0
TOWER D GROUND FLOOR PLASTER WORK | 5771.78 | SQFT |  |  | 09 Feb 2023 |  | 0 | 0 | 44964 | 0
TOWER D GROUND FLOOR FINISHING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR WATERPROOFING WORK | 9800 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR PAINT WORK | 15500 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  | 25 Jan 2023 |  | 0 | 0 | 1044 | 0
TOWER D GROUND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 25 Jan 2023 |  | 0 | 0 | 1044 | 0
TOWER D GROUND FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D GROUND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D 1ST FLOOR CIVIL WORK | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D 1ST FLOOR RCC WORK | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Nov 2021 |  | 0 | 0 | 44499 | 0
TOWER D 1ST FLOOR RCC WORK THREADING WORK | 1 | NOS | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR RCC WORK SAFETY WORK | 1 | NOS | 17 Mar 2020 |  | 20 Apr 2022 |  | 0 | 0 | 764 | 0
TOWER D 1ST FLOOR MASONRY WORK | 0 |  |  |  | 08 Jul 2022 |  | 0 | 0 | 44748 | 0
TOWER D 1ST FLOOR MASONRY WORK | 5771.78 | SQFT |  |  | 08 Jul 2022 |  | 0 | 0 | 44748 | 0
TOWER D 1ST FLOOR PLASTER WORK | 0 |  |  |  | 14 Dec 2022 |  | 0 | 0 | 44907 | 0
TOWER D 1ST FLOOR PLASTER WORK | 1 | SQFT |  |  | 14 Dec 2022 |  | 0 | 0 | 44907 | 0
TOWER D 1ST FLOOR CIVIL EXTRA WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR CIVIL EXTRA WORK | 1 | SQFT | 17 Mar 2020 |  | 27 Dec 2023 |  | 0 | 0 | 1380 | 0
TOWER D 101 | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 101 PLUMBING WORK | 0 |  | 17 Mar 2020 |  | 06 Jul 2023 |  | 0 | 0 | 1206 | 0
TOWER D 101 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  | 06 Jul 2023 |  | 0 | 0 | 1206 | 0
TOWER D 101 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 101 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 101 FLOORING &AMP; DEDO WORK | 0 |  | 17 Mar 2020 |  | 28 Aug 2023 |  | 0 | 0 | 1259 | 0
TOWER D 101 FLOORING & DEDO WORK | 1 | SQFT | 17 Mar 2020 |  | 28 Aug 2023 |  | 0 | 0 | 1259 | 0
TOWER D 101 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  | 24 Feb 2024 |  | 0 | 0 | 1439 | 0
TOWER D 101WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  | 25 Oct 2023 |  | 0 | 0 | 1317 | 0
TOWER D 101WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  | 25 Oct 2023 |  | 0 | 0 | 1317 | 0
TOWER D 101 SH | 0 |  | 17 Mar 2020 |  | 18 Aug 2023 |  | 0 | 0 | 1249 | 0
TOWER D 101 SH PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH CP & SANITARY FITTINGS | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH PLUMBING WORK | 0 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH CONSULTANCY CHARGES | 0 |  | 17 Mar 2020 |  | 18 Aug 2023 |  | 0 | 0 | 1249 | 0
TOWER D 101 SH CONSULTANCY CHARGES | 1 | NOS | 17 Mar 2020 |  | 18 Aug 2023 |  | 0 | 0 | 1249 | 0
TOWER D 101 SH PUNNING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH PUNNING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 20 Oct 2023 |  | 0 | 0 | 1312 | 0
TOWER D 101 SH ELECTRIC WORK | 0 | NOS | 17 Mar 2020 |  | 20 Oct 2023 |  | 0 | 0 | 1312 | 0
TOWER D 101 SH FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  | 28 Aug 2023 |  | 0 | 0 | 1259 | 0
TOWER D 101 SH FLOORING & DEDO WORK | 1 | SQFT | 17 Mar 2020 |  | 28 Aug 2023 |  | 0 | 0 | 1259 | 0
TOWER D 101 SH HVAC WORK | 0 |  | 17 Mar 2020 |  | 06 Oct 2023 |  | 0 | 0 | 1298 | 0
TOWER D 101 SH HVAC WORK | 1 | NOS | 17 Mar 2020 |  | 06 Oct 2023 |  | 0 | 0 | 1298 | 0
TOWER D 101 SH COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH ANTITERMITE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  | 12 Feb 2024 |  | 0 | 0 | 1427 | 0
TOWER D 101 SH COMMON FABRICATION WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH COMMON MISC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH COMMON MISC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH FURNITURE WORK | 0 |  | 17 Mar 2020 |  | 01 Sep 2023 |  | 0 | 0 | 1263 | 0
TOWER D 101 SH FURNITURE WORK | 0 | NOS | 17 Mar 2020 |  | 01 Sep 2023 |  | 0 | 0 | 1263 | 0
TOWER D 101 SH WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  | 31 Aug 2023 |  | 0 | 0 | 1262 | 0
TOWER D 101 SH DRILLING WORK | 1 | NOS | 17 Mar 2020 |  | 31 Aug 2023 |  | 0 | 0 | 1262 | 0
TOWER D 101 SH WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  | 04 Sep 2023 |  | 0 | 0 | 1266 | 0
TOWER D 101 SH AUTOMATION WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH AUTOMATION WORK | 0 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH PAINT WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH TEXTURE WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 101 SH ALUMINIUM WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 | 0 |  | 17 Mar 2020 |  | 15 Oct 2022 |  | 0 | 0 | 942 | 0
TOWER D 102 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  | 31 Aug 2023 |  | 0 | 0 | 1262 | 0
TOWER D 102 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  | 31 Aug 2023 |  | 0 | 0 | 1262 | 0
TOWER D 102 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  | 04 Sep 2023 |  | 0 | 0 | 1266 | 0
TOWER D 102 PLUMBING WORK | 0 |  | 17 Mar 2020 |  | 17 Apr 2023 |  | 0 | 0 | 1126 | 0
TOWER D 102 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  | 17 Apr 2023 |  | 0 | 0 | 1126 | 0
TOWER D 102 CP & SANITARY FITTINGS | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 15 Oct 2022 |  | 0 | 0 | 942 | 0
TOWER D 102 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 15 Oct 2022 |  | 0 | 0 | 942 | 0
TOWER D 102 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  | 26 May 2023 |  | 0 | 0 | 1165 | 0
TOWER D 102 FLOORING & DEDO WORK | 1 | SQFT | 17 Mar 2020 |  | 26 May 2023 |  | 0 | 0 | 1165 | 0
TOWER D 102 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  | 24 Feb 2024 |  | 0 | 0 | 1439 | 0
TOWER D 102 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 ALUMINUM WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 PAINT WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 HVAC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 COMMON WORK | 0 |  | 17 Mar 2020 |  | 28 Mar 2023 |  | 0 | 0 | 1106 | 0
TOWER D 102 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  | 28 Mar 2023 |  | 0 | 0 | 1106 | 0
TOWER D 102 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 102 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 25 Dec 2021 |  | 0 | 0 | 648 | 0
TOWER D 1ST FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  | 25 Jan 2023 |  | 0 | 0 | 1044 | 0
TOWER D 1ST FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 25 Jan 2023 |  | 0 | 0 | 1044 | 0
TOWER D 1ST FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR COMMON FLOORING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1ST FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 25 Dec 2021 |  | 0 | 0 | 648 | 0
TOWER D 1ST FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 25 Dec 2021 |  | 0 | 0 | 648 | 0
TOWER D 2ND FLOOR | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D 2ND FLOOR CIVIL WORK | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D 2ND FLOOR RCC WORK | 0 |  |  |  | 17 Mar 2020 |  | 0 | 0 | 43905 | 0
TOWER D 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Nov 2021 |  | 0 | 0 | 44499 | 0
TOWER D 2ND FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 17 Mar 2020 |  | 16 Jul 2023 |  | 0 | 0 | 1216 | 0
TOWER D 2ND FLOOR MASONRY WORK | 0 |  |  |  | 01 Aug 2022 |  | 0 | 0 | 44772 | 0
TOWER D 2ND FLOOR MASONRY WORK | 5771.78 | SQFT |  |  | 01 Aug 2022 |  | 0 | 0 | 44772 | 0
TOWER D 2ND FLOOR PLASTER WORK | 0 |  |  |  | 14 Dec 2022 |  | 0 | 0 | 44907 | 0
TOWER D 2ND FLOOR PLASTER WORK | 1 | SQFT |  |  | 14 Dec 2022 |  | 0 | 0 | 44907 | 0
TOWER D 2ND FLOOR CIVIL EXTRA WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR CIVIL EXTRA WORK | 1 | SQFT | 17 Mar 2020 |  | 27 Dec 2023 |  | 0 | 0 | 1380 | 0
TOWER D 201 | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 201 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  | 18 Jan 2024 |  | 0 | 0 | 1402 | 0
TOWER D 201 CP & SANITARY FITTINGS | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 201 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 201 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 FLOORING & DEDO WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 HVAC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 201 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 202 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  | 13 Apr 2023 |  | 0 | 0 | 1122 | 0
TOWER D 202 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  | 13 Apr 2023 |  | 0 | 0 | 1122 | 0
TOWER D 202 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  | 18 Jan 2024 |  | 0 | 0 | 1402 | 0
TOWER D 202 CP & SANITARY FITTINGS | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 202 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 202 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 FLOORING & DEDO WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 HVAC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 202 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 2ND FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D 2ND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 17 Mar 2020 |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 3RD FLOOR CIVIL WORK | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 3RD FLOOR RCC WORK | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 3RD FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 30 Mar 2022 |  | 0 | 0 | 743 | 0
TOWER D 3RD FIRE AND SAFETY WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR MASONRY WORK | 0 |  |  |  | 30 Sep 2022 |  | 0 | 0 | 44832 | 0
TOWER D 3RD FLOOR MASONRY WORK | 5719.378 | SQFT |  |  | 30 Sep 2022 |  | 0 | 0 | 44832 | 0
TOWER D 3RD FLOOR PLASTER WORK | 0 |  |  |  | 14 Dec 2022 |  | 0 | 0 | 44907 | 0
TOWER D 3RD FLOOR PLASTER WORK | 1 | SQFT |  |  | 14 Dec 2022 |  | 0 | 0 | 44907 | 0
TOWER D 3RD FLOOR CIVIL EXTRA WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR CIVIL EXTRA WORK | 1 | SQFT | 17 Mar 2020 |  | 27 Dec 2023 |  | 0 | 0 | 1380 | 0
TOWER D 301 | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 301 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 301 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 301 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 FLOORING & DEDO WORK | 0 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 301 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 302 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 302 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 26 Mar 2023 |  | 0 | 0 | 1104 | 0
TOWER D 302 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 FLOORING & DEDO WORK | 0 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 302 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 31 Mar 2022 |  | 0 | 0 | 744 | 0
TOWER D 3RD FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 3RD FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 3RD FLOOR ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 31 Mar 2022 |  | 0 | 0 | 744 | 0
TOWER D 3RD FLOOR ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 31 Mar 2022 |  | 0 | 0 | 744 | 0
TOWER D 4TH FLOOR | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 4TH FLOOR CIVIL WORK | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 4TH FLOOR RCC WORK | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 4TH FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 07 Sep 2022 |  | 0 | 0 | 904 | 0
TOWER D 4TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 17 Mar 2020 |  | 20 Jul 2023 |  | 0 | 0 | 1220 | 0
TOWER D 4TH FLOOR MASONRY WORK | 0 |  |  |  | 22 Dec 2022 |  | 0 | 0 | 44915 | 0
TOWER D 4TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  | 22 Dec 2022 |  | 0 | 0 | 44915 | 0
TOWER D 4TH FLOOR PLASTER WORK | 0 |  |  |  | 31 Jul 2023 |  | 0 | 0 | 45136 | 0
TOWER D 4TH FLOOR PLASTER WORK | 1 | SQFT |  |  | 31 Jul 2023 |  | 0 | 0 | 45136 | 0
TOWER D 4TH FLOOR CIVIL EXTRA WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 4TH FLOOR CIVIL EXTRA WORK | 1 | SQFT | 17 Mar 2020 |  | 27 Dec 2023 |  | 0 | 0 | 1380 | 0
TOWER D 401 | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 401 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 401 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 401 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 401 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 402 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 402 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 402 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 402 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 4TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 13 Jul 2022 |  | 0 | 0 | 848 | 0
TOWER D 4TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 4TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 4TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 4TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 4TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 4TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 13 Jul 2022 |  | 0 | 0 | 848 | 0
TOWER D 4TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 13 Jul 2022 |  | 0 | 0 | 848 | 0
TOWER D 5TH FLOOR | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 5TH FLOOR CIVIL WORK | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 5TH FLOOR RCC WORK | 0 |  |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 07 Mar 2022 |  | 0 | 0 | 44625 | 0
TOWER D 5TH FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 07 Sep 2022 |  | 0 | 0 | 904 | 0
TOWER D 5TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 17 Mar 2020 |  | 10 Apr 2023 |  | 0 | 0 | 1119 | 0
TOWER D 5TH FLOOR MASONRY WORK | 0 |  |  |  | 22 Dec 2022 |  | 0 | 0 | 44915 | 0
TOWER D 5TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  | 22 Dec 2022 |  | 0 | 0 | 44915 | 0
TOWER D 5TH FLOOR PLASTER WORK | 0 |  |  |  | 31 Jul 2023 |  | 0 | 0 | 45136 | 0
TOWER D 5TH FLOOR PLASTER WORK | 1 | SQFT |  |  | 31 Jul 2023 |  | 0 | 0 | 45136 | 0
TOWER D 5TH FLOOR CIVIL EXTRA WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 5TH FLOOR CIVIL EXTRA WORK | 1 | SQFT | 17 Mar 2020 |  | 27 Dec 2023 |  | 0 | 0 | 1380 | 0
TOWER D 501 | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 501 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 501 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 501 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 501 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 502 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 502 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 502 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 502 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 5TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 11 Sep 2022 |  | 0 | 0 | 908 | 0
TOWER D 5TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 5TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 5TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 5TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 5TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 5TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 11 Sep 2022 |  | 0 | 0 | 908 | 0
TOWER D 5TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 11 Sep 2022 |  | 0 | 0 | 908 | 0
TOWER D 6TH FLOOR | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 6TH FLOOR CIVIL WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 6TH FLOOR RCC WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 6TH FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 27 Nov 2022 |  | 0 | 0 | 985 | 0
TOWER D 6TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 17 Mar 2020 |  | 18 Feb 2023 |  | 0 | 0 | 1068 | 0
TOWER D 6TH FLOOR MASONRY WORK | 0 |  |  |  | 21 Feb 2023 |  | 0 | 0 | 44976 | 0
TOWER D 6TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  | 21 Feb 2023 |  | 0 | 0 | 44976 | 0
TOWER D 6TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 6TH FLOOR PLASTER WORK | 1 | SQFT |  |  | 04 Jan 2024 |  | 0 | 0 | 45293 | 0
TOWER D 601 | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 601 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 601 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 601 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 601 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 602 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 602 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Jul 2023 |  | 0 | 0 | 1205 | 0
TOWER D 602 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 602 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 6TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 17 Nov 2022 |  | 0 | 0 | 975 | 0
TOWER D 6TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 6TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 6TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 6TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 6TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 6TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 17 Nov 2022 |  | 0 | 0 | 975 | 0
TOWER D 6TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 17 Nov 2022 |  | 0 | 0 | 975 | 0
TOWER D 7TH FLOOR | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 7TH FLOOR CIVIL WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 7TH FLOOR RCC WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 7TH FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 27 Nov 2022 |  | 0 | 0 | 985 | 0
TOWER D 7TH FLOOR RCC WORK SAFETY WORK | 0 | NOS | 17 Mar 2020 |  | 11 Oct 2023 |  | 0 | 0 | 1303 | 0
TOWER D 7TH FLOOR MASONRY WORK | 0 |  |  |  | 16 Feb 2023 |  | 0 | 0 | 44971 | 0
TOWER D 7TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  | 16 Feb 2023 |  | 0 | 0 | 44971 | 0
TOWER D 7TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 7TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 701 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 702 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 7TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 08 Dec 2022 |  | 0 | 0 | 996 | 0
TOWER D 7TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 7TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 7TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 7TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 7TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 7TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 08 Dec 2022 |  | 0 | 0 | 996 | 0
TOWER D 7TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 08 Dec 2022 |  | 0 | 0 | 996 | 0
TOWER D 8TH FLOOR | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 8TH FLOOR CIVIL WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 8TH FLOOR RCC WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER D 8TH FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 17 Apr 2023 |  | 0 | 0 | 1126 | 0
TOWER D 8TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 17 Mar 2020 |  | 12 Jan 2024 |  | 0 | 0 | 1396 | 0
TOWER D 8TH FLOOR MASONRY WORK | 0 |  |  |  | 20 Sep 2023 |  | 0 | 0 | 45187 | 0
TOWER D 8TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  | 20 Sep 2023 |  | 0 | 0 | 45187 | 0
TOWER D 8TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 8TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 801 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 01 Mar 2024 |  | 0 | 0 | 1445 | 0
TOWER D 802 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 802 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 8TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 20 Feb 2023 |  | 0 | 0 | 1070 | 0
TOWER D 8TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 8TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 8TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 8TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 8TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 8TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 20 Feb 2023 |  | 0 | 0 | 1070 | 0
TOWER D 8TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 20 Feb 2023 |  | 0 | 0 | 1070 | 0
TOWER D 9TH FLOOR | 0 |  |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 9TH FLOOR CIVIL WORK | 0 |  |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 9TH FLOOR RCC WORK | 0 |  |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 9TH FLOOR RCC WORK THREADING | 1 | NOS | 17 Mar 2020 |  | 17 Apr 2023 |  | 0 | 0 | 1126 | 0
TOWER D 9TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 17 Mar 2020 |  | 11 Oct 2023 |  | 0 | 0 | 1303 | 0
TOWER D 9TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 901 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 DRILLING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 902 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  | 02 May 2023 |  | 0 | 0 | 1141 | 0
TOWER D 9TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 9TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 9TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  | 02 May 2023 |  | 0 | 0 | 1141 | 0
TOWER D 9TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 02 May 2023 |  | 0 | 0 | 1141 | 0
TOWER D 10TH FLOOR | 0 |  |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 10TH FLOOR CIVIL WORK | 0 |  |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 10TH FLOOR RCC WORK | 0 |  |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 17 Nov 2022 |  | 0 | 0 | 44880 | 0
TOWER D 10TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1001 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 CARPENTRY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1002 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 10TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 11TH FLOOR | 0 |  |  |  | 19 Oct 2023 |  | 0 | 0 | 45216 | 0
TOWER D 11TH FLOOR CIVIL WORK | 0 |  |  |  | 19 Oct 2023 |  | 0 | 0 | 45216 | 0
TOWER D 11TH FLOOR RCC WORK | 0 |  |  |  | 19 Oct 2023 |  | 0 | 0 | 45216 | 0
TOWER D 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 04 Jan 2024 |  | 0 | 0 | 45293 | 0
TOWER D 11TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1101 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1102 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 11TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 01 Mar 2024 |  | 0 | 0 | 1445 | 0
TOWER D 12TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 10 Feb 2024 |  | 0 | 0 | 45330 | 0
TOWER D 12TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 17 Mar 2020 |  | 06 Feb 2024 |  | 0 | 0 | 1421 | 0
TOWER D 12TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1201 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1202 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 17 Mar 2020 |  | 05 Mar 2024 |  | 0 | 0 | 1449 | 0
TOWER D 12TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 12TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  | 01 Mar 2024 |  | 0 | 0 | 1445 | 0
TOWER D 13TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 21 Mar 2024 |  | 0 | 0 | 45370 | 0
TOWER D 13TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 17 Mar 2020 |  | 24 Feb 2024 |  | 0 | 0 | 1439 | 0
TOWER D 13TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1301 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1302 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 13TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1401 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1402 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 14TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1501 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1502 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 15TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1601 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 WATERPROOFING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1602 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 16TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR MASONRY WORK | 5719.378 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1701 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1702 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 17TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR CIVIL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR MASONRY WORK | 0 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1801 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 WATERPROOFING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 PLUMBING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 PLUMBING WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 FLOORING & DEDO WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 CARPENTRY WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 ALUMINIUM DOOR & WINDOW | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 PAINT WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 HVAC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 COMMON RAILING WORK | 1 | RFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 COMMON FALSE CEILING WORK | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 COMMON FABRICATION WORK | 1 | NOS | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 1802 ANTI TERMITE TREATMENT | 1 | SQFT | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR COMMON WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR COMMON FLOORING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR COMMON RAILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0
TOWER D 18TH FLOOR COMMON ELECTRIC WORK | 0 |  | 17 Mar 2020 |  |  |  | 0 | 0 | 0 | 0