## Task Details638575868421426954_
Task Details
Project Name : NEPTUNE TRION EXP
Task Name : All
Total Records: 3593 Records 1 to 3593
Page 1 of 1
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
EXCAVATION | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
EXCAVATION WORK | 1 | CMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER A LOWER BASEMENT | 0 |  |  |  | 27 Jun 2022 |  | 0 | 0 | 44737 | 0
TOWER A LOWER BASEMENT CIVIL WORK | 0 |  | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER A LOWER BASEMENT MASONRY WORK | 0 |  |  |  | 27 Jun 2022 |  | 0 | 0 | 44737 | 0
TOWER A LOWER BASEMENT 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER A LOWER BASEMENT RCC WORK | 0 |  |  |  | 22 Nov 2022 |  | 0 | 0 | 44885 | 0
TOWER A LOWER BASEMENT RCC COLUMN | 1 | CMT |  |  | 05 Nov 2023 |  | 0 | 0 | 45233 | 0
TOWER A LOWER BASEMENT RCC RETAINING WALL | 1 | CMT |  |  | 05 Nov 2023 |  | 0 | 0 | 45233 | 0
TOWER A LOWER BASEMENT RCC WORK TRIMIX SMOOTH FINISH | 1 | SQFT | 28 May 2019 |  | 31 Mar 2023 |  | 0 | 0 | 1403 | 0
TOWER A LOWER BASEMENT RCC WORK FOR SLAB_BASEMENT | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 22 Nov 2022 |  | 0 | 0 | 1274 | 0
TOWER A LOWER BASEMENT RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT RCC DRILLING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER A LOWER BASEMENT PLASTER WORK | 0 |  |  |  | 29 Dec 2022 |  | 0 | 0 | 44922 | 0
TOWER A LOWER BASEMENT INTERNAL SINGLE COAT PLASTER | 1 | SQFT |  |  | 29 Dec 2022 |  | 0 | 0 | 44922 | 0
TOWER A LOWER BASEMENT EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT PLUMBING WORK DRAINAGE PLUMBING PVC | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A LOWER BASEMENT ELECTRIC WORK | 0 |  | 28 May 2019 |  | 27 Aug 2022 |  | 0 | 0 | 1187 | 0
TOWER A LOWER BASEMENT ELECTRIC WORK | 1 | NOS | 28 May 2019 |  | 27 Aug 2022 |  | 0 | 0 | 1187 | 0
TOWER A LOWER BASEMENT MISCELLANEOUS WORK | 0 |  |  |  | 20 Jan 2023 |  | 0 | 0 | 44944 | 0
TOWER A LOWER BASEMENT COLOUR WORK | 0 |  | 28 May 2019 |  | 20 Jul 2023 |  | 0 | 0 | 1514 | 0
TOWER A LOWER BASEMENT PAINT WORK | 1 | SQFT | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER A LOWER BASEMENT COLOR WORK APPLY CEILING PUNNING | 1 | SQFT | 28 May 2019 |  | 20 Jul 2023 |  | 0 | 0 | 1514 | 0
TOWER A LOWER BASEMENT WATERROOFING WORK | 0 |  | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER A LOWER BASEMENT WATERROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER A LOWER BASEMENT ANTI TERMITE WORK | 0 |  | 28 May 2019 |  | 22 Apr 2023 |  | 0 | 0 | 1425 | 0
TOWER A LOWER BASEMENT ANTI TERMITE WORK | 1 | SQFT | 28 May 2019 |  | 22 Apr 2023 |  | 0 | 0 | 1425 | 0
TOWER A LOWER BASEMENT FABRICATION WORK | 0 |  | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER A LOWER BASEMENT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER A LOWER BASEMENT FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  | 01 Jul 2022 |  | 0 | 0 | 1130 | 0
TOWER A LOWER BASEMENT FLOORING& DEDO WORK FLOORING & DEDO | 1 | SQFT | 28 May 2019 |  | 01 Jul 2022 |  | 0 | 0 | 1130 | 0
TOWER A UPPER BASEMENT | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER A UPPER BASEMENT CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Jul 2019 |  | 0 | 0 | 59 | 0
TOWER A UPPER BASEMENT MASONRY WORK | 0 |  |  |  | 27 Jun 2022 |  | 0 | 0 | 44737 | 0
TOWER A UPPER BASEMENT 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER A UPPER BASEMENT RCC WORK | 0 |  |  |  | 26 Jul 2019 |  | 0 | 0 | 43670 | 0
TOWER A UPPER BASEMENT RCC WORK | 1 | CMT |  |  | 22 Aug 2023 |  | 0 | 0 | 45158 | 0
TOWER A UPPER BASEMENT RCC WORK FOR TRIMIX | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT RCC WORK FOR RETAINING WALL | 1 | CMT |  |  | 26 Jul 2019 | 26 Jul 2019 | 0 | 0 | 43670 | 43670
TOWER A UPPER BASEMENT RCC WORK FOR SLAB BASEMENT | 1 | SQFT | 28 May 2019 |  | 16 Sep 2020 |  | 0 | 0 | 477 | 0
TOWER A UPPER BASEMENT RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Dec 2023 |  | 0 | 0 | 1648 | 0
TOWER A UPPER BASEMENT RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT ROAD WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT PLASTER WORK | 0 |  |  |  | 29 Dec 2022 |  | 0 | 0 | 44922 | 0
TOWER A UPPER BASEMENT INTERNAL SINGLE COAT PLASTER | 1 | SQFT |  |  | 29 Dec 2022 |  | 0 | 0 | 44922 | 0
TOWER A UPPER BASEMENT EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT PLUMBING WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER A UPPER BASEMENT ELECTRICAL WORK | 0 |  |  |  | 12 Nov 2020 |  | 0 | 0 | 44145 | 0
TOWER A UPPER BASEMENT ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 12 Nov 2020 |  | 0 | 0 | 534 | 0
TOWER A UPPER BASEMENT ELECTRIC WORK | 1 | NOS | 28 May 2019 |  | 27 Aug 2022 |  | 0 | 0 | 1187 | 0
TOWER A UPPER BASEMENT MISCELLANEOUS WORK | 0 |  |  |  | 16 Jun 2022 |  | 0 | 0 | 44726 | 0
TOWER A UPPER BASEMENT COLOUR WORK APPLY CEILING PUNNING | 1 | SQFT | 28 May 2019 |  | 01 Jun 2023 |  | 0 | 0 | 1465 | 0
TOWER A UPPER BASEMENT COLOUR WORK | 0 |  | 28 May 2019 |  | 16 Jun 2022 |  | 0 | 0 | 1115 | 0
TOWER A UPPER BASEMENT PAINT WORK | 1 | SQFT | 28 May 2019 |  | 16 Jun 2022 |  | 0 | 0 | 1115 | 0
TOWER A UPPER BASEMENT FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A UPPER BASEMENT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER A UPPER BASEMENT FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  | 20 Jul 2022 |  | 0 | 0 | 1149 | 0
TOWER A UPPER BASEMENT FLOORING& DEDO WORK FLOORING & DEDO | 1 | SQFT | 28 May 2019 |  | 20 Jul 2022 |  | 0 | 0 | 1149 | 0
TOWER A GROUND FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER A GROUND FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 16 Sep 2019 |  | 0 | 0 | 111 | 0
TOWER A GROUND FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER A GROUND FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER A GROUND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER A GROUND FLOOR 6" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR RCC WORK | 0 |  |  |  | 16 Sep 2019 |  | 0 | 0 | 43722 | 0
TOWER A GROUND FLOOR RCC WORK | 1 | CMT |  |  | 16 Sep 2019 |  | 0 | 0 | 43722 | 0
TOWER A GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 19 Sep 2019 |  | 0 | 0 | 43725 | 0
TOWER A GROUND FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  | 16 Sep 2019 |  | 0 | 0 | 43722 | 0
TOWER A GROUND FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  | 21 Sep 2019 |  | 0 | 0 | 43727 | 0
TOWER A GROUND FLOOR RCC WORK FOR PARKING | 1 | CMT |  |  | 21 Sep 2019 |  | 0 | 0 | 43727 | 0
TOWER A GROUND FLOOR RCC WORK FOR WELDING | 1 | NOS | 28 May 2019 |  | 21 Sep 2019 |  | 0 | 0 | 116 | 0
TOWER A GROUND FLOOR RCC WORK REBARING 12MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER A GROUND FLOOR RCC WORK REBARING 16MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER A GROUND FLOOR RCC WORK REBARING 20MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER A GROUND FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR RCC WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 16 Oct 2021 |  | 0 | 0 | 872 | 0
TOWER A GROUND FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER A GROUND FLOOR PCC WORK | 1 | SQFT | 28 May 2019 |  | 01 Jun 2023 |  | 0 | 0 | 1465 | 0
TOWER A GROUND FLOOR RCC WORK BREAKER | 1 | DAY | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR EXTERNAL DOUBLE COAT PLASTER | 22 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR INTERNAL MALA FINISH PLASTER | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR SHOP NO 21 FACADE WORK | 1 | NOS |  |  | 25 Mar 2022 |  | 0 | 0 | 44643 | 0
TOWER A GROUND FLOOR SHOP NO 22 FACADE WORK | 1 | NOS | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR SHOWROOM A WINDOW WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR PLUMBING WORK | 0 |  | 28 May 2019 |  | 28 Mar 2022 |  | 0 | 0 | 1035 | 0
TOWER A GROUND FLOOR PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 28 Mar 2022 |  | 0 | 0 | 1035 | 0
TOWER A GROUND FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 08 Nov 2022 |  | 0 | 0 | 1260 | 0
TOWER A GROUND FLOOR ELECTRICAL WORK | 0 |  |  |  | 08 Sep 2020 |  | 0 | 0 | 44080 | 0
TOWER A GROUND FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | SQFT | 28 May 2019 |  | 08 Sep 2020 |  | 0 | 0 | 469 | 0
TOWER A GROUND FLOOR ELECTRICAL WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 12 Nov 2020 |  | 0 | 0 | 534 | 0
TOWER A GROUND FLOOR ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 28 Aug 2023 |  | 0 | 0 | 1553 | 0
TRION SITE OFFICE NO 21 ELECTRIC WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TRION SITE OFFICE NO 22 IT WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TRION SITE OFFICE NO 22 ELECTRIC WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 22 Feb 2021 |  | 0 | 0 | 636 | 0
TOWER A GROUND FLOOR COLOUR WORK | 0 |  |  |  | 10 Mar 2022 |  | 0 | 0 | 44628 | 0
TOWER A GROUND FLOOR COLOUR APPLY CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 17 Sep 2023 |  | 0 | 0 | 1573 | 0
TOWER A GROUND FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 10 Mar 2022 |  | 0 | 0 | 1017 | 0
TRION SITE OFFICE NO 21 PAINT WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TRION SITE OFFICE NO 22 PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A GROUND FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A GROUND FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  | 16 Apr 2022 |  | 0 | 0 | 1054 | 0
TOWER A GROUND FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 16 Apr 2022 |  | 0 | 0 | 1054 | 0
TOWER A GROUND FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 22 Feb 2021 |  | 0 | 0 | 636 | 0
TOWER A GROUND FLOOR SHOP NO 18 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2022 |  | 0 | 0 | 1192 | 0
TOWER A GROUND FLOOR SHOP NO 19 & 20 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2022 |  | 0 | 0 | 1192 | 0
TOWER A GROUND FLOOR SHOP NO 23 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2022 |  | 0 | 0 | 1192 | 0
TOWER A GROUND FLOOR SHOP NO 24 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2022 |  | 0 | 0 | 1192 | 0
TOWER A GROUND FLOOR SHOWROOM A ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2022 |  | 0 | 0 | 1192 | 0
TOWER A GROUND FLOOR SHOP NO 22 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 22 Feb 2021 |  | 0 | 0 | 636 | 0
TOWER A GROUND FLOOR SHOP NO 21 ROLLING SHUTTER WORK | 1 | NOS |  |  | 01 Sep 2022 |  | 0 | 0 | 44803 | 0
TOWER A GROUND FLOOR SHOP NO 25 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2022 |  | 0 | 0 | 1192 | 0
TOWER A GROUND FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 25 Jun 2022 |  | 0 | 0 | 1124 | 0
TOWER A GROUND FLOOR FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 25 Jun 2022 |  | 0 | 0 | 1124 | 0
TOWER A GROUND FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A GROUND FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
TOWER A GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
TOWER A GROUND FLOOR BOREWELL WORK | 0 |  | 28 May 2019 |  | 20 Sep 2023 |  | 0 | 0 | 1576 | 0
TOWER A GROUND FLOOR BOREWELL WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2023 |  | 0 | 0 | 1576 | 0
TOWER A GROUND FLOOR CARPENTRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TRION SITE OFFICE NO 22 CARPENTRY WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TRION SITE OFFICE NO 22 FURNITURE WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER A GROUND FLOOR MISCELLANEOUS CIVIL WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR MISCELLANEOUS CIVIL WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  | 28 Dec 2020 |  | 0 | 0 | 580 | 0
TOWER A GROUND FLOOR FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
TOWER A GROUND FLOOR SHOP & SHOWROOM FLOORING | 0 |  | 28 May 2019 |  | 28 Dec 2020 |  | 0 | 0 | 580 | 0
TOWER A GROUND FLOOR SHOP NO 18 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A GROUND FLOOR SHOP NO 19 & 20 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A GROUND FLOOR SHOP NO 23 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A GROUND FLOOR SHOP NO 24 & 25 | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A GROUND FLOOR SHOWROOM A FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TRION SITE OFFICE NO 21 FLOORING WORK | 1 | SQFT |  |  | 06 Sep 2021 |  | 0 | 0 | 44443 | 0
TOWER A GROUND FLOOR SITE OFFICE NO 22 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 Dec 2020 |  | 0 | 0 | 580 | 0
TOWER A 1ST FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER A 1ST FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 14 Feb 2020 |  | 0 | 0 | 262 | 0
TOWER A 1ST FLOOR MASONRY WORK | 0 |  |  |  | 03 Sep 2021 |  | 0 | 0 | 44440 | 0
TOWER A 1ST FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER A 1ST FLOOR DRY WALL WORK | 1 | SQMT | 28 May 2019 |  | 18 Oct 2021 |  | 0 | 0 | 874 | 0
TOWER A 1ST FLOOR BRICK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR RCC WORK | 0 |  |  |  | 14 Feb 2020 |  | 0 | 0 | 43873 | 0
TOWER A 1ST FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Mar 2021 |  | 0 | 0 | 44254 | 0
TOWER A 1ST FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT | 28 May 2019 |  | 14 Feb 2020 |  | 0 | 0 | 262 | 0
TOWER A 1ST FLOOR RCC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 16 Oct 2021 |  | 0 | 0 | 872 | 0
TOWER A 1ST FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER A 1ST FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER A 1ST FLOOR PASAGE RAILING | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER A 1ST FLOOR PASAGE RAILING | 1 | RFT | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER A 1ST FLOOR PLUMBING WORK | 0 |  |  |  | 08 Nov 2022 |  | 0 | 0 | 44871 | 0
TOWER A 1ST FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 08 Nov 2022 |  | 0 | 0 | 1260 | 0
TOWER A 1ST FLOOR COMMON TOILET PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 28 Jul 2023 |  | 0 | 0 | 1522 | 0
TOWER A 1ST FLOOR ELECTRICAL WORK | 0 |  |  |  | 08 Sep 2020 |  | 0 | 0 | 44080 | 0
TOWER A 1ST FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | SQFT | 28 May 2019 |  | 08 Sep 2020 |  | 0 | 0 | 469 | 0
TOWER A 1ST FLOOR ELECTRICAL WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 12 Nov 2020 |  | 0 | 0 | 534 | 0
TOWER A 1ST FLOOR ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 28 Aug 2023 |  | 0 | 0 | 1553 | 0
TOWER A 1ST FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR COLOUR WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER A 1ST FLOOR COLOUR WORK APPLY CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 17 Aug 2023 |  | 0 | 0 | 1542 | 0
TOWER A 1ST FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 1ST FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 1ST FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOWROOM A ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 21 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 22 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 23 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 18 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 19 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 20 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR SHOP NO 17 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER A 1ST FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 1ST FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 1ST FLOOR COMMON TOILET ALUMINUM WORK | 1 | NOS | 28 May 2019 |  | 01 May 2024 |  | 0 | 0 | 1800 | 0
TOWER A 1ST FLOOR COMMON TOILET CARPENTRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR COMMON TOILET CARPENTRY WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER A 1ST FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER A 1ST FLOOR WATERPROOFING WORK TEKIT | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 1ST FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 26 Nov 2021 |  | 0 | 0 | 44524 | 0
TOWER A 1ST FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 30 May 2022 |  | 0 | 0 | 44709 | 0
TOWER A 1ST FLOOR SHOP & SHOWROOM FLOORING WORK | 0 |  | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A 1ST FLOOR SHOP NO 17 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A 1ST FLOOR SHOP NO 18 TO 20 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A 1ST FLOOR SHOP NO 21 TO 23 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 26 Nov 2021 |  | 0 | 0 | 913 | 0
TOWER A 1ST FLOOR SHOWROOM A FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 10 May 2022 |  | 0 | 0 | 1078 | 0
TOWER A 1ST FLOOR COMMON TOILET FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 18 Sep 2023 |  | 0 | 0 | 1574 | 0
GF 9-13 & FF 5-20 FLOORING WORK TEKIT | 1 | SQFT | 28 May 2019 |  | 01 Nov 2023 |  | 0 | 0 | 1618 | 0
TOWER A 2ND FLOOR | 0 |  |  |  | 20 Mar 2020 |  | 0 | 0 | 43908 | 0
TOWER A 2ND FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER A 2ND FLOOR MASONRY WORK | 0 |  |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER A 2ND FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 24 Apr 2021 |  | 0 | 0 | 697 | 0
TOWER A 2ND FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK | 0 |  |  |  | 20 Mar 2020 |  | 0 | 0 | 43908 | 0
TOWER A 2ND FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER A 2ND FLOOR RCC WORK FOR LIFT & PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT | 28 May 2019 |  | 15 Oct 2020 |  | 0 | 0 | 506 | 0
TOWER A 2ND FLOOR RCC WORK FOR TRIMIX SMOOTH FINISH | 1 | SQFT | 28 May 2019 |  | 30 Oct 2020 |  | 0 | 0 | 521 | 0
TOWER A 2ND FLOOR RCC WORK FOR THREADING | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER A 2ND FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER A 2ND FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER A 2ND FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER A 2ND FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 20 Oct 2021 |  | 0 | 0 | 876 | 0
TOWER A 2ND FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER A 2ND FLOOR PLASTER WORK | 0 |  |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER A 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 72 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER A 2ND FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER A 2ND FLOOR PASAGE RAILING | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER A 2ND FLOOR PASAGE RAILING | 1 | RFT | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER A 2ND FLOOR PLUMBING WORK | 0 |  |  |  | 01 Nov 2021 |  | 0 | 0 | 44499 | 0
TOWER A 2ND FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Nov 2021 |  | 0 | 0 | 44499 | 0
TOWER A 2ND FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 08 Nov 2022 |  | 0 | 0 | 1260 | 0
TOWER A 2ND FLOOR ELECTRIC WORK | 0 |  |  |  | 10 Apr 2021 |  | 0 | 0 | 44294 | 0
TOWER A 2ND FLOOR ELECTRIC WORK | 1 | SQFT | 28 May 2019 |  | 01 Feb 2024 |  | 0 | 0 | 1710 | 0
TOWER A 2ND FLOOR ELECTRIC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER A 2ND FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER A 2ND FLOOR COLOR WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR COLOR WORK APPLYING CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR SAFETY | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER A 2ND FLOOR SAFETY | 1 | NOS | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER A 2ND FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 2ND FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 2ND FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 2ND FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 2ND FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER A 2ND FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 2ND FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER A 2ND FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 May 2022 |  | 0 | 0 | 44694 | 0
TOWER A 2ND FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 30 May 2022 |  | 0 | 0 | 44709 | 0
TOWER A 2ND FLOOR SHOP & SHOWROOM FLOORING WORK | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER A 2ND FLOOR SHOWROOM A FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER A 2ND FLOOR SHOP NO 16 TO 18 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 10 Oct 2023 |  | 0 | 0 | 1596 | 0
TOWER A 2ND FLOOR SHOP NO 19 TO 21 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 10 Oct 2023 |  | 0 | 0 | 1596 | 0
TOWER A 3RD FLOOR | 0 |  |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER A 3RD FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 19 Dec 2020 |  | 0 | 0 | 571 | 0
TOWER A 3RD FLOOR MASONRY WORK | 0 |  |  |  | 17 Sep 2021 |  | 0 | 0 | 44454 | 0
TOWER A 3RD FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 17 Sep 2021 |  | 0 | 0 | 843 | 0
TOWER A 3RD FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR RCC WORK | 0 |  |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER A 3RD FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR RCC WORK FOR SLAB - SQ FT | 1 | SQFT |  |  | 18 Mar 2021 |  | 0 | 0 | 44271 | 0
TOWER A 3RD FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR RCC WORK THREADING 20MM | 1 | NOS | 28 May 2019 |  | 19 Dec 2020 |  | 0 | 0 | 571 | 0
TOWER A 3RD FLOOR RCC WORK THREADING 25MM | 1 | NOS | 28 May 2019 |  | 19 Dec 2020 |  | 0 | 0 | 571 | 0
TOWER A 3RD FLOOR RCC WORK THREADING 32MM | 1 | NOS | 28 May 2019 |  | 19 Dec 2020 |  | 0 | 0 | 571 | 0
TOWER A 3RD FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 30 Jan 2021 |  | 0 | 0 | 44224 | 0
Tower A 3RD FLOOR RCC WORK LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 20 Oct 2021 |  | 0 | 0 | 876 | 0
TOWER A 3RD FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER A 3RD FLOOR ROAD WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 522 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR PLUMBING WORK | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A SHOPS TOILETS PROVISIONAL LINES PLUMBING WORK | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A 3RD FLOOR PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 16 May 2022 |  | 0 | 0 | 1084 | 0
TOWER A 3RD FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 08 Nov 2022 |  | 0 | 0 | 1260 | 0
TOWER A 3RD FLOOR ELECTRICAL WORK | 0 |  |  |  | 10 Apr 2021 |  | 0 | 0 | 44294 | 0
TOWER A 3RD FLOOR ELECTRICAL WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER A 3RD FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER A 3RD FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER A 3RD FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER A 3RD FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER A 3RD FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 3RD FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 3RD FLOOR COLOUR WORK | 0 |  | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER A 3RD FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER A 3RD FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 3RD FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 3RD FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR GLASS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR GLASS WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 3RD FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 Aug 2022 |  | 0 | 0 | 44786 | 0
TOWER A 3RD FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 15 Aug 2022 |  | 0 | 0 | 44786 | 0
TOWER A 4TH FLOOR | 0 |  |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER A 4TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 Jan 2021 |  | 0 | 0 | 611 | 0
TOWER A 4TH FLOOR MASONRY WORK | 0 |  |  |  | 03 Sep 2021 |  | 0 | 0 | 44440 | 0
TOWER A 4TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER A 4TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR RCC WORK | 0 |  |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER A 4TH FLOOR RCC COLUMN | 1 | CMT |  |  | 17 Mar 2021 |  | 0 | 0 | 44270 | 0
TOWER A 4TH FLOORRCC WORK FOR SLAB | 1 | SQFT |  |  | 01 May 2021 |  | 0 | 0 | 44315 | 0
TOWER A 4TH FLOORRCC WORK THREADING 20MM | 1 | NOS |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER A 4TH FLOORRCC WORK THREADING 25MM | 1 | NOS |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER A 4TH FLOORRCC WORK THREADING 32MM | 1 | NOS |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER A 4TH FLOORRCC WORK PT CABLE LAYING | 1 | RMT |  |  | 17 Mar 2021 |  | 0 | 0 | 44270 | 0
Tower A 4TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 28 Jan 2021 |  | 0 | 0 | 611 | 0
TOWER A 4TH FLOOR RCC WORK BREAKER | 1 | DAY | 28 May 2019 |  | 13 Feb 2021 |  | 0 | 0 | 627 | 0
TOWER A 4TH FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER A 4TH FLOOR THREADING CHARGES | 1 | NOS | 28 May 2019 |  | 25 Feb 2021 |  | 0 | 0 | 639 | 0
TOWER A 4TH FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER A 4TH PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 72 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 4TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 09 Dec 2022 |  | 0 | 0 | 1291 | 0
TOWER A 4TH FLOOR WATERPROOFING WORK WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 09 Dec 2022 |  | 0 | 0 | 1291 | 0
TOWER A 4TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR PLUMBING WORK | 0 |  |  |  | 02 Apr 2022 |  | 0 | 0 | 44651 | 0
TOWER A 4TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 02 Apr 2022 |  | 0 | 0 | 44651 | 0
TOWER A 4TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 10 Apr 2021 |  | 0 | 0 | 44294 | 0
TOWER A 4TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER A 4TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER A 4TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 4TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 4H FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 4TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 4TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 4TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
FTOWER A 4TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 4TH FLOOR GLASS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR GLASS WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 Aug 2022 |  | 0 | 0 | 44786 | 0
TOWER A 4TH FLOOR FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Aug 2022 |  | 0 | 0 | 1175 | 0
TOWER A 4TH FLOOR TERRACE CABIN FLOORING | 1 | SQFT | 28 May 2019 |  | 15 Jun 2023 |  | 0 | 0 | 1479 | 0
TOWER A 4TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 4TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR | 0 |  |  |  | 11 Apr 2021 |  | 0 | 0 | 44295 | 0
TOWER A 5TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 11 Apr 2021 |  | 0 | 0 | 684 | 0
TOWER A 5TH FLOOR MASONRY WORK | 0 |  |  |  | 26 May 2022 |  | 0 | 0 | 44705 | 0
TOWER A 5TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER A 5TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 26 May 2022 |  | 0 | 0 | 44705 | 0
TOWER A 5TH FLOOR RCC WORK | 0 |  |  |  | 11 Apr 2021 |  | 0 | 0 | 44295 | 0
TOWER A 5TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 11 Apr 2021 |  | 0 | 0 | 44295 | 0
TOWER A 5TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR THREADING 25MM - NOS. | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 06 May 2021 |  | 0 | 0 | 44320 | 0
TOWER A 5TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 06 May 2021 |  | 0 | 0 | 709 | 0
TOWER A 5TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 5TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR PLUMBING WORK | 0 |  |  |  | 03 Dec 2022 |  | 0 | 0 | 44896 | 0
TOWER A 5TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 5TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 03 Dec 2022 |  | 0 | 0 | 1285 | 0
TOWER A 5TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER A 5TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 26 Apr 2021 |  | 0 | 0 | 699 | 0
TOWER A 5TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 5TH FLOOR SAFETY WORK | 0 |  |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER A 5TH FLOOR SAFETY WORK | 1 | SQFT |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER A 5TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 5TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 5TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 5TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 5TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 5TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 5TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 5TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 5TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 5TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 5TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 29 Jan 2024 |  | 0 | 0 | 1707 | 0
TOWER A 5TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 5TH FLOOR SUNK FILLING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR SUNK FILLING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 5TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 15 Dec 2023 |  | 0 | 0 | 45273 | 0
TOWER A 5TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 5TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 5TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 5TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 5TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 6TH FLOOR | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER A 6TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Apr 2021 |  | 0 | 0 | 699 | 0
TOWER A 6TH FLOOR MASONRY WORK | 0 |  |  |  | 20 May 2023 |  | 0 | 0 | 45064 | 0
TOWER A 6TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 20 May 2023 |  | 0 | 0 | 45064 | 0
TOWER A 6TH FLOOR RCC WORK | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER A 6TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 11 Jun 2021 |  | 0 | 0 | 44356 | 0
TOWER A 6TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER A 6TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER A 6TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER A 6TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER A 6TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 06 May 2021 |  | 0 | 0 | 709 | 0
TOWER A 6TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 6TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR PLUMBING WORK | 0 |  |  |  | 20 Dec 2022 |  | 0 | 0 | 44913 | 0
TOWER A 6TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 6TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Dec 2022 |  | 0 | 0 | 1302 | 0
TOWER A 6TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 21 Jul 2021 |  | 0 | 0 | 44396 | 0
TOWER A 6TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 21 Jul 2021 |  | 0 | 0 | 785 | 0
TOWER A 6TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 21 Jul 2021 |  | 0 | 0 | 785 | 0
TOWER A 6TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 6TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 6TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 6TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 6TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 6TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 6TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 6TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 6TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 6TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 6TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 6TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 6TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 6TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 6TH FLOOR SUNK FILLING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR SUNK FILLING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 6TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 15 Dec 2023 |  | 0 | 0 | 45273 | 0
TOWER A 6TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 6TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 6TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 6TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 6TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2023 |  | 0 | 0 | 1662 | 0
TOWER A 7TH FLOOR | 0 |  |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER A 7TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 23 Jun 2021 |  | 0 | 0 | 757 | 0
TOWER A 7TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 7TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER A 7TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 20 May 2023 |  | 0 | 0 | 45064 | 0
TOWER A 7TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR RCC WORK | 0 |  |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER A 7TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 21 Jul 2021 |  | 0 | 0 | 44396 | 0
TOWER A 7TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER A 7TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER A 7TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER A 7TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 18 Aug 2021 |  | 0 | 0 | 44424 | 0
TOWER A 7TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER A 7TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 7TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR PLUMBING WORK | 0 |  |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 7TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 7TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 7TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 7TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 7TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 7TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER A 7TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 7TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 7TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 7TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 7TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 7TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 7TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 7TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 7TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 7TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 7TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER A 7TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 7TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 7TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 19 Feb 2024 |  | 0 | 0 | 45339 | 0
TOWER A 7TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 19 Feb 2024 |  | 0 | 0 | 1728 | 0
TOWER A 7TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 19 Feb 2024 |  | 0 | 0 | 1728 | 0
TOWER A 7TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 19 Feb 2024 |  | 0 | 0 | 1728 | 0
TOWER A 7TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 19 Feb 2024 |  | 0 | 0 | 1728 | 0
TOWER A 7TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 19 Feb 2024 |  | 0 | 0 | 1728 | 0
TOWER A 8TH FLOOR | 0 |  |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER A 8TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 03 Jul 2021 |  | 0 | 0 | 767 | 0
TOWER A 8TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 8TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER A 8TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 16 Aug 2023 |  | 0 | 0 | 45152 | 0
TOWER A 8TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR RCC WORK | 0 |  |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER A 8TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 29 Aug 2021 |  | 0 | 0 | 44435 | 0
TOWER A 8TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER A 8TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER A 8TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER A 8TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 10 Sep 2021 |  | 0 | 0 | 44447 | 0
TOWER A 8TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER A 8TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 8TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR PLUMBING WORK | 0 |  |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 8TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 8TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 8TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 8TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 8TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 8TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 23 Nov 2022 |  | 0 | 0 | 1275 | 0
TOWER A 8TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 8TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 8TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER A 8TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 8TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 8TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 8TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 8TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 11 Mar 2024 |  | 0 | 0 | 45360 | 0
TOWER A 8TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 11 Mar 2024 |  | 0 | 0 | 1749 | 0
TOWER A 8TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 11 Mar 2024 |  | 0 | 0 | 1749 | 0
TOWER A 8TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 11 Mar 2024 |  | 0 | 0 | 1749 | 0
TOWER A 8TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 11 Mar 2024 |  | 0 | 0 | 1749 | 0
TOWER A 8TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 11 Mar 2024 |  | 0 | 0 | 1749 | 0
TOWER A 9TH FLOOR | 0 |  |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 9TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Oct 2021 |  | 0 | 0 | 857 | 0
TOWER A 9TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 9TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER A 9TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 11 Mar 2024 |  | 0 | 0 | 45360 | 0
TOWER A 9TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  | 11 Mar 2024 |  | 0 | 0 | 1749 | 0
TOWER A 9TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK | 0 |  |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 9TH FLOOR RCC WORK FOR RCC COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER A 9TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 23 Oct 2021 |  | 0 | 0 | 44490 | 0
TOWER A 9TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER A 9TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 9TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 9TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 9TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 06 Oct 2021 |  | 0 | 0 | 44473 | 0
TOWER A 9TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 06 Oct 2021 |  | 0 | 0 | 44473 | 0
TOWER A 9TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER A 9TH FLOOR SAFETY WORK | 0 |  |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER A 9TH FLOOR SAFETY WORK | 1 | SQFT |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER A 9TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 23 Nov 2022 |  | 0 | 0 | 1275 | 0
TOWER A 9TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 9TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 9TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 9TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 9TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 9TH FLOOR OFFICE NO 01 TO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR | 0 |  |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER A 10TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 13 Oct 2021 |  | 0 | 0 | 869 | 0
TOWER A 10TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 10TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 10TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR RCC WORK | 0 |  |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER A 10TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 28 Nov 2021 |  | 0 | 0 | 44526 | 0
TOWER A 10TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER A 10TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER A 10TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER A 10TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 02 Dec 2021 |  | 0 | 0 | 44530 | 0
TOWER A 10TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER A 10TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER A 10TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 10TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 10TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 10TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 28 Nov 2021 |  | 0 | 0 | 44526 | 0
TOWER A 10TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 28 Nov 2021 |  | 0 | 0 | 44526 | 0
TOWER A 10TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 08 Jan 2022 |  | 0 | 0 | 956 | 0
TOWER A 10TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 08 Jan 2022 |  | 0 | 0 | 956 | 0
TOWER A 10TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 08 Jan 2022 |  | 0 | 0 | 956 | 0
TOWER A 10TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 23 Nov 2022 |  | 0 | 0 | 1275 | 0
TOWER A 10TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 10TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 10TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 10TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 10TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 10TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR | 0 |  |  |  | 13 Dec 2021 |  | 0 | 0 | 44541 | 0
TOWER A 11TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 13 Dec 2021 |  | 0 | 0 | 930 | 0
TOWER A 11TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 11TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 11TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 14 May 2024 |  | 0 | 0 | 45424 | 0
TOWER A 11TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR RCC WORK | 0 |  |  |  | 13 Dec 2021 |  | 0 | 0 | 44541 | 0
TOWER A 11TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 13 Dec 2021 |  | 0 | 0 | 44541 | 0
TOWER A 11TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 13 Dec 2021 |  | 0 | 0 | 44541 | 0
TOWER A 11TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 13 Dec 2021 |  | 0 | 0 | 44541 | 0
TOWER A 11TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 10 Jan 2022 |  | 0 | 0 | 44569 | 0
TOWER A 11TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER A 11TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 11TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 11TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 11TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 20 Jan 2022 |  | 0 | 0 | 968 | 0
TOWER A 11TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 20 Jan 2022 |  | 0 | 0 | 968 | 0
TOWER A 11TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 19 Apr 2022 |  | 0 | 0 | 1057 | 0
TOWER A 11TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 23 Nov 2022 |  | 0 | 0 | 1275 | 0
TOWER A 11TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 11TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 19 Apr 2022 |  | 0 | 0 | 1057 | 0
TOWER A 11TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 19 Apr 2022 |  | 0 | 0 | 1057 | 0
TOWER A 11TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 11TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 11TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 11TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 11TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR | 0 |  |  |  | 20 Jan 2022 |  | 0 | 0 | 44579 | 0
TOWER A 12TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 20 Jan 2022 |  | 0 | 0 | 968 | 0
TOWER A 12TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 12TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 12TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 14 May 2024 |  | 0 | 0 | 45424 | 0
TOWER A 12TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR RCC WORK | 0 |  |  |  | 20 Jan 2022 |  | 0 | 0 | 44579 | 0
TOWER A 12TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 20 Jan 2022 |  | 0 | 0 | 44579 | 0
TOWER A 12TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 20 Jan 2022 |  | 0 | 0 | 44579 | 0
TOWER A 12TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 20 Jan 2022 |  | 0 | 0 | 44579 | 0
TOWER A 12TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 20 Feb 2022 |  | 0 | 0 | 44610 | 0
TOWER A 12TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER A 12TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 12TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 12TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 12TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 23 Feb 2022 |  | 0 | 0 | 1002 | 0
TOWER A 12TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 23 Feb 2022 |  | 0 | 0 | 1002 | 0
TOWER A 12TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 23 Nov 2022 |  | 0 | 0 | 1275 | 0
TOWER A 12TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 23 Nov 2022 |  | 0 | 0 | 1275 | 0
TOWER A 12TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 12TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 12TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER A 12TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER A 12TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER A 12TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 12TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 12TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A 13TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER A 13TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 13TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 13TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 14 May 2024 |  | 0 | 0 | 45424 | 0
TOWER A 13TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR RCC WORK | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A 13TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 May 2022 |  | 0 | 0 | 44680 | 0
TOWER A 13TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A 13TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A 13TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER A 13TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 25 Apr 2022 |  | 0 | 0 | 44674 | 0
TOWER A 13TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 13TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR THREADING CHARGES | 1 | NOS | 28 May 2019 |  | 08 Apr 2022 |  | 0 | 0 | 1046 | 0
TOWER A 13TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 13TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 13TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2024 |  | 0 | 0 | 1850 | 0
TOWER A 13TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 25 Apr 2022 |  | 0 | 0 | 1063 | 0
TOWER A 13TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 25 Apr 2022 |  | 0 | 0 | 1063 | 0
TOWER A 13TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER A 13TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER A 13TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 13TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 28 Mar 2024 |  | 0 | 0 | 1766 | 0
TOWER A 13TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOORFALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 13TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER A 13TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER A 13TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 13TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR | 0 |  |  |  | 25 Apr 2022 |  | 0 | 0 | 44674 | 0
TOWER A 14TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 25 Apr 2022 |  | 0 | 0 | 1063 | 0
TOWER A 14TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER A 14TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 14TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR RCC WORK | 0 |  |  |  | 25 Apr 2022 |  | 0 | 0 | 44674 | 0
TOWER A 14TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Jul 2022 |  | 0 | 0 | 44770 | 0
TOWER A 14TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 25 Apr 2022 |  | 0 | 0 | 44674 | 0
TOWER A 14TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 25 Apr 2022 |  | 0 | 0 | 44674 | 0
TOWER A 14TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 25 Apr 2022 |  | 0 | 0 | 44674 | 0
TOWER A 14TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER A 14TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 08 May 2023 |  | 0 | 0 | 45052 | 0
TOWER A 14TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 14TH FLOOR INTERNAL MAL FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 14TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 13 Jul 2022 |  | 0 | 0 | 1142 | 0
TOWER A 14TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 13 Jul 2022 |  | 0 | 0 | 1142 | 0
TOWER A 14TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER A 14TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER A 14TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 14TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER A 14TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER A 14TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 28 Mar 2024 |  | 0 | 0 | 1766 | 0
TOWER A 14TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 14TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 14TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER A 15TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER A 15TH FLOOR MASONRY WORK | 0 |  |  |  | 08 May 2023 |  | 0 | 0 | 45052 | 0
TOWER A 15TH FLOOR 9" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR 4.5" AAC BLOCK WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 15TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR RCC WORK | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER A 15TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 22 Oct 2022 |  | 0 | 0 | 44854 | 0
TOWER A 15TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 23 Jul 2022 |  | 0 | 0 | 44763 | 0
TOWER A 15TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 23 Jul 2022 |  | 0 | 0 | 44763 | 0
TOWER A 15TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER A 15TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 08 May 2023 |  | 0 | 0 | 45052 | 0
TOWER A 15TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 15TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 15TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 24 Sep 2022 |  | 0 | 0 | 1215 | 0
TOWER A 15TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 24 Sep 2022 |  | 0 | 0 | 1215 | 0
TOWER A 15TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 15TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 15TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 15TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 May 2023 |  | 0 | 0 | 1453 | 0
TOWER A 15TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 May 2023 |  | 0 | 0 | 1453 | 0
TOWER A 15TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 15TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 15TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 15TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 15TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR | 0 |  |  |  | 01 Jul 2022 |  | 0 | 0 | 44741 | 0
TOWER A 16TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Jul 2022 |  | 0 | 0 | 1130 | 0
TOWER A 16TH FLOOR MASONRY WORK | 0 |  |  |  | 08 May 2023 |  | 0 | 0 | 45052 | 0
TOWER A 16TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 16TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR RCC WORK | 0 |  |  |  | 01 Jul 2022 |  | 0 | 0 | 44741 | 0
TOWER A 16TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Jul 2022 |  | 0 | 0 | 44741 | 0
TOWER A 16TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 01 Sep 2022 |  | 0 | 0 | 44803 | 0
TOWER A 16TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 01 Sep 2022 |  | 0 | 0 | 44803 | 0
TOWER A 16TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 01 Sep 2022 |  | 0 | 0 | 44803 | 0
TOWER A 16TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 19 Nov 2022 |  | 0 | 0 | 44882 | 0
TOWER A 16TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 08 May 2023 |  | 0 | 0 | 45052 | 0
TOWER A 16TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 16TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 16TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 22 Nov 2022 |  | 0 | 0 | 1274 | 0
TOWER A 16TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 22 Nov 2022 |  | 0 | 0 | 1274 | 0
TOWER A 16TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 16TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 16TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 16TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 16TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 16TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER A 16TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER A 16TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 16TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 16TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER A 17TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 30 Aug 2022 |  | 0 | 0 | 1190 | 0
TOWER A 17TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 05 Dec 2023 |  | 0 | 0 | 1652 | 0
TOWER A 17TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR RCC WORK | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER A 17TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER A 17TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR RCC WORK FOR THREADING WORK | 1 | NOS |  |  | 07 Dec 2022 |  | 0 | 0 | 44900 | 0
TOWER A 17TH FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 07 Dec 2022 |  | 0 | 0 | 44900 | 0
TOWER A 17TH FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 07 Dec 2022 |  | 0 | 0 | 44900 | 0
TOWER A 17TH FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 06 Feb 2023 |  | 0 | 0 | 44961 | 0
TOWER A 17TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER A 17TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A 17TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 18 Jun 2024 |  | 0 | 0 | 45459 | 0
TOWER A 17TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 16 Feb 2023 |  | 0 | 0 | 1360 | 0
TOWER A 17TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 16 Feb 2023 |  | 0 | 0 | 1360 | 0
TOWER A 17TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 17TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 17TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A 17TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 17TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER A 17TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER A 17TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER A 17TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER A 17TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A 17TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE | 0 |  | 28 May 2019 |  | 14 Mar 2023 |  | 0 | 0 | 1386 | 0
TOWER A TERRACE CIVIL WORK | 0 |  | 28 May 2019 |  | 14 Mar 2023 |  | 0 | 0 | 1386 | 0
TOWER A TERRACE PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A TERRACE INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 14 Mar 2023 |  | 0 | 0 | 44997 | 0
TOWER A TERRACE MASONRY WORK | 0 |  |  |  | 21 Aug 2023 |  | 0 | 0 | 45157 | 0
TOWER A TERRACE 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  | 21 Aug 2023 |  | 0 | 0 | 45157 | 0
TOWER A TERRACE RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER A TERRACE RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE RCC COLUMN WORK | 1 | CFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE RCC WORK PARAPAT WALL | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE PLUMBING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE PLUMBING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE ELECTRICAL WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE ELECTRIC WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 26 Aug 2023 |  | 0 | 0 | 1551 | 0
TOWER A TERRACE FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Feb 2024 |  | 0 | 0 | 1721 | 0
TOWER A TERRACE FABRICATION WORK | 0 |  | 28 May 2019 |  | 26 Aug 2023 |  | 0 | 0 | 1551 | 0
TOWER A TERRACE FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 26 Aug 2023 |  | 0 | 0 | 1551 | 0
TOWER A TERRACE WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 20 Nov 2023 |  | 0 | 0 | 1637 | 0
TOWER A TERRACE WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Nov 2023 |  | 0 | 0 | 1637 | 0
TOWER A TERRACE PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A TERRACE FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 10 Feb 2024 |  | 0 | 0 | 1719 | 0
TOWER B | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B LOWER BASEMENT | 0 |  |  |  | 26 Jul 2019 |  | 0 | 0 | 43670 | 0
TOWER B LOWER BASEMENT CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Jul 2019 |  | 0 | 0 | 59 | 0
TOWER B LOWER BASEMENT MASONRY WORK | 0 |  |  |  | 27 Jun 2022 |  | 0 | 0 | 44737 | 0
TOWER B LOWER BASEMENT 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B LOWER BASEMENT 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B LOWER BASEMENT MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER B LOWER BASEMENT RCC WORK | 0 |  |  |  | 26 Jul 2019 |  | 0 | 0 | 43670 | 0
TOWER B LOWER BASEMENT RCC WORK FOR COLUMN | 1 | CMT |  |  | 26 Jul 2019 | 26 Jul 2019 | 0 | 0 | 43670 | 43670
TOWER B LOWER BASEMENT RCC WORK FOR RETAINING WALL | 1 | CMT |  |  | 26 Jul 2019 | 26 Jul 2019 | 0 | 0 | 43670 | 43670
TOWER B LOWER BASEMENT RCC WORK FOR TRIMIX SMOOTH FINISH | 1 | SQFT | 28 May 2019 |  | 31 Mar 2023 |  | 0 | 0 | 1403 | 0
TOWER B LOWER BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B LOWER BASEMENT RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 22 Nov 2022 |  | 0 | 0 | 1274 | 0
TOWER B LOWER BASEMENT RCC DRILLING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER B LOWER BASEMENT PLASTER WORK | 0 |  |  |  | 29 Dec 2022 |  | 0 | 0 | 44922 | 0
TOWER B LOWER BASEMENT INTERNAL SINGLE COAT PLASTER WORK | 1 | SQFT |  |  | 29 Dec 2022 |  | 0 | 0 | 44922 | 0
TOWER B LOWER BASEMENT EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B LOWER BASEMENT PLUMBING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B LOWER BASEMENT ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 27 Aug 2022 |  | 0 | 0 | 1187 | 0
TOWER B LOWER BASEMENT ELECTRICAL | 1 | NOS | 28 May 2019 |  | 27 Aug 2022 |  | 0 | 0 | 1187 | 0
TOWER B LOWER BASEMENT MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER B LOWER BASEMENT COLOUR WORK | 0 |  |  |  | 29 May 2023 |  | 0 | 0 | 45073 | 0
TOWER B LOWER BASEMENT COLOUR WORK CEILING PUNNING | 1 | SQFT | 28 May 2019 |  | 29 May 2023 |  | 0 | 0 | 1462 | 0
TOWER B LOWER BASEMENT PAINT WORK | 1 | SQFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER B LOWER BASEMENT MISC WATERROOFING WORK | 0 |  | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER B LOWER BASEMENT MISC WATERROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER B LOWER BASEMENT ANTI TERMITE WORK | 0 |  | 28 May 2019 |  | 22 Apr 2023 |  | 0 | 0 | 1425 | 0
TOWER B LOWER BASEMENT ANTI TERMITE WORK | 1 | SQFT | 28 May 2019 |  | 22 Apr 2023 |  | 0 | 0 | 1425 | 0
TOWER B LOWER BASEMENT FABRICATION WORK | 0 |  | 28 May 2019 |  | 02 Oct 2023 |  | 0 | 0 | 1588 | 0
TOWER B LOWER BASEMENT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER B LOWER BASEMENT FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B LOWER BASEMENT FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 01 Apr 2024 |  | 0 | 0 | 1770 | 0
TOWER B UPPER BASEMENT | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B UPPER BASEMENT CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Jul 2019 |  | 0 | 0 | 59 | 0
TOWER B UPPER BASEMENT MASONRY WORK | 0 |  |  |  | 27 Jun 2022 |  | 0 | 0 | 44737 | 0
TOWER B UPPER BASEMENT 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER B UPPER BASEMENT RCC WORK | 0 |  |  |  | 26 Jul 2019 |  | 0 | 0 | 43670 | 0
TOWER B UPPER BASEMENT RCC WORK | 1 | CMT |  |  | 22 Aug 2023 |  | 0 | 0 | 45158 | 0
TOWER B UPPER BASEMENT RCC WORK FOR FLOOR RCC (TRIMIX) | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT RCC WORK FOR RETAINING WALL | 1 | CMT |  |  | 26 Jul 2019 | 26 Jul 2019 | 0 | 0 | 43670 | 43670
TOWER B UPPER BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Dec 2023 |  | 0 | 0 | 1648 | 0
TOWER B UPPER BASEMENT RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT INTERNAL SINGLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT PLUMBING WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER B UPPER BASEMENT ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 27 Aug 2022 |  | 0 | 0 | 1187 | 0
TOWER B UPPER BASEMENT ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 01 Nov 2023 |  | 0 | 0 | 1618 | 0
TOWER B UPPER BASEMENT MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 24 Feb 2021 |  | 0 | 0 | 638 | 0
TOWER B UPPER BASEMENT COLOUR WORK | 0 |  | 28 May 2019 |  | 24 Feb 2021 |  | 0 | 0 | 638 | 0
TOWER B UPPER BASEMENT COLOUR WORK CEILING PUNNING | 1 | SQFT | 28 May 2019 |  | 24 Feb 2021 |  | 0 | 0 | 638 | 0
TOWER B UPPER BASEMENT PAINT WORK | 1 | SQFT | 28 May 2019 |  | 14 Jul 2022 |  | 0 | 0 | 1143 | 0
TOWER B UPPER BASEMENT FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B UPPER BASEMENT FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 01 Apr 2024 |  | 0 | 0 | 1770 | 0
TOWER B GROUND FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B GROUND FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 21 Sep 2019 |  | 0 | 0 | 116 | 0
TOWER B GROUND FLOOR MASONRY WORK | 0 |  |  |  | 19 Jun 2021 |  | 0 | 0 | 44364 | 0
TOWER B GROUND FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER B GROUND FLOOR 6" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR RCC WORK | 0 |  |  |  | 21 Sep 2019 |  | 0 | 0 | 43727 | 0
TOWER B GROUND FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 21 Sep 2019 |  | 0 | 0 | 43727 | 0
TOWER B GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 21 Sep 2019 |  | 0 | 0 | 43727 | 0
TOWER B GROUND FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR RCC WORK FOR REBARING 12MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER B GROUND FLOOR RCC WORK FOR REBARING 16MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER B GROUND FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR RCC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 04 Feb 2023 |  | 0 | 0 | 1348 | 0
TOWER B GROUND FLOOR RCC WORK EXPANSION JOINT | 1 | NOS | 28 May 2019 |  | 21 Apr 2022 |  | 0 | 0 | 1059 | 0
TOWER B GROUND FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR PCC WORK | 1 | SQFT | 28 May 2019 |  | 12 Jul 2023 |  | 0 | 0 | 1506 | 0
TOWER B GROUND FLOOR RCC WORK BREAKER | 1 | DAY | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR PLASTER WORK | 0 |  |  |  | 01 Jan 2022 |  | 0 | 0 | 44560 | 0
TOWER B GROUND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 15775.45 | SQFT |  |  | 01 Jan 2022 |  | 0 | 0 | 44560 | 0
TOWER B GROUND FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOWROOM A WINDOW WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR PLUMBING WORK | 0 |  |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER B GROUND FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER B GROUND FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER B GROUND FLOOR ELECTRIC WORK | 0 |  |  |  | 28 Aug 2023 |  | 0 | 0 | 45164 | 0
TOWER B GROUND FLOOR ELECTRIC WORK FOR SLEEVE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR ELECTRIC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 28 Aug 2023 |  | 0 | 0 | 1553 | 0
TOWER B GROUND FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR COLOUR WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B GROUND FLOOR COLOR WORK CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 02 Nov 2020 |  | 0 | 0 | 524 | 0
TOWER B GROUND FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
GF 9-13 PAINT WORK TEKIT | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B GROUND FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B GROUND FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 24 Mar 2022 |  | 0 | 0 | 1031 | 0
TOWER B GROUND FLOOR FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 24 Mar 2022 |  | 0 | 0 | 1031 | 0
TOWER B GROUND FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER B GROUND FLOOR SHOP NO 17 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR SHOP NO 16 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR SHOP NO 10 & 11 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR SHOWROOM B ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER B GROUND FLOOR SHOP NO 15 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR SHOP NO 14 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR SHOP NO 13 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR SHOP NO 12 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 20 Sep 2022 |  | 0 | 0 | 1211 | 0
TOWER B GROUND FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER B GROUND FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
TOWER B GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
TOWER B GROUND FLOOR RAILING WORK | 0 |  | 28 May 2019 |  | 04 Oct 2023 |  | 0 | 0 | 1590 | 0
GF 9-13 RAILING WORK TEKIT | 1 | RFT | 28 May 2019 |  | 04 Oct 2023 |  | 0 | 0 | 1590 | 0
TOWER B GROUND FLOORNAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER B GROUND FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B GROUND FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 20 Sep 2022 |  | 0 | 0 | 44822 | 0
TOWER B GROUND FLOOR SHOP & SHOWROOM FLOORING WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 17 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 17 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 16 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 16 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 10 & 11 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 10 & 11 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOWROOM B | 0 |  | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER B GROUND FLOOR SHOWROOM B FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER B GROUND FLOOR SHOP NO 15 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 15 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 14 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 14 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 13 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 13 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 12 | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B GROUND FLOOR SHOP NO 12 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B 1ST FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 07 Jan 2020 |  | 0 | 0 | 224 | 0
TOWER B 1ST FLOOR MASONRY WORK | 0 |  |  |  | 03 Sep 2021 |  | 0 | 0 | 44440 | 0
TOWER B 1ST FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  | 08 Sep 2023 |  | 0 | 0 | 45175 | 0
TOWER B 1ST FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER B 1ST FLOOR DRY WALL WORK | 1 | SQMT |  |  | 18 Oct 2021 |  | 0 | 0 | 44485 | 0
TOWER B 1ST FLOOR RCC WORK | 0 |  |  |  | 07 Jan 2020 |  | 0 | 0 | 43835 | 0
TOWER B 1ST FLOOR RCC WORK FOR RCC COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR RCC WORK FOR REBARING 12MM | 1 | NOS | 28 May 2019 |  | 07 Jan 2020 |  | 0 | 0 | 224 | 0
TOWER B 1ST FLOOR RCC WORK FOR REBARING 16MM | 1 | NOS | 28 May 2019 |  | 07 Jan 2020 |  | 0 | 0 | 224 | 0
TOWER B 1ST FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR RCC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER B 1ST FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR PLASTER WORK | 0 |  |  |  | 27 Feb 2022 |  | 0 | 0 | 44617 | 0
TOWER B 1ST FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 27 Feb 2022 |  | 0 | 0 | 44617 | 0
TOWER B 1ST FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER B 1ST FLOOR PASAGE RAILING | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER B 1ST FLOOR PASAGE RAILING | 1 | RFT | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER B 1ST FLOOR PLUMBING WORK | 0 |  |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER B 1ST FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER B 1ST FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR ELECTRIC WORK | 0 |  |  |  | 08 Sep 2020 |  | 0 | 0 | 44080 | 0
TOWER B 1ST FLOOR ELECTRIC WORK | 1 | SQFT | 28 May 2019 |  | 08 Sep 2020 |  | 0 | 0 | 469 | 0
TOWER B 1ST FLOOR ELECTRIC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 08 Sep 2020 |  | 0 | 0 | 469 | 0
TOWER B 1ST FLOOR ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 28 Aug 2023 |  | 0 | 0 | 1553 | 0
GF 9-13 & FF 5-20 AC WORK TEKIT | 1 | NOS | 28 May 2019 |  | 10 Sep 2023 |  | 0 | 0 | 1566 | 0
TOWER B 1ST FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR COLOUR WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER B 1ST FLOOR COLOR WORK CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 22 Sep 2021 |  | 0 | 0 | 848 | 0
TOWER B 1ST FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
FF 5-20 PAINT WORK TEKIT | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 1ST FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 1ST FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOWROOM B ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 9 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 10 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 11 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 12 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 13 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 14 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 15 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR SHOP NO 16 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER B 1ST FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 18 Sep 2023 |  | 0 | 0 | 1574 | 0
TOWER B 1ST FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 29 Feb 2024 |  | 0 | 0 | 1738 | 0
GF 9-13 & FF 5-20 FABRICATION WORK TEKIT | 1 | NOS | 28 May 2019 |  | 18 Sep 2023 |  | 0 | 0 | 1574 | 0
TOWER B 1ST FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER B 1ST FLOOR CARPENTRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
GF 9-13 & FF 5-20 CARPENTRY WORK TEKIT | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 1ST FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER B 1ST FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 17 Feb 2023 |  | 0 | 0 | 44972 | 0
TOWER B 1ST FLOOR SHOP & SHOWROOM FLOORING WORK | 0 |  | 28 May 2019 |  | 01 Dec 2021 |  | 0 | 0 | 918 | 0
TOWER B 1ST FLOOR SHOWROOM B AND SHOWROOM C | 0 |  | 28 May 2019 |  | 10 May 2022 |  | 0 | 0 | 1078 | 0
TOWER B 1ST FLOOR SHOWROOM B AND SHOWROOM C FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 10 May 2022 |  | 0 | 0 | 1078 | 0
TOWER B 1ST FLOOR SHOP NO 9 TO 16 | 0 |  | 28 May 2019 |  | 01 Dec 2021 |  | 0 | 0 | 918 | 0
TOWER B 1ST FLOOR SHOP NO 9 TO 16 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 01 Dec 2021 |  | 0 | 0 | 918 | 0
TOWER B 2ND FLOOR | 0 |  |  |  | 24 Jun 2020 |  | 0 | 0 | 44004 | 0
TOWER B 2ND FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 24 Jun 2020 |  | 0 | 0 | 393 | 0
TOWER B 2ND FLOOR MASONRY WORK | 0 |  |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER B 2ND FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 24 Apr 2021 |  | 0 | 0 | 697 | 0
TOWER B 2ND FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR RCC WORK | 0 |  |  |  | 24 Jun 2020 |  | 0 | 0 | 44004 | 0
TOWER B 2ND FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 24 Jul 2020 |  | 0 | 0 | 44034 | 0
TOWER B 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Mar 2021 |  | 0 | 0 | 44254 | 0
TOWER B 2ND FLOOR RCC WORK FOR LIFT & PARDI | 1 | CMT |  |  | 24 Jul 2020 |  | 0 | 0 | 44034 | 0
TOWER B 2ND FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR RCC WORK FOR THREADING | 1 | NOS | 28 May 2019 |  | 24 Jun 2020 |  | 0 | 0 | 393 | 0
TOWER B 2ND FLOOR RCC WORK FOR FOR THREADING 20MM | 1 | NOS | 28 May 2019 |  | 24 Jun 2020 |  | 0 | 0 | 393 | 0
TOWER B 2ND FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS | 28 May 2019 |  | 24 Jun 2020 |  | 0 | 0 | 393 | 0
TOWER B 2ND FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS | 28 May 2019 |  | 24 Jun 2020 |  | 0 | 0 | 393 | 0
TOWER B 2ND FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 10 Oct 2020 |  | 0 | 0 | 44112 | 0
TOWER B 2ND FLOOR RCC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 19 Oct 2020 |  | 0 | 0 | 510 | 0
TOWER B 2ND FLOOR RCC WORK FOR TRIMIX SMOOTH FINISH | 1 | SQFT | 28 May 2019 |  | 09 Oct 2020 |  | 0 | 0 | 500 | 0
TOWER B 2ND FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B 2ND FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR PLASTER WORK | 0 |  |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 70 | SQFT |  |  | 27 Feb 2022 |  | 0 | 0 | 44617 | 0
TOWER B 2ND FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 2ND FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER B 2ND FLOOR PASAGE RAILING | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER B 2ND FLOOR PASAGE RAILING | 1 | RFT | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER B 2ND FLOOR PLUMBING WORK | 0 |  |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER B 2ND FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Jan 2021 |  | 0 | 0 | 44195 | 0
TOWER B 2ND FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER B 2ND FLOOR ELECTRICAL WORK | 0 |  |  |  | 19 Oct 2020 |  | 0 | 0 | 44121 | 0
TOWER B 2ND FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 19 Oct 2020 |  | 0 | 0 | 510 | 0
TOWER B 2ND FLOOR FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 19 Oct 2020 |  | 0 | 0 | 510 | 0
TOWER B 2ND FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER B 2ND FLOOR COLOUR WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B - 2ND FLOOR COLOR WORK APPLYING CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 2ND FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 2ND FLOOR SAFETY | 0 |  |  |  | 30 Jul 2021 |  | 0 | 0 | 44405 | 0
TOWER B 2ND FLOOR SAFETY | 1 | NOS | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER B 2ND FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 2ND FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 2ND FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 12 Mar 2024 |  | 0 | 0 | 1750 | 0
TOWER B 2ND FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER B 2ND FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 2ND FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER B 2ND FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 May 2022 |  | 0 | 0 | 44694 | 0
TOWER B 2ND FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 30 May 2022 |  | 0 | 0 | 44709 | 0
TOWER B 2ND FLOOR SHOP & SHOWROOM FLOORING WORK | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER B 2ND FLOOR SHOWROOM B | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER B 2ND FLOOR SHOWROOM B FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER B 2ND FLOOR SHOP NO 8 TO 15 | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER B 2ND FLOOR SHOP NO 8 TO 15 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER B 3RD FLOOR | 0 |  |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER B 3RD FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 31 Oct 2020 |  | 0 | 0 | 522 | 0
TOWER B 3RD FLOOR MASONRY WORK | 0 |  |  |  | 21 Jan 2021 |  | 0 | 0 | 44215 | 0
TOWER B 3RD FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 21 Jan 2021 |  | 0 | 0 | 604 | 0
TOWER B 3RD FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR RCC WORK | 0 |  |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER B 3RD FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 21 Jan 2021 |  | 0 | 0 | 44215 | 0
TOWER B 3RD FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR RCC WORK FOR THREADING 20MM | 1 | NOS |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER B 3RD FLOOR RCC WORK FOR THREADING 25MM | 1 | NOS |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER B 3RD FLOOR RCC WORK FOR THREADING 32MM | 1 | NOS |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER B 3RD FLOOR RCC WORK FOR PT CABLE LAYING | 1 | RMT |  |  | 06 Jan 2021 |  | 0 | 0 | 44200 | 0
TOWER B 3RD FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER B 3RD FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR PLASTER WORK | 0 |  |  |  | 27 Feb 2022 |  | 0 | 0 | 44617 | 0
TOWER B 3RD FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 27 Feb 2022 |  | 0 | 0 | 44617 | 0
TOWER B 3RD FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Apr 2022 |  | 0 | 0 | 44650 | 0
TOWER B 3RD FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR PLUMBING WORK | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B 3RD FLOOR PLUMBING WORK | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B SHOPS TOILETS PROVISIONAL LINES PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER B 3RD FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 28 Jul 2023 |  | 0 | 0 | 1522 | 0
TOWER B 3RD FLOOR ELECTRIC WORK | 0 |  |  |  | 18 Oct 2023 |  | 0 | 0 | 45215 | 0
TOWER B 3RD FLOOR ELECTRIC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR ELECTRIC WORK | 1 | SQFT | 28 May 2019 |  | 18 Oct 2023 |  | 0 | 0 | 1604 | 0
TOWER B 3RD FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER B 3RD FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER B 3RD FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER B 3RD FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 3RD FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 3RD FLOOR COLOUR WORK | 0 |  | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER B 3RD FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER B 3RD FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 3RD FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 3RD FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 01 Apr 2024 |  | 0 | 0 | 45381 | 0
TOWER B 4TH FLOOR | 0 |  |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER B 4TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 19 Dec 2020 |  | 0 | 0 | 571 | 0
TOWER B 4TH FLOOR MASONRY WORK | 0 |  |  |  | 18 Mar 2021 |  | 0 | 0 | 44271 | 0
TOWER B 4TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 18 Mar 2021 |  | 0 | 0 | 660 | 0
TOWER B 4TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR RCC WORK | 0 |  |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER B 4TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 18 Mar 2021 |  | 0 | 0 | 44271 | 0
TOWER B 4TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER B 4TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER B 4TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER B 4TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 08 Apr 2021 |  | 0 | 0 | 44292 | 0
TOWER B 4TH FLOOR RCC WORK LEGS WELDING | 1 | RFT | 28 May 2019 |  | 28 Jan 2021 |  | 0 | 0 | 611 | 0
TOWER B 4TH FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER B 4TH FLOOR RCC WORK BREAKER | 1 | DAY | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 70 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 4TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 4TH FLOOR WATERPROOFING | 0 |  | 28 May 2019 |  | 20 Jun 2022 |  | 0 | 0 | 1119 | 0
TOWER B 4TH FLOOR WATERPROOFING WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Jun 2022 |  | 0 | 0 | 1119 | 0
TOWER B 4TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR PLUMBING WORK | 0 |  |  |  | 02 Apr 2022 |  | 0 | 0 | 44651 | 0
TOWER B 4TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 02 Apr 2022 |  | 0 | 0 | 44651 | 0
TOWER B 4TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 26 Mar 2021 |  | 0 | 0 | 44279 | 0
TOWER B 4TH FLOOR ELECTRICAL WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 26 Mar 2021 |  | 0 | 0 | 668 | 0
TOWER B 4TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 26 Mar 2021 |  | 0 | 0 | 668 | 0
TOWER B 4TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 4TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 4TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 4TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 31 Jan 2023 |  | 0 | 0 | 1344 | 0
TOWER B 4TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 31 Jan 2023 |  | 0 | 0 | 1344 | 0
TOWER B 4TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 01 - 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 04 - 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 07 - 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 11 - 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 14 - 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 4TH FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 29 May 2023 |  | 0 | 0 | 45073 | 0
TOWER B 4TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 29 May 2023 |  | 0 | 0 | 45073 | 0
TOWER B 4TH FLOOR OFFICE NO 01 - 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 04 - 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 07 - 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 11 - 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 4TH FLOOR OFFICE NO 14 - 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR | 0 |  |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER B 5TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 24 Mar 2021 |  | 0 | 0 | 666 | 0
TOWER B 5TH FLOOR MASONRY WORK | 0 |  |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER B 5TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 24 Apr 2021 |  | 0 | 0 | 697 | 0
TOWER B 5TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 01 Jul 2022 |  | 0 | 0 | 44741 | 0
TOWER B 5TH FLOOR RCC WORK | 0 |  |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER B 5TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER B 5TH FLOOR RCC WORK LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER B 5TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 14 Apr 2021 |  | 0 | 0 | 44298 | 0
TOWER B 5TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 03 Sep 2021 |  | 0 | 0 | 44440 | 0
TOWER B 5TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 06 May 2021 |  | 0 | 0 | 709 | 0
TOWER B 5TH FLOOR RCC WORK THREADING CHARGES | 1 | NOS | 28 May 2019 |  | 03 Jun 2021 |  | 0 | 0 | 737 | 0
TOWER B 5TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 5TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 5TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR PLUMBING WORK | 0 |  |  |  | 03 Dec 2022 |  | 0 | 0 | 44896 | 0
TOWER B 5TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 11 Jan 2023 |  | 0 | 0 | 44935 | 0
TOWER B 5TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 03 Dec 2022 |  | 0 | 0 | 1285 | 0
TOWER B 5TH FLOOR CP Fittings & Sanitary | 1 | NOS | 28 May 2019 |  | 28 Jul 2023 |  | 0 | 0 | 1522 | 0
TOWER B 5TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 12 Apr 2021 |  | 0 | 0 | 44296 | 0
TOWER B 5TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 12 Apr 2021 |  | 0 | 0 | 685 | 0
TOWER B 5TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 12 Apr 2021 |  | 0 | 0 | 685 | 0
TOWER B 5TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER B 5TH FLOOR SAFETY WORK | 0 |  |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER B 5TH FLOOR SAFETY WORK | 1 | SQFT |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER B 5TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 5TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 5TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 5TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 5TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 5TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 5TH FLOOR SUNK FILLING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR SUNK FILLING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER B 5TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 5TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 05 - 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 5TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER B 6TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Apr 2021 |  | 0 | 0 | 699 | 0
TOWER B 6TH FLOOR MASONRY WORK | 0 |  |  |  | 16 Aug 2023 |  | 0 | 0 | 45152 | 0
TOWER B 6TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 16 Aug 2023 |  | 0 | 0 | 45152 | 0
TOWER B 6TH FLOOR RCC WORK | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER B 6TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Mar 2022 |  | 0 | 0 | 44619 | 0
TOWER B 6TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER B 6TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER B 6TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER B 6TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 10 Jun 2021 |  | 0 | 0 | 44355 | 0
TOWER B 6TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 03 Jul 2021 |  | 0 | 0 | 767 | 0
TOWER B 6TH FLOOR RCC WORK THREADING CHARGES | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 6TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 6TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR PLUMBING WORK | 0 |  |  |  | 20 Dec 2022 |  | 0 | 0 | 44913 | 0
TOWER B 6TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 05 Apr 2023 |  | 0 | 0 | 45019 | 0
TOWER B 6TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 20 Dec 2022 |  | 0 | 0 | 1302 | 0
TOWER B 6TH FLOOR CP Fittings & Sanitary | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 14 Jun 2021 |  | 0 | 0 | 44359 | 0
TOWER B 6TH FLOOR ELECTRIC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 14 Jun 2021 |  | 0 | 0 | 748 | 0
TOWER B 6TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 14 Jun 2021 |  | 0 | 0 | 748 | 0
TOWER B 6TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER B 6TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 6TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 6TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER B 6TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER B 6TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 6TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 6TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOROFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 6TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 6TH FLOOR SUNK FILLING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR SUNK FILLING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER B 6TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 6TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 6TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER B 7TH FLOOR | 0 |  |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER B 7TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 23 Jun 2021 |  | 0 | 0 | 757 | 0
TOWER B 7TH FLOOR MASONRY WORK | 0 |  |  |  | 20 Jul 2021 |  | 0 | 0 | 44395 | 0
TOWER B 7TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 20 Jul 2021 |  | 0 | 0 | 784 | 0
TOWER B 7TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 11 Aug 2023 |  | 0 | 0 | 45147 | 0
TOWER B 7TH FLOOR RCC WORK | 0 |  |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER B 7TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 20 Apr 2022 |  | 0 | 0 | 44669 | 0
TOWER B 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Mar 2022 |  | 0 | 0 | 44619 | 0
TOWER B 7TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER B 7TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER B 7TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER B 7TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 15 Jul 2021 |  | 0 | 0 | 44390 | 0
TOWER B 7TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER B 7TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER B 7TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 7TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 7TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 01 Apr 2023 |  | 0 | 0 | 45015 | 0
TOWER B 7TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 01 Apr 2023 |  | 0 | 0 | 1404 | 0
TOWER B 7TH FLOOR CP Fittings & Sanitary | 1 | NOS | 28 May 2019 |  | 01 Apr 2023 |  | 0 | 0 | 1404 | 0
TOWER B 7TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 17 Aug 2021 |  | 0 | 0 | 44423 | 0
TOWER B 7TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 17 Aug 2021 |  | 0 | 0 | 44423 | 0
TOWER B 7TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER B 7TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 7TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 7TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER B 7TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 03 Dec 2021 |  | 0 | 0 | 920 | 0
TOWER B 7TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 7TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 7TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 7TH FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 15 Oct 2023 |  | 0 | 0 | 45212 | 0
TOWER B 7TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 7TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 02 - 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 7TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 15 Oct 2023 |  | 0 | 0 | 1601 | 0
TOWER B 8TH FLOOR | 0 |  |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER B 8TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 03 Jul 2021 |  | 0 | 0 | 767 | 0
TOWER B 8TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 8TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 8TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR RCC WORK | 0 |  |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER B 8TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 13 Aug 2021 |  | 0 | 0 | 44419 | 0
TOWER B 8TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER B 8TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER B 8TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER B 8TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 10 Sep 2021 |  | 0 | 0 | 44447 | 0
TOWER B 8TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 17 Sep 2021 |  | 0 | 0 | 44454 | 0
TOWER B 8TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER B 8TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 8TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 8TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER B 8TH FLOOR CP Fittings & Sanitary | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER B 8TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 26 Aug 2021 |  | 0 | 0 | 44432 | 0
TOWER B 8TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 23 Nov 2021 |  | 0 | 0 | 910 | 0
TOWER B 8TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 8TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 8TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 23 Nov 2021 |  | 0 | 0 | 910 | 0
TOWER B 8TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 23 Nov 2021 |  | 0 | 0 | 910 | 0
TOWER B 8TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 8TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 8TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOROFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 8TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 8TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR | 0 |  |  |  | 01 Sep 2021 |  | 0 | 0 | 44438 | 0
TOWER B 9TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Sep 2021 |  | 0 | 0 | 827 | 0
TOWER B 9TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 9TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 9TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR RCC WORK | 0 |  |  |  | 01 Sep 2021 |  | 0 | 0 | 44438 | 0
TOWER B 9TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Sep 2021 |  | 0 | 0 | 44438 | 0
TOWER B 9TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
RCC WORK RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 16 Oct 2021 |  | 0 | 0 | 44483 | 0
TOWER B 9TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 16 Oct 2021 |  | 0 | 0 | 44483 | 0
TOWER B 9TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 16 Oct 2021 |  | 0 | 0 | 44483 | 0
TOWER B 9TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 17 Sep 2021 |  | 0 | 0 | 44454 | 0
TOWER B 9TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER B 9TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 9TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 9TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR ELECTRICAL WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER B 9TH FLOOR SAFETY WORK | 0 |  |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER B 9TH FLOOR SAFETY WORK | 1 | SQFT |  |  | 29 Mar 2022 |  | 0 | 0 | 44647 | 0
TOWER B 9TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 9TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 9TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 9TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 13 Oct 2023 |  | 0 | 0 | 1599 | 0
TOWER B 9TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 9TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 04 - 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 9TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR | 0 |  |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER B 10TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 13 Oct 2021 |  | 0 | 0 | 869 | 0
TOWER B 10TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 10TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 10TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR RCC WORK | 0 |  |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER B 10TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 15 Apr 2022 |  | 0 | 0 | 44664 | 0
TOWER B 10TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER B 10TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER B 10TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER B 10TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 02 Dec 2021 |  | 0 | 0 | 44530 | 0
TOWER B 10TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 28 Oct 2021 |  | 0 | 0 | 44495 | 0
TOWER B 10TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER B 10TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 10TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 10TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER B 10TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER B 10TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 08 Jan 2022 |  | 0 | 0 | 956 | 0
TOWER B 10TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 08 Jan 2022 |  | 0 | 0 | 956 | 0
TOWER B 10TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 08 Jan 2022 |  | 0 | 0 | 956 | 0
TOWER B 10TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 10TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 10TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 05 Feb 2024 |  | 0 | 0 | 1714 | 0
TOWER B 10TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 10TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 10TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR | 0 |  |  |  | 01 Nov 2021 |  | 0 | 0 | 44499 | 0
TOWER B 11TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 17 Nov 2021 |  | 0 | 0 | 904 | 0
TOWER B 11TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 11TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 11TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR RCC WORK | 0 |  |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER B 11TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER B 11TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER B 11TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER B 11TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 24 Dec 2021 |  | 0 | 0 | 44552 | 0
TOWER B 11TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 23 Nov 2021 |  | 0 | 0 | 44521 | 0
TOWER B 11TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 11TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 11TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 01 Nov 2021 |  | 0 | 0 | 888 | 0
TOWER B 11TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 01 Nov 2021 |  | 0 | 0 | 888 | 0
TOWER B 11TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 11TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 11TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 11TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER B 11TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER B 11TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 05 Feb 2024 |  | 0 | 0 | 1714 | 0
TOWER B 11TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 11TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 11TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR | 0 |  |  |  | 05 Dec 2021 |  | 0 | 0 | 44533 | 0
TOWER B 12TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 05 Dec 2021 |  | 0 | 0 | 922 | 0
TOWER B 12TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 12TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 12TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR RCC WORK | 0 |  |  |  | 05 Dec 2021 |  | 0 | 0 | 44533 | 0
TOWER B 12TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 20 Apr 2022 |  | 0 | 0 | 44669 | 0
TOWER B 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 05 Dec 2021 |  | 0 | 0 | 44533 | 0
TOWER B 12TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 05 Dec 2021 |  | 0 | 0 | 44533 | 0
TOWER B 12TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 05 Dec 2021 |  | 0 | 0 | 44533 | 0
TOWER B 12TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 23 Feb 2022 |  | 0 | 0 | 44613 | 0
TOWER B 12TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER B 12TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 12TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 12TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 10 Feb 2022 |  | 0 | 0 | 989 | 0
TOWER B 12TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 10 Feb 2022 |  | 0 | 0 | 989 | 0
TOWER B 12TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 12TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 05 Jun 2022 |  | 0 | 0 | 1104 | 0
TOWER B 12TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 12TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 13 Oct 2022 |  | 0 | 0 | 1234 | 0
TOWER B 12TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 13 Oct 2022 |  | 0 | 0 | 1234 | 0
TOWER B 12TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 05 Feb 2024 |  | 0 | 0 | 1714 | 0
TOWER B 12TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 12TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 12TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR | 0 |  |  |  | 28 Jan 2022 |  | 0 | 0 | 44587 | 0
TOWER B 13TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 Jan 2022 |  | 0 | 0 | 976 | 0
TOWER B 13TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 13TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 13TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR RCC WORK | 0 |  |  |  | 28 Jan 2022 |  | 0 | 0 | 44587 | 0
TOWER B 13TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 20 Apr 2022 |  | 0 | 0 | 44669 | 0
TOWER B 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 15 Apr 2022 |  | 0 | 0 | 44664 | 0
TOWER B 13TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 28 Jan 2022 |  | 0 | 0 | 44587 | 0
TOWER B 13TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 28 Jan 2022 |  | 0 | 0 | 44587 | 0
TOWER B 13TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 28 Jan 2022 |  | 0 | 0 | 44587 | 0
TOWER B 13TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 16 Apr 2022 |  | 0 | 0 | 44665 | 0
TOWER B 13TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER B 13TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 13TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 13TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 14 Apr 2022 |  | 0 | 0 | 1052 | 0
TOWER B 13TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 14 Apr 2022 |  | 0 | 0 | 1052 | 0
TOWER B 13TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER B 13TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER B 13TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 13TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 05 Feb 2024 |  | 0 | 0 | 1714 | 0
TOWER B 13TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 13TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER B 13TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER B 13TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 13TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR | 0 |  |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 14TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B 14TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 14TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 14TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR RCC WORK | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B 14TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B 14TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B 14TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER B 14TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER B 14TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER B 14TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 14TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 14TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 23 Jun 2022 |  | 0 | 0 | 1122 | 0
TOWER B 14TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 23 Jun 2022 |  | 0 | 0 | 1122 | 0
TOWER B 14TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER B 14TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 14TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER B 14TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TOWER B 14TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 05 Feb 2024 |  | 0 | 0 | 1714 | 0
TOWER B 14TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 14TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 14TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR | 0 |  |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 15TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B 15TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER B 15TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER B 15TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR RCC WORK | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER B 15TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER B 15TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 15 Jun 2022 |  | 0 | 0 | 44725 | 0
TOWER B 15TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 15 Jun 2022 |  | 0 | 0 | 44725 | 0
TOWER B 15TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER B 15TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER B 15TH FLOOR THREADING CHARGES | 1 | NOS | 28 May 2019 |  | 15 Jun 2022 |  | 0 | 0 | 1114 | 0
TOWER B 15TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 15TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 15TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 25 Aug 2022 |  | 0 | 0 | 1185 | 0
TOWER B 15TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 25 Aug 2022 |  | 0 | 0 | 1185 | 0
TOWER B 15TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER B 15TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 13 Jun 2023 |  | 0 | 0 | 1477 | 0
TOWER B 15TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 15TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER B 15TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 02 Jun 2023 |  | 0 | 0 | 1466 | 0
TOWER B 15TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 12 Mar 2024 |  | 0 | 0 | 1750 | 0
TOWER B 15TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 15TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 15TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR | 0 |  |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 16TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B 16TH FLOOR MASONRY WORK | 0 |  |  |  | 08 May 2023 |  | 0 | 0 | 45052 | 0
TOWER B 16TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 08 May 2023 |  | 0 | 0 | 1441 | 0
TOWER B 16TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR RCC WORK | 0 |  |  |  | 18 Aug 2022 |  | 0 | 0 | 44789 | 0
TOWER B 16TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER B 16TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 18 Aug 2022 |  | 0 | 0 | 44789 | 0
TOWER B 16TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 18 Aug 2022 |  | 0 | 0 | 44789 | 0
TOWER B 16TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 04 Oct 2022 |  | 0 | 0 | 44836 | 0
TOWER B 16TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 03 Nov 2022 |  | 0 | 0 | 44866 | 0
TOWER B 16TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER B 16TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 16TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 16TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 05 Nov 2022 |  | 0 | 0 | 1257 | 0
TOWER B 16TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 05 Nov 2022 |  | 0 | 0 | 1257 | 0
TOWER B 16TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 13 Jun 2023 |  | 0 | 0 | 1477 | 0
TOWER B 16TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 13 Jun 2023 |  | 0 | 0 | 1477 | 0
TOWER B 16TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 16TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 12 Mar 2024 |  | 0 | 0 | 1750 | 0
TOWER B 16TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 16TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER B 16TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER B 16TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 16TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR | 0 |  |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 17TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B 17TH FLOOR MASONRY WORK | 0 |  |  |  | 15 May 2023 |  | 0 | 0 | 45059 | 0
TOWER B 17TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 15 May 2023 |  | 0 | 0 | 1448 | 0
TOWER B 17TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR RCC WORK | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER B 17TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER B 17TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR RCC WORK THREADING WORK | 1 | NOS |  |  | 13 Jan 2023 |  | 0 | 0 | 44937 | 0
TOWER B 17TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 13 Jan 2023 |  | 0 | 0 | 44937 | 0
TOWER B 17TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 13 Jan 2023 |  | 0 | 0 | 44937 | 0
TOWER B 17TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 11 Jan 2023 |  | 0 | 0 | 44935 | 0
TOWER B 17TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER B 17TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 17TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Feb 2022 |  | 0 | 0 | 44591 | 0
TOWER B 17TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 18 Jan 2023 |  | 0 | 0 | 1331 | 0
TOWER B 17TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 18 Jan 2023 |  | 0 | 0 | 1331 | 0
TOWER B 17TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 13 Jun 2023 |  | 0 | 0 | 1477 | 0
TOWER B 17TH FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 13 Jun 2023 |  | 0 | 0 | 1477 | 0
TOWER B 17TH FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B 17TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR DUCT FABRICATION WORK | 1 | KG | 28 May 2019 |  | 12 Mar 2024 |  | 0 | 0 | 1750 | 0
TOWER B 17TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 06 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 07 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 08 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 09 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 10 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 11 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 12 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 13 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 14 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 15 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 16 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B 17TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER B 17TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER B 17TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 09 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 10 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 11 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 12 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 13 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 14 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 15 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B 17TH FLOOR OFFICE NO 16 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE | 0 |  | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B TERRACE CIVIL WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE MASONRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE RCC WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B TERRACE RCC WORK PARAPAT WALL | 1 | SQFT | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B TERRACE RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B TERRACE PLASTER WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B TERRACE EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT | 28 May 2019 |  | 01 Feb 2022 |  | 0 | 0 | 980 | 0
TOWER B TERRACE EXTERNAL FACADE & WINDOW | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE PLUMBING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE PLUMBING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE ELECTRICAL WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE ELECTRIC WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 26 Aug 2023 |  | 0 | 0 | 1551 | 0
TOWER B TERRACE FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER B TERRACE WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE FABRICATION WORK | 0 |  | 28 May 2019 |  | 26 Aug 2023 |  | 0 | 0 | 1551 | 0
TOWER B TERRACE FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 26 Aug 2023 |  | 0 | 0 | 1551 | 0
TOWER B TERRACE PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE PAINT WORK | 1 | SQFT | 28 May 2019 |  | 09 Mar 2024 |  | 0 | 0 | 1747 | 0
TOWER B TERRACE FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B TERRACE FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT | 0 |  | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER C LOWER BASEMENT CIVIL WORK | 0 |  | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER C LOWER BASEMENT MASONRY WORK | 0 |  | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER C LOWER BASEMENT 9" AAC BLOCK MASONRY WORK | 0 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT 4.5" AAC BLOCK MASONRY WORK | 0 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER C LOWER BASEMENT RCC WORK | 0 |  | 28 May 2019 |  | 31 Mar 2023 |  | 0 | 0 | 1403 | 0
TOWER C LOWER BASEMENT RCC WORK SLAB BASEMENT | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT RCC WORK FOR TRIMIX SMOOTH FINISH | 1 | SQFT | 28 May 2019 |  | 31 Mar 2023 |  | 0 | 0 | 1403 | 0
TOWER C LOWER BASEMENT RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER C LOWER BASEMENT RCC DRILLING WORK | 1 | NOS | 28 May 2019 |  | 01 Feb 2024 |  | 0 | 0 | 1710 | 0
TOWER C LOWER BASEMENT PLASTER WORK | 0 |  | 28 May 2019 |  | 29 Dec 2022 |  | 0 | 0 | 1311 | 0
TOWER C LOWER BASEMENT INTERNAL SINGLE COAT PLASTER WORK | 1 | SQFT | 28 May 2019 |  | 29 Dec 2022 |  | 0 | 0 | 1311 | 0
TOWER C LOWER BASEMENT EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT PLUMBING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 02 Nov 2022 |  | 0 | 0 | 1254 | 0
TOWER C LOWER BASEMENT ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 02 Nov 2022 |  | 0 | 0 | 1254 | 0
TOWER C LOWER BASEMENT MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER C LOWER BASEMENT COLOUR WORK | 0 |  | 28 May 2019 |  | 01 Jul 2023 |  | 0 | 0 | 1495 | 0
TOWER C LOWER BASEMENT COLOUR WORK PUNNING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C LOWER BASEMENT PAINT WORK | 1 | SQFT | 28 May 2019 |  | 01 Jul 2023 |  | 0 | 0 | 1495 | 0
TOWER C LOWER BASEMENT MISC WATERROOFING WORK | 0 |  | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER C LOWER BASEMENT MISC WATERROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Jan 2023 |  | 0 | 0 | 1333 | 0
TOWER C LOWER BASEMENT ANTI TERMITE WORK | 0 |  | 28 May 2019 |  | 22 Apr 2023 |  | 0 | 0 | 1425 | 0
TOWER C LOWER BASEMENT ANTI TERMITE WORK | 1 | SQFT | 28 May 2019 |  | 22 Apr 2023 |  | 0 | 0 | 1425 | 0
TOWER C LOWER BASEMENT FALSE CEILING WORK | 0 |  | 28 May 2019 |  | 22 May 2023 |  | 0 | 0 | 1455 | 0
TOWER C LOWER BASEMENT FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 22 May 2023 |  | 0 | 0 | 1455 | 0
TOWER C LOWER BASEMENT FABRICATION WORK | 0 |  | 28 May 2019 |  | 02 Oct 2023 |  | 0 | 0 | 1588 | 0
TOWER C LOWER BASEMENT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 02 Oct 2023 |  | 0 | 0 | 1588 | 0
TOWER C LOWER BASEMENT FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  | 17 Feb 2023 |  | 0 | 0 | 1361 | 0
TOWER C LOWER BASEMENT FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 17 Feb 2023 |  | 0 | 0 | 1361 | 0
TOWER C UPPER BASEMENT | 0 |  |  |  | 26 Jul 2019 |  | 0 | 0 | 43670 | 0
TOWER C UPPER BASEMENT CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Jul 2019 |  | 0 | 0 | 59 | 0
TOWER C UPPER BASEMENT MASONRY WORK | 0 |  |  |  | 27 Jun 2022 |  | 0 | 0 | 44737 | 0
TOWER C UPPER BASEMENT 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 27 Jun 2022 |  | 0 | 0 | 1126 | 0
TOWER C UPPER BASEMENT RCC WORK | 0 |  |  |  | 26 Jul 2019 |  | 0 | 0 | 43670 | 0
TOWER C UPPER BASEMENT RCC WORK | 1 | CMT |  |  | 22 Aug 2023 |  | 0 | 0 | 45158 | 0
TOWER C UPPER BASEMENT RCC WORK FOR FLOOR RCC (TRIMIX) | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT RCC WORK FOR RETAINING WALL | 1 | CMT |  |  | 26 Jul 2019 | 26 Jul 2019 | 0 | 0 | 43670 | 43670
TOWER C UPPER BASEMENT RCC WORK FOR FOR SLAB_BASEMENT | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER C UPPER BASEMENT ROAD WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT INTERNAL SINGLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C UPPER BASEMENT PLUMBING WORK | 0 |  | 28 May 2019 |  | 01 Jan 2021 |  | 0 | 0 | 584 | 0
TOWER C UPPER BASEMENT PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2021 |  | 0 | 0 | 584 | 0
TOWER C UPPER BASEMENT PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 26 Nov 2022 |  | 0 | 0 | 1278 | 0
TOWER C UPPER BASEMENT ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 03 Oct 2023 |  | 0 | 0 | 1589 | 0
TOWER C UPPER BASEMENT ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 03 Oct 2023 |  | 0 | 0 | 1589 | 0
TOWER C UPPER BASEMENT MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Mar 2021 |  | 0 | 0 | 644 | 0
TOWER C UPPER BASEMENT COLOUR WORK | 0 |  | 28 May 2019 |  | 02 Mar 2021 |  | 0 | 0 | 644 | 0
TOWER C UPPER BASEMENT COLOUR WORK CEILING PUNNING | 1 | SQFT | 28 May 2019 |  | 02 Mar 2021 |  | 0 | 0 | 644 | 0
TOWER C UPPER BASEMENT PAINT WORK | 1 | SQFT | 28 May 2019 |  | 01 Aug 2023 |  | 0 | 0 | 1526 | 0
TOWER C UPPER BASEMENT FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  | 10 Aug 2022 |  | 0 | 0 | 1170 | 0
TOWER C UPPER BASEMENT FLOORING & DEDO WORK FLOORING & DEDO | 1 | SQFT | 28 May 2019 |  | 10 Aug 2022 |  | 0 | 0 | 1170 | 0
TOWER C GROUND FLOOR | 0 |  |  |  | 17 Sep 2019 |  | 0 | 0 | 43723 | 0
TOWER C GROUND FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 17 Sep 2019 |  | 0 | 0 | 112 | 0
TOWER C GROUND FLOOR MASONRY WORK | 0 |  |  |  | 01 Mar 2021 |  | 0 | 0 | 44254 | 0
TOWER C GROUND FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR 4.5" AAC BLOCK MASONRY WORK | 15852.37 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR MASONRY WORK REBARING 08MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER C GROUND FLOOR MASONRY WORK REBARING 10MM | 1 | NOS | 28 May 2019 |  | 01 Mar 2021 |  | 0 | 0 | 643 | 0
TOWER C GROUND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER C GROUND FLOOR 6" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR BRICK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RCC WORK | 0 |  |  |  | 17 Sep 2019 |  | 0 | 0 | 43723 | 0
TOWER C GROUND FLOOR RCC WORK | 1 | CMT |  |  | 21 Sep 2019 | 17 Sep 2019 | 0 | 0 | 43727 | 43723
TOWER C GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 21 Sep 2019 | 17 Sep 2019 | 0 | 0 | 43727 | 43723
TOWER C GROUND FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT | 28 May 2019 |  | 17 Sep 2019 | 17 Sep 2019 | 0 | 0 | 112 | 43723
TOWER C GROUND FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RCC WORK FOR PARKING | 1 | CMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RCC WORK BREAKER | 1 | DAY | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER C GROUND FLOOR RCC WORK BREAKER | 1 | HRS | 28 May 2019 |  | 04 Jan 2020 |  | 0 | 0 | 221 | 0
TOWER C GROUND FLOOR RCC WORK REBARING WORK 12MM | 10 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER C GROUND FLOOR RCC WORK REBARING 16MM | 44 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER C GROUND FLOOR RCC WORK REBARING 20MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER C GROUND FLOOR RCC WORK REBARING 10MM | 1 | NOS | 28 May 2019 |  | 19 Jun 2021 |  | 0 | 0 | 753 | 0
TOWER C GROUND FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RCC WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 08 Dec 2021 |  | 0 | 0 | 925 | 0
TOWER C GROUND FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER C GROUND FLOOR PCC WORK | 1 | SQFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER C GROUND FLOOR PLASTER WORK | 0 |  |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C GROUND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 6 | SQFT | 28 May 2019 |  | 01 Dec 2021 |  | 0 | 0 | 918 | 0
TOWER C GROUND FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT | 28 May 2019 |  | 12 Dec 2021 |  | 0 | 0 | 929 | 0
TOWER C GROUND FLOOR CIVIL WORK - AXIS BANK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR CIVIL WORK - AXIS BANK | 1 | NOS | 28 May 2019 |  | 01 May 2024 |  | 0 | 0 | 1800 | 0
TOWER C GROUND FLOOR FABRICATION WORK - AXIS BANK | 1 | NOS | 28 May 2019 |  | 01 May 2024 |  | 0 | 0 | 1800 | 0
TOWER C GROUND FLOOR PLUMBING WORK - AXIS BANK | 1 | NOS | 28 May 2019 |  | 01 May 2024 |  | 0 | 0 | 1800 | 0
TOWER C GROUND FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR EXTERNAL FACADE & WINDOWS WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR PLUMBING WORK | 0 |  |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER C GROUND FLOOR PLUMBING WORK | 1 | NOS |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER C GROUND FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C GROUND FLOOR ELECTRICAL WORK | 0 |  |  |  | 28 Aug 2023 |  | 0 | 0 | 45164 | 0
TOWER C GROUND FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR ELECTRICAL WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 28 Aug 2023 |  | 0 | 0 | 1553 | 0
TOWER C GROUND FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Nov 2020 |  | 0 | 0 | 524 | 0
TOWER C GROUND FLOOR SAFETY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR SAFETY WORK NET FIXING | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR SAFETY WORK FIXING OLD MATERIAL | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR COLOUR WORK | 0 |  | 28 May 2019 |  | 02 Nov 2020 |  | 0 | 0 | 524 | 0
TOWER C GROUND FLOOR COLOUR WORK CEILING PUNNING | 1 | SQFT | 28 May 2019 |  | 02 Nov 2020 |  | 0 | 0 | 524 | 0
TOWER C GROUND FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 03 Sep 2023 |  | 0 | 0 | 1559 | 0
TOWER C GROUND FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER C GROUND FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER C GROUND FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER C GROUND FLOOR SHOWROOM C ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER C GROUND FLOOR SHOP NO 1 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR SHOP NO 2 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR SHOP NO 3 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR SHOP NO 4 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR SHOP NO 5 & 6 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR SHOP NO 7 & 8 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR SHOP NO 9 ROLLING SHUTTER WORK | 1 | NOS | 28 May 2019 |  | 05 Oct 2022 |  | 0 | 0 | 1226 | 0
TOWER C GROUND FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C GROUND FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C GROUND FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER C GROUND FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 20 Sep 2023 |  | 0 | 0 | 1576 | 0
TOWER C GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Sep 2023 |  | 0 | 0 | 1576 | 0
TOWER C GROUND FLOOR LIFT | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR SHOWROOM C GOODS LIFT WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR LIFT OFFICE NO 9 PASSANGER LIFT WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER C GROUND FLOOR RAILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR RAILING WORK - AXIS BANK | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR LANDSCAPING & GARDENING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C GROUND FLOOR LANDSCAPING & GARDENING WORK | 1 | SQFT | 28 May 2019 |  | 01 Jul 2024 |  | 0 | 0 | 1861 | 0
TOWER C GROUND FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 05 Jan 2021 |  | 0 | 0 | 44199 | 0
TOWER C GROUND FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 15 Oct 2023 |  | 0 | 0 | 45212 | 0
TOWER C GROUND FLOOR SHOPS & SHOWROOM | 0 |  | 28 May 2019 |  | 05 Jan 2021 |  | 0 | 0 | 588 | 0
TOWER C GROUND FLOOR SHOWROOM C | 0 |  | 28 May 2019 |  | 05 Jan 2021 |  | 0 | 0 | 588 | 0
TOWER C GROUND FLOOR SHOWROOM C FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 05 Jan 2021 |  | 0 | 0 | 588 | 0
TOWER C GROUND FLOOR SHOP NO 1 | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR AXIS BANK SHOP NO 1 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 2 | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 2 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 3 | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 3 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 4 | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 4 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C GROUND FLOOR SHOP NO 5 TO 9 | 0 |  | 28 May 2019 |  | 15 Dec 2021 |  | 0 | 0 | 932 | 0
TOWER C GROUND FLOOR SHOP NO 5 TO 9 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2021 |  | 0 | 0 | 932 | 0
TOWER C 1ST FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER C 1ST FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 24 Sep 2019 |  | 0 | 0 | 119 | 0
TOWER C 1ST FLOOR MASONRY WORK | 0 |  |  |  | 03 Sep 2021 |  | 0 | 0 | 44440 | 0
TOWER C 1ST FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  | 08 Sep 2023 |  | 0 | 0 | 45175 | 0
TOWER C 1ST FLOOR DRY WALL WORK | 1 | SQFT | 28 May 2019 |  | 18 Oct 2021 |  | 0 | 0 | 874 | 0
TOWER C 1ST FLOOR MASONRY WORK REBARING 10MM | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER C 1ST FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER C 1ST FLOOR RCC WORK | 0 |  |  |  | 24 Sep 2019 |  | 0 | 0 | 43730 | 0
TOWER C 1ST FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 24 Sep 2019 |  | 0 | 0 | 43730 | 0
TOWER C 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Oct 2020 |  | 0 | 0 | 44132 | 0
TOWER C 1ST FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR RCC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 11 Sep 2021 |  | 0 | 0 | 837 | 0
TOWER C 1ST FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER C 1ST FLOOR PLASTER WORK | 0 |  |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C 1ST FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT | 28 May 2019 |  | 01 Dec 2021 |  | 0 | 0 | 918 | 0
TOWER C 1ST FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 20 Sep 2023 |  | 0 | 0 | 1576 | 0
TOWER C 1ST FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER C 1ST FLOOR PASAGE RAILING | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER C 1ST FLOOR PASAGE RAILING | 1 | RFT | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER C 1ST FLOOR PLUMBING WORK | 0 |  |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER C 1ST FLOOR PLUMBING WORK | 1 | NOS |  |  | 29 Oct 2021 |  | 0 | 0 | 44496 | 0
TOWER C 1ST FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 1ST FLOOR COMMON TOILET PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 28 Jul 2023 |  | 0 | 0 | 1522 | 0
TOWER C 1ST FLOOR ELECTRICAL WORK | 0 |  |  |  | 28 Aug 2023 |  | 0 | 0 | 45164 | 0
TOWER C 1ST FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR ELECTRICAL WORK | 1 | NOS | 28 May 2019 |  | 28 Aug 2023 |  | 0 | 0 | 1553 | 0
TOWER C 1ST FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR COLOUR WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER C 1ST FLOOR COLOR WORK APPLYING CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 22 Feb 2021 |  | 0 | 0 | 636 | 0
TOWER C 1ST FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR DEBRIS CHUTE | 0 |  |  |  | 02 Jan 2022 |  | 0 | 0 | 44561 | 0
TOWER C 1ST FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 1ST FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER C 1ST FLOOR SHOWROOM C ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 22 Dec 2021 |  | 0 | 0 | 939 | 0
TOWER C 1ST FLOOR SHOP NO 1 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 2 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 3 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 4 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 5 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 6 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 7 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR SHOP NO 8 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 12 Jan 2023 |  | 0 | 0 | 1325 | 0
TOWER C 1ST FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 1ST FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 1ST FLOOR COMMON TOILET ALUMINUM WORK | 1 | NOS | 28 May 2019 |  | 01 May 2024 |  | 0 | 0 | 1800 | 0
TOWER C 1ST FLOOR COMMON TOILET CARPENTRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR COMMON TOILET CARPENTRY WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  | 12 Jul 2023 |  | 0 | 0 | 1506 | 0
TOWER C 1ST FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 12 Jul 2023 |  | 0 | 0 | 1506 | 0
TOWER C 1ST FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR COMMON TOILET WATERPROOFING TEKIT | 1 | SQFT | 28 May 2019 |  | 01 Nov 2023 |  | 0 | 0 | 1618 | 0
TOWER C 1ST FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 1ST FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER C 1ST FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 02 Jan 2021 |  | 0 | 0 | 44196 | 0
TOWER C 1ST FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 30 May 2022 |  | 0 | 0 | 44709 | 0
TOWER C 1ST FLOOR SHOP & SHOWROOM | 0 |  | 28 May 2019 |  | 02 Jan 2021 |  | 0 | 0 | 585 | 0
TOWER C 1ST FLOOR SHOWROOM C | 0 |  | 28 May 2019 |  | 10 May 2022 |  | 0 | 0 | 1078 | 0
TOWER C 1ST FLOOR SHOWROOM C FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 10 May 2022 |  | 0 | 0 | 1078 | 0
TOWER C 1ST FLOOR SHOP NO 1 TO 4 | 0 |  | 28 May 2019 |  | 15 Feb 2022 |  | 0 | 0 | 994 | 0
TOWER C 1ST FLOOR SHOP NO 1 TO 4 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 Feb 2022 |  | 0 | 0 | 994 | 0
TOWER C 1ST FLOOR SHOP NO 5 TO 7 | 0 |  | 28 May 2019 |  | 02 Jan 2021 |  | 0 | 0 | 585 | 0
TOWER C 1ST FLOOR SHOP NO 5 TO 7 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 02 Jan 2021 |  | 0 | 0 | 585 | 0
TOWER C 1ST FLOOR SHOP NO 8 | 0 |  | 28 May 2019 |  | 10 Dec 2021 |  | 0 | 0 | 927 | 0
TOWER C 1ST FLOOR SHOP NO 8 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 10 Dec 2021 |  | 0 | 0 | 927 | 0
TOWER C 1ST FLOOR COMMON TOILET FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 18 Sep 2023 |  | 0 | 0 | 1574 | 0
TOWER C 2ND FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER C 2ND FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER C 2ND FLOOR MASONRY WORK | 0 |  |  |  | 03 Sep 2021 |  | 0 | 0 | 44440 | 0
TOWER C 2ND FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER C 2ND FLOOR MASONRY WORK REBARING 10MM | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER C 2ND FLOOR DRY WALL WORK | 1 | SQMT |  |  | 13 Oct 2022 |  | 0 | 0 | 44845 | 0
TOWER C 2ND FLOOR RCC WORK | 0 |  |  |  | 20 Mar 2020 |  | 0 | 0 | 43908 | 0
TOWER C 2ND FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 24 Jul 2020 |  | 0 | 0 | 44034 | 0
TOWER C 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C 2ND FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  | 24 Jul 2020 |  | 0 | 0 | 44034 | 0
TOWER C 2ND FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR RCC WORK PT CABLE LAYING | 1 | RMT | 28 May 2019 |  | 27 Aug 2020 |  | 0 | 0 | 457 | 0
TOWER C 2ND FLOOR RCC WORK TRIMIX SMOOTH FINISH | 1 | SQFT | 28 May 2019 |  | 02 Oct 2020 |  | 0 | 0 | 493 | 0
TOWER C 2ND FLOOR RCC WORK THREADING | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR RCC WORK THREADING 20MM | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER C 2ND FLOOR RCC WORK THREADING 25MM | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER C 2ND FLOOR RCC WORK THREADING 32MM | 1 | NOS | 28 May 2019 |  | 20 Mar 2020 |  | 0 | 0 | 297 | 0
TOWER C 2ND FLOOR RCC WORK LEGS WELDING | 1 | RFT | 28 May 2019 |  | 23 May 2020 |  | 0 | 0 | 361 | 0
TOWER C 2ND FLOOR RCC WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR RCC WORK REBARING 12MM | 1 | NOS | 28 May 2019 |  | 24 Apr 2021 |  | 0 | 0 | 697 | 0
TOWER C 2ND FLOOR RCC WORK REBARING 16MM | 1 | NOS | 28 May 2019 |  | 24 Apr 2021 |  | 0 | 0 | 697 | 0
TOWER C 2ND FLOOR RCC WORK REBARING 20MM | 1 | NOS | 28 May 2019 |  | 24 Apr 2021 |  | 0 | 0 | 697 | 0
TOWER C 2ND FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 11 Sep 2021 |  | 0 | 0 | 837 | 0
TOWER C 2ND FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER C 2ND FLOOR PLASTER WORK | 0 |  |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 50 | SQFT |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C 2ND FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER C 2ND FLOOR PASAGE RAILING | 0 |  | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER C 2ND FLOOR PASAGE RAILING | 1 | RFT | 28 May 2019 |  | 29 Mar 2023 |  | 0 | 0 | 1401 | 0
TOWER C 2ND FLOOR PLUMBING WORK | 0 |  |  |  | 30 Oct 2021 |  | 0 | 0 | 44497 | 0
TOWER C 2ND FLOOR PLUMBING WORK | 1 | NOS |  |  | 30 Oct 2021 |  | 0 | 0 | 44497 | 0
TOWER C 2ND FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 2ND FLOOR COMMON TOILET PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 28 Jul 2023 |  | 0 | 0 | 1522 | 0
TOWER C 2ND FLOOR ELECTRIC WORK | 0 |  |  |  | 08 Sep 2020 |  | 0 | 0 | 44080 | 0
TOWER C 2ND FLOOR ELECTRIC WORK | 1 | SQFT | 28 May 2019 |  | 01 Feb 2024 |  | 0 | 0 | 1710 | 0
TOWER C 2ND FLOOR ELECTRICAL WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 08 Sep 2020 |  | 0 | 0 | 469 | 0
TOWER C 2ND FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR COLOUR WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER C 2ND FLOOR COLOUR WORK CEILING PUNNING WORK | 1 | SQFT | 28 May 2019 |  | 22 May 2023 |  | 0 | 0 | 1455 | 0
TOWER C 2ND FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR SAFETY | 0 |  |  |  | 30 Jul 2021 |  | 0 | 0 | 44405 | 0
TOWER C 2ND FLOOR SAFETY | 1 | NOS | 28 May 2019 |  | 30 Jul 2021 |  | 0 | 0 | 794 | 0
TOWER C 2ND FLOOR DEBRIS CHUTE | 0 |  |  |  | 02 Jan 2022 |  | 0 | 0 | 44561 | 0
TOWER C 2ND FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 2ND FLOOR ROLLING SHUTTER WORK | 0 |  | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2ND FLOOR SHOWROOM C ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2ND FLOOR SHOP NO 1 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2ND FLOOR SHOP NO 2 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2ND FLOOR SHOP NO 3 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2ND FLOOR SHOP NO 4 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2nd FLOOR SHOP NO 5 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2nd FLOOR SHOP NO 6 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2nd FLOOR SHOP NO 7 ROLLING SHUTTER WORK | 1 | KG | 28 May 2019 |  | 11 Sep 2023 |  | 0 | 0 | 1567 | 0
TOWER C 2ND FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 2ND FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 2ND FLOOR COMMON TOILET ALUMINUM WORK | 1 | NOS | 28 May 2019 |  | 01 May 2024 |  | 0 | 0 | 1800 | 0
TOWER C 2ND FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  | 01 Mar 2024 |  | 0 | 0 | 1739 | 0
TOWER C 2ND FLOOR CARPENTRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR CARPENTRY WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR COMMON TOILET CARPENTRY WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR NAME PLATE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR NAME PLATE | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER C 2ND FLOOR WATERPROOFING WORK TEKIT | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 2ND FLOOR WATERPROOFING WORK TEKIT | 1 | SQFT | 28 May 2019 |  | 01 Nov 2023 |  | 0 | 0 | 1618 | 0
TOWER C 2ND FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 09 Nov 2020 |  | 0 | 0 | 44142 | 0
TOWER C 2ND FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 30 May 2022 |  | 0 | 0 | 44709 | 0
TOWER C 2ND FLOOR GROUTING | 0 |  | 28 May 2019 |  | 09 Nov 2020 |  | 0 | 0 | 531 | 0
TOWER C 2ND FLOOR GROUTING | 1 | SQFT | 28 May 2019 |  | 09 Nov 2020 |  | 0 | 0 | 531 | 0
TOWER C 2ND FLOOR SHOP & SHOWROOM | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2ND FLOOR SHOWROOM C | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2ND FLOOR SHOWROOM C FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2ND FLOOR SHOP NO 1 TO 4 | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2ND FLOOR SHOP NO 1 TO 4 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2ND FLOOR SHOP NO 5 TO 7 | 0 |  | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2nd FLOOR SHOP NO 5 TO 7 FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 15 May 2022 |  | 0 | 0 | 1083 | 0
TOWER C 2ND FLOOR COMMON TOILET FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 18 Sep 2023 |  | 0 | 0 | 1574 | 0
TOWER C 3RD FLOOR | 0 |  |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER C 3RD FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 31 Oct 2020 |  | 0 | 0 | 522 | 0
TOWER C 3RD FLOOR MASONRY WORK | 0 |  |  |  | 21 Dec 2020 |  | 0 | 0 | 44184 | 0
TOWER C 3RD FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR MASONRY WORK REBARING 8MM | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 3RD FLOOR MASONRY WORK REBARING 10MM | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 3RD FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 21 Dec 2020 |  | 0 | 0 | 573 | 0
TOWER C 3RD FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR RCC WORK | 0 |  |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER C 3RD FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 01 Dec 2021 |  | 0 | 0 | 44529 | 0
TOWER C 3RD FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER C 3RD FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER C 3RD FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 31 Oct 2020 |  | 0 | 0 | 44133 | 0
TOWER C 3RD FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 09 Nov 2020 |  | 0 | 0 | 44142 | 0
TOWER C 3RD FLOOR RCC WORK LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER C 3RD FLOOR RCC WORK WATERPROOFING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER C 3RD FLOOR ROAD WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR PLASTER WORK | 0 |  |  |  | 01 Jan 2022 |  | 0 | 0 | 44560 | 0
TOWER C 3RD FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  | 01 Jan 2022 |  | 0 | 0 | 44560 | 0
TOWER C 3RD FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR PLUMBING WORK | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 3RD FLOOR PLUMBING WORK | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C SHOPS TOILETS PROVISIONAL LINES PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER C 3RD FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 28 Jul 2023 |  | 0 | 0 | 1522 | 0
TOWER C 3RD FLOOR ELECTRIC WORK | 0 |  |  |  | 10 Apr 2021 |  | 0 | 0 | 44294 | 0
TOWER C 3RD FLOOR ELECTRIC WORK FOR SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER C 3RD FLOOR ELECTRIC WORK | 1 | SQFT | 28 May 2019 |  | 10 Apr 2021 |  | 0 | 0 | 683 | 0
TOWER C 3RD FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 18 Aug 2021 |  | 0 | 0 | 813 | 0
TOWER C 3RD FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 18 Aug 2021 |  | 0 | 0 | 813 | 0
TOWER C 3RD FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 18 Aug 2021 |  | 0 | 0 | 813 | 0
TOWER C 3RD FLOOR DEBRIS CHUTE | 0 |  |  |  | 02 Jan 2022 |  | 0 | 0 | 44561 | 0
TOWER C 3RD FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 3RD FLOOR COLOUR WORK | 0 |  | 28 May 2019 |  | 02 Sep 2023 |  | 0 | 0 | 1558 | 0
TOWER C 3RD FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
TOWER C 3RD FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 3RD FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 20 Dec 2023 |  | 0 | 0 | 1667 | 0
TOWER C 3RD FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR GLASS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR GLASS WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR CARPENTRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR CARPENTRY WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 3RD FLOOR FLOORING & DEDO WORK | 0 |  |  |  | 10 Aug 2022 |  | 0 | 0 | 44781 | 0
TOWER C 3RD FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  | 10 Aug 2022 |  | 0 | 0 | 44781 | 0
TOWER C 4TH FLOOR | 0 |  |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER C 4TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 19 Dec 2020 |  | 0 | 0 | 571 | 0
TOWER C 4TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Mar 2021 |  | 0 | 0 | 44254 | 0
TOWER C 4TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS |  |  | 06 Feb 2024 |  | 0 | 0 | 45326 | 0
VOID | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR 6" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR RCC WORK | 0 |  |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER C 4TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER C 4TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER C 4TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 19 Dec 2020 |  | 0 | 0 | 44182 | 0
TOWER C 4TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 28 Jan 2021 |  | 0 | 0 | 44222 | 0
TOWER C 4TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 22 Feb 2021 |  | 0 | 0 | 44247 | 0
TOWER C 4TH FLOOR RCC WORK LEGS WELDING | 1 | RFT | 28 May 2019 |  | 28 Jan 2021 |  | 0 | 0 | 611 | 0
TOWER C 4TH FLOOR RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 03 Sep 2021 |  | 0 | 0 | 829 | 0
TOWER C 4TH FLOOR RCC WORK EXPANSION JOINT | 1 | RFT | 28 May 2019 |  | 04 Aug 2023 |  | 0 | 0 | 1529 | 0
TOWER C 4TH FLOOR RCC WORK BREAKER | 1 | DAY | 28 May 2019 |  | 10 May 2024 |  | 0 | 0 | 1809 | 0
TOWER C 4TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 50 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 08 May 2022 |  | 0 | 0 | 1076 | 0
TOWER C 4TH FLOOR WATERPROOFING WORK WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 08 May 2022 |  | 0 | 0 | 1076 | 0
TOWER C 4TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR PLUMBING WORK | 0 |  | 28 May 2019 |  | 02 Apr 2022 |  | 0 | 0 | 1040 | 0
TOWER C 4TH FLOOR PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 02 Apr 2022 |  | 0 | 0 | 1040 | 0
TOWER C 4TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 12 Apr 2021 |  | 0 | 0 | 44296 | 0
TOWER C 4TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 12 Apr 2021 |  | 0 | 0 | 685 | 0
TOWER C 4TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 12 Apr 2021 |  | 0 | 0 | 685 | 0
TOWER C 4TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER C 4TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 02 Jan 2022 |  | 0 | 0 | 44561 | 0
TOWER C 4TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 4TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 4TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 20 Dec 2023 |  | 0 | 0 | 1667 | 0
TOWER C 4TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR PAINT WORK | 0 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR GLASS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR GLASS WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  | 29 May 2023 |  | 0 | 0 | 1462 | 0
TOWER C 4TH FLOOR FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 29 May 2023 |  | 0 | 0 | 1462 | 0
TOWER C 4TH FLOOR TERRACE CABIN FLOORING | 1 | SQFT | 28 May 2019 |  | 15 Jun 2023 |  | 0 | 0 | 1479 | 0
TOWER C 4TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 4TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR | 0 |  |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER C 5TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 24 Mar 2021 |  | 0 | 0 | 666 | 0
TOWER C 5TH FLOOR MASONRY WORK | 0 |  |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER C 5TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 5TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 19 Feb 2024 |  | 0 | 0 | 45339 | 0
TOWER C 5TH FLOOR RCC WORK | 0 |  |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER C 5TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER C 5TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER C 5TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 24 Mar 2021 |  | 0 | 0 | 44277 | 0
TOWER C 5TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 14 Apr 2021 |  | 0 | 0 | 44298 | 0
TOWER C 5TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 24 Apr 2021 |  | 0 | 0 | 44308 | 0
TOWER C 5TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 06 May 2021 |  | 0 | 0 | 709 | 0
TOWER C 5TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR PLUMBING WORK | 0 |  |  |  | 09 Mar 2022 |  | 0 | 0 | 44627 | 0
TOWER C 5TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 11 Oct 2022 |  | 0 | 0 | 44843 | 0
TOWER C 5TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 11 Oct 2022 |  | 0 | 0 | 1232 | 0
TOWER C 5TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 12 Apr 2021 |  | 0 | 0 | 44296 | 0
TOWER C 5TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 12 Apr 2021 |  | 0 | 0 | 685 | 0
TOWER C 5TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 12 Apr 2021 |  | 0 | 0 | 685 | 0
TOWER C 5TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 02 Jan 2022 |  | 0 | 0 | 950 | 0
TOWER C 5TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER C 5TH FLOOR SAFETY WORK | 1 | NOS | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER C 5TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 02 Jan 2022 |  | 0 | 0 | 44561 | 0
TOWER C 5TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 5TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 5TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 20 Dec 2023 |  | 0 | 0 | 1667 | 0
TOWER C 5TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 5TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER C 6TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 26 Apr 2021 |  | 0 | 0 | 699 | 0
TOWER C 6TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 6TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 19 Feb 2024 |  | 0 | 0 | 45339 | 0
TOWER C 6TH FLOOR RCC WORK | 0 |  |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER C 6TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER C 6TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER C 6TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 26 Apr 2021 |  | 0 | 0 | 44310 | 0
TOWER C 6TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 10 Jun 2021 |  | 0 | 0 | 44355 | 0
TOWER C 6TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  | 06 May 2021 |  | 0 | 0 | 709 | 0
TOWER C 6TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR PLUMBING WORK | 0 |  |  |  | 12 Apr 2022 |  | 0 | 0 | 44661 | 0
TOWER C 6TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 11 Oct 2022 |  | 0 | 0 | 44843 | 0
TOWER C 6TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 11 Oct 2022 |  | 0 | 0 | 1232 | 0
TOWER C 6TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 21 Jul 2021 |  | 0 | 0 | 44396 | 0
TOWER C 6TH FLOOR ELECTRICAL WORK SLAB CONDUTE | 1 | SQFT | 28 May 2019 |  | 21 Jul 2021 |  | 0 | 0 | 785 | 0
TOWER C 6TH FLOOR ELECTRICAL WORK FOR SLEEVE | 1 | NOS | 28 May 2019 |  | 21 Jul 2021 |  | 0 | 0 | 785 | 0
TOWER C 6TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 6TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 02 Jan 2022 |  | 0 | 0 | 44561 | 0
TOWER C 6TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 6TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 6TH FLOOR SAFETY WORK | 1 | NOS | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 6TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 6TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 20 Dec 2023 |  | 0 | 0 | 1667 | 0
TOWER C 6TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 6TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR | 0 |  |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER C 7TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 23 Jun 2021 |  | 0 | 0 | 757 | 0
TOWER C 7TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER C 7TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 7TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER C 7TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR RCC WORK | 0 |  |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER C 7TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER C 7TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER C 7TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 23 Jun 2021 |  | 0 | 0 | 44368 | 0
TOWER C 7TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 10 Sep 2021 |  | 0 | 0 | 44447 | 0
TOWER C 7TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 11 Sep 2021 |  | 0 | 0 | 44448 | 0
TOWER C 7TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER C 7TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR PLUMBING WORK | 0 |  |  |  | 19 May 2022 |  | 0 | 0 | 44698 | 0
TOWER C 7TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 11 Oct 2022 |  | 0 | 0 | 44843 | 0
TOWER C 7TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 11 Oct 2022 |  | 0 | 0 | 1232 | 0
TOWER C 7TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER C 7TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 01 Oct 2021 |  | 0 | 0 | 44468 | 0
TOWER C 7TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 7TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 7TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 7TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 7TH FLOOR SAFETY WORK | 1 | NOS | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 7TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 7TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 7TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 7TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR | 0 |  |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER C 8TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 03 Jul 2021 |  | 0 | 0 | 767 | 0
TOWER C 8TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER C 8TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 8TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 11 Mar 2024 |  | 0 | 0 | 45360 | 0
TOWER C 8TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR RCC WORK | 0 |  |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER C 8TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Sep 2021 |  | 0 | 0 | 44467 | 0
TOWER C 8TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 16 Oct 2021 |  | 0 | 0 | 44483 | 0
TOWER C 8TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 16 Oct 2021 |  | 0 | 0 | 44483 | 0
TOWER C 8TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 16 Oct 2021 |  | 0 | 0 | 44483 | 0
TOWER C 8TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 23 Oct 2021 |  | 0 | 0 | 44490 | 0
TOWER C 8TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 17 Sep 2021 |  | 0 | 0 | 44454 | 0
TOWER C 8TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 03 Jul 2021 |  | 0 | 0 | 44378 | 0
TOWER C 8TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR PLUMBING WORK | 0 |  |  |  | 23 Aug 2022 |  | 0 | 0 | 44794 | 0
TOWER C 8TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 11 Oct 2022 |  | 0 | 0 | 44843 | 0
TOWER C 8TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 11 Oct 2022 |  | 0 | 0 | 1232 | 0
TOWER C 8TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 06 Oct 2021 |  | 0 | 0 | 44473 | 0
TOWER C 8TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 06 Oct 2021 |  | 0 | 0 | 44473 | 0
TOWER C 8TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 8TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 8TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 8TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 8TH FLOOR SAFETY WORK | 1 | NOS | 28 May 2019 |  | 18 Nov 2021 |  | 0 | 0 | 905 | 0
TOWER C 8TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 8TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 8TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 8TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR | 0 |  |  |  | 11 Sep 2021 |  | 0 | 0 | 44448 | 0
TOWER C 9TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 11 Sep 2021 |  | 0 | 0 | 837 | 0
TOWER C 9TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER C 9TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER C 9TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 11 Mar 2024 |  | 0 | 0 | 45360 | 0
TOWER C 9TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR RCC WORK | 0 |  |  |  | 11 Sep 2021 |  | 0 | 0 | 44448 | 0
TOWER C 9TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 11 Sep 2021 |  | 0 | 0 | 44448 | 0
TOWER C 9TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER C 9TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER C 9TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 13 Oct 2021 |  | 0 | 0 | 44480 | 0
TOWER C 9TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 06 Dec 2021 |  | 0 | 0 | 44534 | 0
TOWER C 9TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 21 Nov 2021 |  | 0 | 0 | 44519 | 0
TOWER C 9TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER C 9TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR PLUMBING WORK | 1 | NOS |  |  | 11 Oct 2022 |  | 0 | 0 | 44843 | 0
TOWER C 9TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  | 11 Oct 2022 |  | 0 | 0 | 1232 | 0
TOWER C 9TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 21 Nov 2021 |  | 0 | 0 | 44519 | 0
TOWER C 9TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 21 Nov 2021 |  | 0 | 0 | 44519 | 0
TOWER C 9TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 01 Jan 2022 |  | 0 | 0 | 949 | 0
TOWER C 9TH FLOOR SAFETY WORK | 0 |  |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER C 9TH FLOOR SAFETY WORK | 1 | SQFT |  |  | 25 Aug 2022 |  | 0 | 0 | 44796 | 0
TOWER C 9TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 01 Jan 2022 |  | 0 | 0 | 44560 | 0
TOWER C 9TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 9TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 30 Jan 2023 |  | 0 | 0 | 1343 | 0
TOWER C 9TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER C 9TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 9TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR | 0 |  |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER C 10TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 27 Oct 2021 |  | 0 | 0 | 883 | 0
TOWER C 10TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER C 10TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER C 10TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR RCC WORK | 0 |  |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER C 10TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 07 Feb 2022 |  | 0 | 0 | 44597 | 0
TOWER C 10TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER C 10TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER C 10TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 17 Nov 2021 |  | 0 | 0 | 44515 | 0
TOWER C 10TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 02 Feb 2022 |  | 0 | 0 | 44592 | 0
TOWER C 10TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 02 Dec 2021 |  | 0 | 0 | 44530 | 0
TOWER C 10TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT |  |  | 27 Oct 2021 |  | 0 | 0 | 44494 | 0
TOWER C 10TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR ELECTRICAL WORK | 0 |  |  |  | 03 Feb 2022 |  | 0 | 0 | 44593 | 0
TOWER C 10TH FLOOR ELECTRICAL WORK | 1 | SQFT |  |  | 03 Feb 2022 |  | 0 | 0 | 44593 | 0
TOWER C 10TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER C 10TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 10TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 10TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER C 10TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 29 Mar 2022 |  | 0 | 0 | 1036 | 0
TOWER C 10TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 14 Dec 2022 |  | 0 | 0 | 1296 | 0
TOWER C 10TH FLOOR FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 14 Dec 2022 |  | 0 | 0 | 1296 | 0
TOWER C 10TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 10TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER C 11TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR MASONRY WORK | 0 |  |  |  | 01 Jan 2023 |  | 0 | 0 | 44925 | 0
TOWER C 11TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2023 |  | 0 | 0 | 1314 | 0
TOWER C 11TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 13 Mar 2024 |  | 0 | 0 | 45362 | 0
TOWER C 11TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR RCC WORK | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
TOWER C 11TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 12 Jan 2022 |  | 0 | 0 | 44571 | 0
TOWER C 11TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 12 Jan 2022 |  | 0 | 0 | 44571 | 0
TOWER C 11TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 12 Jan 2022 |  | 0 | 0 | 44571 | 0
TOWER C 11TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 24 Mar 2022 |  | 0 | 0 | 44642 | 0
TOWER C 11TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 11TH FLOOR THREADING CHARGES | 1 | NOS | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 10 Mar 2022 |  | 0 | 0 | 1017 | 0
TOWER C 11TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 10 Mar 2022 |  | 0 | 0 | 1017 | 0
TOWER C 11TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 25 Aug 2022 |  | 0 | 0 | 1185 | 0
TOWER C 11TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 11TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 11TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 25 Aug 2022 |  | 0 | 0 | 1185 | 0
TOWER C 11TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 25 Aug 2022 |  | 0 | 0 | 1185 | 0
TOWER C 11TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 11TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 12TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 14 Mar 2022 |  | 0 | 0 | 1021 | 0
TOWER C 12TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 12TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 06 Feb 2024 |  | 0 | 0 | 45326 | 0
TOWER C 12TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR RCC WORK | 0 |  |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 12TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 12TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 12TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 14 Mar 2022 |  | 0 | 0 | 44632 | 0
TOWER C 12TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 12TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER C 12TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 02 Jun 2022 |  | 0 | 0 | 1101 | 0
TOWER C 12TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 02 Jun 2022 |  | 0 | 0 | 1101 | 0
TOWER C 12TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 15 Nov 2022 |  | 0 | 0 | 1267 | 0
TOWER C 12TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 12TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 12TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Dec 2022 |  | 0 | 0 | 1302 | 0
TOWER C 12TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 12 Dec 2023 |  | 0 | 0 | 1659 | 0
TOWER C 12TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 12TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 12TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 12TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 13TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C 13TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 13TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 13 Mar 2024 |  | 0 | 0 | 45362 | 0
TOWER C 13TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR RCC WORK | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 13TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 13TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 28 May 2022 |  | 0 | 0 | 44707 | 0
TOWER C 13TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 28 May 2022 |  | 0 | 0 | 44707 | 0
TOWER C 13TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 13TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 22 Jun 2022 |  | 0 | 0 | 44732 | 0
TOWER C 13TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 06 Aug 2022 |  | 0 | 0 | 1166 | 0
TOWER C 13TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 06 Aug 2022 |  | 0 | 0 | 1166 | 0
TOWER C 13TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 15 Nov 2022 |  | 0 | 0 | 1267 | 0
TOWER C 13TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 15 Nov 2022 |  | 0 | 0 | 44878 | 0
TOWER C 13TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 13TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 13TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 13TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 03 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 04 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 05 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER C 13TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER C 13TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 13TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 14TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C 14TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 14TH FLOOR DRY WALL WORK | 1 | SQMT |  |  | 13 Mar 2024 |  | 0 | 0 | 45362 | 0
TOWER C 14TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR RCC WORK | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 14TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 14TH FLOOR FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 18 Aug 2022 |  | 0 | 0 | 44789 | 0
TOWER C 14TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 18 Aug 2022 |  | 0 | 0 | 44789 | 0
TOWER C 14TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 14TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 06 Oct 2022 |  | 0 | 0 | 44838 | 0
TOWER C 14TH FLOOR RCC WORK FOR LEGS WELDING | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 10 Oct 2022 |  | 0 | 0 | 1231 | 0
TOWER C 14TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 10 Oct 2022 |  | 0 | 0 | 1231 | 0
TOWER C 14TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 14TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 03 Apr 2023 |  | 0 | 0 | 45017 | 0
TOWER C 14TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 14TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 14TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 14TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 04 May 2023 |  | 0 | 0 | 1437 | 0
TOWER C 14TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 04 May 2023 |  | 0 | 0 | 1437 | 0
TOWER C 14TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 14TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 15TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 28 Apr 2022 |  | 0 | 0 | 1066 | 0
TOWER C 15TH FLOOR MASONRY WORK | 0 |  |  |  | 15 Sep 2023 |  | 0 | 0 | 45182 | 0
TOWER C 15TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 15 Sep 2023 |  | 0 | 0 | 1571 | 0
TOWER C 15TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR RCC WORK | 0 |  |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 15TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 15TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 01 Sep 2022 |  | 0 | 0 | 44803 | 0
TOWER C 15TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 01 Sep 2022 |  | 0 | 0 | 44803 | 0
TOWER C 15TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 28 Apr 2022 |  | 0 | 0 | 44677 | 0
TOWER C 15TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 12 Jan 2023 |  | 0 | 0 | 44936 | 0
TOWER C 15TH FLOOR THREADING CHARGES | 1 | NOS | 28 May 2019 |  | 05 Sep 2022 |  | 0 | 0 | 1196 | 0
TOWER C 15TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 15 Dec 2022 |  | 0 | 0 | 1297 | 0
TOWER C 15TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 15 Dec 2022 |  | 0 | 0 | 1297 | 0
TOWER C 15TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 05 Feb 2023 |  | 0 | 0 | 1349 | 0
TOWER C 15TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 03 Apr 2023 |  | 0 | 0 | 45017 | 0
TOWER C 15TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 15TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 05 Feb 2023 |  | 0 | 0 | 1349 | 0
TOWER C 15TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 05 Feb 2023 |  | 0 | 0 | 1349 | 0
TOWER C 15TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 15TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 03 Apr 2023 |  | 0 | 0 | 1406 | 0
TOWER C 15TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 15TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 16TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 30 Aug 2022 |  | 0 | 0 | 1190 | 0
TOWER C 16TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 16TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR RCC WORK | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 16TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 16TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 09 Dec 2022 |  | 0 | 0 | 44902 | 0
TOWER C 16TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 09 Dec 2022 |  | 0 | 0 | 44902 | 0
TOWER C 16TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 09 Dec 2022 |  | 0 | 0 | 44902 | 0
TOWER C 16TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 16 Mar 2023 |  | 0 | 0 | 44999 | 0
TOWER C 16TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 01 Sep 2023 |  | 0 | 0 | 45168 | 0
TOWER C 16TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 28 Feb 2023 |  | 0 | 0 | 1372 | 0
TOWER C 16TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 28 Feb 2023 |  | 0 | 0 | 1372 | 0
TOWER C 16TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 20 May 2023 |  | 0 | 0 | 1453 | 0
TOWER C 16TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 22 Sep 2023 |  | 0 | 0 | 45189 | 0
TOWER C 16TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 16TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 12 Sep 2023 |  | 0 | 0 | 1568 | 0
TOWER C 16TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 12 Sep 2023 |  | 0 | 0 | 1568 | 0
TOWER C 16TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 May 2023 |  | 0 | 0 | 1453 | 0
TOWER C 16TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 May 2023 |  | 0 | 0 | 1453 | 0
TOWER C 16TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 16TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 17TH FLOOR CIVIL WORK | 0 |  | 28 May 2019 |  | 30 Aug 2022 |  | 0 | 0 | 1190 | 0
TOWER C 17TH FLOOR MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR 9" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 06 Feb 2024 |  | 0 | 0 | 1715 | 0
TOWER C 17TH FLOOR DRY WALL WORK | 1 | SQMT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR 6" AAC BLOCK WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR RCC WORK | 0 |  |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 17TH FLOOR RCC WORK FOR COLUMN | 1 | CMT |  |  | 02 Dec 2023 |  | 0 | 0 | 45260 | 0
TOWER C 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT |  |  | 30 Aug 2022 |  | 0 | 0 | 44801 | 0
TOWER C 17TH FLOOR RCC WORK FOR LIFT PARDI | 1 | CMT |  |  | 02 Dec 2023 |  | 0 | 0 | 45260 | 0
TOWER C 17TH FLOOR RCC WORK FOR SILL & LINTEL | 1 | CMT |  |  | 02 Dec 2023 |  | 0 | 0 | 45260 | 0
TOWER C 17TH FLOOR RCC WORK THREADING 20MM | 1 | NOS |  |  | 20 Feb 2023 |  | 0 | 0 | 44975 | 0
TOWER C 17TH FLOOR RCC WORK THREADING 25MM | 1 | NOS |  |  | 20 Feb 2023 |  | 0 | 0 | 44975 | 0
TOWER C 17TH FLOOR RCC WORK THREADING 32MM | 1 | NOS |  |  | 20 Feb 2023 |  | 0 | 0 | 44975 | 0
TOWER C 17TH FLOOR RCC WORK PT CABLE LAYING | 1 | RMT |  |  | 20 Jun 2023 |  | 0 | 0 | 45095 | 0
TOWER C 17TH FLOOR RCC WORK REBARING WORK | 1 | NOS |  |  | 24 May 2023 |  | 0 | 0 | 45068 | 0
TOWER C 17TH FLOOR PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR PLUMBING WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR PLUMBING WORK | 1 | NOS |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR PLUMBING CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 12 Jul 2023 |  | 0 | 0 | 1506 | 0
TOWER C 17TH FLOOR ELECTRICAL WORK | 1 | SQFT | 28 May 2019 |  | 12 Jul 2023 |  | 0 | 0 | 1506 | 0
TOWER C 17TH FLOOR MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 12 Sep 2023 |  | 0 | 0 | 1568 | 0
TOWER C 17TH FLOOR DEBRIS CHUTE | 0 |  |  |  | 22 Sep 2023 |  | 0 | 0 | 45189 | 0
TOWER C 17TH FLOOR DEBRIS CHUTE | 1 | NOS |  |  | 12 Dec 2023 |  | 0 | 0 | 45270 | 0
TOWER C 17TH FLOOR FABRICATION WORK | 0 |  | 28 May 2019 |  | 12 Sep 2023 |  | 0 | 0 | 1568 | 0
TOWER C 17TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 12 Sep 2023 |  | 0 | 0 | 1568 | 0
TOWER C 17TH FLOOR WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR OFFICE NO 01 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR OFFICE NO 02 WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR FALSE CEILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR FALSE CEILING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR SAFETY WORK | 0 |  | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER C 17TH FLOOR SAFETY WORK | 1 | SQFT | 28 May 2019 |  | 20 Oct 2023 |  | 0 | 0 | 1606 | 0
TOWER C 17TH FLOOR FLOORING & DEDO WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR FLOORING & DEDO WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C 17TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE | 0 |  |  |  | 05 Aug 2023 |  | 0 | 0 | 45141 | 0
TOWER C TERRACE CIVIL WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE RCC WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C TERRACE RCC WORK FOR SLAB | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE RCC WORK PARAPAT WALL | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE RCC WORK REBARING WORK | 1 | NOS | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TOWER C TERRACE MASONRY WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C TERRACE 4.5" AAC BLOCK MASONRY WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE PLASTER WORK | 0 | [5 empty] | 0 | 0 | 0 | 0
TOWER C TERRACE INTERNAL MALA FINISH PLASTER WORK | 1 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE EXTERNAL DOUBLE COAT PLASTER WORK | 1263.34 | SQFT |  |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE EXTERNAL FACADE & WINDOWS WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE PLUMBING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE PLUMBING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 05 Aug 2023 |  | 0 | 0 | 1530 | 0
TOWER C TERRACE ELECTRIC WORK | 1 | NOS | 28 May 2019 |  | 05 Aug 2023 |  | 0 | 0 | 1530 | 0
TOWER C TERRACE MISCELLANEOUS WORK | 0 |  | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER C TERRACE FABRICATION WORK | 0 |  | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER C TERRACE FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 14 Sep 2023 |  | 0 | 0 | 1570 | 0
TOWER C TERRACE WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE PAINT WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE PAINT WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE FLOOR DEBRIS CHUTE | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE FLOOR DEBRIS CHUTE | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C TERRACE FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
INFRA | 0 |  |  |  | 28 May 2019 |  | 0 | 0 | 43611 | 0
FIRE FIGHTING | 0 |  | 28 May 2019 |  | 29 Jun 2022 |  | 0 | 0 | 1128 | 0
FIRE FIGHTING (2B TO 2ND FLOOR) | 1 | NOS | 28 May 2019 |  | 29 Jun 2022 |  | 0 | 0 | 1128 | 0
FIRE FIGHTING (3RD FLOOR TO ALL FLOOR) | 1 | NOS | 28 May 2019 |  | 10 Jul 2023 |  | 0 | 0 | 1504 | 0
FIRE FIGHTING FIRE ALARM WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
DG SET | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
DG SET | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
ESCALATOR/ELEVATORS | 0 |  | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
PASSANGER LIFT WORK | 1 | NOS | 28 May 2019 |  | 28 May 2019 |  | 0 | 0 | 0 | 0
INFRA CAR ELEVATOR | 1 | NOS | 28 May 2019 |  | 10 Feb 2023 |  | 0 | 0 | 1354 | 0
TOWER A PASSANGER LIFT | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A PASSANGER LIFT(16) - 1 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A PASSANGER LIFT(15) - 2 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B PASSANGER LIFT | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B PASSANGER LIFT(16) - 1 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B PASSANGER LIFT(15) - 2 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B PASSANGER LIFT(15) - 3 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER B PASSANGER LIFT(15) - 4 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C PASSANGER LIFT | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C PASSANGER LIFT(16) - 1 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C PASSANGER LIFT(15) - 2 | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
CONSULTANCY CHARGES | 0 |  | 28 May 2019 |  | 14 Dec 2022 |  | 0 | 0 | 1296 | 0
CONSULTANCY CHARGES | 1 | NOS | 28 May 2019 |  | 14 Dec 2022 |  | 0 | 0 | 1296 | 0
COMMON WORK | 0 |  | 28 May 2019 |  | 01 Feb 2014 |  | 0 | 0 | 0 | 0
COMMON CIVIL WORK | 0 |  | 28 May 2019 |  | 14 May 2020 |  | 0 | 0 | 352 | 0
COMMON CIVIL WORK | 1 | NOS | 28 May 2019 |  | 07 May 2024 |  | 0 | 0 | 1806 | 0
COMMON THREADING WORK | 0 |  | 28 May 2019 |  | 28 Jun 2021 |  | 0 | 0 | 762 | 0
COMMON THREADING WORK | 1 | MONTHS | 28 May 2019 |  | 28 Jun 2021 |  | 0 | 0 | 762 | 0
QC MATERIAL TESTING | 0 |  | 28 May 2019 |  | 06 Jul 2021 |  | 0 | 0 | 770 | 0
QC MATERIAL TESTING | 1 | NOS | 28 May 2019 |  | 06 Jul 2021 |  | 0 | 0 | 770 | 0
BOREWELL | 0 |  | 28 May 2019 |  | 23 May 2020 |  | 0 | 0 | 361 | 0
BOREWELL WORK | 1 | NOS | 28 May 2019 |  | 31 Oct 2020 |  | 0 | 0 | 522 | 0
REPAIR OF MUD PUMP | 1 | NOS | 28 May 2019 |  | 23 May 2020 |  | 0 | 0 | 361 | 0
INSTALLATION OF SUBMERSIBLE PUMP | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
REPAIR OF SUBMERSIBLE PUMP | 1 | NOS | 28 May 2019 |  | 23 May 2020 |  | 0 | 0 | 361 | 0
DEWATERING | 0 |  | 28 May 2019 |  | 14 May 2020 |  | 0 | 0 | 352 | 0
DEWATERING OPERATE DEWATERING PUMP | 1 | NOS | 28 May 2019 |  | 14 May 2020 |  | 0 | 0 | 352 | 0
COMMON PAVER BLOCK WORK | 0 |  | 28 May 2019 |  | 31 Oct 2020 |  | 0 | 0 | 522 | 0
COMMON PAVER BLOCK WORK | 1 | SQFT | 28 May 2019 |  | 31 Oct 2020 |  | 0 | 0 | 522 | 0
COMMON COMPOUND WALL | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON COMPOUND WALL MASONRY WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON COMPOUND WALL MASONRY WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON ROAD WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
ROAD WORK EXCAVATION | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
ROAD WORK RUBBLE SOILING | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
ROAD WORK METAL WMM | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
ROAD WORK QUARRY DUST | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON ROAD WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON LIFT WORK | 0 |  | 28 May 2019 |  | 01 Jul 2022 |  | 0 | 0 | 1130 | 0
COMMON PASSENGER LIFT (TOWER A-1) | 1 | NOS | 28 May 2019 |  | 30 Jul 2022 |  | 0 | 0 | 1159 | 0
COMMON PASSENGER LIFT (TOWER A-2) | 1 | NOS | 28 May 2019 |  | 30 Jul 2022 |  | 0 | 0 | 1159 | 0
COMMON PASSENGER LIFT (TOWER C-1) | 1 | NOS | 28 May 2019 |  | 30 Jul 2022 |  | 0 | 0 | 1159 | 0
COMMON PASSENGER LIFT (TOWER C-2) | 1 | NOS | 28 May 2019 |  | 30 Jul 2022 |  | 0 | 0 | 1159 | 0
COMMON LIFT MATERIAL HOIST : TOWER A | 1 | NOS | 28 May 2019 |  | 16 Dec 2022 |  | 0 | 0 | 1298 | 0
COMMON LIFT MATERIAL HOIST : TOWER C | 1 | NOS | 28 May 2019 |  | 16 Dec 2022 |  | 0 | 0 | 1298 | 0
COMMON LIFT WORK | 1 | NOS | 28 May 2019 |  | 01 Mar 2023 |  | 0 | 0 | 1373 | 0
COMMON LIFT MATERIAL HOIST : TOWER B | 1 | NOS | 28 May 2019 |  | 01 Mar 2023 |  | 0 | 0 | 1373 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER A-1) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER A-2) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER B-1) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER B-2) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER B-3) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER B-4) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER C-1) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON LIFT WORK COMMON PASSENGER LIFT REAR (TOWER C-2) | 1 | NOS | 28 May 2019 |  | 06 Apr 2024 |  | 0 | 0 | 1775 | 0
COMMON WORK EXTERNAL FACADE & WINDOWS | 0 |  | 28 May 2019 |  | 19 May 2023 |  | 0 | 0 | 1452 | 0
EXTERNAL FACADE WORK 4TH TO 17TH FLOOR | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL FACADE WORK : TOWER A | 1 | NOS | 28 May 2019 |  | 28 Feb 2024 |  | 0 | 0 | 1737 | 0
EXTERNAL FACADE WORK : TOWER B | 1 | NOS | 28 May 2019 |  | 27 Nov 2023 |  | 0 | 0 | 1644 | 0
EXTERNAL FACADE WORK : TOWER C | 1 | NOS | 28 May 2019 |  | 16 Feb 2024 |  | 0 | 0 | 1725 | 0
EXTERNAL FACADE WORK GF TO 3RD FLOOR | 0 |  | 28 May 2019 |  | 19 May 2023 |  | 0 | 0 | 1452 | 0
EXTERNAL FACADE WORK GF TO 3RD FLOOR | 1 | NOS | 28 May 2019 |  | 19 May 2023 |  | 0 | 0 | 1452 | 0
EXTERNAL FACADE TESTING WORK | 0 |  | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
EXTERNAL FACADE TESTING WORK | 1 | NOS | 28 May 2019 |  | 01 Oct 2023 |  | 0 | 0 | 1587 | 0
COMMON ELECTRICAL WORK | 0 |  | 28 May 2019 |  | 01 Mar 2022 |  | 0 | 0 | 1008 | 0
COMMON ELECTRIC WORK | 1 | NOS | 28 May 2019 |  | 01 Mar 2022 |  | 0 | 0 | 1008 | 0
COMMON CCTV WORK | 1 | NOS | 28 May 2019 |  | 01 Feb 2023 |  | 0 | 0 | 1345 | 0
COMMON ELECTRICAL HT CABLE LAYING WORK | 1 | NOS | 28 May 2019 |  | 21 Feb 2024 |  | 0 | 0 | 1730 | 0
COMMON MISC ELECTRICAL EARTHINGS WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON PLUMBING WORK | 0 |  | 28 May 2019 |  | 12 Apr 2023 |  | 0 | 0 | 1415 | 0
COMMON PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
COMMON STP PLUMBING WORK | 1 | SQFT | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
COMMON WATER SOFTNER SYSTEM | 1 | NOS | 28 May 2019 |  | 12 Apr 2024 |  | 0 | 0 | 1781 | 0
COMMON WATER PRESSURE SYSTEM | 1 | NOS | 28 May 2019 |  | 12 Apr 2024 |  | 0 | 0 | 1781 | 0
COMMON MISCELLENEOUS WORK | 0 |  | 28 May 2019 |  | 01 Feb 2014 |  | 0 | 0 | 0 | 0
COMMON MAINTANANCE WORK | 0 |  | 28 May 2019 |  | 24 Jul 2020 |  | 0 | 0 | 423 | 0
COMMON MAINTANANCE WORK | 1 | NOS | 28 May 2019 |  | 24 Jul 2020 |  | 0 | 0 | 423 | 0
COMMON CARTING EXPENSES | 0 |  | 28 May 2019 |  | 01 Feb 2014 |  | 0 | 0 | 0 | 0
COMMON CARTING EXPENSES | 1 | NOS | 28 May 2019 |  | 07 May 2024 |  | 0 | 0 | 1806 | 0
COMMON WORK GARDENING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON WORK GARDENING WORK | 1 | SQFT | 28 May 2019 |  | 01 Jul 2024 |  | 0 | 0 | 1861 | 0
COMMON LANDSCAPING & GARDENING WORK | 1 | SQFT | 28 May 2019 |  | 01 Jul 2024 |  | 0 | 0 | 1861 | 0
COMMON MISCELLENEOUS WORK | 0 |  | 28 May 2019 |  | 04 Jul 2020 |  | 0 | 0 | 403 | 0
COMMON MISC FIRE AND SAFETY WORK | 1 | NOS | 28 May 2019 |  | 21 Dec 2020 |  | 0 | 0 | 573 | 0
COMMON MISC HOUSEKEEPING | 1 | NOS | 28 May 2019 |  | 04 Jul 2020 |  | 0 | 0 | 403 | 0
MISCELLANEOUS SAFETY WORK | 1 | NOS | 28 May 2019 |  | 23 Jul 2021 |  | 0 | 0 | 787 | 0
COMMON MISC WORK | 1 | NOS | 28 May 2019 |  | 16 Oct 2021 |  | 0 | 0 | 872 | 0
COMMON MISC FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 20 Nov 2021 |  | 0 | 0 | 907 | 0
COMMON EXHAUST SYSTEM | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON EXHAUST SYSTEM | 1 | NOS | 28 May 2019 |  | 01 Jul 2022 |  | 0 | 0 | 1130 | 0
COMMON UG TANK | 0 |  | 28 May 2019 |  | 05 Apr 2023 |  | 0 | 0 | 1408 | 0
COMMON UG TANK WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 05 Apr 2023 |  | 0 | 0 | 1408 | 0
COMMON UG TANK PLASTER WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON UG TANK FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 20 Feb 2024 |  | 0 | 0 | 1729 | 0
COMMON TEXTURE WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON TEXTURE WORK | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON RAILING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER A STAIRCASE RAILING WORK - RETAIL AREA | 1 | RFT | 28 May 2019 |  | 01 Feb 2024 |  | 0 | 0 | 1710 | 0
TOWER B STAIRCASE RAILING WORK - RETAIL AREA | 1 | RFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TOWER C STAIRCASE RAILING WORK - RETAIL AREA | 1 | RFT | 28 May 2019 |  | 01 Feb 2024 |  | 0 | 0 | 1710 | 0
COMMON WATERPROOFING WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON STP WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Jan 2024 |  | 0 | 0 | 1679 | 0
COMMON SOLAR SYSTEM | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON SOLAR SYSTEM | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON FLOORING & DEDO WORK | 0 |  | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
COMMON FLOORING & DEDO WORK | 1 | SQFT | 28 May 2019 |  | 01 Apr 2024 |  | 0 | 0 | 1770 | 0
COMMON FABRICATION WORK | 0 |  | 28 May 2019 |  | 22 Jun 2021 |  | 0 | 0 | 756 | 0
COMMON FABRICATION WORK BRIDGE CONNECTION WORK | 1 | LUMSUM | 28 May 2019 |  | 06 Oct 2022 |  | 0 | 0 | 1227 | 0
COMMON FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 22 Jun 2021 |  | 0 | 0 | 756 | 0
SALES | 0 |  | 28 May 2019 |  | 11 Aug 2021 |  | 0 | 0 | 806 | 0
TOWER A | 0 |  | 28 May 2019 |  | 11 Aug 2021 |  | 0 | 0 | 806 | 0
TOWER A 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 28 Aug 2021 | 28 Aug 2021 | 0 | 0 | 823 | 44434
TOWER A 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 11 Aug 2021 | 11 Aug 2021 | 0 | 0 | 806 | 44417
TOWER B | 0 |  | 28 May 2019 |  | 11 Aug 2021 |  | 0 | 0 | 806 | 0
TOWER B 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 28 Aug 2021 | 28 Aug 2021 | 0 | 0 | 823 | 44434
TOWER B 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 11 Aug 2021 | 11 Aug 2021 | 0 | 0 | 806 | 44417
TOWER C | 0 |  | 28 May 2019 |  | 11 Aug 2021 |  | 0 | 0 | 806 | 0
TOWER C 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 28 Aug 2021 | 28 Aug 2021 | 0 | 0 | 823 | 44434
TOWER C 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 28 May 2019 |  | 11 Aug 2021 | 11 Aug 2021 | 0 | 0 | 806 | 44417
TRION (I) | 0 |  | 28 May 2019 |  | 10 Aug 2021 |  | 0 | 0 | 805 | 0
TRION (I) ROAD WORK | 0 |  | 28 May 2019 |  | 10 Aug 2021 |  | 0 | 0 | 805 | 0
TRION (I) ROAD WORK | 1 | SQFT | 28 May 2019 |  | 10 Aug 2021 |  | 0 | 0 | 805 | 0
TRION (I) WATERPROOFING WORK | 0 |  | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TRION (I) WATERPROOFING WORK | 1 | SQFT | 28 May 2019 |  | 01 Sep 2023 |  | 0 | 0 | 1557 | 0
TRION (I) WATERPROOFING WORK CHINA MOSAIC | 1 | SQFT | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TRION (I) MISC WORK | 0 |  | 28 May 2019 |  | 12 Aug 2023 |  | 0 | 0 | 1537 | 0
TRION (I) MISC WORK | 1 | NOS | 28 May 2019 |  | 12 Aug 2023 |  | 0 | 0 | 1537 | 0
TRION (I) FABRICATION WORK | 0 |  | 28 May 2019 |  | 11 Mar 2023 |  | 0 | 0 | 1383 | 0
TRION (I) FABRICATION WORK | 1 | NOS | 28 May 2019 |  | 11 Mar 2023 |  | 0 | 0 | 1383 | 0
TRION (I) PAINT WORK | 0 |  | 28 May 2019 |  | 14 Oct 2021 |  | 0 | 0 | 870 | 0
TRION (I) PAINT WORK | 1 | SQFT | 28 May 2019 |  | 04 Sep 2023 |  | 0 | 0 | 1560 | 0
TRION (I) COLOUR WORK OFICE NO 501 | 1 | SQFT | 28 May 2019 |  | 14 Oct 2021 |  | 0 | 0 | 870 | 0
TRION (I) COLOUR WORK OFFICE NO 701 | 1 | SQMT | 28 May 2019 |  | 14 Oct 2021 |  | 0 | 0 | 870 | 0
TRION (I) COLOUR WORK OFFICE NO 901 | 1 | SQMT | 28 May 2019 |  | 14 Oct 2021 |  | 0 | 0 | 870 | 0
TRION (I) FLOORING WORK | 0 |  | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TRION (I) FLOORING WORK | 1 | SQFT | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TRION (I) GROUTING WORK | 1 | SQFT | 28 May 2019 |  | 22 Aug 2023 |  | 0 | 0 | 1547 | 0
TRION (I) CIVIL WORK | 0 |  | 28 May 2019 |  | 22 Nov 2022 |  | 0 | 0 | 1274 | 0
TRION (I) CIVIL WORK | 1 | NOS | 28 May 2019 |  | 22 Nov 2022 |  | 0 | 0 | 1274 | 0
TRION (I) CIVIL WORK CORE CUTTING WORK | 1 | NOS | 28 May 2019 |  |  |  | 0 | 0 | 0 | 0
TRION (I) CARTING EXPENSES | 0 |  | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TRION (I) CARTING EXPENSES | 1 | NOS | 28 May 2019 |  | 02 Dec 2022 |  | 0 | 0 | 1284 | 0
TRION (I) ELECTRIC WORK | 0 |  | 28 May 2019 |  | 20 Jun 2023 |  | 0 | 0 | 1484 | 0
TRION (I) ELECTRIC WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2023 |  | 0 | 0 | 1484 | 0
TRION (I) PUNNING WORK | 0 |  | 28 May 2019 |  | 13 Mar 2023 |  | 0 | 0 | 1385 | 0
TRION (I) PUNNING WORK OFFICE NO 212-213 | 0 |  | 28 May 2019 |  | 13 Mar 2023 |  | 0 | 0 | 1385 | 0
TRION (I) PUNNING WORK OFFICE NO 212-213 | 1 | SQFT | 28 May 2019 |  | 13 Mar 2023 |  | 0 | 0 | 1385 | 0
TRION (I) PUNNING WORK GYPSUM WORK | 0 |  | 28 May 2019 |  | 17 May 2023 |  | 0 | 0 | 1450 | 0
TRION (I) PUNNING WORK GYPSUM WORK | 1 | RFT | 28 May 2019 |  | 17 May 2023 |  | 0 | 0 | 1450 | 0
TRION (I) CARPENTRY WORK | 0 |  | 28 May 2019 |  | 11 Mar 2023 |  | 0 | 0 | 1383 | 0
TRION (I) CARPENTRY WORK | 1 | NOS | 28 May 2019 |  | 11 Mar 2023 |  | 0 | 0 | 1383 | 0
TRION (I) GLASS WORK | 0 |  | 28 May 2019 |  | 27 Mar 2023 |  | 0 | 0 | 1399 | 0
TRION (I) GLASS WORK | 1 | SQFT | 28 May 2019 |  | 27 Mar 2023 |  | 0 | 0 | 1399 | 0
TRION (I) PLUMBING WORK | 0 |  | 28 May 2019 |  | 12 Apr 2023 |  | 0 | 0 | 1415 | 0
TRION (I) PLUMBING WORK | 1 | NOS | 28 May 2019 |  | 12 Apr 2023 |  | 0 | 0 | 1415 | 0
TRION (I) TENNIS COURT | 0 |  | 28 May 2019 |  | 12 Aug 2023 |  | 0 | 0 | 1537 | 0
TRION (I) TENNIS COURT | 1 | NOS | 28 May 2019 |  | 12 Aug 2023 |  | 0 | 0 | 1537 | 0
TRION (I) BORE WELL WORK | 0 |  | 28 May 2019 |  | 20 Jun 2023 |  | 0 | 0 | 1484 | 0
TRION (I) BORE WELL WORK | 1 | NOS | 28 May 2019 |  | 20 Jun 2023 |  | 0 | 0 | 1484 | 0