## Task Details638628626902702042_
Task Details
Project Name : NEPTUNE TRION EXP
Task Name : TOWER A 17TH FLOOR DUCT FABRICATION WORK
Total Records: 1 Records 1 to 1
Page 1 of 1
TaskType | Level | TaskNo | Identification1 | Identification2 | Identification3 | ParentTask | Task | VOLOFWORK M | M Unit | VOLOFWORK L | L Unit | Task Rate | Task Category 1 | Task Status | Estimated Mat Amt | Estimated Lab Amt | Estimated Task Amt | % Comp | Est Cost of Completion(BCWP) | Actual Cost Material | Actual Cost Labour | Actual Cost | Planned Start(PS) | Planned Finish(PF) | Actual Start(AS) | Actual Finish(AF) | Planned Duration=(PS)-(PF) Days | Actual Duration=(AS)-(AF) Days | Start Variance=(PS)-(AS) Days | Finish Variance=(PF)-(AF) Days | Library Task Name | Task Description
Task | 6 | 34072 |  |  |  | TOWER A 17TH FLOOR FABRICATION WORK | TOWER A 17TH FLOOR DUCT FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 26515.64 | 26515.64 | 28 May 2019 |  | 03 Apr 2023 |  | - | - | 1407 | - | MISCELLANEOUS FABRICATION WORK