## Task Details638658825777059270_
Task Details
Project Name : GREENWOODS AARANYA
Task Name : All
Total Records: 5858 Records 1 to 5000
Page 1 of 2
TaskType | Level | TaskNo | Identification1 | Identification2 | Identification3 | ParentTask | Task | VOLOFWORK M | M Unit | VOLOFWORK L | L Unit | Task Rate | Task Category 1 | Task Status | Estimated Mat Amt | Estimated Lab Amt | Estimated Task Amt | % Comp | Est Cost of Completion(BCWP) | Actual Cost Material | Actual Cost Labour | Actual Cost | Planned Start(PS) | Planned Finish(PF) | Actual Start(AS) | Actual Finish(AF) | Planned Duration=(PS)-(PF) Days | Actual Duration=(AS)-(AF) Days | Start Variance=(PS)-(AS) Days | Finish Variance=(PF)-(AF) Days | Library Task Name | Task Description
Group | 2 | 24079 |  |  |  |  | TOWER A | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Apr 2022 |  | - | - | 760 | -
Group | 3 | 24080 |  |  |  | TOWER A | TOWER A BASEMENT | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Apr 2022 |  | - | - | 760 | -
Group | 4 | 24083 |  |  |  | TOWER A BASEMENT | TOWER A BASEMENT CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Apr 2022 |  | - | - | 760 | -
Group | 5 | 24084 |  |  |  | TOWER A BASEMENT CIVIL WORK | TOWER A BASEMENT RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Apr 2022 |  | - | - | 760 | -
Task | 6 | 24086 |  |  |  | TOWER A BASEMENT RCC WORK | TOWER A BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 374917.5 |  | Started | 354917.5 | 20000 | 374917.5 | 32.63 | 12234749.51 | 0 | 7355648 | 7355648 | 17 Mar 2020 |  | 20 Sep 2022 |  | - | - | 918 | - | RCC WORK FOR SLAB
Task | 6 | 25961 |  |  |  | TOWER A BASEMENT RCC WORK | TOWER A BASEMENT RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 123103.52 | 123103.52 | 17 Mar 2020 |  | 15 Apr 2022 |  | - | - | 760 | - | THREADING
Task | 6 | 35201 |  |  |  | TOWER A BASEMENT RCC WORK | TOWER A BASEMENT RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 98530 | 98530 | 17 Mar 2020 |  | 12 May 2023 |  | - | - | 1152 | - | REBARING WORK
Group | 5 | 24085 |  |  |  | TOWER A BASEMENT CIVIL WORK | TOWER A BASEMENT PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 24087 |  |  |  | TOWER A BASEMENT PLASTER WORK | TOWER A BASEMENT PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 24866 |  |  |  | TOWER A BASEMENT | TOWER A BASEMENT FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2022 |  | - | - | - | -
Group | 5 | 24869 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Jul 2023 |  | - | - | 1216 | -
Task | 6 | 24867 |  |  |  | TOWER A BASEMENT WATERPROOFING WORK | TOWER A BASEMENT WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 9.8 | 0 | 0 | 459405.45 | 459405.45 |  |  | 15 Jul 2023 |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27510 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 25892 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Sep 2022 |  | - | - | 918 | -
Task | 6 | 25893 |  |  |  | TOWER A BASEMENT ELECTRIC WORK | TOWER A BASEMENT ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 106589.4 | 106589.4 | 17 Mar 2020 |  | 20 Sep 2022 |  | - | - | 918 | - | ELECTRIC WORK
Group | 5 | 27511 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27517 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27512 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27516 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27521 |  |  |  | TOWER A BASEMENT FINISHING WORK | TOWER A BASEMENT HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 27513 |  |  |  | TOWER A BASEMENT | TOWER A BASEMENT COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27520 |  |  |  | TOWER A BASEMENT COMMON WORK | TOWER A BASEMENT COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39399 |  |  |  | TOWER A BASEMENT COMMON DEBRISH CHUTE WORK | TOWER A BASEMENT COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27518 |  |  |  | TOWER A BASEMENT COMMON WORK | TOWER A BASEMENT COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27519 |  |  |  | TOWER A BASEMENT COMMON WORK | TOWER A BASEMENT COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27711 |  |  |  | TOWER A BASEMENT COMMON WORK | TOWER A BASEMENT COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29454 |  |  |  | TOWER A BASEMENT COMMON WORK | TOWER A BASEMENT COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 39323 |  |  |  | TOWER A BASEMENT | TOWER A BASEMENT EXTRA CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 39324 |  |  |  | TOWER A BASEMENT EXTRA CIVIL WORK | TOWER A BASEMENT EXTRA CIVIL WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 119978.01 | 119978.01 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | CIVIL EXTRA WORK
Group | 3 | 24081 |  |  |  | TOWER A | TOWER A GROUND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2022 |  | - | - | 910 | -
Group | 4 | 24088 |  |  |  | TOWER A GROUND FLOOR | TOWER A GROUND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2022 |  | - | - | 910 | -
Group | 5 | 24089 |  |  |  | TOWER A GROUND FLOOR CIVIL WORK | TOWER A GROUND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2022 |  | - | - | 910 | -
Task | 6 | 24092 |  |  |  | TOWER A GROUND FLOOR RCC WORK | TOWER A GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 338152.96 |  | Started | 338152.96 | 0 | 338152.96 | 11.07 | 3744205.41 | 0 | 2199474.7 | 2199474.7 | 17 Mar 2020 |  | 14 Nov 2022 |  | - | - | 973 | - | RCC WORK FOR SLAB
Task | 6 | 32569 |  |  |  | TOWER A GROUND FLOOR RCC WORK | TOWER A GROUND FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 60534 | 60534 | 17 Mar 2020 |  | 12 Sep 2022 |  | - | - | 910 | - | THREADING
Task | 6 | 32666 |  |  |  | TOWER A GROUND FLOOR RCC WORK | TOWER A GROUND FLOOR RCC REBARING WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 23434.8 | 23434.8 | 17 Mar 2020 |  | 10 Jan 2023 |  | - | - | 1030 | - | REBARING WORK
Group | 5 | 24090 |  |  |  | TOWER A GROUND FLOOR CIVIL WORK | TOWER A GROUND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 24093 |  |  |  | TOWER A GROUND FLOOR MASONRY WORK | TOWER A GROUND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 618068.15 |  | Started | 618068.15 | 0 | 618068.15 | 0 | 618.07 | 0 | 470930.92 | 470930.92 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | MASONRY WORK
Group | 5 | 24091 |  |  |  | TOWER A GROUND FLOOR CIVIL WORK | TOWER A GROUND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 24112 |  |  |  | TOWER A GROUND FLOOR PLASTER WORK | TOWER A GROUND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27522 |  |  |  | TOWER A GROUND FLOOR | TOWER A GROUND FLOOR FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | -
Group | 5 | 27524 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27523 |  |  |  | TOWER A GROUND FLOOR WATERPROOFING WORK | TOWER A GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27527 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27525 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | -
Task | 6 | 27526 |  |  |  | TOWER A GROUND FLOOR ELECTRIC WORK | TOWER A GROUND FLOOR ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 143430.88 | 143430.88 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | - | ELECTRIC WORK
Group | 5 | 27528 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42034 |  |  |  | TOWER A GROUND FLOOR FLOORING & DEDO WORK | TOWER A GROUND FLOOR FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 60 |  | Tentative | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27531 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27529 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27530 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27532 |  |  |  | TOWER A GROUND FLOOR FINISHING WORK | TOWER A GROUND FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 27566 |  |  |  | TOWER A GROUND FLOOR | TOWER A GROUND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | -
Group | 5 | 27569 |  |  |  | TOWER A GROUND FLOOR COMMON WORK | TOWER A GROUND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39275 |  |  |  | TOWER A GROUND FLOOR COMMON DEBRISH CHUTE WORK | TOWER A GROUND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27567 |  |  |  | TOWER A GROUND FLOOR COMMON WORK | TOWER A GROUND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 28 May 2023 |  | - | - | 1168 | -
Task | 6 | 37093 |  |  |  | TOWER A GROUND FLOOR COMMON FLOORING WORK | TOWER A GROUND FLOOR COMMON FLOORING WORK QC LAB | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6403.76 | 6403.76 | 17 Mar 2020 |  | 28 May 2023 |  | - | - | 1168 | - | FLOORING & DEDO
Group | 5 | 27568 |  |  |  | TOWER A GROUND FLOOR COMMON WORK | TOWER A GROUND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27712 |  |  |  | TOWER A GROUND FLOOR COMMON WORK | TOWER A GROUND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27715 |  |  |  | TOWER A GROUND FLOOR COMMON WORK | TOWER A GROUND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | -
Task | 6 | 33436 |  |  |  | TOWER A GROUND FLOOR COMMON ELECTRIC WORK | TOWER A GROUND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 117.9 |  | Started | 117.9 | 0 | 117.9 | 0 | 0.12 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | - | ELECTRIC WORK
Group | 5 | 42247 |  |  |  | TOWER A GROUND FLOOR COMMON WORK | TOWER A GROUND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42248 |  |  |  | TOWER A GROUND FLOOR WPC PANNELING WORK | TOWER A GROUND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24082 |  |  |  | TOWER A | TOWER A 1ST FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 03 Oct 2022 |  | - | - | 931 | -
Group | 4 | 24129 |  |  |  | TOWER A 1ST FLOOR | TOWER A 1ST FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 03 Oct 2022 |  | - | - | - | -
Group | 5 | 24130 |  |  |  | TOWER A 1ST FLOOR CIVIL WORK | TOWER A 1ST FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 03 Oct 2022 |  | - | - | - | -
Task | 6 | 24133 |  |  |  | TOWER A 1ST FLOOR RCC WORK | TOWER A 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 53025.84 |  | Started | 53025.84 | 0 | 53025.84 | 8.9 | 472003.36 | 0 | 1686739.22 | 1686739.22 |  |  | 03 Mar 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33354 |  |  |  | TOWER A 1ST FLOOR RCC WORK | TOWER A 1ST FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 70587.6 | 70587.6 | 17 Mar 2020 |  | 03 Oct 2022 |  | - | - | 931 | - | THREADING
Group | 5 | 24131 |  |  |  | TOWER A 1ST FLOOR CIVIL WORK | TOWER A 1ST FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 Jul 2023 |  | - | - | - | -
Task | 6 | 24134 |  |  |  | TOWER A 1ST FLOOR MASONRY WORK | TOWER A 1ST FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Started | 640621.7 | 0 | 640621.7 | 8.9 | 5702419.75 | 0 | 430630.41 | 430630.41 |  |  | 19 Oct 2023 |  | - | - | - | - | MASONRY WORK
Task | 6 | 38101 |  |  |  | TOWER A 1ST FLOOR MASONRY WORK | TOWER A 1ST FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 37630.2 | 37630.2 | 17 Mar 2020 |  | 16 Jul 2023 |  | - | - | 1217 | - | REBARING WORK
Group | 5 | 24132 |  |  |  | TOWER A 1ST FLOOR CIVIL WORK | TOWER A 1ST FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24135 |  |  |  | TOWER A 1ST FLOOR PLASTER WORK | TOWER A 1ST FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27570 |  |  |  | TOWER A 1ST FLOOR | TOWER A 101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27535 |  |  |  | TOWER A 101 | TOWER A 101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27534 |  |  |  | TOWER A 101 WATERPROOFING WORK | TOWER A 101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27538 |  |  |  | TOWER A 101 | TOWER A 101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41052 |  |  |  | TOWER A 101 PLUMBING WORK | TOWER A 101 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 800 | 800 | 17 Mar 2020 |  | 06 Sep 2024 |  | - | - | 1635 | - | PLUMBING WORK
Task | 6 | 41521 |  |  |  | TOWER A 101 PLUMBING WORK | TOWER A 101 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Sep 2024 |  | - | - | 1635 | - | CP & SANITARY FITTINGS
Group | 5 | 27536 |  |  |  | TOWER A 101 | TOWER A 101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27537 |  |  |  | TOWER A 101 ELECTRIC WORK | TOWER A 101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27539 |  |  |  | TOWER A 101 | TOWER A 101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38431 |  |  |  | TOWER A 101 FLOORING & DEDO WORK | TOWER A 101 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27542 |  |  |  | TOWER A 101 | TOWER A 101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27540 |  |  |  | TOWER A 101 | TOWER A 101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27541 |  |  |  | TOWER A 101 | TOWER A 101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27543 |  |  |  | TOWER A 101 | TOWER A 101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42139 |  |  |  | TOWER A 101 HVAC WORK | TOWER A 101 HVAC WORK | 1 | NOS | 1 | NOS | 36.32 |  | Tentative | 36.32 | 0 | 36.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HVAC INSTALLATION
Group | 5 | 34617 |  |  |  | TOWER A 101 | TOWER A 101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34618 |  |  |  | TOWER A 101 COMMON WORK | TOWER A 101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34619 |  |  |  | TOWER A 101 COMMON WORK | TOWER A 101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34620 |  |  |  | TOWER A 101 COMMON WORK | TOWER A 101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27589 |  |  |  | TOWER A 1ST FLOOR | TOWER A 102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27580 |  |  |  | TOWER A 102 | TOWER A 102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27579 |  |  |  | TOWER A 102 WATERPROOFING WORK | TOWER A 102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27583 |  |  |  | TOWER A 102 | TOWER A 102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41053 |  |  |  | TOWER A 102 PLUMBING WORK | TOWER A 102 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 800 | 800 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | PLUMBING WORK
Task | 6 | 41522 |  |  |  | TOWER A 102 PLUMBING WORK | TOWER A 102 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | CP & SANITARY FITTINGS
Group | 5 | 27581 |  |  |  | TOWER A 102 | TOWER A 102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27582 |  |  |  | TOWER A 102 ELECTRIC WORK | TOWER A 102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27584 |  |  |  | TOWER A 102 | TOWER A 102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41648 |  |  |  | TOWER A 102 FLOORING & DEDO WORK | TOWER A 102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27587 |  |  |  | TOWER A 102 | TOWER A 102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27585 |  |  |  | TOWER A 102 | TOWER A 102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27586 |  |  |  | TOWER A 102 | TOWER A 102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27588 |  |  |  | TOWER A 102 | TOWER A 102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42140 |  |  |  | TOWER A 102 HVAC WORK | TOWER A 102 HVAC WORK | 1 | NOS | 1 | NOS | 36.32 |  | Tentative | 36.32 | 0 | 36.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HVAC INSTALLATION
Group | 5 | 34621 |  |  |  | TOWER A 102 | TOWER A 102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34622 |  |  |  | TOWER A 102 COMMON WORK | TOWER A 102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34623 |  |  |  | TOWER A 102 COMMON WORK | TOWER A 102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34624 |  |  |  | TOWER A 102 COMMON WORK | TOWER A 102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27601 |  |  |  | TOWER A 1ST FLOOR | TOWER A 103 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27592 |  |  |  | TOWER A 103 | TOWER A 103 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27591 |  |  |  | TOWER A 103 WATERPROOFING WORK | TOWER A 103 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27595 |  |  |  | TOWER A 103 | TOWER A 103 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41054 |  |  |  | TOWER A 103 PLUMBING WORK | TOWER A 103 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 700 | 700 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | PLUMBING WORK
Task | 6 | 41523 |  |  |  | TOWER A 103 PLUMBING WORK | TOWER A 103 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | CP & SANITARY FITTINGS
Group | 5 | 27593 |  |  |  | TOWER A 103 | TOWER A 103 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27594 |  |  |  | TOWER A 103 ELECTRIC WORK | TOWER A 103 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27596 |  |  |  | TOWER A 103 | TOWER A 103 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41652 |  |  |  | TOWER A 103 FLOORING & DEDO WORK | TOWER A 103 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27599 |  |  |  | TOWER A 103 | TOWER A 103 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27597 |  |  |  | TOWER A 103 | TOWER A 103 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27598 |  |  |  | TOWER A 103 | TOWER A 103 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27600 |  |  |  | TOWER A 103 | TOWER A 103 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34625 |  |  |  | TOWER A 103 | TOWER A 103 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34626 |  |  |  | TOWER A 103 COMMON WORK | TOWER A 103 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34627 |  |  |  | TOWER A 103 COMMON WORK | TOWER A 103 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34628 |  |  |  | TOWER A 103 COMMON WORK | TOWER A 103 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27613 |  |  |  | TOWER A 1ST FLOOR | TOWER A 104 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27604 |  |  |  | TOWER A 104 | TOWER A 104 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27603 |  |  |  | TOWER A 104 WATERPROOFING WORK | TOWER A 104 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27607 |  |  |  | TOWER A 104 | TOWER A 104 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41055 |  |  |  | TOWER A 104 PLUMBING WORK | TOWER A 104 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 350 | 350 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | PLUMBING WORK
Task | 6 | 41524 |  |  |  | TOWER A 104 PLUMBING WORK | TOWER A 104 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | CP & SANITARY FITTINGS
Group | 5 | 27605 |  |  |  | TOWER A 104 | TOWER A 104 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27606 |  |  |  | TOWER A 104 ELECTRIC WORK | TOWER A 104 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27608 |  |  |  | TOWER A 104 | TOWER A 104 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41649 |  |  |  | TOWER A 104 FLOORING & DEDO WORK | TOWER A 104 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27611 |  |  |  | TOWER A 104 | TOWER A 104 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27609 |  |  |  | TOWER A 104 | TOWER A 104 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27610 |  |  |  | TOWER A 104 | TOWER A 104 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27612 |  |  |  | TOWER A 104 | TOWER A 104 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34629 |  |  |  | TOWER A 104 | TOWER A 104 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34630 |  |  |  | TOWER A 104 COMMON WORK | TOWER A 104 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34631 |  |  |  | TOWER A 104 COMMON WORK | TOWER A 104 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34632 |  |  |  | TOWER A 104 COMMON WORK | TOWER A 104 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27614 |  |  |  | TOWER A 1ST FLOOR | TOWER A 1ST FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 03 Mar 2023 |  | - | - | 1082 | -
Group | 5 | 27617 |  |  |  | TOWER A 1ST FLOOR COMMON WORK | TOWER A 1ST FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39276 |  |  |  | TOWER A 1ST FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 1ST FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27615 |  |  |  | TOWER A 1ST FLOOR COMMON WORK | TOWER A 1ST FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41947 |  |  |  | TOWER A 1ST FLOOR COMMON FLOORING WORK | TOWER A 1ST FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 27616 |  |  |  | TOWER A 1ST FLOOR COMMON WORK | TOWER A 1ST FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27708 |  |  |  | TOWER A 1ST FLOOR COMMON WORK | TOWER A 1ST FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29455 |  |  |  | TOWER A 1ST FLOOR COMMON WORK | TOWER A 1ST FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 03 Mar 2023 |  | - | - | 1082 | -
Task | 6 | 33039 |  |  |  | TOWER A 1ST FLOOR COMMON ELECTRIC WORK | TOWER A 1ST FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 03 Mar 2023 |  | - | - | 1082 | - | SLAB CONDUTE
Group | 5 | 42249 |  |  |  | TOWER A 1ST FLOOR COMMON WORK | TOWER A 1ST FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42250 |  |  |  | TOWER A 1ST FLOOR WPC PANNELING WORK | TOWER A 1ST FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24136 |  |  |  | TOWER A | TOWER A 2ND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Group | 4 | 24137 |  |  |  | TOWER A 2ND FLOOR | TOWER A 2ND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Group | 5 | 24138 |  |  |  | TOWER A 2ND FLOOR CIVIL WORK | TOWER A 2ND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24141 |  |  |  | TOWER A 2ND FLOOR RCC WORK | TOWER A 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 62654.98 |  | Started | 62654.98 | 0 | 62654.98 | 8.71 | 545736.78 | 0 | 1650678.4 | 1650678.4 |  |  | 23 Jun 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33637 |  |  |  | TOWER A 2ND FLOOR RCC WORK | TOWER A 2ND FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 64831.56 | 64831.56 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | THREADING
Group | 5 | 24139 |  |  |  | TOWER A 2ND FLOOR CIVIL WORK | TOWER A 2ND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24142 |  |  |  | TOWER A 2ND FLOOR MASONRY WORK | TOWER A 2ND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Started | 640621.7 | 0 | 640621.7 | 0 | 640.62 | 0 | 416551.8 | 416551.8 |  |  | 20 Sep 2024 |  | - | - | - | - | MASONRY WORK
Task | 6 | 38684 |  |  |  | TOWER A 2ND FLOOR MASONRY WORK | TOWER A 2ND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21523.2 | 21523.2 | 17 Mar 2020 |  | 14 Mar 2024 |  | - | - | 1459 | - | REBARING WORK
Group | 5 | 24140 |  |  |  | TOWER A 2ND FLOOR CIVIL WORK | TOWER A 2ND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24143 |  |  |  | TOWER A 2ND FLOOR PLASTER WORK | TOWER A 2ND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27618 |  |  |  | TOWER A 2ND FLOOR | TOWER A 201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27546 |  |  |  | TOWER A 201 | TOWER A 201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27545 |  |  |  | TOWER A 201 WATERPROOFING WORK | TOWER A 201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27549 |  |  |  | TOWER A 201 | TOWER A 201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41056 |  |  |  | TOWER A 201 PLUMBING WORK | TOWER A 201 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41525 |  |  |  | TOWER A 201 PLUMBING WORK | TOWER A 201 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27547 |  |  |  | TOWER A 201 | TOWER A 201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27548 |  |  |  | TOWER A 201 ELECTRIC WORK | TOWER A 201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 0 | 0 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27550 |  |  |  | TOWER A 201 | TOWER A 201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41650 |  |  |  | TOWER A 201 FLOORING & DEDO WORK | TOWER A 201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27553 |  |  |  | TOWER A 201 | TOWER A 201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27551 |  |  |  | TOWER A 201 | TOWER A 201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27552 |  |  |  | TOWER A 201 | TOWER A 201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27554 |  |  |  | TOWER A 201 | TOWER A 201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34633 |  |  |  | TOWER A 201 | TOWER A 201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34634 |  |  |  | TOWER A 201 COMMON WORK | TOWER A 201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34635 |  |  |  | TOWER A 201 COMMON WORK | TOWER A 201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34636 |  |  |  | TOWER A 201 COMMON WORK | TOWER A 201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27630 |  |  |  | TOWER A 2ND FLOOR | TOWER A 202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27621 |  |  |  | TOWER A 202 | TOWER A 202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27620 |  |  |  | TOWER A 202 WATERPROOFING WORK | TOWER A 202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27624 |  |  |  | TOWER A 202 | TOWER A 202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41057 |  |  |  | TOWER A 202 PLUMBING WORK | TOWER A 202 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41526 |  |  |  | TOWER A 202 PLUMBING WORK | TOWER A 202 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27622 |  |  |  | TOWER A 202 | TOWER A 202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27623 |  |  |  | TOWER A 202 ELECTRIC WORK | TOWER A 202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27625 |  |  |  | TOWER A 202 | TOWER A 202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41651 |  |  |  | TOWER A 202 FLOORING & DEDO WORK | TOWER A 202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27628 |  |  |  | TOWER A 202 | TOWER A 202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27626 |  |  |  | TOWER A 202 | TOWER A 202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27627 |  |  |  | TOWER A 202 | TOWER A 202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27629 |  |  |  | TOWER A 202 | TOWER A 202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34637 |  |  |  | TOWER A 202 | TOWER A 202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34638 |  |  |  | TOWER A 202 COMMON WORK | TOWER A 202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34639 |  |  |  | TOWER A 202 COMMON WORK | TOWER A 202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34640 |  |  |  | TOWER A 202 COMMON WORK | TOWER A 202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27642 |  |  |  | TOWER A 2ND FLOOR | TOWER A 203 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27633 |  |  |  | TOWER A 203 | TOWER A 203 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27632 |  |  |  | TOWER A 203 WATERPROOFING WORK | TOWER A 203 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27636 |  |  |  | TOWER A 203 | TOWER A 203 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41058 |  |  |  | TOWER A 203 PLUMBING WORK | TOWER A 203 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41527 |  |  |  | TOWER A 203 PLUMBING WORK | TOWER A 203 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27634 |  |  |  | TOWER A 203 | TOWER A 203 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27635 |  |  |  | TOWER A 203 ELECTRIC WORK | TOWER A 203 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27637 |  |  |  | TOWER A 203 | TOWER A 203 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41653 |  |  |  | TOWER A 203 FLOORING & DEDO WORK | TOWER A 203 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27640 |  |  |  | TOWER A 203 | TOWER A 203 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27638 |  |  |  | TOWER A 203 | TOWER A 203 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27639 |  |  |  | TOWER A 203 | TOWER A 203 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27641 |  |  |  | TOWER A 203 | TOWER A 203 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34641 |  |  |  | TOWER A 203 | TOWER A 203 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34642 |  |  |  | TOWER A 203 COMMON WORK | TOWER A 203 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34643 |  |  |  | TOWER A 203 COMMON WORK | TOWER A 203 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34644 |  |  |  | TOWER A 203 COMMON WORK | TOWER A 203 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27654 |  |  |  | TOWER A 2ND FLOOR | TOWER A 204 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27645 |  |  |  | TOWER A 204 | TOWER A 204 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27644 |  |  |  | TOWER A 204 WATERPROOFING WORK | TOWER A 204 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27648 |  |  |  | TOWER A 204 | TOWER A 204 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41059 |  |  |  | TOWER A 204 PLUMBING WORK | TOWER A 204 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41528 |  |  |  | TOWER A 204 PLUMBING WORK | TOWER A 204 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27646 |  |  |  | TOWER A 204 | TOWER A 204 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27647 |  |  |  | TOWER A 204 ELECTRIC WORK | TOWER A 204 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 38142.9 | 38142.9 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27649 |  |  |  | TOWER A 204 | TOWER A 204 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41654 |  |  |  | TOWER A 204 FLOORING & DEDO WORK | TOWER A 204 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27652 |  |  |  | TOWER A 204 | TOWER A 204 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27650 |  |  |  | TOWER A 204 | TOWER A 204 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27651 |  |  |  | TOWER A 204 | TOWER A 204 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27653 |  |  |  | TOWER A 204 | TOWER A 204 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34645 |  |  |  | TOWER A 204 | TOWER A 204 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34646 |  |  |  | TOWER A 204 COMMON WORK | TOWER A 204 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34647 |  |  |  | TOWER A 204 COMMON WORK | TOWER A 204 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34648 |  |  |  | TOWER A 204 COMMON WORK | TOWER A 204 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27655 |  |  |  | TOWER A 2ND FLOOR | TOWER A 2ND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Jun 2023 |  | - | - | 1194 | -
Group | 5 | 27658 |  |  |  | TOWER A 2ND FLOOR COMMON WORK | TOWER A 2ND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39277 |  |  |  | TOWER A 2ND FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 2ND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27656 |  |  |  | TOWER A 2ND FLOOR COMMON WORK | TOWER A 2ND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41948 |  |  |  | TOWER A 2ND FLOOR COMMON FLOORING WORK | TOWER A 2ND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 27709 |  |  |  | TOWER A 2ND FLOOR COMMON WORK | TOWER A 2ND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27710 |  |  |  | TOWER A 2ND FLOOR COMMON WORK | TOWER A 2ND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29456 |  |  |  | TOWER A 2ND FLOOR COMMON WORK | TOWER A 2ND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Jun 2023 |  | - | - | 1194 | -
Task | 6 | 33040 |  |  |  | TOWER A 2ND FLOOR COMMON ELECTRIC WORK | TOWER A 2ND FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 23 Jun 2023 |  | - | - | 1194 | - | SLAB CONDUTE
Group | 5 | 42251 |  |  |  | TOWER A 2ND FLOOR COMMON WORK | TOWER A 2ND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42252 |  |  |  | TOWER A 2ND FLOOR WPC PANNELING WORK | TOWER A 2ND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24144 |  |  |  | TOWER A | TOWER A 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 Aug 2023 |  | - | - | - | -
Group | 4 | 24145 |  |  |  | TOWER A 3RD FLOOR | TOWER A 3RD FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2023 |  | - | - | - | -
Group | 5 | 24146 |  |  |  | TOWER A 3RD FLOOR CIVIL WORK | TOWER A 3RD FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2023 |  | - | - | - | -
Task | 6 | 24149 |  |  |  | TOWER A 3RD FLOOR RCC WORK | TOWER A 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 59544.86 |  | Started | 59544.86 | 0 | 59544.86 | 0 | 59.54 | 0 | 1649168 | 1649168 |  |  | 26 Sep 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33638 |  |  |  | TOWER A 3RD FLOOR RCC WORK | TOWER A 3RD FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 67658.26 | 67658.26 | 17 Mar 2020 |  | 20 Sep 2023 |  | - | - | 1283 | - | THREADING
Task | 6 | 38769 |  |  |  | TOWER A 3RD FLOOR RCC WORK | TOWER A 3RD FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 672 |  | Started | 672 | 0 | 672 | 0 | 0.67 | 0 | 95629.5 | 95629.5 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | SAFETY NET FIXING
Group | 5 | 24147 |  |  |  | TOWER A 3RD FLOOR CIVIL WORK | TOWER A 3RD FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24150 |  |  |  | TOWER A 3RD FLOOR MASONRY WORK | TOWER A 3RD FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 667366.7 |  | Started | 667366.7 | 0 | 667366.7 | 0 | 667.37 | 0 | 416551.8 | 416551.8 |  |  | 19 Oct 2024 |  | - | - | - | - | MASONRY WORK
Task | 6 | 39347 |  |  |  | TOWER A 3RD FLOOR MASONRY WORK | TOWER A 3RD FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 20 Aug 2024 |  | - | - | 1618 | - | REBARING WORK
Group | 5 | 24148 |  |  |  | TOWER A 3RD FLOOR CIVIL WORK | TOWER A 3RD FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24151 |  |  |  | TOWER A 3RD FLOOR PLASTER WORK | TOWER A 3RD FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27661 |  |  |  | TOWER A 3RD FLOOR | TOWER A 301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27557 |  |  |  | TOWER A 301 | TOWER A 301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27556 |  |  |  | TOWER A 301 WATERPROOFING WORK | TOWER A 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27560 |  |  |  | TOWER A 301 | TOWER A 301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41061 |  |  |  | TOWER A 301 PLUMBING WORK | TOWER A 301 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41529 |  |  |  | TOWER A 301 PLUMBING WORK | TOWER A 301 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27558 |  |  |  | TOWER A 301 | TOWER A 301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27559 |  |  |  | TOWER A 301 ELECTRIC WORK | TOWER A 301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27561 |  |  |  | TOWER A 301 | TOWER A 301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41655 |  |  |  | TOWER A 301 FLOORING & DEDO WORK | TOWER A 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27564 |  |  |  | TOWER A 301 | TOWER A 301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27562 |  |  |  | TOWER A 301 | TOWER A 301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27563 |  |  |  | TOWER A 301 | TOWER A 301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27565 |  |  |  | TOWER A 301 | TOWER A 301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34649 |  |  |  | TOWER A 301 | TOWER A 301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34650 |  |  |  | TOWER A 301 COMMON WORK | TOWER A 301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34651 |  |  |  | TOWER A 301 COMMON WORK | TOWER A 301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34652 |  |  |  | TOWER A 301 COMMON WORK | TOWER A 301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27679 |  |  |  | TOWER A 3RD FLOOR | TOWER A 302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27670 |  |  |  | TOWER A 302 | TOWER A 302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27669 |  |  |  | TOWER A 302 WATERPROOFING WORK | TOWER A 302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27673 |  |  |  | TOWER A 302 | TOWER A 302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41063 |  |  |  | TOWER A 302 PLUMBING WORK | TOWER A 302 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41530 |  |  |  | TOWER A 302 PLUMBING WORK | TOWER A 302 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27671 |  |  |  | TOWER A 302 | TOWER A 302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27672 |  |  |  | TOWER A 302 ELECTRIC WORK | TOWER A 302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27674 |  |  |  | TOWER A 302 | TOWER A 302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41656 |  |  |  | TOWER A 302 FLOORING & DEDO WORK | TOWER A 302 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27677 |  |  |  | TOWER A 302 | TOWER A 302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27675 |  |  |  | TOWER A 302 | TOWER A 302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27676 |  |  |  | TOWER A 302 | TOWER A 302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27678 |  |  |  | TOWER A 302 | TOWER A 302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34653 |  |  |  | TOWER A 302 | TOWER A 302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34654 |  |  |  | TOWER A 302 COMMON WORK | TOWER A 302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34655 |  |  |  | TOWER A 302 COMMON WORK | TOWER A 302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34656 |  |  |  | TOWER A 302 COMMON WORK | TOWER A 302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27691 |  |  |  | TOWER A 3RD FLOOR | TOWER A 303 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27682 |  |  |  | TOWER A 303 | TOWER A 303 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27681 |  |  |  | TOWER A 303 WATERPROOFING WORK | TOWER A 303 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27685 |  |  |  | TOWER A 303 | TOWER A 303 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41064 |  |  |  | TOWER A 303 PLUMBING WORK | TOWER A 303 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41531 |  |  |  | TOWER A 303 PLUMBING WORK | TOWER A 303 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27683 |  |  |  | TOWER A 303 | TOWER A 303 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27684 |  |  |  | TOWER A 303 ELECTRIC WORK | TOWER A 303 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27686 |  |  |  | TOWER A 303 | TOWER A 303 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41657 |  |  |  | TOWER A 303 FLOORING & DEDO WORK | TOWER A 303 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27689 |  |  |  | TOWER A 303 | TOWER A 303 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27687 |  |  |  | TOWER A 303 | TOWER A 303 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27688 |  |  |  | TOWER A 303 | TOWER A 303 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27690 |  |  |  | TOWER A 303 | TOWER A 303 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34657 |  |  |  | TOWER A 303 | TOWER A 303 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34658 |  |  |  | TOWER A 303 COMMON WORK | TOWER A 303 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34659 |  |  |  | TOWER A 303 COMMON WORK | TOWER A 303 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34660 |  |  |  | TOWER A 303 COMMON WORK | TOWER A 303 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27703 |  |  |  | TOWER A 3RD FLOOR | TOWER A 304 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27694 |  |  |  | TOWER A 304 | TOWER A 304 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27693 |  |  |  | TOWER A 304 WATERPROOFING WORK | TOWER A 304 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27697 |  |  |  | TOWER A 304 | TOWER A 304 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41065 |  |  |  | TOWER A 304 PLUMBING WORK | TOWER A 304 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41532 |  |  |  | TOWER A 304 PLUMBING WORK | TOWER A 304 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 27695 |  |  |  | TOWER A 304 | TOWER A 304 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27696 |  |  |  | TOWER A 304 ELECTRIC WORK | TOWER A 304 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27698 |  |  |  | TOWER A 304 | TOWER A 304 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41658 |  |  |  | TOWER A 304 FLOORING & DEDO WORK | TOWER A 304 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27701 |  |  |  | TOWER A 304 | TOWER A 304 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27699 |  |  |  | TOWER A 304 | TOWER A 304 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27700 |  |  |  | TOWER A 304 | TOWER A 304 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27702 |  |  |  | TOWER A 304 | TOWER A 304 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34661 |  |  |  | TOWER A 304 | TOWER A 304 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34662 |  |  |  | TOWER A 304 COMMON WORK | TOWER A 304 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34663 |  |  |  | TOWER A 304 COMMON WORK | TOWER A 304 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34664 |  |  |  | TOWER A 304 COMMON WORK | TOWER A 304 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27664 |  |  |  | TOWER A 3RD FLOOR | TOWER A 3RD FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Aug 2023 |  | - | - | 1244 | -
Group | 5 | 27667 |  |  |  | TOWER A 3RD FLOOR COMMON WORK | TOWER A 3RD FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39278 |  |  |  | TOWER A 3RD FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 3RD FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27665 |  |  |  | TOWER A 3RD FLOOR COMMON WORK | TOWER A 3RD FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41949 |  |  |  | TOWER A 3RD FLOOR COMMON FLOORING WORK | TOWER A 3RD FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 27713 |  |  |  | TOWER A 3RD FLOOR COMMON WORK | TOWER A 3RD FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27714 |  |  |  | TOWER A 3RD FLOOR COMMON WORK | TOWER A 3RD FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29457 |  |  |  | TOWER A 3RD FLOOR COMMON WORK | TOWER A 3RD FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Aug 2023 |  | - | - | 1244 | -
Task | 6 | 33041 |  |  |  | TOWER A 3RD FLOOR COMMON ELECTRIC WORK | TOWER A 3RD FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 12 Aug 2023 |  | - | - | 1244 | - | SLAB CONDUTE
Group | 5 | 42253 |  |  |  | TOWER A 3RD FLOOR COMMON WORK | TOWER A 3RD FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42254 |  |  |  | TOWER A 3RD FLOOR WPC PANNELING WORK | TOWER A 3RD FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24152 |  |  |  | TOWER A | TOWER A 4TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2023 |  | - | - | - | -
Group | 4 | 24153 |  |  |  | TOWER A 4TH FLOOR | TOWER A 4TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2023 |  | - | - | - | -
Group | 5 | 24154 |  |  |  | TOWER A 4TH FLOOR CIVIL WORK | TOWER A 4TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2023 |  | - | - | - | -
Task | 6 | 24157 |  |  |  | TOWER A 4TH FLOOR RCC WORK | TOWER A 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 63121.5 |  | Started | 63121.5 | 0 | 63121.5 | 0 | 63.12 | 0 | 1649168 | 1649168 |  |  | 26 Sep 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33639 |  |  |  | TOWER A 4TH FLOOR RCC WORK | TOWER A 4TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 24822.48 | 24822.48 | 17 Mar 2020 |  | 20 Sep 2023 |  | - | - | 1283 | - | THREADING
Group | 5 | 24155 |  |  |  | TOWER A 4TH FLOOR CIVIL WORK | TOWER A 4TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24158 |  |  |  | TOWER A 4TH FLOOR MASONRY WORK | TOWER A 4TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Started | 640621.7 | 0 | 640621.7 | 0 | 640.62 | 0 | 416551.8 | 416551.8 |  |  | 19 Oct 2024 |  | - | - | - | - | MASONRY WORK
Task | 6 | 39348 |  |  |  | TOWER A 4TH FLOOR MASONRY WORK | TOWER A 4TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 14 Mar 2024 |  | - | - | 1459 | - | REBARING WORK
Group | 5 | 24156 |  |  |  | TOWER A 4TH FLOOR CIVIL WORK | TOWER A 4TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24159 |  |  |  | TOWER A 4TH FLOOR PLASTER WORK | TOWER A 4TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27726 |  |  |  | TOWER A 4TH FLOOR | TOWER A 401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27717 |  |  |  | TOWER A 401 | TOWER A 401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27716 |  |  |  | TOWER A 401 WATERPROOFING WORK | TOWER A 401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27720 |  |  |  | TOWER A 401 | TOWER A 401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41066 |  |  |  | TOWER A 401 PLUMBING WORK | TOWER A 401 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27718 |  |  |  | TOWER A 401 | TOWER A 401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27719 |  |  |  | TOWER A 401 ELECTRIC WORK | TOWER A 401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27721 |  |  |  | TOWER A 401 | TOWER A 401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41659 |  |  |  | TOWER A 401 FLOORING & DEDO WORK | TOWER A 401 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27724 |  |  |  | TOWER A 401 | TOWER A 401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27722 |  |  |  | TOWER A 401 | TOWER A 401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27723 |  |  |  | TOWER A 401 | TOWER A 401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27725 |  |  |  | TOWER A 401 | TOWER A 401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34665 |  |  |  | TOWER A 401 | TOWER A 401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34666 |  |  |  | TOWER A 401 COMMON WORK | TOWER A 401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34667 |  |  |  | TOWER A 401 COMMON WORK | TOWER A 401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34668 |  |  |  | TOWER A 401 COMMON WORK | TOWER A 401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27737 |  |  |  | TOWER A 4TH FLOOR | TOWER A 402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27728 |  |  |  | TOWER A 402 | TOWER A 402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27727 |  |  |  | TOWER A 402 WATERPROOFING WORK | TOWER A 402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27731 |  |  |  | TOWER A 402 | TOWER A 402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41067 |  |  |  | TOWER A 402 PLUMBING WORK | TOWER A 402 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27729 |  |  |  | TOWER A 402 | TOWER A 402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27730 |  |  |  | TOWER A 402 ELECTRIC WORK | TOWER A 402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27732 |  |  |  | TOWER A 402 | TOWER A 402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41660 |  |  |  | TOWER A 402 FLOORING & DEDO WORK | TOWER A 402 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27735 |  |  |  | TOWER A 402 | TOWER A 402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27733 |  |  |  | TOWER A 402 | TOWER A 402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27734 |  |  |  | TOWER A 402 | TOWER A 402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27736 |  |  |  | TOWER A 402 | TOWER A 402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34669 |  |  |  | TOWER A 402 | TOWER A 402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34670 |  |  |  | TOWER A 402 COMMON WORK | TOWER A 402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34671 |  |  |  | TOWER A 402 COMMON WORK | TOWER A 402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34672 |  |  |  | TOWER A 402 COMMON WORK | TOWER A 402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27748 |  |  |  | TOWER A 4TH FLOOR | TOWER A 403 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27739 |  |  |  | TOWER A 403 | TOWER A 403 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27738 |  |  |  | TOWER A 403 WATERPROOFING WORK | TOWER A 403 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27742 |  |  |  | TOWER A 403 | TOWER A 403 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41068 |  |  |  | TOWER A 403 PLUMBING WORK | TOWER A 403 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27740 |  |  |  | TOWER A 403 | TOWER A 403 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27741 |  |  |  | TOWER A 403 ELECTRIC WORK | TOWER A 403 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27743 |  |  |  | TOWER A 403 | TOWER A 403 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41661 |  |  |  | TOWER A 403 FLOORING & DEDO WORK | TOWER A 403 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27746 |  |  |  | TOWER A 403 | TOWER A 403 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27744 |  |  |  | TOWER A 403 | TOWER A 403 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27745 |  |  |  | TOWER A 403 | TOWER A 403 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27747 |  |  |  | TOWER A 403 | TOWER A 403 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34673 |  |  |  | TOWER A 403 | TOWER A 403 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34674 |  |  |  | TOWER A 403 COMMON WORK | TOWER A 403 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34675 |  |  |  | TOWER A 403 COMMON WORK | TOWER A 403 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34676 |  |  |  | TOWER A 403 COMMON WORK | TOWER A 403 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27759 |  |  |  | TOWER A 4TH FLOOR | TOWER A 404 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27750 |  |  |  | TOWER A 404 | TOWER A 404 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27749 |  |  |  | TOWER A 404 WATERPROOFING WORK | TOWER A 404 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27753 |  |  |  | TOWER A 404 | TOWER A 404 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41069 |  |  |  | TOWER A 404 PLUMBING WORK | TOWER A 404 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27751 |  |  |  | TOWER A 404 | TOWER A 404 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27752 |  |  |  | TOWER A 404 ELECTRIC WORK | TOWER A 404 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27754 |  |  |  | TOWER A 404 | TOWER A 404 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41662 |  |  |  | TOWER A 404 FLOORING & DEDO WORK | TOWER A 404 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27757 |  |  |  | TOWER A 404 | TOWER A 404 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27755 |  |  |  | TOWER A 404 | TOWER A 404 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27756 |  |  |  | TOWER A 404 | TOWER A 404 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27758 |  |  |  | TOWER A 404 | TOWER A 404 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34677 |  |  |  | TOWER A 404 | TOWER A 404 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34678 |  |  |  | TOWER A 404 COMMON WORK | TOWER A 404 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34679 |  |  |  | TOWER A 404 COMMON WORK | TOWER A 404 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34680 |  |  |  | TOWER A 404 COMMON WORK | TOWER A 404 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27760 |  |  |  | TOWER A 4TH FLOOR | TOWER A 4TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | -
Group | 5 | 27762 |  |  |  | TOWER A 4TH FLOOR COMMON WORK | TOWER A 4TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39279 |  |  |  | TOWER A 4TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 4TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27761 |  |  |  | TOWER A 4TH FLOOR COMMON WORK | TOWER A 4TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41950 |  |  |  | TOWER A 4TH FLOOR COMMON FLOORING WORK | TOWER A 4TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 27763 |  |  |  | TOWER A 4TH FLOOR COMMON WORK | TOWER A 4TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27764 |  |  |  | TOWER A 4TH FLOOR COMMON WORK | TOWER A 4TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29458 |  |  |  | TOWER A 4TH FLOOR COMMON WORK | TOWER A 4TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | -
Task | 6 | 33042 |  |  |  | TOWER A 4TH FLOOR COMMON ELECTRIC WORK | TOWER A 4TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | SLAB CONDUTE
Group | 5 | 42255 |  |  |  | TOWER A 4TH FLOOR COMMON WORK | TOWER A 4TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42256 |  |  |  | TOWER A 4TH FLOOR WPC PANNELING WORK | TOWER A 4TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24160 |  |  |  | TOWER A | TOWER A 5TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Oct 2023 |  | - | - | - | -
Group | 4 | 24161 |  |  |  | TOWER A 5TH FLOOR | TOWER A 5TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Oct 2023 |  | - | - | - | -
Group | 5 | 24162 |  |  |  | TOWER A 5TH FLOOR CIVIL WORK | TOWER A 5TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Oct 2023 |  | - | - | - | -
Task | 6 | 24165 |  |  |  | TOWER A 5TH FLOOR RCC WORK | TOWER A 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 50898.3 |  | Started | 50898.3 | 0 | 50898.3 | 0 | 50.9 | 0 | 1644448 | 1644448 |  |  | 09 Nov 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33640 |  |  |  | TOWER A 5TH FLOOR RCC WORK | TOWER A 5TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 35400 | 35400 | 17 Mar 2020 |  | 17 Oct 2023 |  | - | - | 1310 | - | THREADING
Group | 5 | 24163 |  |  |  | TOWER A 5TH FLOOR CIVIL WORK | TOWER A 5TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24166 |  |  |  | TOWER A 5TH FLOOR MASONRY WORK | TOWER A 5TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39349 |  |  |  | TOWER A 5TH FLOOR MASONRY WORK | TOWER A 5TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 19399.2 | 19399.2 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | REBARING WORK
Group | 5 | 24164 |  |  |  | TOWER A 5TH FLOOR CIVIL WORK | TOWER A 5TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24167 |  |  |  | TOWER A 5TH FLOOR PLASTER WORK | TOWER A 5TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27775 |  |  |  | TOWER A 5TH FLOOR | TOWER A 501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27766 |  |  |  | TOWER A 501 | TOWER A 501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27765 |  |  |  | TOWER A 501 WATERPROOFING WORK | TOWER A 501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27769 |  |  |  | TOWER A 501 | TOWER A 501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41070 |  |  |  | TOWER A 501 PLUMBING WORK | TOWER A 501 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27767 |  |  |  | TOWER A 501 | TOWER A 501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27768 |  |  |  | TOWER A 501 ELECTRIC WORK | TOWER A 501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27770 |  |  |  | TOWER A 501 | TOWER A 501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41663 |  |  |  | TOWER A 501 FLOORING & DEDO WORK | TOWER A 501 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27773 |  |  |  | TOWER A 501 | TOWER A 501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27771 |  |  |  | TOWER A 501 | TOWER A 501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27772 |  |  |  | TOWER A 501 | TOWER A 501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27774 |  |  |  | TOWER A 501 | TOWER A 501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34681 |  |  |  | TOWER A 501 | TOWER A 501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34682 |  |  |  | TOWER A 501 COMMON WORK | TOWER A 501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34683 |  |  |  | TOWER A 501 COMMON WORK | TOWER A 501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34684 |  |  |  | TOWER A 501 COMMON WORK | TOWER A 501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27786 |  |  |  | TOWER A 5TH FLOOR | TOWER A 502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27777 |  |  |  | TOWER A 502 | TOWER A 502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27776 |  |  |  | TOWER A 502 WATERPROOFING WORK | TOWER A 502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27780 |  |  |  | TOWER A 502 | TOWER A 502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41071 |  |  |  | TOWER A 502 PLUMBING WORK | TOWER A 502 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27778 |  |  |  | TOWER A 502 | TOWER A 502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27779 |  |  |  | TOWER A 502 ELECTRIC WORK | TOWER A 502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27781 |  |  |  | TOWER A 502 | TOWER A 502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41664 |  |  |  | TOWER A 502 FLOORING & DEDO WORK | TOWER A 502 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27784 |  |  |  | TOWER A 502 | TOWER A 502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27782 |  |  |  | TOWER A 502 | TOWER A 502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27783 |  |  |  | TOWER A 502 | TOWER A 502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27785 |  |  |  | TOWER A 502 | TOWER A 502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34685 |  |  |  | TOWER A 502 | TOWER A 502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34686 |  |  |  | TOWER A 502 COMMON WORK | TOWER A 502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34687 |  |  |  | TOWER A 502 COMMON WORK | TOWER A 502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34688 |  |  |  | TOWER A 502 COMMON WORK | TOWER A 502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27797 |  |  |  | TOWER A 5TH FLOOR | TOWER A 503 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27788 |  |  |  | TOWER A 503 | TOWER A 503 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27787 |  |  |  | TOWER A 503 WATERPROOFING WORK | TOWER A 503 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27791 |  |  |  | TOWER A 503 | TOWER A 503 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41072 |  |  |  | TOWER A 503 PLUMBING WORK | TOWER A 503 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27789 |  |  |  | TOWER A 503 | TOWER A 503 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27790 |  |  |  | TOWER A 503 ELECTRIC WORK | TOWER A 503 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27792 |  |  |  | TOWER A 503 | TOWER A 503 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41665 |  |  |  | TOWER A 503 FLOORING & DEDO WORK | TOWER A 503 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27795 |  |  |  | TOWER A 503 | TOWER A 503 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27793 |  |  |  | TOWER A 503 | TOWER A 503 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27794 |  |  |  | TOWER A 503 | TOWER A 503 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27796 |  |  |  | TOWER A 503 | TOWER A 503 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34689 |  |  |  | TOWER A 503 | TOWER A 503 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34690 |  |  |  | TOWER A 503 COMMON WORK | TOWER A 503 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34691 |  |  |  | TOWER A 503 COMMON WORK | TOWER A 503 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34692 |  |  |  | TOWER A 503 COMMON WORK | TOWER A 503 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27808 |  |  |  | TOWER A 5TH FLOOR | TOWER A 504 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27799 |  |  |  | TOWER A 504 | TOWER A 504 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27798 |  |  |  | TOWER A 504 WATERPROOFING WORK | TOWER A 504 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27802 |  |  |  | TOWER A 504 | TOWER A 504 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41074 |  |  |  | TOWER A 504 PLUMBING WORK | TOWER A 504 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27800 |  |  |  | TOWER A 504 | TOWER A 504 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27801 |  |  |  | TOWER A 504 ELECTRIC WORK | TOWER A 504 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27803 |  |  |  | TOWER A 504 | TOWER A 504 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41666 |  |  |  | TOWER A 504 FLOORING & DEDO WORK | TOWER A 504 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27806 |  |  |  | TOWER A 504 | TOWER A 504 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27804 |  |  |  | TOWER A 504 | TOWER A 504 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27805 |  |  |  | TOWER A 504 | TOWER A 504 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27807 |  |  |  | TOWER A 504 | TOWER A 504 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34693 |  |  |  | TOWER A 504 | TOWER A 504 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34694 |  |  |  | TOWER A 504 COMMON WORK | TOWER A 504 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34695 |  |  |  | TOWER A 504 COMMON WORK | TOWER A 504 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34696 |  |  |  | TOWER A 504 COMMON WORK | TOWER A 504 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27990 |  |  |  | TOWER A 5TH FLOOR | TOWER A 5TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 22 Nov 2023 |  | - | - | 1346 | -
Group | 5 | 27992 |  |  |  | TOWER A 5TH FLOOR COMMON WORK | TOWER A 5TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39280 |  |  |  | TOWER A 5TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 5TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27991 |  |  |  | TOWER A 5TH FLOOR COMMON WORK | TOWER A 5TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41951 |  |  |  | TOWER A 5TH FLOOR COMMON FLOORING WORK | TOWER A 5TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 27993 |  |  |  | TOWER A 5TH FLOOR COMMON WORK | TOWER A 5TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27994 |  |  |  | TOWER A 5TH FLOOR COMMON WORK | TOWER A 5TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29459 |  |  |  | TOWER A 5TH FLOOR COMMON WORK | TOWER A 5TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 22 Nov 2023 |  | - | - | 1346 | -
Task | 6 | 33043 |  |  |  | TOWER A 5TH FLOOR COMMON ELECTRIC WORK | TOWER A 5TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 22 Nov 2023 |  | - | - | 1346 | - | SLAB CONDUTE
Group | 5 | 42257 |  |  |  | TOWER A 5TH FLOOR COMMON WORK | TOWER A 5TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42258 |  |  |  | TOWER A 5TH FLOOR WPC PANNELING WORK | TOWER A 5TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24168 |  |  |  | TOWER A | TOWER A 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24169 |  |  |  | TOWER A 6TH FLOOR | TOWER A 6TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24170 |  |  |  | TOWER A 6TH FLOOR CIVIL WORK | TOWER A 6TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24173 |  |  |  | TOWER A 6TH FLOOR RCC WORK | TOWER A 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 44638.02 |  | Started | 44638.02 | 0 | 44638.02 | 0 | 44.64 | 0 | 1644448 | 1644448 |  |  | 04 Feb 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33641 |  |  |  | TOWER A 6TH FLOOR RCC WORK | TOWER A 6TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 67584.5 | 67584.5 | 17 Mar 2020 |  | 06 Dec 2023 |  | - | - | 1360 | - | THREADING
Task | 6 | 40090 |  |  |  | TOWER A 6TH FLOOR RCC WORK | TOWER A 6TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53988.3 | 53988.3 | 17 Mar 2020 |  | 22 Mar 2024 |  | - | - | 1467 | - | SAFETY NET FIXING
Group | 5 | 24171 |  |  |  | TOWER A 6TH FLOOR CIVIL WORK | TOWER A 6TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24174 |  |  |  | TOWER A 6TH FLOOR MASONRY WORK | TOWER A 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39350 |  |  |  | TOWER A 6TH FLOOR MASONRY WORK | TOWER A 6TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24172 |  |  |  | TOWER A 6TH FLOOR CIVIL WORK | TOWER A 6TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24175 |  |  |  | TOWER A 6TH FLOOR PLASTER WORK | TOWER A 6TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27819 |  |  |  | TOWER A 6TH FLOOR | TOWER A 601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27810 |  |  |  | TOWER A 601 | TOWER A 601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27809 |  |  |  | TOWER A 601 WATERPROOFING WORK | TOWER A 601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27813 |  |  |  | TOWER A 601 | TOWER A 601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41075 |  |  |  | TOWER A 601 PLUMBING WORK | TOWER A 601 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27811 |  |  |  | TOWER A 601 | TOWER A 601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27812 |  |  |  | TOWER A 601 ELECTRIC WORK | TOWER A 601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27814 |  |  |  | TOWER A 601 | TOWER A 601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41667 |  |  |  | TOWER A 601 FLOORING & DEDO WORK | TOWER A 601 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27817 |  |  |  | TOWER A 601 | TOWER A 601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27815 |  |  |  | TOWER A 601 | TOWER A 601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27816 |  |  |  | TOWER A 601 | TOWER A 601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27818 |  |  |  | TOWER A 601 | TOWER A 601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34697 |  |  |  | TOWER A 601 | TOWER A 601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34698 |  |  |  | TOWER A 601 COMMON WORK | TOWER A 601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34699 |  |  |  | TOWER A 601 COMMON WORK | TOWER A 601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34700 |  |  |  | TOWER A 601 COMMON WORK | TOWER A 601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27830 |  |  |  | TOWER A 6TH FLOOR | TOWER A 602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27821 |  |  |  | TOWER A 602 | TOWER A 602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27820 |  |  |  | TOWER A 602 WATERPROOFING WORK | TOWER A 602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27824 |  |  |  | TOWER A 602 | TOWER A 602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41076 |  |  |  | TOWER A 602 PLUMBING WORK | TOWER A 602 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27822 |  |  |  | TOWER A 602 | TOWER A 602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27823 |  |  |  | TOWER A 602 ELECTRIC WORK | TOWER A 602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27825 |  |  |  | TOWER A 602 | TOWER A 602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41668 |  |  |  | TOWER A 602 FLOORING & DEDO WORK | TOWER A 602 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27828 |  |  |  | TOWER A 602 | TOWER A 602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27826 |  |  |  | TOWER A 602 | TOWER A 602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27827 |  |  |  | TOWER A 602 | TOWER A 602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27829 |  |  |  | TOWER A 602 | TOWER A 602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34701 |  |  |  | TOWER A 602 | TOWER A 602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34702 |  |  |  | TOWER A 602 COMMON WORK | TOWER A 602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34703 |  |  |  | TOWER A 602 COMMON WORK | TOWER A 602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34704 |  |  |  | TOWER A 602 COMMON WORK | TOWER A 602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27841 |  |  |  | TOWER A 6TH FLOOR | TOWER A 603 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27832 |  |  |  | TOWER A 603 | TOWER A 603 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27831 |  |  |  | TOWER A 603 WATERPROOFING WORK | TOWER A 603 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27835 |  |  |  | TOWER A 603 | TOWER A 603 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41077 |  |  |  | TOWER A 603 PLUMBING WORK | TOWER A 603 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27833 |  |  |  | TOWER A 603 | TOWER A 603 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27834 |  |  |  | TOWER A 603 ELECTRIC WORK | TOWER A 603 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27836 |  |  |  | TOWER A 603 | TOWER A 603 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41669 |  |  |  | TOWER A 603 FLOORING & DEDO WORK | TOWER A 603 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27839 |  |  |  | TOWER A 603 | TOWER A 603 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27837 |  |  |  | TOWER A 603 | TOWER A 603 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27838 |  |  |  | TOWER A 603 | TOWER A 603 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27840 |  |  |  | TOWER A 603 | TOWER A 603 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34705 |  |  |  | TOWER A 603 | TOWER A 603 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34706 |  |  |  | TOWER A 603 COMMON WORK | TOWER A 603 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34707 |  |  |  | TOWER A 603 COMMON WORK | TOWER A 603 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34708 |  |  |  | TOWER A 603 COMMON WORK | TOWER A 603 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27852 |  |  |  | TOWER A 6TH FLOOR | TOWER A 604 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27843 |  |  |  | TOWER A 604 | TOWER A 604 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27842 |  |  |  | TOWER A 604 WATERPROOFING WORK | TOWER A 604 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27846 |  |  |  | TOWER A 604 | TOWER A 604 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41078 |  |  |  | TOWER A 604 PLUMBING WORK | TOWER A 604 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27844 |  |  |  | TOWER A 604 | TOWER A 604 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27845 |  |  |  | TOWER A 604 ELECTRIC WORK | TOWER A 604 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27847 |  |  |  | TOWER A 604 | TOWER A 604 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41670 |  |  |  | TOWER A 604 FLOORING & DEDO WORK | TOWER A 604 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27850 |  |  |  | TOWER A 604 | TOWER A 604 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27848 |  |  |  | TOWER A 604 | TOWER A 604 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27849 |  |  |  | TOWER A 604 | TOWER A 604 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27851 |  |  |  | TOWER A 604 | TOWER A 604 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34709 |  |  |  | TOWER A 604 | TOWER A 604 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34710 |  |  |  | TOWER A 604 COMMON WORK | TOWER A 604 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34711 |  |  |  | TOWER A 604 COMMON WORK | TOWER A 604 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34712 |  |  |  | TOWER A 604 COMMON WORK | TOWER A 604 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27995 |  |  |  | TOWER A 6TH FLOOR | TOWER A 6TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27997 |  |  |  | TOWER A 6TH FLOOR COMMON WORK | TOWER A 6TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39401 |  |  |  | TOWER A 6TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 6TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 27996 |  |  |  | TOWER A 6TH FLOOR COMMON WORK | TOWER A 6TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41952 |  |  |  | TOWER A 6TH FLOOR COMMON FLOORING WORK | TOWER A 6TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 27998 |  |  |  | TOWER A 6TH FLOOR COMMON WORK | TOWER A 6TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27999 |  |  |  | TOWER A 6TH FLOOR COMMON WORK | TOWER A 6TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29460 |  |  |  | TOWER A 6TH FLOOR COMMON WORK | TOWER A 6TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33044 |  |  |  | TOWER A 6TH FLOOR COMMON ELECTRIC WORK | TOWER A 6TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 28 Jan 2024 |  | - | - | 1413 | - | SLAB CONDUTE
Group | 5 | 42259 |  |  |  | TOWER A 6TH FLOOR COMMON WORK | TOWER A 6TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42260 |  |  |  | TOWER A 6TH FLOOR WPC PANNELING WORK | TOWER A 6TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24176 |  |  |  | TOWER A | TOWER A 7TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24177 |  |  |  | TOWER A 7TH FLOOR | TOWER A 7TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24178 |  |  |  | TOWER A 7TH FLOOR CIVIL WORK | TOWER A 7TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24181 |  |  |  | TOWER A 7TH FLOOR RCC WORK | TOWER A 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 49848.56 |  | Started | 49848.56 | 0 | 49848.56 | 0 | 49.85 | 0 | 1644448.02 | 1644448.02 |  |  | 08 May 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33642 |  |  |  | TOWER A 7TH FLOOR RCC WORK | TOWER A 7TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 11310.3 | 11310.3 | 17 Mar 2020 |  | 20 Dec 2023 |  | - | - | 1374 | - | THREADING
Group | 5 | 24179 |  |  |  | TOWER A 7TH FLOOR CIVIL WORK | TOWER A 7TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24182 |  |  |  | TOWER A 7TH FLOOR MASONRY WORK | TOWER A 7TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39351 |  |  |  | TOWER A 7TH FLOOR MASONRY WORK | TOWER A 7TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24180 |  |  |  | TOWER A 7TH FLOOR CIVIL WORK | TOWER A 7TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24183 |  |  |  | TOWER A 7TH FLOOR PLASTER WORK | TOWER A 7TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27863 |  |  |  | TOWER A 7TH FLOOR | TOWER A 701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27854 |  |  |  | TOWER A 701 | TOWER A 701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27853 |  |  |  | TOWER A 701 WATERPROOFING WORK | TOWER A 701 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27857 |  |  |  | TOWER A 701 | TOWER A 701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41079 |  |  |  | TOWER A 701 PLUMBING WORK | TOWER A 701 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27855 |  |  |  | TOWER A 701 | TOWER A 701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27856 |  |  |  | TOWER A 701 ELECTRIC WORK | TOWER A 701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27858 |  |  |  | TOWER A 701 | TOWER A 701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41671 |  |  |  | TOWER A 701 FLOORING & DEDO WORK | TOWER A 701 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27861 |  |  |  | TOWER A 701 | TOWER A 701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27859 |  |  |  | TOWER A 701 | TOWER A 701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27860 |  |  |  | TOWER A 701 | TOWER A 701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27862 |  |  |  | TOWER A 701 | TOWER A 701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34713 |  |  |  | TOWER A 701 | TOWER A 701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34714 |  |  |  | TOWER A 701 COMMON WORK | TOWER A 701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34715 |  |  |  | TOWER A 701 COMMON WORK | TOWER A 701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34716 |  |  |  | TOWER A 701 COMMON WORK | TOWER A 701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27874 |  |  |  | TOWER A 7TH FLOOR | TOWER A 702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27865 |  |  |  | TOWER A 702 | TOWER A 702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27864 |  |  |  | TOWER A 702 WATERPROOFING WORK | TOWER A 702 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27868 |  |  |  | TOWER A 702 | TOWER A 702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41080 |  |  |  | TOWER A 702 PLUMBING WORK | TOWER A 702 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27866 |  |  |  | TOWER A 702 | TOWER A 702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27867 |  |  |  | TOWER A 702 ELECTRIC WORK | TOWER A 702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27869 |  |  |  | TOWER A 702 | TOWER A 702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41672 |  |  |  | TOWER A 702 FLOORING & DEDO WORK | TOWER A 702 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27872 |  |  |  | TOWER A 702 | TOWER A 702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27870 |  |  |  | TOWER A 702 | TOWER A 702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27871 |  |  |  | TOWER A 702 | TOWER A 702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27873 |  |  |  | TOWER A 702 | TOWER A 702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34717 |  |  |  | TOWER A 702 | TOWER A 702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34718 |  |  |  | TOWER A 702 COMMON WORK | TOWER A 702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34719 |  |  |  | TOWER A 702 COMMON WORK | TOWER A 702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34720 |  |  |  | TOWER A 702 COMMON WORK | TOWER A 702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27885 |  |  |  | TOWER A 7TH FLOOR | TOWER A 703 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27876 |  |  |  | TOWER A 703 | TOWER A 703 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27875 |  |  |  | TOWER A 703 WATERPROOFING WORK | TOWER A 703 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27879 |  |  |  | TOWER A 703 | TOWER A 703 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41081 |  |  |  | TOWER A 703 PLUMBING WORK | TOWER A 703 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27877 |  |  |  | TOWER A 703 | TOWER A 703 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27878 |  |  |  | TOWER A 703 ELECTRIC WORK | TOWER A 703 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27880 |  |  |  | TOWER A 703 | TOWER A 703 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41673 |  |  |  | TOWER A 703 FLOORING & DEDO WORK | TOWER A 703 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27883 |  |  |  | TOWER A 703 | TOWER A 703 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27881 |  |  |  | TOWER A 703 | TOWER A 703 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27882 |  |  |  | TOWER A 703 | TOWER A 703 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27884 |  |  |  | TOWER A 703 | TOWER A 703 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34721 |  |  |  | TOWER A 703 | TOWER A 703 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34722 |  |  |  | TOWER A 703 COMMON WORK | TOWER A 703 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34723 |  |  |  | TOWER A 703 COMMON WORK | TOWER A 703 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34724 |  |  |  | TOWER A 703 COMMON WORK | TOWER A 703 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27896 |  |  |  | TOWER A 7TH FLOOR | TOWER A 704 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27887 |  |  |  | TOWER A 704 | TOWER A 704 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27886 |  |  |  | TOWER A 704 WATERPROOFING WORK | TOWER A 704 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27890 |  |  |  | TOWER A 704 | TOWER A 704 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41082 |  |  |  | TOWER A 704 PLUMBING WORK | TOWER A 704 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27888 |  |  |  | TOWER A 704 | TOWER A 704 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27889 |  |  |  | TOWER A 704 ELECTRIC WORK | TOWER A 704 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27891 |  |  |  | TOWER A 704 | TOWER A 704 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41674 |  |  |  | TOWER A 704 FLOORING & DEDO WORK | TOWER A 704 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27894 |  |  |  | TOWER A 704 | TOWER A 704 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27892 |  |  |  | TOWER A 704 | TOWER A 704 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27893 |  |  |  | TOWER A 704 | TOWER A 704 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27895 |  |  |  | TOWER A 704 | TOWER A 704 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34725 |  |  |  | TOWER A 704 | TOWER A 704 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34726 |  |  |  | TOWER A 704 COMMON WORK | TOWER A 704 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34727 |  |  |  | TOWER A 704 COMMON WORK | TOWER A 704 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34728 |  |  |  | TOWER A 704 COMMON WORK | TOWER A 704 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28000 |  |  |  | TOWER A 7TH FLOOR | TOWER A 7TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28002 |  |  |  | TOWER A 7TH FLOOR COMMON WORK | TOWER A 7TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39402 |  |  |  | TOWER A 7TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 7TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 28001 |  |  |  | TOWER A 7TH FLOOR COMMON WORK | TOWER A 7TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41953 |  |  |  | TOWER A 7TH FLOOR COMMON FLOORING WORK | TOWER A 7TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28003 |  |  |  | TOWER A 7TH FLOOR COMMON WORK | TOWER A 7TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28004 |  |  |  | TOWER A 7TH FLOOR COMMON WORK | TOWER A 7TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29461 |  |  |  | TOWER A 7TH FLOOR COMMON WORK | TOWER A 7TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33045 |  |  |  | TOWER A 7TH FLOOR COMMON ELECTRIC WORK | TOWER A 7TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 15 May 2024 |  | - | - | 1521 | - | SLAB CONDUTE
Group | 5 | 42261 |  |  |  | TOWER A 7TH FLOOR COMMON WORK | TOWER A 7TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42262 |  |  |  | TOWER A 7TH FLOOR WPC PANNELING WORK | TOWER A 7TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24184 |  |  |  | TOWER A | TOWER A 8TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24185 |  |  |  | TOWER A 8TH FLOOR | TOWER A 8TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24186 |  |  |  | TOWER A 8TH FLOOR CIVIL WORK | TOWER A 8TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24189 |  |  |  | TOWER A 8TH FLOOR RCC WORK | TOWER A 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 54557.2 |  | Started | 54557.2 | 0 | 54557.2 | 0 | 54.56 | 0 | 1644448 | 1644448 |  |  | 20 Sep 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33643 |  |  |  | TOWER A 8TH FLOOR RCC WORK | TOWER A 8TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 61802.5 | 61802.5 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Group | 5 | 24187 |  |  |  | TOWER A 8TH FLOOR CIVIL WORK | TOWER A 8TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24190 |  |  |  | TOWER A 8TH FLOOR MASONRY WORK | TOWER A 8TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39352 |  |  |  | TOWER A 8TH FLOOR MASONRY WORK | TOWER A 8TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24188 |  |  |  | TOWER A 8TH FLOOR CIVIL WORK | TOWER A 8TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24191 |  |  |  | TOWER A 8TH FLOOR PLASTER WORK | TOWER A 8TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27907 |  |  |  | TOWER A 8TH FLOOR | TOWER A 801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27898 |  |  |  | TOWER A 801 | TOWER A 801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27897 |  |  |  | TOWER A 801 WATERPROOFING WORK | TOWER A 801 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27901 |  |  |  | TOWER A 801 | TOWER A 801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41083 |  |  |  | TOWER A 801 PLUMBING WORK | TOWER A 801 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27899 |  |  |  | TOWER A 801 | TOWER A 801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27900 |  |  |  | TOWER A 801 ELECTRIC WORK | TOWER A 801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 24225 | 24225 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27902 |  |  |  | TOWER A 801 | TOWER A 801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41675 |  |  |  | TOWER A 801 FLOORING & DEDO WORK | TOWER A 801 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27905 |  |  |  | TOWER A 801 | TOWER A 801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27903 |  |  |  | TOWER A 801 | TOWER A 801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27904 |  |  |  | TOWER A 801 | TOWER A 801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27906 |  |  |  | TOWER A 801 | TOWER A 801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34729 |  |  |  | TOWER A 801 | TOWER A 801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34730 |  |  |  | TOWER A 801 COMMON WORK | TOWER A 801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34731 |  |  |  | TOWER A 801 COMMON WORK | TOWER A 801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34732 |  |  |  | TOWER A 801 COMMON WORK | TOWER A 801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27918 |  |  |  | TOWER A 8TH FLOOR | TOWER A 802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27909 |  |  |  | TOWER A 802 | TOWER A 802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27908 |  |  |  | TOWER A 802 WATERPROOFING WORK | TOWER A 802 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27912 |  |  |  | TOWER A 802 | TOWER A 802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41084 |  |  |  | TOWER A 802 PLUMBING WORK | TOWER A 802 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27910 |  |  |  | TOWER A 802 | TOWER A 802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27911 |  |  |  | TOWER A 802 ELECTRIC WORK | TOWER A 802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 24225 | 24225 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27913 |  |  |  | TOWER A 802 | TOWER A 802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41676 |  |  |  | TOWER A 802 FLOORING & DEDO WORK | TOWER A 802 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27916 |  |  |  | TOWER A 802 | TOWER A 802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27914 |  |  |  | TOWER A 802 | TOWER A 802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27915 |  |  |  | TOWER A 802 | TOWER A 802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27917 |  |  |  | TOWER A 802 | TOWER A 802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34733 |  |  |  | TOWER A 802 | TOWER A 802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34734 |  |  |  | TOWER A 802 COMMON WORK | TOWER A 802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34735 |  |  |  | TOWER A 802 COMMON WORK | TOWER A 802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34736 |  |  |  | TOWER A 802 COMMON WORK | TOWER A 802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27929 |  |  |  | TOWER A 8TH FLOOR | TOWER A 803 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27920 |  |  |  | TOWER A 803 | TOWER A 803 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27919 |  |  |  | TOWER A 803 WATERPROOFING WORK | TOWER A 803 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27923 |  |  |  | TOWER A 803 | TOWER A 803 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41085 |  |  |  | TOWER A 803 PLUMBING WORK | TOWER A 803 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27921 |  |  |  | TOWER A 803 | TOWER A 803 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27922 |  |  |  | TOWER A 803 ELECTRIC WORK | TOWER A 803 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 24225 | 24225 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27924 |  |  |  | TOWER A 803 | TOWER A 803 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41677 |  |  |  | TOWER A 803 FLOORING & DEDO WORK | TOWER A 803 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27927 |  |  |  | TOWER A 803 | TOWER A 803 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27925 |  |  |  | TOWER A 803 | TOWER A 803 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27926 |  |  |  | TOWER A 803 | TOWER A 803 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27928 |  |  |  | TOWER A 803 | TOWER A 803 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34737 |  |  |  | TOWER A 803 | TOWER A 803 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34738 |  |  |  | TOWER A 803 COMMON WORK | TOWER A 803 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34739 |  |  |  | TOWER A 803 COMMON WORK | TOWER A 803 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34740 |  |  |  | TOWER A 803 COMMON WORK | TOWER A 803 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27940 |  |  |  | TOWER A 8TH FLOOR | TOWER A 804 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27931 |  |  |  | TOWER A 804 | TOWER A 804 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27930 |  |  |  | TOWER A 804 WATERPROOFING WORK | TOWER A 804 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27934 |  |  |  | TOWER A 804 | TOWER A 804 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41086 |  |  |  | TOWER A 804 PLUMBING WORK | TOWER A 804 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27932 |  |  |  | TOWER A 804 | TOWER A 804 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27933 |  |  |  | TOWER A 804 ELECTRIC WORK | TOWER A 804 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 24225 | 24225 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | ELECTRIC WORK
Group | 5 | 27935 |  |  |  | TOWER A 804 | TOWER A 804 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41678 |  |  |  | TOWER A 804 FLOORING & DEDO WORK | TOWER A 804 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27938 |  |  |  | TOWER A 804 | TOWER A 804 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27936 |  |  |  | TOWER A 804 | TOWER A 804 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27937 |  |  |  | TOWER A 804 | TOWER A 804 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27939 |  |  |  | TOWER A 804 | TOWER A 804 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34741 |  |  |  | TOWER A 804 | TOWER A 804 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34742 |  |  |  | TOWER A 804 COMMON WORK | TOWER A 804 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34743 |  |  |  | TOWER A 804 COMMON WORK | TOWER A 804 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34744 |  |  |  | TOWER A 804 COMMON WORK | TOWER A 804 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28005 |  |  |  | TOWER A 8TH FLOOR | TOWER A 8TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28007 |  |  |  | TOWER A 8TH FLOOR COMMON WORK | TOWER A 8TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39403 |  |  |  | TOWER A 8TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 8TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 28006 |  |  |  | TOWER A 8TH FLOOR COMMON WORK | TOWER A 8TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41954 |  |  |  | TOWER A 8TH FLOOR COMMON FLOORING WORK | TOWER A 8TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28008 |  |  |  | TOWER A 8TH FLOOR COMMON WORK | TOWER A 8TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28009 |  |  |  | TOWER A 8TH FLOOR COMMON WORK | TOWER A 8TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29462 |  |  |  | TOWER A 8TH FLOOR COMMON WORK | TOWER A 8TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33046 |  |  |  | TOWER A 8TH FLOOR COMMON ELECTRIC WORK | TOWER A 8TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42265 |  |  |  | TOWER A 8TH FLOOR COMMON WORK | TOWER A 8TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42266 |  |  |  | TOWER A 8TH FLOOR WPC PANNELING WORK | TOWER A 8TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24192 |  |  |  | TOWER A | TOWER A 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24193 |  |  |  | TOWER A 9TH FLOOR | TOWER A 9TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24194 |  |  |  | TOWER A 9TH FLOOR CIVIL WORK | TOWER A 9TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24197 |  |  |  | TOWER A 9TH FLOOR RCC WORK | TOWER A 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 54398.12 |  | Started | 54398.12 | 0 | 54398.12 | 0 | 54.4 | 0 | 1644448 | 1644448 |  |  | 19 Oct 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33644 |  |  |  | TOWER A 9TH FLOOR RCC WORK | TOWER A 9TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 52510 | 52510 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | THREADING
Group | 5 | 24195 |  |  |  | TOWER A 9TH FLOOR CIVIL WORK | TOWER A 9TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24198 |  |  |  | TOWER A 9TH FLOOR MASONRY WORK | TOWER A 9TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39353 |  |  |  | TOWER A 9TH FLOOR MASONRY WORK | TOWER A 9TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24196 |  |  |  | TOWER A 9TH FLOOR CIVIL WORK | TOWER A 9TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24199 |  |  |  | TOWER A 9TH FLOOR PLASTER WORK | TOWER A 9TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 27951 |  |  |  | TOWER A 9TH FLOOR | TOWER A 901 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27942 |  |  |  | TOWER A 901 | TOWER A 901 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27941 |  |  |  | TOWER A 901 WATERPROOFING WORK | TOWER A 901 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27945 |  |  |  | TOWER A 901 | TOWER A 901 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41087 |  |  |  | TOWER A 901 PLUMBING WORK | TOWER A 901 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27943 |  |  |  | TOWER A 901 | TOWER A 901 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27944 |  |  |  | TOWER A 901 ELECTRIC WORK | TOWER A 901 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27946 |  |  |  | TOWER A 901 | TOWER A 901 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41679 |  |  |  | TOWER A 901 FLOORING & DEDO WORK | TOWER A 901 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27949 |  |  |  | TOWER A 901 | TOWER A 901 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27947 |  |  |  | TOWER A 901 | TOWER A 901 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27948 |  |  |  | TOWER A 901 | TOWER A 901 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27950 |  |  |  | TOWER A 901 | TOWER A 901 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34745 |  |  |  | TOWER A 901 | TOWER A 901 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34746 |  |  |  | TOWER A 901 COMMON WORK | TOWER A 901 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34747 |  |  |  | TOWER A 901 COMMON WORK | TOWER A 901 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34748 |  |  |  | TOWER A 901 COMMON WORK | TOWER A 901 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27962 |  |  |  | TOWER A 9TH FLOOR | TOWER A 902 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27953 |  |  |  | TOWER A 902 | TOWER A 902 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27952 |  |  |  | TOWER A 902 WATERPROOFING WORK | TOWER A 902 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27956 |  |  |  | TOWER A 902 | TOWER A 902 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41088 |  |  |  | TOWER A 902 PLUMBING WORK | TOWER A 902 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27954 |  |  |  | TOWER A 902 | TOWER A 902 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27955 |  |  |  | TOWER A 902 ELECTRIC WORK | TOWER A 902 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27957 |  |  |  | TOWER A 902 | TOWER A 902 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41680 |  |  |  | TOWER A 902 FLOORING & DEDO WORK | TOWER A 902 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27960 |  |  |  | TOWER A 902 | TOWER A 902 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27958 |  |  |  | TOWER A 902 | TOWER A 902 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27959 |  |  |  | TOWER A 902 | TOWER A 902 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27961 |  |  |  | TOWER A 902 | TOWER A 902 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34749 |  |  |  | TOWER A 902 | TOWER A 902 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34750 |  |  |  | TOWER A 902 COMMON WORK | TOWER A 902 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34751 |  |  |  | TOWER A 902 COMMON WORK | TOWER A 902 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34752 |  |  |  | TOWER A 902 COMMON WORK | TOWER A 902 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27973 |  |  |  | TOWER A 9TH FLOOR | TOWER A 903 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27964 |  |  |  | TOWER A 903 | TOWER A 903 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27963 |  |  |  | TOWER A 903 WATERPROOFING WORK | TOWER A 903 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27967 |  |  |  | TOWER A 903 | TOWER A 903 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41089 |  |  |  | TOWER A 903 PLUMBING WORK | TOWER A 903 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27965 |  |  |  | TOWER A 903 | TOWER A 903 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27966 |  |  |  | TOWER A 903 ELECTRIC WORK | TOWER A 903 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27968 |  |  |  | TOWER A 903 | TOWER A 903 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41681 |  |  |  | TOWER A 903 FLOORING & DEDO WORK | TOWER A 903 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27971 |  |  |  | TOWER A 903 | TOWER A 903 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27969 |  |  |  | TOWER A 903 | TOWER A 903 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27970 |  |  |  | TOWER A 903 | TOWER A 903 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27972 |  |  |  | TOWER A 903 | TOWER A 903 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34753 |  |  |  | TOWER A 903 | TOWER A 903 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34754 |  |  |  | TOWER A 903 COMMON WORK | TOWER A 903 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34755 |  |  |  | TOWER A 903 COMMON WORK | TOWER A 903 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34756 |  |  |  | TOWER A 903 COMMON WORK | TOWER A 903 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 27984 |  |  |  | TOWER A 9TH FLOOR | TOWER A 904 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27975 |  |  |  | TOWER A 904 | TOWER A 904 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27974 |  |  |  | TOWER A 904 WATERPROOFING WORK | TOWER A 904 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 27978 |  |  |  | TOWER A 904 | TOWER A 904 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41090 |  |  |  | TOWER A 904 PLUMBING WORK | TOWER A 904 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 27976 |  |  |  | TOWER A 904 | TOWER A 904 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 27977 |  |  |  | TOWER A 904 ELECTRIC WORK | TOWER A 904 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 27979 |  |  |  | TOWER A 904 | TOWER A 904 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41682 |  |  |  | TOWER A 904 FLOORING & DEDO WORK | TOWER A 904 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 27982 |  |  |  | TOWER A 904 | TOWER A 904 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27980 |  |  |  | TOWER A 904 | TOWER A 904 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27981 |  |  |  | TOWER A 904 | TOWER A 904 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 27983 |  |  |  | TOWER A 904 | TOWER A 904 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34757 |  |  |  | TOWER A 904 | TOWER A 904 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34758 |  |  |  | TOWER A 904 COMMON WORK | TOWER A 904 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34759 |  |  |  | TOWER A 904 COMMON WORK | TOWER A 904 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34760 |  |  |  | TOWER A 904 COMMON WORK | TOWER A 904 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28010 |  |  |  | TOWER A 9TH FLOOR | TOWER A 9TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28012 |  |  |  | TOWER A 9TH FLOOR COMMON WORK | TOWER A 9TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39404 |  |  |  | TOWER A 9TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 9TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 28011 |  |  |  | TOWER A 9TH FLOOR COMMON WORK | TOWER A 9TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41955 |  |  |  | TOWER A 9TH FLOOR COMMON FLOORING WORK | TOWER A 9TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28013 |  |  |  | TOWER A 9TH FLOOR COMMON WORK | TOWER A 9TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28014 |  |  |  | TOWER A 9TH FLOOR COMMON WORK | TOWER A 9TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29463 |  |  |  | TOWER A 9TH FLOOR COMMON WORK | TOWER A 9TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33047 |  |  |  | TOWER A 9TH FLOOR COMMON ELECTRIC WORK | TOWER A 9TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42267 |  |  |  | TOWER A 9TH FLOOR COMMON WORK | TOWER A 9TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42268 |  |  |  | TOWER A 9TH FLOOR WPC PANNELING WORK | TOWER A 9TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24200 |  |  |  | TOWER A | TOWER A 10TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24201 |  |  |  | TOWER A 10TH FLOOR | TOWER A 10TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24202 |  |  |  | TOWER A 10TH FLOOR CIVIL WORK | TOWER A 10TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24205 |  |  |  | TOWER A 10TH FLOOR RCC WORK | TOWER A 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 39671.92 |  | Tentative | 39671.92 | 0 | 39671.92 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33645 |  |  |  | TOWER A 10TH FLOOR RCC WORK | TOWER A 10TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24203 |  |  |  | TOWER A 10TH FLOOR CIVIL WORK | TOWER A 10TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24206 |  |  |  | TOWER A 10TH FLOOR MASONRY WORK | TOWER A 10TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39354 |  |  |  | TOWER A 10TH FLOOR MASONRY WORK | TOWER A 10TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24204 |  |  |  | TOWER A 10TH FLOOR CIVIL WORK | TOWER A 10TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24207 |  |  |  | TOWER A 10TH FLOOR PLASTER WORK | TOWER A 10TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28025 |  |  |  | TOWER A 10TH FLOOR | TOWER A 1001 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28016 |  |  |  | TOWER A 1001 | TOWER A 1001 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28015 |  |  |  | TOWER A 1001 WATERPROOFING WORK | TOWER A 1001 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28019 |  |  |  | TOWER A 1001 | TOWER A 1001 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41091 |  |  |  | TOWER A 1001 PLUMBING WORK | TOWER A 1001 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28017 |  |  |  | TOWER A 1001 | TOWER A 1001 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28018 |  |  |  | TOWER A 1001 ELECTRIC WORK | TOWER A 1001 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28020 |  |  |  | TOWER A 1001 | TOWER A 1001 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41683 |  |  |  | TOWER A 1001 FLOORING & DEDO WORK | TOWER A 1001 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28023 |  |  |  | TOWER A 1001 | TOWER A 1001 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28021 |  |  |  | TOWER A 1001 | TOWER A 1001 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28022 |  |  |  | TOWER A 1001 | TOWER A 1001 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28024 |  |  |  | TOWER A 1001 | TOWER A 1001 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34761 |  |  |  | TOWER A 1001 | TOWER A 1001 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34762 |  |  |  | TOWER A 1001 COMMON WORK | TOWER A 1001 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34763 |  |  |  | TOWER A 1001 COMMON WORK | TOWER A 1001 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34764 |  |  |  | TOWER A 1001 COMMON WORK | TOWER A 1001 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28036 |  |  |  | TOWER A 10TH FLOOR | TOWER A 1002 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28027 |  |  |  | TOWER A 1002 | TOWER A 1002 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28026 |  |  |  | TOWER A 1002 WATERPROOFING WORK | TOWER A 1002 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28030 |  |  |  | TOWER A 1002 | TOWER A 1002 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41092 |  |  |  | TOWER A 1002 PLUMBING WORK | TOWER A 1002 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28028 |  |  |  | TOWER A 1002 | TOWER A 1002 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28029 |  |  |  | TOWER A 1002 ELECTRIC WORK | TOWER A 1002 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28031 |  |  |  | TOWER A 1002 | TOWER A 1002 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41684 |  |  |  | TOWER A 1002 FLOORING & DEDO WORK | TOWER A 1002 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28034 |  |  |  | TOWER A 1002 | TOWER A 1002 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28032 |  |  |  | TOWER A 1002 | TOWER A 1002 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28033 |  |  |  | TOWER A 1002 | TOWER A 1002 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28035 |  |  |  | TOWER A 1002 | TOWER A 1002 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34765 |  |  |  | TOWER A 1002 | TOWER A 1002 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34766 |  |  |  | TOWER A 1002 COMMON WORK | TOWER A 1002 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34767 |  |  |  | TOWER A 1002 COMMON WORK | TOWER A 1002 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34768 |  |  |  | TOWER A 1002 COMMON WORK | TOWER A 1002 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28047 |  |  |  | TOWER A 10TH FLOOR | TOWER A 1003 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28038 |  |  |  | TOWER A 1003 | TOWER A 1003 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28037 |  |  |  | TOWER A 1003 WATERPROOFING WORK | TOWER A 1003 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28041 |  |  |  | TOWER A 1003 | TOWER A 1003 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41093 |  |  |  | TOWER A 1003 PLUMBING WORK | TOWER A 1003 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28039 |  |  |  | TOWER A 1003 | TOWER A 1003 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28040 |  |  |  | TOWER A 1003 ELECTRIC WORK | TOWER A 1003 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28042 |  |  |  | TOWER A 1003 | TOWER A 1003 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41685 |  |  |  | TOWER A 1003 FLOORING & DEDO WORK | TOWER A 1003 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28045 |  |  |  | TOWER A 1003 | TOWER A 1003 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28043 |  |  |  | TOWER A 1003 | TOWER A 1003 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28044 |  |  |  | TOWER A 1003 | TOWER A 1003 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28046 |  |  |  | TOWER A 1003 | TOWER A 1003 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34769 |  |  |  | TOWER A 1003 | TOWER A 1003 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34770 |  |  |  | TOWER A 1003 COMMON WORK | TOWER A 1003 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34771 |  |  |  | TOWER A 1003 COMMON WORK | TOWER A 1003 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34772 |  |  |  | TOWER A 1003 COMMON WORK | TOWER A 1003 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28058 |  |  |  | TOWER A 10TH FLOOR | TOWER A 1004 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28049 |  |  |  | TOWER A 1004 | TOWER A 1004 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28048 |  |  |  | TOWER A 1004 WATERPROOFING WORK | TOWER A 1004 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28052 |  |  |  | TOWER A 1004 | TOWER A 1004 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41094 |  |  |  | TOWER A 1004 PLUMBING WORK | TOWER A 1004 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28050 |  |  |  | TOWER A 1004 | TOWER A 1004 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28051 |  |  |  | TOWER A 1004 ELECTRIC WORK | TOWER A 1004 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28053 |  |  |  | TOWER A 1004 | TOWER A 1004 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41686 |  |  |  | TOWER A 1004 FLOORING & DEDO WORK | TOWER A 1004 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28056 |  |  |  | TOWER A 1004 | TOWER A 1004 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28054 |  |  |  | TOWER A 1004 | TOWER A 1004 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28055 |  |  |  | TOWER A 1004 | TOWER A 1004 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28057 |  |  |  | TOWER A 1004 | TOWER A 1004 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34773 |  |  |  | TOWER A 1004 | TOWER A 1004 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34774 |  |  |  | TOWER A 1004 COMMON WORK | TOWER A 1004 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34775 |  |  |  | TOWER A 1004 COMMON WORK | TOWER A 1004 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34776 |  |  |  | TOWER A 1004 COMMON WORK | TOWER A 1004 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28059 |  |  |  | TOWER A 10TH FLOOR | TOWER A 10TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28061 |  |  |  | TOWER A 10TH FLOOR COMMON WORK | TOWER A 10TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39405 |  |  |  | TOWER A 10TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER A 10TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 28060 |  |  |  | TOWER A 10TH FLOOR COMMON WORK | TOWER A 10TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41956 |  |  |  | TOWER A 10TH FLOOR COMMON FLOORING WORK | TOWER A 10TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28062 |  |  |  | TOWER A 10TH FLOOR COMMON WORK | TOWER A 10TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28063 |  |  |  | TOWER A 10TH FLOOR COMMON WORK | TOWER A 10TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29464 |  |  |  | TOWER A 10TH FLOOR COMMON WORK | TOWER A 10TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33048 |  |  |  | TOWER A 10TH FLOOR COMMON ELECTRIC WORK | TOWER A 10TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42269 |  |  |  | TOWER A 10TH FLOOR COMMON WORK | TOWER A 10TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42270 |  |  |  | TOWER A 10TH FLOOR WPC PANNELING WORK | TOWER A 10TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24208 |  |  |  | TOWER A | TOWER A 11TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24209 |  |  |  | TOWER A 11TH FLOOR | TOWER A 11TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24210 |  |  |  | TOWER A 11TH FLOOR CIVIL WORK | TOWER A 11TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24213 |  |  |  | TOWER A 11TH FLOOR RCC WORK | TOWER A 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 1095 |  | Tentative | 1095 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33646 |  |  |  | TOWER A 11TH FLOOR RCC WORK | TOWER A 11TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24211 |  |  |  | TOWER A 11TH FLOOR CIVIL WORK | TOWER A 11TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24214 |  |  |  | TOWER A 11TH FLOOR MASONRY WORK | TOWER A 11TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39355 |  |  |  | TOWER A 11TH FLOOR MASONRY WORK | TOWER A 11TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24212 |  |  |  | TOWER A 11TH FLOOR CIVIL WORK | TOWER A 11TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24215 |  |  |  | TOWER A 11TH FLOOR PLASTER WORK | TOWER A 11TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28074 |  |  |  | TOWER A 11TH FLOOR | TOWER A 1101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28065 |  |  |  | TOWER A 1101 | TOWER A 1101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28064 |  |  |  | TOWER A 1101 WATERPROOFING WORK | TOWER A 1101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28068 |  |  |  | TOWER A 1101 | TOWER A 1101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41095 |  |  |  | TOWER A 1101 PLUMBING WORK | TOWER A 1101 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28066 |  |  |  | TOWER A 1101 | TOWER A 1101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28067 |  |  |  | TOWER A 1101 ELECTRIC WORK | TOWER A 1101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28069 |  |  |  | TOWER A 1101 | TOWER A 1101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41687 |  |  |  | TOWER A 1101 FLOORING & DEDO WORK | TOWER A 1101 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28072 |  |  |  | TOWER A 1101 | TOWER A 1101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28070 |  |  |  | TOWER A 1101 | TOWER A 1101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28071 |  |  |  | TOWER A 1101 | TOWER A 1101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28073 |  |  |  | TOWER A 1101 | TOWER A 1101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34777 |  |  |  | TOWER A 1101 | TOWER A 1101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34778 |  |  |  | TOWER A 1101 COMMON WORK | TOWER A 1101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34779 |  |  |  | TOWER A 1101 COMMON WORK | TOWER A 1101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34780 |  |  |  | TOWER A 1101 COMMON WORK | TOWER A 1101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28173 |  |  |  | TOWER A 11TH FLOOR | TOWER A 1102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28164 |  |  |  | TOWER A 1102 | TOWER A 1102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28163 |  |  |  | TOWER A 1102 WATERPROOFING WORK | TOWER A 1102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28167 |  |  |  | TOWER A 1102 | TOWER A 1102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41096 |  |  |  | TOWER A 1102 PLUMBING WORK | TOWER A 1102 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28165 |  |  |  | TOWER A 1102 | TOWER A 1102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28166 |  |  |  | TOWER A 1102 ELECTRIC WORK | TOWER A 1102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28168 |  |  |  | TOWER A 1102 | TOWER A 1102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41688 |  |  |  | TOWER A 1102 FLOORING & DEDO WORK | TOWER A 1102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28171 |  |  |  | TOWER A 1102 | TOWER A 1102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28169 |  |  |  | TOWER A 1102 | TOWER A 1102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28170 |  |  |  | TOWER A 1102 | TOWER A 1102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28172 |  |  |  | TOWER A 1102 | TOWER A 1102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34781 |  |  |  | TOWER A 1102 | TOWER A 1102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34782 |  |  |  | TOWER A 1102 COMMON WORK | TOWER A 1102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34783 |  |  |  | TOWER A 1102 COMMON WORK | TOWER A 1102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34784 |  |  |  | TOWER A 1102 COMMON WORK | TOWER A 1102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28272 |  |  |  | TOWER A 11TH FLOOR | TOWER A 1103 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28263 |  |  |  | TOWER A 1103 | TOWER A 1103 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28262 |  |  |  | TOWER A 1103 WATERPROOFING WORK | TOWER A 1103 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28266 |  |  |  | TOWER A 1103 | TOWER A 1103 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41097 |  |  |  | TOWER A 1103 PLUMBING WORK | TOWER A 1103 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28264 |  |  |  | TOWER A 1103 | TOWER A 1103 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28265 |  |  |  | TOWER A 1103 ELECTRIC WORK | TOWER A 1103 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28267 |  |  |  | TOWER A 1103 | TOWER A 1103 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41689 |  |  |  | TOWER A 1103 FLOORING & DEDO WORK | TOWER A 1103 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28270 |  |  |  | TOWER A 1103 | TOWER A 1103 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28268 |  |  |  | TOWER A 1103 | TOWER A 1103 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28269 |  |  |  | TOWER A 1103 | TOWER A 1103 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28271 |  |  |  | TOWER A 1103 | TOWER A 1103 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34785 |  |  |  | TOWER A 1103 | TOWER A 1103 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34786 |  |  |  | TOWER A 1103 COMMON WORK | TOWER A 1103 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34787 |  |  |  | TOWER A 1103 COMMON WORK | TOWER A 1103 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34788 |  |  |  | TOWER A 1103 COMMON WORK | TOWER A 1103 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28371 |  |  |  | TOWER A 11TH FLOOR | TOWER A 1104 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28362 |  |  |  | TOWER A 1104 | TOWER A 1104 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28361 |  |  |  | TOWER A 1104 WATERPROOFING WORK | TOWER A 1104 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28365 |  |  |  | TOWER A 1104 | TOWER A 1104 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41098 |  |  |  | TOWER A 1104 PLUMBING WORK | TOWER A 1104 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28363 |  |  |  | TOWER A 1104 | TOWER A 1104 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28364 |  |  |  | TOWER A 1104 ELECTRIC WORK | TOWER A 1104 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28366 |  |  |  | TOWER A 1104 | TOWER A 1104 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41690 |  |  |  | TOWER A 1104 FLOORING & DEDO WORK | TOWER A 1104 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28369 |  |  |  | TOWER A 1104 | TOWER A 1104 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28367 |  |  |  | TOWER A 1104 | TOWER A 1104 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28368 |  |  |  | TOWER A 1104 | TOWER A 1104 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28370 |  |  |  | TOWER A 1104 | TOWER A 1104 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34789 |  |  |  | TOWER A 1104 | TOWER A 1104 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34790 |  |  |  | TOWER A 1104 COMMON WORK | TOWER A 1104 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34791 |  |  |  | TOWER A 1104 COMMON WORK | TOWER A 1104 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34792 |  |  |  | TOWER A 1104 COMMON WORK | TOWER A 1104 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28460 |  |  |  | TOWER A 11TH FLOOR | TOWER A 11TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28462 |  |  |  | TOWER A 11TH FLOOR COMMON WORK | TOWER A 11TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28461 |  |  |  | TOWER A 11TH FLOOR COMMON WORK | TOWER A 11TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41957 |  |  |  | TOWER A 11TH FLOOR COMMON FLOORING WORK | TOWER A 11TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28463 |  |  |  | TOWER A 11TH FLOOR COMMON WORK | TOWER A 11TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28464 |  |  |  | TOWER A 11TH FLOOR COMMON WORK | TOWER A 11TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29465 |  |  |  | TOWER A 11TH FLOOR COMMON WORK | TOWER A 11TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33049 |  |  |  | TOWER A 11TH FLOOR COMMON ELECTRIC WORK | TOWER A 11TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42271 |  |  |  | TOWER A 11TH FLOOR COMMON WORK | TOWER A 11TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42272 |  |  |  | TOWER A 11TH FLOOR WPC PANNELING WORK | TOWER A 11TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24216 |  |  |  | TOWER A | TOWER A 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24217 |  |  |  | TOWER A 12TH FLOOR | TOWER A 12TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24218 |  |  |  | TOWER A 12TH FLOOR CIVIL WORK | TOWER A 12TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24221 |  |  |  | TOWER A 12TH FLOOR RCC WORK | TOWER A 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24219 |  |  |  | TOWER A 12TH FLOOR CIVIL WORK | TOWER A 12TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24222 |  |  |  | TOWER A 12TH FLOOR MASONRY WORK | TOWER A 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39356 |  |  |  | TOWER A 12TH FLOOR MASONRY WORK | TOWER A 12TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24220 |  |  |  | TOWER A 12TH FLOOR CIVIL WORK | TOWER A 12TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24223 |  |  |  | TOWER A 12TH FLOOR PLASTER WORK | TOWER A 12TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28085 |  |  |  | TOWER A 12TH FLOOR | TOWER A 1201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28076 |  |  |  | TOWER A 1201 | TOWER A 1201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28075 |  |  |  | TOWER A 1201 WATERPROOFING WORK | TOWER A 1201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28079 |  |  |  | TOWER A 1201 | TOWER A 1201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41099 |  |  |  | TOWER A 1201 PLUMBING WORK | TOWER A 1201 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28077 |  |  |  | TOWER A 1201 | TOWER A 1201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28078 |  |  |  | TOWER A 1201 ELECTRIC WORK | TOWER A 1201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28080 |  |  |  | TOWER A 1201 | TOWER A 1201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41691 |  |  |  | TOWER A 1201 FLOORING & DEDO WORK | TOWER A 1201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28083 |  |  |  | TOWER A 1201 | TOWER A 1201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28081 |  |  |  | TOWER A 1201 | TOWER A 1201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28082 |  |  |  | TOWER A 1201 | TOWER A 1201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28084 |  |  |  | TOWER A 1201 | TOWER A 1201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34793 |  |  |  | TOWER A 1201 | TOWER A 1201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34794 |  |  |  | TOWER A 1201 COMMON WORK | TOWER A 1201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34795 |  |  |  | TOWER A 1201 COMMON WORK | TOWER A 1201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34796 |  |  |  | TOWER A 1201 COMMON WORK | TOWER A 1201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28184 |  |  |  | TOWER A 12TH FLOOR | TOWER A 1202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28175 |  |  |  | TOWER A 1202 | TOWER A 1202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28174 |  |  |  | TOWER A 1202 WATERPROOFING WORK | TOWER A 1202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28178 |  |  |  | TOWER A 1202 | TOWER A 1202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41100 |  |  |  | TOWER A 1202 PLUMBING WORK | TOWER A 1202 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28176 |  |  |  | TOWER A 1202 | TOWER A 1202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28177 |  |  |  | TOWER A 1202 ELECTRIC WORK | TOWER A 1202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28179 |  |  |  | TOWER A 1202 | TOWER A 1202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41692 |  |  |  | TOWER A 1202 FLOORING & DEDO WORK | TOWER A 1202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28182 |  |  |  | TOWER A 1202 | TOWER A 1202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28180 |  |  |  | TOWER A 1202 | TOWER A 1202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28181 |  |  |  | TOWER A 1202 | TOWER A 1202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28183 |  |  |  | TOWER A 1202 | TOWER A 1202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34797 |  |  |  | TOWER A 1202 | TOWER A 1202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34798 |  |  |  | TOWER A 1202 COMMON WORK | TOWER A 1202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34799 |  |  |  | TOWER A 1202 COMMON WORK | TOWER A 1202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34800 |  |  |  | TOWER A 1202 COMMON WORK | TOWER A 1202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28283 |  |  |  | TOWER A 12TH FLOOR | TOWER A 1203 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28274 |  |  |  | TOWER A 1203 | TOWER A 1203 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28273 |  |  |  | TOWER A 1203 WATERPROOFING WORK | TOWER A 1203 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28277 |  |  |  | TOWER A 1203 | TOWER A 1203 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41101 |  |  |  | TOWER A 1203 PLUMBING WORK | TOWER A 1203 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28275 |  |  |  | TOWER A 1203 | TOWER A 1203 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28276 |  |  |  | TOWER A 1203 ELECTRIC WORK | TOWER A 1203 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28278 |  |  |  | TOWER A 1203 | TOWER A 1203 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41693 |  |  |  | TOWER A 1203 FLOORING & DEDO WORK | TOWER A 1203 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28281 |  |  |  | TOWER A 1203 | TOWER A 1203 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28279 |  |  |  | TOWER A 1203 | TOWER A 1203 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28280 |  |  |  | TOWER A 1203 | TOWER A 1203 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28282 |  |  |  | TOWER A 1203 | TOWER A 1203 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34801 |  |  |  | TOWER A 1203 | TOWER A 1203 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34802 |  |  |  | TOWER A 1203 COMMON WORK | TOWER A 1203 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34803 |  |  |  | TOWER A 1203 COMMON WORK | TOWER A 1203 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34804 |  |  |  | TOWER A 1203 COMMON WORK | TOWER A 1203 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28382 |  |  |  | TOWER A 12TH FLOOR | TOWER A 1204 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28373 |  |  |  | TOWER A 1204 | TOWER A 1204 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28372 |  |  |  | TOWER A 1204 WATERPROOFING WORK | TOWER A 1204 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28376 |  |  |  | TOWER A 1204 | TOWER A 1204 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41102 |  |  |  | TOWER A 1204 PLUMBING WORK | TOWER A 1204 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28374 |  |  |  | TOWER A 1204 | TOWER A 1204 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28375 |  |  |  | TOWER A 1204 ELECTRIC WORK | TOWER A 1204 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28377 |  |  |  | TOWER A 1204 | TOWER A 1204 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41694 |  |  |  | TOWER A 1204 FLOORING & DEDO WORK | TOWER A 1204 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28380 |  |  |  | TOWER A 1204 | TOWER A 1204 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28378 |  |  |  | TOWER A 1204 | TOWER A 1204 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28379 |  |  |  | TOWER A 1204 | TOWER A 1204 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28381 |  |  |  | TOWER A 1204 | TOWER A 1204 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34805 |  |  |  | TOWER A 1204 | TOWER A 1204 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34806 |  |  |  | TOWER A 1204 COMMON WORK | TOWER A 1204 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34807 |  |  |  | TOWER A 1204 COMMON WORK | TOWER A 1204 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34808 |  |  |  | TOWER A 1204 COMMON WORK | TOWER A 1204 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28465 |  |  |  | TOWER A 12TH FLOOR | TOWER A 12TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28467 |  |  |  | TOWER A 12TH FLOOR COMMON WORK | TOWER A 12TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28466 |  |  |  | TOWER A 12TH FLOOR COMMON WORK | TOWER A 12TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41958 |  |  |  | TOWER A 12TH FLOOR COMMON FLOORING WORK | TOWER A 12TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28468 |  |  |  | TOWER A 12TH FLOOR COMMON WORK | TOWER A 12TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28469 |  |  |  | TOWER A 12TH FLOOR COMMON WORK | TOWER A 12TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29466 |  |  |  | TOWER A 12TH FLOOR COMMON WORK | TOWER A 12TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33050 |  |  |  | TOWER A 12TH FLOOR COMMON ELECTRIC WORK | TOWER A 12TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42273 |  |  |  | TOWER A 12TH FLOOR COMMON WORK | TOWER A 12TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42274 |  |  |  | TOWER A 12TH FLOOR WPC PANNELING WORK | TOWER A 12TH FLOOR PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24224 |  |  |  | TOWER A | TOWER A 13TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24225 |  |  |  | TOWER A 13TH FLOOR | TOWER A 13TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24226 |  |  |  | TOWER A 13TH FLOOR CIVIL WORK | TOWER A 13TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24229 |  |  |  | TOWER A 13TH FLOOR RCC WORK | TOWER A 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24227 |  |  |  | TOWER A 13TH FLOOR CIVIL WORK | TOWER A 13TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24230 |  |  |  | TOWER A 13TH FLOOR MASONRY WORK | TOWER A 13TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39357 |  |  |  | TOWER A 13TH FLOOR MASONRY WORK | TOWER A 13TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24228 |  |  |  | TOWER A 13TH FLOOR CIVIL WORK | TOWER A 13TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24231 |  |  |  | TOWER A 13TH FLOOR PLASTER WORK | TOWER A 13TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28096 |  |  |  | TOWER A 13TH FLOOR | TOWER A 1301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28087 |  |  |  | TOWER A 1301 | TOWER A 1301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28086 |  |  |  | TOWER A 1301 WATERPROOFING WORK | TOWER A 1301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28090 |  |  |  | TOWER A 1301 | TOWER A 1301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41103 |  |  |  | TOWER A 1301 PLUMBING WORK | TOWER A 1301 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28088 |  |  |  | TOWER A 1301 | TOWER A 1301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28089 |  |  |  | TOWER A 1301 ELECTRIC WORK | TOWER A 1301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28091 |  |  |  | TOWER A 1301 | TOWER A 1301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41695 |  |  |  | TOWER A 1301 FLOORING & DEDO WORK | TOWER A 1301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28094 |  |  |  | TOWER A 1301 | TOWER A 1301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28092 |  |  |  | TOWER A 1301 | TOWER A 1301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28093 |  |  |  | TOWER A 1301 | TOWER A 1301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28095 |  |  |  | TOWER A 1301 | TOWER A 1301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34809 |  |  |  | TOWER A 1301 | TOWER A 1301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34810 |  |  |  | TOWER A 1301 COMMON WORK | TOWER A 1301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34811 |  |  |  | TOWER A 1301 COMMON WORK | TOWER A 1301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34812 |  |  |  | TOWER A 1301 COMMON WORK | TOWER A 1301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28195 |  |  |  | TOWER A 13TH FLOOR | TOWER A 1302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28186 |  |  |  | TOWER A 1302 | TOWER A 1302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28185 |  |  |  | TOWER A 1302 WATERPROOFING WORK | TOWER A 1302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28189 |  |  |  | TOWER A 1302 | TOWER A 1302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41104 |  |  |  | TOWER A 1302 PLUMBING WORK | TOWER A 1302 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28187 |  |  |  | TOWER A 1302 | TOWER A 1302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28188 |  |  |  | TOWER A 1302 ELECTRIC WORK | TOWER A 1302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28190 |  |  |  | TOWER A 1302 | TOWER A 1302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41696 |  |  |  | TOWER A 1302 FLOORING & DEDO WORK | TOWER A 1302 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28193 |  |  |  | TOWER A 1302 | TOWER A 1302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28191 |  |  |  | TOWER A 1302 | TOWER A 1302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28192 |  |  |  | TOWER A 1302 | TOWER A 1302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28194 |  |  |  | TOWER A 1302 | TOWER A 1302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34813 |  |  |  | TOWER A 1302 | TOWER A 1302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34814 |  |  |  | TOWER A 1302 COMMON WORK | TOWER A 1302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34815 |  |  |  | TOWER A 1302 COMMON WORK | TOWER A 1302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34816 |  |  |  | TOWER A 1302 COMMON WORK | TOWER A 1302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28294 |  |  |  | TOWER A 13TH FLOOR | TOWER A 1303 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28285 |  |  |  | TOWER A 1303 | TOWER A 1303 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28284 |  |  |  | TOWER A 1303 WATERPROOFING WORK | TOWER A 1303 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28288 |  |  |  | TOWER A 1303 | TOWER A 1303 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41105 |  |  |  | TOWER A 1303 PLUMBING WORK | TOWER A 1303 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28286 |  |  |  | TOWER A 1303 | TOWER A 1303 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28287 |  |  |  | TOWER A 1303 ELECTRIC WORK | TOWER A 1303 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28289 |  |  |  | TOWER A 1303 | TOWER A 1303 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41697 |  |  |  | TOWER A 1303 FLOORING & DEDO WORK | TOWER A 1303 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28292 |  |  |  | TOWER A 1303 | TOWER A 1303 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28290 |  |  |  | TOWER A 1303 | TOWER A 1303 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28291 |  |  |  | TOWER A 1303 | TOWER A 1303 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28293 |  |  |  | TOWER A 1303 | TOWER A 1303 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34817 |  |  |  | TOWER A 1303 | TOWER A 1303 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34818 |  |  |  | TOWER A 1303 COMMON WORK | TOWER A 1303 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34819 |  |  |  | TOWER A 1303 COMMON WORK | TOWER A 1303 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34820 |  |  |  | TOWER A 1303 COMMON WORK | TOWER A 1303 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28393 |  |  |  | TOWER A 13TH FLOOR | TOWER A 1304 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28384 |  |  |  | TOWER A 1304 | TOWER A 1304 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28383 |  |  |  | TOWER A 1304 WATERPROOFING WORK | TOWER A 1304 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28387 |  |  |  | TOWER A 1304 | TOWER A 1304 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41106 |  |  |  | TOWER A 1304 PLUMBING WORK | TOWER A 1304 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28385 |  |  |  | TOWER A 1304 | TOWER A 1304 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28386 |  |  |  | TOWER A 1304 ELECTRIC WORK | TOWER A 1304 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28388 |  |  |  | TOWER A 1304 | TOWER A 1304 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41698 |  |  |  | TOWER A 1304 FLOORING & DEDO WORK | TOWER A 1304 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28391 |  |  |  | TOWER A 1304 | TOWER A 1304 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28389 |  |  |  | TOWER A 1304 | TOWER A 1304 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28390 |  |  |  | TOWER A 1304 | TOWER A 1304 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28392 |  |  |  | TOWER A 1304 | TOWER A 1304 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34821 |  |  |  | TOWER A 1304 | TOWER A 1304 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34822 |  |  |  | TOWER A 1304 COMMON WORK | TOWER A 1304 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34823 |  |  |  | TOWER A 1304 COMMON WORK | TOWER A 1304 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34824 |  |  |  | TOWER A 1304 COMMON WORK | TOWER A 1304 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28470 |  |  |  | TOWER A 13TH FLOOR | TOWER A 13TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28472 |  |  |  | TOWER A 13TH FLOOR COMMON WORK | TOWER A 13TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28471 |  |  |  | TOWER A 13TH FLOOR COMMON WORK | TOWER A 13TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41959 |  |  |  | TOWER A 13TH FLOOR COMMON FLOORING WORK | TOWER A 13TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28473 |  |  |  | TOWER A 13TH FLOOR COMMON WORK | TOWER A 13TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28474 |  |  |  | TOWER A 13TH FLOOR COMMON WORK | TOWER A 13TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29467 |  |  |  | TOWER A 13TH FLOOR COMMON WORK | TOWER A 13TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33051 |  |  |  | TOWER A 13TH FLOOR COMMON ELECTRIC WORK | TOWER A 13TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42275 |  |  |  | TOWER A 13TH FLOOR COMMON WORK | TOWER A 13TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42276 |  |  |  | TOWER A 13TH FLOOR WPC PANNELING WORK | TOWER A 13TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24232 |  |  |  | TOWER A | TOWER A 14TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24233 |  |  |  | TOWER A 14TH FLOOR | TOWER A 14TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24234 |  |  |  | TOWER A 14TH FLOOR CIVIL WORK | TOWER A 14TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24237 |  |  |  | TOWER A 14TH FLOOR RCC WORK | TOWER A 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24235 |  |  |  | TOWER A 14TH FLOOR CIVIL WORK | TOWER A 14TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24238 |  |  |  | TOWER A 14TH FLOOR MASONRY WORK | TOWER A 14TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39358 |  |  |  | TOWER A 14TH FLOOR MASONRY WORK | TOWER A 14TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24236 |  |  |  | TOWER A 14TH FLOOR CIVIL WORK | TOWER A 14TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24239 |  |  |  | TOWER A 14TH FLOOR PLASTER WORK | TOWER A 14TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28107 |  |  |  | TOWER A 14TH FLOOR | TOWER A 1401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28098 |  |  |  | TOWER A 1401 | TOWER A 1401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28097 |  |  |  | TOWER A 1401 WATERPROOFING WORK | TOWER A 1401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28101 |  |  |  | TOWER A 1401 | TOWER A 1401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41107 |  |  |  | TOWER A 1401 PLUMBING WORK | TOWER A 1401 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28099 |  |  |  | TOWER A 1401 | TOWER A 1401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28100 |  |  |  | TOWER A 1401 ELECTRIC WORK | TOWER A 1401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28102 |  |  |  | TOWER A 1401 | TOWER A 1401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41699 |  |  |  | TOWER A 1401 FLOORING & DEDO WORK | TOWER A 1401 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28105 |  |  |  | TOWER A 1401 | TOWER A 1401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28103 |  |  |  | TOWER A 1401 | TOWER A 1401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28104 |  |  |  | TOWER A 1401 | TOWER A 1401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28106 |  |  |  | TOWER A 1401 | TOWER A 1401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34825 |  |  |  | TOWER A 1401 | TOWER A 1401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34826 |  |  |  | TOWER A 1401 COMMON WORK | TOWER A 1401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34827 |  |  |  | TOWER A 1401 COMMON WORK | TOWER A 1401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34828 |  |  |  | TOWER A 1401 COMMON WORK | TOWER A 1401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28206 |  |  |  | TOWER A 14TH FLOOR | TOWER A 1402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28197 |  |  |  | TOWER A 1402 | TOWER A 1402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28196 |  |  |  | TOWER A 1402 WATERPROOFING WORK | TOWER A 1402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28200 |  |  |  | TOWER A 1402 | TOWER A 1402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41108 |  |  |  | TOWER A 1402 PLUMBING WORK | TOWER A 1402 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28198 |  |  |  | TOWER A 1402 | TOWER A 1402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28199 |  |  |  | TOWER A 1402 ELECTRIC WORK | TOWER A 1402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28201 |  |  |  | TOWER A 1402 | TOWER A 1402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41700 |  |  |  | TOWER A 1402 FLOORING & DEDO WORK | TOWER A 1402 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28204 |  |  |  | TOWER A 1402 | TOWER A 1402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28202 |  |  |  | TOWER A 1402 | TOWER A 1402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28203 |  |  |  | TOWER A 1402 | TOWER A 1402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28205 |  |  |  | TOWER A 1402 | TOWER A 1402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34829 |  |  |  | TOWER A 1402 | TOWER A 1402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34830 |  |  |  | TOWER A 1402 COMMON WORK | TOWER A 1402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34831 |  |  |  | TOWER A 1402 COMMON WORK | TOWER A 1402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34832 |  |  |  | TOWER A 1402 COMMON WORK | TOWER A 1402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28305 |  |  |  | TOWER A 14TH FLOOR | TOWER A 1403 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28296 |  |  |  | TOWER A 1403 | TOWER A 1403 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28295 |  |  |  | TOWER A 1403 WATERPROOFING WORK | TOWER A 1403 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28299 |  |  |  | TOWER A 1403 | TOWER A 1403 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41109 |  |  |  | TOWER A 1403 PLUMBING WORK | TOWER A 1403 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28297 |  |  |  | TOWER A 1403 | TOWER A 1403 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28298 |  |  |  | TOWER A 1403 ELECTRIC WORK | TOWER A 1403 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28300 |  |  |  | TOWER A 1403 | TOWER A 1403 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41701 |  |  |  | TOWER A 1403 FLOORING & DEDO WORK | TOWER A 1403 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28303 |  |  |  | TOWER A 1403 | TOWER A 1403 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28301 |  |  |  | TOWER A 1403 | TOWER A 1403 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28302 |  |  |  | TOWER A 1403 | TOWER A 1403 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28304 |  |  |  | TOWER A 1403 | TOWER A 1403 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34833 |  |  |  | TOWER A 1403 | TOWER A 1403 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34834 |  |  |  | TOWER A 1403 COMMON WORK | TOWER A 1403 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34835 |  |  |  | TOWER A 1403 COMMON WORK | TOWER A 1403 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34836 |  |  |  | TOWER A 1403 COMMON WORK | TOWER A 1403 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28404 |  |  |  | TOWER A 14TH FLOOR | TOWER A 1404 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28395 |  |  |  | TOWER A 1404 | TOWER A 1404 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28394 |  |  |  | TOWER A 1404 WATERPROOFING WORK | TOWER A 1404 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28398 |  |  |  | TOWER A 1404 | TOWER A 1404 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41110 |  |  |  | TOWER A 1404 PLUMBING WORK | TOWER A 1404 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28396 |  |  |  | TOWER A 1404 | TOWER A 1404 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28397 |  |  |  | TOWER A 1404 ELECTRIC WORK | TOWER A 1404 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28399 |  |  |  | TOWER A 1404 | TOWER A 1404 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41702 |  |  |  | TOWER A 1404 FLOORING & DEDO WORK | TOWER A 1404 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28402 |  |  |  | TOWER A 1404 | TOWER A 1404 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28400 |  |  |  | TOWER A 1404 | TOWER A 1404 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28401 |  |  |  | TOWER A 1404 | TOWER A 1404 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28403 |  |  |  | TOWER A 1404 | TOWER A 1404 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34837 |  |  |  | TOWER A 1404 | TOWER A 1404 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34838 |  |  |  | TOWER A 1404 COMMON WORK | TOWER A 1404 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34839 |  |  |  | TOWER A 1404 COMMON WORK | TOWER A 1404 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34840 |  |  |  | TOWER A 1404 COMMON WORK | TOWER A 1404 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28475 |  |  |  | TOWER A 14TH FLOOR | TOWER A 14TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28477 |  |  |  | TOWER A 14TH FLOOR COMMON WORK | TOWER A 14TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28476 |  |  |  | TOWER A 14TH FLOOR COMMON WORK | TOWER A 14TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41960 |  |  |  | TOWER A 14TH FLOOR COMMON FLOORING WORK | TOWER A 14TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28478 |  |  |  | TOWER A 14TH FLOOR COMMON WORK | TOWER A 14TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28479 |  |  |  | TOWER A 14TH FLOOR COMMON WORK | TOWER A 14TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29468 |  |  |  | TOWER A 14TH FLOOR COMMON WORK | TOWER A 14TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33052 |  |  |  | TOWER A 14TH FLOOR COMMON ELECTRIC WORK | TOWER A 14TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42277 |  |  |  | TOWER A 14TH FLOOR COMMON WORK | TOWER A 14TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42278 |  |  |  | TOWER A 14TH FLOOR WPC PANNELING WORK | TOWER A 14TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24240 |  |  |  | TOWER A | TOWER A 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24241 |  |  |  | TOWER A 15TH FLOOR | TOWER A 15TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24242 |  |  |  | TOWER A 15TH FLOOR CIVIL WORK | TOWER A 15TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24245 |  |  |  | TOWER A 15TH FLOOR RCC WORK | TOWER A 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24243 |  |  |  | TOWER A 15TH FLOOR CIVIL WORK | TOWER A 15TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24246 |  |  |  | TOWER A 15TH FLOOR MASONRY WORK | TOWER A 15TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39359 |  |  |  | TOWER A 15TH FLOOR MASONRY WORK | TOWER A 15TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24244 |  |  |  | TOWER A 15TH FLOOR CIVIL WORK | TOWER A 15TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24247 |  |  |  | TOWER A 15TH FLOOR PLASTER WORK | TOWER A 15TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28118 |  |  |  | TOWER A 15TH FLOOR | TOWER A 1501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28109 |  |  |  | TOWER A 1501 | TOWER A 1501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28108 |  |  |  | TOWER A 1501 WATERPROOFING WORK | TOWER A 1501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28112 |  |  |  | TOWER A 1501 | TOWER A 1501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41111 |  |  |  | TOWER A 1501 PLUMBING WORK | TOWER A 1501 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28110 |  |  |  | TOWER A 1501 | TOWER A 1501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28111 |  |  |  | TOWER A 1501 ELECTRIC WORK | TOWER A 1501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28113 |  |  |  | TOWER A 1501 | TOWER A 1501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41703 |  |  |  | TOWER A 1501 FLOORING & DEDO WORK | TOWER A 1501 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28116 |  |  |  | TOWER A 1501 | TOWER A 1501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28114 |  |  |  | TOWER A 1501 | TOWER A 1501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28115 |  |  |  | TOWER A 1501 | TOWER A 1501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28117 |  |  |  | TOWER A 1501 | TOWER A 1501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34841 |  |  |  | TOWER A 1501 | TOWER A 1501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34842 |  |  |  | TOWER A 1501 COMMON WORK | TOWER A 1501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34843 |  |  |  | TOWER A 1501 COMMON WORK | TOWER A 1501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34844 |  |  |  | TOWER A 1501 COMMON WORK | TOWER A 1501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28217 |  |  |  | TOWER A 15TH FLOOR | TOWER A 1502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28208 |  |  |  | TOWER A 1502 | TOWER A 1502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28207 |  |  |  | TOWER A 1502 WATERPROOFING WORK | TOWER A 1502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28211 |  |  |  | TOWER A 1502 | TOWER A 1502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41112 |  |  |  | TOWER A 1502 PLUMBING WORK | TOWER A 1502 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28209 |  |  |  | TOWER A 1502 | TOWER A 1502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28210 |  |  |  | TOWER A 1502 ELECTRIC WORK | TOWER A 1502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28212 |  |  |  | TOWER A 1502 | TOWER A 1502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41704 |  |  |  | TOWER A 1502 FLOORING & DEDO WORK | TOWER A 1502 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28215 |  |  |  | TOWER A 1502 | TOWER A 1502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28213 |  |  |  | TOWER A 1502 | TOWER A 1502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28214 |  |  |  | TOWER A 1502 | TOWER A 1502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28216 |  |  |  | TOWER A 1502 | TOWER A 1502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34845 |  |  |  | TOWER A 1502 | TOWER A 1502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34846 |  |  |  | TOWER A 1502 COMMON WORK | TOWER A 1502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34847 |  |  |  | TOWER A 1502 COMMON WORK | TOWER A 1502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34848 |  |  |  | TOWER A 1502 COMMON WORK | TOWER A 1502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28316 |  |  |  | TOWER A 15TH FLOOR | TOWER A 1503 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28307 |  |  |  | TOWER A 1503 | TOWER A 1503 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28306 |  |  |  | TOWER A 1503 WATERPROOFING WORK | TOWER A 1503 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28310 |  |  |  | TOWER A 1503 | TOWER A 1503 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41113 |  |  |  | TOWER A 1503 PLUMBING WORK | TOWER A 1503 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28308 |  |  |  | TOWER A 1503 | TOWER A 1503 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28309 |  |  |  | TOWER A 1503 ELECTRIC WORK | TOWER A 1503 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28311 |  |  |  | TOWER A 1503 | TOWER A 1503 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41705 |  |  |  | TOWER A 1503 FLOORING & DEDO WORK | TOWER A 1503 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28314 |  |  |  | TOWER A 1503 | TOWER A 1503 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28312 |  |  |  | TOWER A 1503 | TOWER A 1503 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28313 |  |  |  | TOWER A 1503 | TOWER A 1503 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28315 |  |  |  | TOWER A 1503 | TOWER A 1503 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34849 |  |  |  | TOWER A 1503 | TOWER A 1503 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34850 |  |  |  | TOWER A 1503 COMMON WORK | TOWER A 1503 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34851 |  |  |  | TOWER A 1503 COMMON WORK | TOWER A 1503 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34852 |  |  |  | TOWER A 1503 COMMON WORK | TOWER A 1503 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28415 |  |  |  | TOWER A 15TH FLOOR | TOWER A 1504 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28406 |  |  |  | TOWER A 1504 | TOWER A 1504 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28405 |  |  |  | TOWER A 1504 WATERPROOFING WORK | TOWER A 1504 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28409 |  |  |  | TOWER A 1504 | TOWER A 1504 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41114 |  |  |  | TOWER A 1504 PLUMBING WORK | TOWER A 1504 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28407 |  |  |  | TOWER A 1504 | TOWER A 1504 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28408 |  |  |  | TOWER A 1504 ELECTRIC WORK | TOWER A 1504 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28410 |  |  |  | TOWER A 1504 | TOWER A 1504 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41706 |  |  |  | TOWER A 1504 FLOORING & DEDO WORK | TOWER A 1504 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28413 |  |  |  | TOWER A 1504 | TOWER A 1504 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28411 |  |  |  | TOWER A 1504 | TOWER A 1504 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28412 |  |  |  | TOWER A 1504 | TOWER A 1504 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28414 |  |  |  | TOWER A 1504 | TOWER A 1504 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34853 |  |  |  | TOWER A 1504 | TOWER A 1504 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34854 |  |  |  | TOWER A 1504 COMMON WORK | TOWER A 1504 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34855 |  |  |  | TOWER A 1504 COMMON WORK | TOWER A 1504 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34856 |  |  |  | TOWER A 1504 COMMON WORK | TOWER A 1504 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28480 |  |  |  | TOWER A 15TH FLOOR | TOWER A 15TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28482 |  |  |  | TOWER A 15TH FLOOR COMMON WORK | TOWER A 15TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28481 |  |  |  | TOWER A 15TH FLOOR COMMON WORK | TOWER A 15TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41961 |  |  |  | TOWER A 15TH FLOOR COMMON FLOORING WORK | TOWER A 15TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28483 |  |  |  | TOWER A 15TH FLOOR COMMON WORK | TOWER A 15TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28484 |  |  |  | TOWER A 15TH FLOOR COMMON WORK | TOWER A 15TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29469 |  |  |  | TOWER A 15TH FLOOR COMMON WORK | TOWER A 15TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33053 |  |  |  | TOWER A 15TH FLOOR COMMON ELECTRIC WORK | TOWER A 15TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42279 |  |  |  | TOWER A 15TH FLOOR COMMON WORK | TOWER A 15TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42280 |  |  |  | TOWER A 15TH FLOOR WPC PANNELING WORK | TOWER A 15TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24248 |  |  |  | TOWER A | TOWER A 16TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24249 |  |  |  | TOWER A 16TH FLOOR | TOWER A 16TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24250 |  |  |  | TOWER A 16TH FLOOR CIVIL WORK | TOWER A 16TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24253 |  |  |  | TOWER A 16TH FLOOR RCC WORK | TOWER A 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24251 |  |  |  | TOWER A 16TH FLOOR CIVIL WORK | TOWER A 16TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24254 |  |  |  | TOWER A 16TH FLOOR MASONRY WORK | TOWER A 16TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24252 |  |  |  | TOWER A 16TH FLOOR CIVIL WORK | TOWER A 16TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24255 |  |  |  | TOWER A 16TH FLOOR PLASTER WORK | TOWER A 16TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28129 |  |  |  | TOWER A 16TH FLOOR | TOWER A 1601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28120 |  |  |  | TOWER A 1601 | TOWER A 1601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28119 |  |  |  | TOWER A 1601 WATERPROOFING WORK | TOWER A 1601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28123 |  |  |  | TOWER A 1601 | TOWER A 1601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28121 |  |  |  | TOWER A 1601 | TOWER A 1601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28122 |  |  |  | TOWER A 1601 ELECTRIC WORK | TOWER A 1601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28124 |  |  |  | TOWER A 1601 | TOWER A 1601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28127 |  |  |  | TOWER A 1601 | TOWER A 1601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28125 |  |  |  | TOWER A 1601 | TOWER A 1601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28126 |  |  |  | TOWER A 1601 | TOWER A 1601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28128 |  |  |  | TOWER A 1601 | TOWER A 1601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34857 |  |  |  | TOWER A 1601 | TOWER A 1601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34858 |  |  |  | TOWER A 1601 COMMON WORK | TOWER A 1601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34859 |  |  |  | TOWER A 1601 COMMON WORK | TOWER A 1601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34860 |  |  |  | TOWER A 1601 COMMON WORK | TOWER A 1601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28228 |  |  |  | TOWER A 16TH FLOOR | TOWER A 1602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28219 |  |  |  | TOWER A 1602 | TOWER A 1602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28218 |  |  |  | TOWER A 1602 WATERPROOFING WORK | TOWER A 1602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28222 |  |  |  | TOWER A 1602 | TOWER A 1602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28220 |  |  |  | TOWER A 1602 | TOWER A 1602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28221 |  |  |  | TOWER A 1602 ELECTRIC WORK | TOWER A 1602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28223 |  |  |  | TOWER A 1602 | TOWER A 1602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28226 |  |  |  | TOWER A 1602 | TOWER A 1602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28224 |  |  |  | TOWER A 1602 | TOWER A 1602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28225 |  |  |  | TOWER A 1602 | TOWER A 1602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28227 |  |  |  | TOWER A 1602 | TOWER A 1602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34861 |  |  |  | TOWER A 1602 | TOWER A 1602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34862 |  |  |  | TOWER A 1602 COMMON WORK | TOWER A 1602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34863 |  |  |  | TOWER A 1602 COMMON WORK | TOWER A 1602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34864 |  |  |  | TOWER A 1602 COMMON WORK | TOWER A 1602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28327 |  |  |  | TOWER A 16TH FLOOR | TOWER A 1603 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28318 |  |  |  | TOWER A 1603 | TOWER A 1603 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28317 |  |  |  | TOWER A 1603 WATERPROOFING WORK | TOWER A 1603 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28321 |  |  |  | TOWER A 1603 | TOWER A 1603 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28319 |  |  |  | TOWER A 1603 | TOWER A 1603 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28320 |  |  |  | TOWER A 1603 ELECTRIC WORK | TOWER A 1603 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28322 |  |  |  | TOWER A 1603 | TOWER A 1603 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28325 |  |  |  | TOWER A 1603 | TOWER A 1603 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28323 |  |  |  | TOWER A 1603 | TOWER A 1603 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28324 |  |  |  | TOWER A 1603 | TOWER A 1603 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28326 |  |  |  | TOWER A 1603 | TOWER A 1603 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34865 |  |  |  | TOWER A 1603 | TOWER A 1603 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34866 |  |  |  | TOWER A 1603 COMMON WORK | TOWER A 1603 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34867 |  |  |  | TOWER A 1603 COMMON WORK | TOWER A 1603 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34868 |  |  |  | TOWER A 1603 COMMON WORK | TOWER A 1603 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28426 |  |  |  | TOWER A 16TH FLOOR | TOWER A 1604 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28417 |  |  |  | TOWER A 1604 | TOWER A 1604 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28416 |  |  |  | TOWER A 1604 WATERPROOFING WORK | TOWER A 1604 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28420 |  |  |  | TOWER A 1604 | TOWER A 1604 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28418 |  |  |  | TOWER A 1604 | TOWER A 1604 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28419 |  |  |  | TOWER A 1604 ELECTRIC WORK | TOWER A 1604 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28421 |  |  |  | TOWER A 1604 | TOWER A 1604 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28424 |  |  |  | TOWER A 1604 | TOWER A 1604 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28422 |  |  |  | TOWER A 1604 | TOWER A 1604 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28423 |  |  |  | TOWER A 1604 | TOWER A 1604 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28425 |  |  |  | TOWER A 1604 | TOWER A 1604 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34869 |  |  |  | TOWER A 1604 | TOWER A 1604 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34870 |  |  |  | TOWER A 1604 COMMON WORK | TOWER A 1604 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34871 |  |  |  | TOWER A 1604 COMMON WORK | TOWER A 1604 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34872 |  |  |  | TOWER A 1604 COMMON WORK | TOWER A 1604 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28485 |  |  |  | TOWER A 16TH FLOOR | TOWER A 16TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28487 |  |  |  | TOWER A 16TH FLOOR COMMON WORK | TOWER A 16TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28486 |  |  |  | TOWER A 16TH FLOOR COMMON WORK | TOWER A 16TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41962 |  |  |  | TOWER A 16TH FLOOR COMMON FLOORING WORK | TOWER A 16TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28488 |  |  |  | TOWER A 16TH FLOOR COMMON WORK | TOWER A 16TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28489 |  |  |  | TOWER A 16TH FLOOR COMMON WORK | TOWER A 16TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29470 |  |  |  | TOWER A 16TH FLOOR COMMON WORK | TOWER A 16TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33054 |  |  |  | TOWER A 16TH FLOOR COMMON ELECTRIC WORK | TOWER A 16TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42281 |  |  |  | TOWER A 16TH FLOOR COMMON WORK | TOWER A 16TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42282 |  |  |  | TOWER A 16TH FLOOR WPC PANNELING WORK | TOWER A 16TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24256 |  |  |  | TOWER A | TOWER A 17TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24257 |  |  |  | TOWER A 17TH FLOOR | TOWER A 17TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24258 |  |  |  | TOWER A 17TH FLOOR CIVIL WORK | TOWER A 17TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24261 |  |  |  | TOWER A 17TH FLOOR RCC WORK | TOWER A 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24259 |  |  |  | TOWER A 17TH FLOOR CIVIL WORK | TOWER A 17TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24262 |  |  |  | TOWER A 17TH FLOOR MASONRY WORK | TOWER A 17TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 303577.4 |  | Tentative | 303577.4 | 0 | 303577.4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24260 |  |  |  | TOWER A 17TH FLOOR CIVIL WORK | TOWER A 17TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24263 |  |  |  | TOWER A 17TH FLOOR PLASTER WORK | TOWER A 17TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28140 |  |  |  | TOWER A 17TH FLOOR | TOWER A 1701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28131 |  |  |  | TOWER A 1701 | TOWER A 1701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28130 |  |  |  | TOWER A 1701 WATERPROOFING WORK | TOWER A 1701 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28134 |  |  |  | TOWER A 1701 | TOWER A 1701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28132 |  |  |  | TOWER A 1701 | TOWER A 1701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28133 |  |  |  | TOWER A 1701 ELECTRIC WORK | TOWER A 1701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28135 |  |  |  | TOWER A 1701 | TOWER A 1701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28138 |  |  |  | TOWER A 1701 | TOWER A 1701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28136 |  |  |  | TOWER A 1701 | TOWER A 1701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28137 |  |  |  | TOWER A 1701 | TOWER A 1701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28139 |  |  |  | TOWER A 1701 | TOWER A 1701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34873 |  |  |  | TOWER A 1701 | TOWER A 1701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34874 |  |  |  | TOWER A 1701 COMMON WORK | TOWER A 1701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34875 |  |  |  | TOWER A 1701 COMMON WORK | TOWER A 1701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34876 |  |  |  | TOWER A 1701 COMMON WORK | TOWER A 1701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28239 |  |  |  | TOWER A 17TH FLOOR | TOWER A 1702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28230 |  |  |  | TOWER A 1702 | TOWER A 1702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28229 |  |  |  | TOWER A 1702 WATERPROOFING WORK | TOWER A 1702 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28233 |  |  |  | TOWER A 1702 | TOWER A 1702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28231 |  |  |  | TOWER A 1702 | TOWER A 1702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28232 |  |  |  | TOWER A 1702 ELECTRIC WORK | TOWER A 1702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28234 |  |  |  | TOWER A 1702 | TOWER A 1702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28237 |  |  |  | TOWER A 1702 | TOWER A 1702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28235 |  |  |  | TOWER A 1702 | TOWER A 1702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28236 |  |  |  | TOWER A 1702 | TOWER A 1702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28238 |  |  |  | TOWER A 1702 | TOWER A 1702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34877 |  |  |  | TOWER A 1702 | TOWER A 1702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34878 |  |  |  | TOWER A 1702 COMMON WORK | TOWER A 1702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34879 |  |  |  | TOWER A 1702 COMMON WORK | TOWER A 1702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34880 |  |  |  | TOWER A 1702 COMMON WORK | TOWER A 1702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28338 |  |  |  | TOWER A 17TH FLOOR | TOWER A 1703 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28329 |  |  |  | TOWER A 1703 | TOWER A 1703 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28328 |  |  |  | TOWER A 1703 WATERPROOFING WORK | TOWER A 1703 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28332 |  |  |  | TOWER A 1703 | TOWER A 1703 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28330 |  |  |  | TOWER A 1703 | TOWER A 1703 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28331 |  |  |  | TOWER A 1703 ELECTRIC WORK | TOWER A 1703 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28333 |  |  |  | TOWER A 1703 | TOWER A 1703 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28336 |  |  |  | TOWER A 1703 | TOWER A 1703 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28334 |  |  |  | TOWER A 1703 | TOWER A 1703 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28335 |  |  |  | TOWER A 1703 | TOWER A 1703 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28337 |  |  |  | TOWER A 1703 | TOWER A 1703 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34881 |  |  |  | TOWER A 1703 | TOWER A 1703 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34882 |  |  |  | TOWER A 1703 COMMON WORK | TOWER A 1703 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34883 |  |  |  | TOWER A 1703 COMMON WORK | TOWER A 1703 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34884 |  |  |  | TOWER A 1703 COMMON WORK | TOWER A 1703 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28437 |  |  |  | TOWER A 17TH FLOOR | TOWER A 1704 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28428 |  |  |  | TOWER A 1704 | TOWER A 1704 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28427 |  |  |  | TOWER A 1704 WATERPROOFING WORK | TOWER A 1704 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28431 |  |  |  | TOWER A 1704 | TOWER A 1704 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28429 |  |  |  | TOWER A 1704 | TOWER A 1704 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28430 |  |  |  | TOWER A 1704 ELECTRIC WORK | TOWER A 1704 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28432 |  |  |  | TOWER A 1704 | TOWER A 1704 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28435 |  |  |  | TOWER A 1704 | TOWER A 1704 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28433 |  |  |  | TOWER A 1704 | TOWER A 1704 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28434 |  |  |  | TOWER A 1704 | TOWER A 1704 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28436 |  |  |  | TOWER A 1704 | TOWER A 1704 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34885 |  |  |  | TOWER A 1704 | TOWER A 1704 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34886 |  |  |  | TOWER A 1704 COMMON WORK | TOWER A 1704 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34887 |  |  |  | TOWER A 1704 COMMON WORK | TOWER A 1704 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34888 |  |  |  | TOWER A 1704 COMMON WORK | TOWER A 1704 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28490 |  |  |  | TOWER A 17TH FLOOR | TOWER A 17TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28492 |  |  |  | TOWER A 17TH FLOOR COMMON WORK | TOWER A 17TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28491 |  |  |  | TOWER A 17TH FLOOR COMMON WORK | TOWER A 17TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41963 |  |  |  | TOWER A 17TH FLOOR COMMON FLOORING WORK | TOWER A 17TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28493 |  |  |  | TOWER A 17TH FLOOR COMMON WORK | TOWER A 17TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28494 |  |  |  | TOWER A 17TH FLOOR COMMON WORK | TOWER A 17TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29471 |  |  |  | TOWER A 17TH FLOOR COMMON WORK | TOWER A 17TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33055 |  |  |  | TOWER A 17TH FLOOR COMMON ELECTRIC WORK | TOWER A 17TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42283 |  |  |  | TOWER A 17TH FLOOR COMMON WORK | TOWER A 17TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42284 |  |  |  | TOWER A 17TH FLOOR WPC PANNELING WORK | TOWER A 17TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24264 |  |  |  | TOWER A | TOWER A 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24265 |  |  |  | TOWER A 18TH FLOOR | TOWER A 18TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24266 |  |  |  | TOWER A 18TH FLOOR CIVIL WORK | TOWER A 18TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24269 |  |  |  | TOWER A 18TH FLOOR RCC WORK | TOWER A 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24267 |  |  |  | TOWER A 18TH FLOOR CIVIL WORK | TOWER A 18TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24270 |  |  |  | TOWER A 18TH FLOOR MASONRY WORK | TOWER A 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24268 |  |  |  | TOWER A 18TH FLOOR CIVIL WORK | TOWER A 18TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24271 |  |  |  | TOWER A 18TH FLOOR PLASTER WORK | TOWER A 18TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28151 |  |  |  | TOWER A 18TH FLOOR | TOWER A 1801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28142 |  |  |  | TOWER A 1801 | TOWER A 1801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28145 |  |  |  | TOWER A 1801 | TOWER A 1801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28143 |  |  |  | TOWER A 1801 | TOWER A 1801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40413 |  |  |  | TOWER A 1801 ELECTRIC WORK | TOWER A 1801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28146 |  |  |  | TOWER A 1801 | TOWER A 1801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28149 |  |  |  | TOWER A 1801 | TOWER A 1801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28147 |  |  |  | TOWER A 1801 | TOWER A 1801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28148 |  |  |  | TOWER A 1801 | TOWER A 1801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28150 |  |  |  | TOWER A 1801 | TOWER A 1801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34889 |  |  |  | TOWER A 1801 | TOWER A 1801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34890 |  |  |  | TOWER A 1801 COMMON WORK | TOWER A 1801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34891 |  |  |  | TOWER A 1801 COMMON WORK | TOWER A 1801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34892 |  |  |  | TOWER A 1801 COMMON WORK | TOWER A 1801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28250 |  |  |  | TOWER A 18TH FLOOR | TOWER A 1802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28241 |  |  |  | TOWER A 1802 | TOWER A 1802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28240 |  |  |  | TOWER A 1802 WATERPROOFING WORK | TOWER A 1802 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28244 |  |  |  | TOWER A 1802 | TOWER A 1802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28242 |  |  |  | TOWER A 1802 | TOWER A 1802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28243 |  |  |  | TOWER A 1802 ELECTRIC WORK | TOWER A 1802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28245 |  |  |  | TOWER A 1802 | TOWER A 1802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28248 |  |  |  | TOWER A 1802 | TOWER A 1802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28246 |  |  |  | TOWER A 1802 | TOWER A 1802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28247 |  |  |  | TOWER A 1802 | TOWER A 1802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28249 |  |  |  | TOWER A 1802 | TOWER A 1802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34893 |  |  |  | TOWER A 1802 | TOWER A 1802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34894 |  |  |  | TOWER A 1802 COMMON WORK | TOWER A 1802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34895 |  |  |  | TOWER A 1802 COMMON WORK | TOWER A 1802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34896 |  |  |  | TOWER A 1802 COMMON WORK | TOWER A 1802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28349 |  |  |  | TOWER A 18TH FLOOR | TOWER A 1803 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28340 |  |  |  | TOWER A 1803 | TOWER A 1803 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28339 |  |  |  | TOWER A 1803 WATERPROOFING WORK | TOWER A 1803 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28343 |  |  |  | TOWER A 1803 | TOWER A 1803 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28341 |  |  |  | TOWER A 1803 | TOWER A 1803 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28342 |  |  |  | TOWER A 1803 ELECTRIC WORK | TOWER A 1803 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28344 |  |  |  | TOWER A 1803 | TOWER A 1803 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28347 |  |  |  | TOWER A 1803 | TOWER A 1803 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28345 |  |  |  | TOWER A 1803 | TOWER A 1803 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28346 |  |  |  | TOWER A 1803 | TOWER A 1803 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28348 |  |  |  | TOWER A 1803 | TOWER A 1803 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34897 |  |  |  | TOWER A 1803 | TOWER A 1803 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34898 |  |  |  | TOWER A 1803 COMMON WORK | TOWER A 1803 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34899 |  |  |  | TOWER A 1803 COMMON WORK | TOWER A 1803 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34900 |  |  |  | TOWER A 1803 COMMON WORK | TOWER A 1803 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28448 |  |  |  | TOWER A 18TH FLOOR | TOWER A 1804 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28439 |  |  |  | TOWER A 1804 | TOWER A 1804 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28438 |  |  |  | TOWER A 1804 WATERPROOFING WORK | TOWER A 1804 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28442 |  |  |  | TOWER A 1804 | TOWER A 1804 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28440 |  |  |  | TOWER A 1804 | TOWER A 1804 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28441 |  |  |  | TOWER A 1804 ELECTRIC WORK | TOWER A 1804 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28443 |  |  |  | TOWER A 1804 | TOWER A 1804 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28446 |  |  |  | TOWER A 1804 | TOWER A 1804 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28444 |  |  |  | TOWER A 1804 | TOWER A 1804 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28445 |  |  |  | TOWER A 1804 | TOWER A 1804 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28447 |  |  |  | TOWER A 1804 | TOWER A 1804 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34901 |  |  |  | TOWER A 1804 | TOWER A 1804 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34902 |  |  |  | TOWER A 1804 COMMON WORK | TOWER A 1804 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34903 |  |  |  | TOWER A 1804 COMMON WORK | TOWER A 1804 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34904 |  |  |  | TOWER A 1804 COMMON WORK | TOWER A 1804 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28495 |  |  |  | TOWER A 18TH FLOOR | TOWER A 18TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28497 |  |  |  | TOWER A 18TH FLOOR COMMON WORK | TOWER A 18TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28496 |  |  |  | TOWER A 18TH FLOOR COMMON WORK | TOWER A 18TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41964 |  |  |  | TOWER A 18TH FLOOR COMMON FLOORING WORK | TOWER A 18TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28498 |  |  |  | TOWER A 18TH FLOOR COMMON WORK | TOWER A 18TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28499 |  |  |  | TOWER A 18TH FLOOR COMMON WORK | TOWER A 18TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29472 |  |  |  | TOWER A 18TH FLOOR COMMON WORK | TOWER A 18TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33056 |  |  |  | TOWER A 18TH FLOOR COMMON ELECTRIC WORK | TOWER A 18TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42285 |  |  |  | TOWER A 18TH FLOOR COMMON WORK | TOWER A 18TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42286 |  |  |  | TOWER A 18TH FLOOR WPC PANNELING WORK | TOWER A 18TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 41485 |  |  |  | TOWER A | TOWER A TERRACE | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41486 |  |  |  | TOWER A TERRACE | TOWER A TERRACE CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41487 |  |  |  | TOWER A TERRACE CIVIL WORK | TOWER A TERRACE RCC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41490 |  |  |  | TOWER A TERRACE RCC WORK | TOWER A TERRACE RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 41488 |  |  |  | TOWER A TERRACE CIVIL WORK | TOWER A TERRACE MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41491 |  |  |  | TOWER A TERRACE MASONRY WORK | TOWER A TERRACE MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 41489 |  |  |  | TOWER A TERRACE CIVIL WORK | TOWER A TERRACE PLASTER WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41492 |  |  |  | TOWER A TERRACE PLASTER WORK | TOWER A TERRACE PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 41441 |  |  |  | TOWER A | TOWER A COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41442 |  |  |  | TOWER A COMMON WORK | TOWER A COMMON PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41443 |  |  |  | TOWER A COMMON PLUMBING WORK | TOWER A COMMON DUCT PLUMBING WORK | 1 | NOS | 1 | NOS | 553.42 |  | Tentative | 553.42 | 0 | 553.42 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING DUCT-PVC-SWR DRAINAGE PIPING WO
Group | 4 | 41473 |  |  |  | TOWER A COMMON WORK | TOWER A COMMON ELECTRIC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41474 |  |  |  | TOWER A COMMON ELECTRIC WORK | TOWER A COMMON ELECTRIC WORK | 1 | POINT | 1 | POINT | 217.9 | ELECTRIC WORK | Tentative | 217.9 | 0 | 217.9 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | TOWER COMMON ELECTRIC WORK
Group | 4 | 42149 | Block/Building/Tower/Wing |  | Externall Plaster | TOWER A COMMON WORK | TOWER A EXTERNAL PAINT WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 42150 |  |  |  | TOWER A EXTERNAL PAINT WORK | TOWER A EXTERNAL PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | EXTERNAL PAINT WORK
Group | 2 | 24077 |  |  |  |  | TOWER B | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 3 | 24094 |  |  |  | TOWER B | TOWER B BASEMENT | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24095 |  |  |  | TOWER B BASEMENT | TOWER B BASEMENT CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24096 |  |  |  | TOWER B BASEMENT CIVIL WORK | TOWER B BASEMENT RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24098 |  |  |  | TOWER B BASEMENT RCC WORK | TOWER B BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 510514.7 |  | Started | 510514.7 | 0 | 510514.7 | 24.08 | 12292025.92 | 23020339.73 | 5731209.53 | 28751549.26 |  |  | 20 Sep 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 25960 |  |  |  | TOWER B BASEMENT RCC WORK | TOWER B BASEMENT RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 148701.22 | 148701.22 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 30525 |  |  |  | TOWER B BASEMENT RCC WORK | TOWER B BASEMENT RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 5771 |  | Started | 0 | 5771 | 5771 | 0 | 5.77 | 0 | 71602.4 | 71602.4 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | REBARING WORK
Group | 5 | 24097 |  |  |  | TOWER B BASEMENT CIVIL WORK | TOWER B BASEMENT PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24099 |  |  |  | TOWER B BASEMENT PLASTER WORK | TOWER B BASEMENT PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 5 | 37590 |  |  |  | TOWER B BASEMENT CIVIL WORK | TOWER B BASEMENT CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 37592 |  |  |  | TOWER B BASEMENT CIVIL EXTRA WORK | TOWER B BASEMENT CIVIL EXTRA WORK CIVIL EXTRA WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 3529349.37 | 3529349.37 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | CIVIL EXTRA WORK
Group | 4 | 24864 |  |  |  | TOWER B BASEMENT | TOWER B BASEMENT FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2022 |  | - | - | - | -
Group | 5 | 24870 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Jul 2023 |  | - | - | 1216 | -
Task | 6 | 24865 |  |  |  | TOWER B BASEMENT WATERPROOFING WORK | TOWER B BASEMENT WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 9.8 | 0 | 0 | 219035.67 | 219035.67 |  |  | 15 Jul 2023 |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29306 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29307 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Sep 2022 |  | - | - | 918 | -
Task | 6 | 29308 |  |  |  | TOWER B BASEMENT ELECTRIC WORK | TOWER B BASEMENT ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 65867.6 | 65867.6 | 17 Mar 2020 |  | 20 Sep 2022 |  | - | - | 918 | - | ELECTRIC WORK
Group | 5 | 29309 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29310 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29311 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29312 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29313 |  |  |  | TOWER B BASEMENT FINISHING WORK | TOWER B BASEMENT FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 28505 |  |  |  | TOWER B BASEMENT | TOWER B BASEMENT COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28508 |  |  |  | TOWER B BASEMENT COMMON WORK | TOWER B BASEMENT COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39400 |  |  |  | TOWER B BASEMENT COMMON DEBRISH CHUTE WORK | TOWER B BASEMENT COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 28506 |  |  |  | TOWER B BASEMENT COMMON WORK | TOWER B BASEMENT COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28507 |  |  |  | TOWER B BASEMENT COMMON WORK | TOWER B BASEMENT COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28509 |  |  |  | TOWER B BASEMENT COMMON WORK | TOWER B BASEMENT COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29474 |  |  |  | TOWER B BASEMENT COMMON WORK | TOWER B BASEMENT COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 24113 |  |  |  | TOWER B | TOWER B GROUND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 08 Apr 2022 |  | - | - | - | -
Group | 4 | 24114 |  |  |  | TOWER B GROUND FLOOR | TOWER B GROUND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 08 Apr 2022 |  | - | - | - | -
Group | 5 | 24115 |  |  |  | TOWER B GROUND FLOOR CIVIL WORK | TOWER B GROUND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 08 Apr 2022 |  | - | - | - | -
Task | 6 | 24118 |  |  |  | TOWER B GROUND FLOOR RCC WORK | TOWER B GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 102274.98 |  | Started | 102274.98 | 0 | 102274.98 | 11.07 | 1132441.76 | 0 | 2199477.17 | 2199477.17 |  |  | 03 Oct 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 27048 |  |  |  | TOWER B GROUND FLOOR RCC WORK | TOWER B GROUND FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 70798.06 | 70798.06 | 17 Mar 2020 |  | 08 Apr 2022 |  | - | - | 753 | - | THREADING
Task | 6 | 32138 |  |  |  | TOWER B GROUND FLOOR RCC WORK | TOWER B GROUND FLOOR RCC WORK PT CABLE LAYING | 1 | RMT | 1 | RMT | 0 |  | Started | 0 | 0 | 0 | 2.12 | 0 | 0 | 351877.76 | 351877.76 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | - | PT CABLE LAYING
Task | 6 | 41840 |  |  |  | TOWER B GROUND FLOOR RCC WORK | TOWER B GROUND FLOOR RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 07 Oct 2024 |  | - | - | 1666 | - | REBARING WORK
Group | 5 | 24116 |  |  |  | TOWER B GROUND FLOOR CIVIL WORK | TOWER B GROUND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24119 |  |  |  | TOWER B GROUND FLOOR MASONRY WORK | TOWER B GROUND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 425785.65 |  | Started | 425785.65 | 0 | 425785.65 | 0 | 425.79 | 0 | 470930.94 | 470930.94 |  |  | 19 Sep 2024 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24117 |  |  |  | TOWER B GROUND FLOOR CIVIL WORK | TOWER B GROUND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24120 |  |  |  | TOWER B GROUND FLOOR PLASTER WORK | TOWER B GROUND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28510 |  |  |  | TOWER B GROUND FLOOR | TOWER B GROUND FLOOR FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | -
Group | 5 | 28512 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 28511 |  |  |  | TOWER B GROUND FLOOR WATERPROOFING WORK | TOWER B GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28515 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28513 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | -
Task | 6 | 28514 |  |  |  | TOWER B GROUND FLOOR ELECTRIC WORK | TOWER B GROUND FLOOR ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 143430.88 | 143430.88 | 17 Mar 2020 |  | 10 Nov 2022 |  | - | - | 969 | - | ELECTRIC WORK
Group | 5 | 28516 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42159 |  |  |  | TOWER B GROUND FLOOR FLOORING & DEDO WORK | TOWER B GROUND FLOOR FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1121 |  | Tentative | 1121 | 0 | 1121 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28519 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28517 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28518 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28520 |  |  |  | TOWER B GROUND FLOOR FINISHING WORK | TOWER B GROUND FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 28521 |  |  |  | TOWER B GROUND FLOOR | TOWER B GROUND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | -
Group | 5 | 28524 |  |  |  | TOWER B GROUND FLOOR COMMON WORK | TOWER B GROUND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39281 |  |  |  | TOWER B GROUND FLOOR COMMON DEBRISH CHUTE WORK | TOWER B GROUND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 28522 |  |  |  | TOWER B GROUND FLOOR COMMON WORK | TOWER B GROUND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40603 |  |  |  | TOWER B GROUND FLOOR COMMON FLOORING WORK | TOWER B GROUND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 472 |  | Tentative | 472 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 28523 |  |  |  | TOWER B GROUND FLOOR COMMON WORK | TOWER B GROUND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28525 |  |  |  | TOWER B GROUND FLOOR COMMON WORK | TOWER B GROUND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42051 |  |  |  | TOWER B GROUND FLOOR COMMON FALSE CEILING WORK | TOWER B GROUND FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29453 |  |  |  | TOWER B GROUND FLOOR COMMON WORK | TOWER B GROUND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | -
Task | 6 | 33437 |  |  |  | TOWER B GROUND FLOOR COMMON ELECTRIC WORK | TOWER B GROUND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 145.22 |  | Started | 145.22 | 0 | 145.22 | 0 | 0.15 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | - | ELECTRIC WORK
Group | 5 | 42287 |  |  |  | TOWER B GROUND FLOOR COMMON WORK | TOWER B GROUND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42288 |  |  |  | TOWER B GROUND FLOOR WPC PANNELING WORK | TOWER B GROUND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24328 |  |  |  | TOWER B | TOWER B 1ST FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 03 Oct 2022 |  | - | - | - | -
Group | 4 | 24329 |  |  |  | TOWER B 1ST FLOOR | TOWER B 1ST FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 03 Oct 2022 |  | - | - | - | -
Group | 5 | 24330 |  |  |  | TOWER B 1ST FLOOR CIVIL WORK | TOWER B 1ST FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 03 Oct 2022 |  | - | - | - | -
Task | 6 | 24333 |  |  |  | TOWER B 1ST FLOOR RCC WORK | TOWER B 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 53229.48 |  | Started | 53229.48 | 0 | 53229.48 | 9.78 | 520318.81 | 0 | 1776231.13 | 1776231.13 |  |  | 16 Dec 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33355 |  |  |  | TOWER B 1ST FLOOR RCC WORK | TOWER B 1ST FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 68523.78 | 68523.78 | 17 Mar 2020 |  | 03 Oct 2022 |  | - | - | 931 | - | THREADING
Group | 5 | 24331 |  |  |  | TOWER B 1ST FLOOR CIVIL WORK | TOWER B 1ST FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 11 Jun 2023 |  | - | - | - | -
Task | 6 | 24334 |  |  |  | TOWER B 1ST FLOOR MASONRY WORK | TOWER B 1ST FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Started | 640621.7 | 0 | 640621.7 | 9.78 | 6262084.8 | 0 | 430630.41 | 430630.41 |  |  | 11 Jun 2023 |  | - | - | - | - | MASONRY WORK
Task | 6 | 38102 |  |  |  | TOWER B 1ST FLOOR MASONRY WORK | TOWER B 1ST FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 11 Jun 2023 |  | - | - | 1182 | - | REBARING WORK
Group | 5 | 24332 |  |  |  | TOWER B 1ST FLOOR CIVIL WORK | TOWER B 1ST FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24335 |  |  |  | TOWER B 1ST FLOOR PLASTER WORK | TOWER B 1ST FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Started | 500 | 0 | 500 | 0 | 0.5 | 0 | 349851.91 | 349851.91 |  |  | 20 Sep 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 28535 |  |  |  | TOWER B 1ST FLOOR | TOWER B 101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28527 |  |  |  | TOWER B 101 | TOWER B 101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40327 |  |  |  | TOWER B 101 WATERPROOFING WORK | TOWER B 101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 7.5 |  | Tentative | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28529 |  |  |  | TOWER B 101 | TOWER B 101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41115 |  |  |  | TOWER B 101 PLUMBING WORK | TOWER B 101 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 23312 | 23312 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | PLUMBING WORK
Task | 6 | 41172 |  |  |  | TOWER B 101 PLUMBING WORK | TOWER B 101 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | CP & SANITARY FITTINGS
Group | 5 | 28528 |  |  |  | TOWER B 101 | TOWER B 101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40414 |  |  |  | TOWER B 101 ELECTRIC WORK | TOWER B 101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28530 |  |  |  | TOWER B 101 | TOWER B 101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38432 |  |  |  | TOWER B 101 FLOORING & DEDO WORK | TOWER B 101 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4102.08 |  | Started | 2188.08 | 1914 | 4102.08 | 0 | 4.1 | 0 | 56665.15 | 56665.15 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | FLOORING & DEDO
Group | 5 | 28533 |  |  |  | TOWER B 101 | TOWER B 101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40853 |  |  |  | TOWER B 101 CARPENTRY WORK | TOWER B 101 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28531 |  |  |  | TOWER B 101 | TOWER B 101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28532 |  |  |  | TOWER B 101 | TOWER B 101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28534 |  |  |  | TOWER B 101 | TOWER B 101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42136 |  |  |  | TOWER B 101 HVAC WORK | TOWER B 101 HVAC WORK | 1 | NOS | 1 | NOS | 36.32 |  | Tentative | 36.32 | 0 | 36.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HVAC INSTALLATION
Group | 5 | 34905 |  |  |  | TOWER B 101 | TOWER B 101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34906 |  |  |  | TOWER B 101 COMMON WORK | TOWER B 101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Started | 0 | 8960 | 8960 | 0 | 8.96 | 0 | 55104.82 | 55104.82 | 17 Mar 2020 |  | 14 Jun 2024 |  | - | - | 1551 | - | BALCONY RAILING
Task | 6 | 34907 |  |  |  | TOWER B 101 COMMON WORK | TOWER B 101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34908 |  |  |  | TOWER B 101 COMMON WORK | TOWER B 101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28544 |  |  |  | TOWER B 1ST FLOOR | TOWER B 102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28536 |  |  |  | TOWER B 102 | TOWER B 102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40328 |  |  |  | TOWER B 102 WATERPROOFING WORK | TOWER B 102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 7.5 |  | Tentative | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28538 |  |  |  | TOWER B 102 | TOWER B 102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41116 |  |  |  | TOWER B 102 PLUMBING WORK | TOWER B 102 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 22862 | 22862 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | PLUMBING WORK
Task | 6 | 41173 |  |  |  | TOWER B 102 PLUMBING WORK | TOWER B 102 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | CP & SANITARY FITTINGS
Group | 5 | 28537 |  |  |  | TOWER B 102 | TOWER B 102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40415 |  |  |  | TOWER B 102 ELECTRIC WORK | TOWER B 102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28539 |  |  |  | TOWER B 102 | TOWER B 102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38433 |  |  |  | TOWER B 102 FLOORING & DEDO WORK | TOWER B 102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 3995.88 |  | Started | 2081.88 | 1914 | 3995.88 | 0 | 4 | 0 | 56665.15 | 56665.15 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | FLOORING & DEDO
Group | 5 | 28542 |  |  |  | TOWER B 102 | TOWER B 102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40854 |  |  |  | TOWER B 102 CARPENTRY WORK | TOWER B 102 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28540 |  |  |  | TOWER B 102 | TOWER B 102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28541 |  |  |  | TOWER B 102 | TOWER B 102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28543 |  |  |  | TOWER B 102 | TOWER B 102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42137 |  |  |  | TOWER B 102 HVAC WORK | TOWER B 102 HVAC WORK | 1 | NOS | 1 | NOS | 36.32 |  | Tentative | 36.32 | 0 | 36.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HVAC INSTALLATION
Group | 5 | 34909 |  |  |  | TOWER B 102 | TOWER B 102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34910 |  |  |  | TOWER B 102 COMMON WORK | TOWER B 102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Started | 0 | 8960 | 8960 | 0 | 8.96 | 0 | 55104.82 | 55104.82 | 17 Mar 2020 |  | 14 Jun 2024 |  | - | - | 1551 | - | BALCONY RAILING
Task | 6 | 34911 |  |  |  | TOWER B 102 COMMON WORK | TOWER B 102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34912 |  |  |  | TOWER B 102 COMMON WORK | TOWER B 102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28553 |  |  |  | TOWER B 1ST FLOOR | TOWER B 103 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28545 |  |  |  | TOWER B 103 | TOWER B 103 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40329 |  |  |  | TOWER B 103 WATERPROOFING WORK | TOWER B 103 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28547 |  |  |  | TOWER B 103 | TOWER B 103 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40177 |  |  |  | TOWER B 103 PLUMBING WORK | TOWER B 103 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 129.46 |  | Started | 129.46 | 0 | 129.46 | 0 | 0.13 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Jun 2024 |  | - | - | 1557 | - | CP & SANITARY FITTINGS
Task | 6 | 40604 |  |  |  | TOWER B 103 PLUMBING WORK | TOWER B 103 PLUMBING WORK | 1 | NOS | 1 | NOS | 792.3 |  | Started | 792.3 | 0 | 792.3 | 0 | 0.79 | 0 | 31454 | 31454 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | PLUMBING WORK
Group | 5 | 28546 |  |  |  | TOWER B 103 | TOWER B 103 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40411 |  |  |  | TOWER B 103 ELECTRIC WORK | TOWER B 103 ELECTRIC WORK | 1 | NOS | 1 | NOS | 318.88 |  | Started | 318.88 | 0 | 318.88 | 0 | 0.32 | 0 | 76979.26 | 76979.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28548 |  |  |  | TOWER B 103 | TOWER B 103 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38434 |  |  |  | TOWER B 103 FLOORING & DEDO WORK | TOWER B 103 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 6167.318 |  | Started | 3745.32 | 2422 | 6167.32 | 0 | 6.17 | 0 | 156663.11 | 156663.11 | 17 Mar 2020 |  | 08 May 2024 |  | - | - | 1514 | - | FLOORING & DEDO
Group | 5 | 28551 |  |  |  | TOWER B 103 | TOWER B 103 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40197 |  |  |  | TOWER B 103 CARPENTRY WORK | TOWER B 103 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Jul 2024 |  | - | - | 1577 | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 28549 |  |  |  | TOWER B 103 | TOWER B 103 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40840 |  |  |  | TOWER B 103 ALUMINIUM DOOR & WINDOW | TOWER B 103 ALUMINIUM WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 272994.74 | 272994.74 | 17 Mar 2020 |  | 24 Jun 2024 |  | - | - | 1561 | - | ALUMINUM WINDOW WORK
Group | 5 | 28550 |  |  |  | TOWER B 103 | TOWER B 103 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40912 |  |  |  | TOWER B 103 PAINT WORK | TOWER B 103 PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PAINT WORK
Group | 5 | 28552 |  |  |  | TOWER B 103 | TOWER B 103 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41013 |  |  |  | TOWER B 103 HVAC WORK | TOWER B 103 HVAC WORK | 1 | NOS | 1 | NOS | 50288.2 |  | Started | 50288.2 | 0 | 50288.2 | 0 | 50.29 | 0 | 0 | 0 | 17 Mar 2020 |  | 21 Jul 2024 |  | - | - | 1588 | - | HVAC INSTALLATION
Group | 5 | 34913 |  |  |  | TOWER B 103 | TOWER B 103 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34914 |  |  |  | TOWER B 103 COMMON WORK | TOWER B 103 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Started | 0 | 8960 | 8960 | 0 | 8.96 | 0 | 55104.82 | 55104.82 | 17 Mar 2020 |  | 14 Jun 2024 |  | - | - | 1551 | - | BALCONY RAILING
Task | 6 | 34915 |  |  |  | TOWER B 103 COMMON WORK | TOWER B 103 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 82.6 |  | Tentative | 0 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34916 |  |  |  | TOWER B 103 COMMON WORK | TOWER B 103 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Jul 2024 |  | - | - | 1573 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40388 |  |  |  | TOWER B 103 COMMON WORK | TOWER B 103 COMMON WORK ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 4137 |  | Started | 0 | 4137 | 4137 | 0 | 4.14 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Jul 2024 |  | - | - | 1579 | - | ANTI TERMITE TREATMENT
Group | 4 | 28562 |  |  |  | TOWER B 1ST FLOOR | TOWER B 104 | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28554 |  |  |  | TOWER B 104 | TOWER B 104 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40330 |  |  |  | TOWER B 104 WATERPROOFING WORK | TOWER B 104 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28556 |  |  |  | TOWER B 104 | TOWER B 104 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41117 |  |  |  | TOWER B 104 PLUMBING WORK | TOWER B 104 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Started | 511.18 | 0 | 511.18 | 0 | 0.51 | 0 | 22962 | 22962 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | PLUMBING WORK
Task | 6 | 41174 |  |  |  | TOWER B 104 PLUMBING WORK | TOWER B 104 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Started | 7.54 | 0 | 7.54 | 0 | 0.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | CP & SANITARY FITTINGS
Group | 5 | 28555 |  |  |  | TOWER B 104 | TOWER B 104 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40416 |  |  |  | TOWER B 104 ELECTRIC WORK | TOWER B 104 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28557 |  |  |  | TOWER B 104 | TOWER B 104 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38435 |  |  |  | TOWER B 104 FLOORING & DEDO WORK | TOWER B 104 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4102.08 |  | Started | 2188.08 | 1914 | 4102.08 | 0 | 4.1 | 0 | 56665.15 | 56665.15 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | FLOORING & DEDO
Group | 5 | 28560 |  |  |  | TOWER B 104 | TOWER B 104 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40855 |  |  |  | TOWER B 104 CARPENTRY WORK | TOWER B 104 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28558 |  |  |  | TOWER B 104 | TOWER B 104 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28559 |  |  |  | TOWER B 104 | TOWER B 104 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28561 |  |  |  | TOWER B 104 | TOWER B 104 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42138 |  |  |  | TOWER B 104 HVAC WORK | TOWER B 104 HVAC WORK | 1 | NOS | 1 | NOS | 36.32 |  | Tentative | 36.32 | 0 | 36.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HVAC INSTALLATION
Group | 5 | 34917 |  |  |  | TOWER B 104 | TOWER B 104 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34918 |  |  |  | TOWER B 104 COMMON WORK | TOWER B 104 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 55104.82 | 55104.82 | 17 Mar 2020 |  | 14 Jun 2024 |  | - | - | 1551 | - | BALCONY RAILING
Task | 6 | 34919 |  |  |  | TOWER B 104 COMMON WORK | TOWER B 104 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34920 |  |  |  | TOWER B 104 COMMON WORK | TOWER B 104 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29211 |  |  |  | TOWER B 1ST FLOOR | TOWER B 1ST FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | -
Group | 5 | 29214 |  |  |  | TOWER B 1ST FLOOR COMMON WORK | TOWER B 1ST FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39282 |  |  |  | TOWER B 1ST FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 1ST FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29212 |  |  |  | TOWER B 1ST FLOOR COMMON WORK | TOWER B 1ST FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41022 |  |  |  | TOWER B 1ST FLOOR COMMON FLOORING WORK | TOWER B 1ST FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 1601.142 |  | Started | 1601.14 | 0 | 1601.14 | 0 | 1.6 | 0 | 35022.9 | 35022.9 | 17 Mar 2020 |  | 20 Jul 2024 |  | - | - | 1587 | - | FLOORING & DEDO
Group | 5 | 29213 |  |  |  | TOWER B 1ST FLOOR COMMON WORK | TOWER B 1ST FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29215 |  |  |  | TOWER B 1ST FLOOR COMMON WORK | TOWER B 1ST FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42052 |  |  |  | TOWER B 1ST FLOOR COMMON FALSE CEILING WORK | TOWER B 1ST FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29475 |  |  |  | TOWER B 1ST FLOOR COMMON WORK | TOWER B 1ST FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | -
Task | 6 | 33057 |  |  |  | TOWER B 1ST FLOOR COMMON ELECTRIC WORK | TOWER B 1ST FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 35.4 |  | Started | 35.4 | 0 | 35.4 | 0 | 0 | 0 | 85083.9 | 85083.9 | 17 Mar 2020 |  | 01 Dec 2022 |  | - | - | 990 | - | SLAB CONDUTE
Group | 5 | 42289 |  |  |  | TOWER B 1ST FLOOR COMMON WORK | TOWER B 1ST FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42290 |  |  |  | TOWER B 1ST FLOOR WPC PANNELING WORK | TOWER B 1ST FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24336 |  |  |  | TOWER B | TOWER B 2ND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 Jan 2023 |  | - | - | - | -
Group | 4 | 24337 |  |  |  | TOWER B 2ND FLOOR | TOWER B 2ND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 Jan 2023 |  | - | - | - | -
Group | 5 | 24338 |  |  |  | TOWER B 2ND FLOOR CIVIL WORK | TOWER B 2ND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 Jan 2023 |  | - | - | - | -
Task | 6 | 24341 |  |  |  | TOWER B 2ND FLOOR RCC WORK | TOWER B 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 54884.8 |  | Started | 54884.8 | 0 | 54884.8 | 0 | 54.88 | 0 | 1650678.4 | 1650678.4 |  |  | 04 Jan 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33647 |  |  |  | TOWER B 2ND FLOOR RCC WORK | TOWER B 2ND FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 143071.46 | 143071.46 | 17 Mar 2020 |  | 10 Jan 2023 |  | - | - | 1030 | - | THREADING
Group | 5 | 24339 |  |  |  | TOWER B 2ND FLOOR CIVIL WORK | TOWER B 2ND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 11 Oct 2023 |  | - | - | - | -
Task | 6 | 24342 |  |  |  | TOWER B 2ND FLOOR MASONRY WORK | TOWER B 2ND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Started | 640621.7 | 0 | 640621.7 | 8.71 | 5579936.73 | 0 | 714307.1 | 714307.1 |  |  | 04 Jan 2024 |  | - | - | - | - | MASONRY WORK
Task | 6 | 38685 |  |  |  | TOWER B 2ND FLOOR MASONRY WORK | TOWER B 2ND FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | REBARING WORK
Group | 5 | 24340 |  |  |  | TOWER B 2ND FLOOR CIVIL WORK | TOWER B 2ND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24343 |  |  |  | TOWER B 2ND FLOOR PLASTER WORK | TOWER B 2ND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Started | 500 | 0 | 500 | 0 | 0.5 | 0 | 170166 | 170166 |  |  | 24 May 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 28571 |  |  |  | TOWER B 2ND FLOOR | TOWER B 201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28563 |  |  |  | TOWER B 201 | TOWER B 201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40331 |  |  |  | TOWER B 201 WATERPROOFING WORK | TOWER B 201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28565 |  |  |  | TOWER B 201 | TOWER B 201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41118 |  |  |  | TOWER B 201 PLUMBING WORK | TOWER B 201 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Tentative | 511.18 | 0 | 511.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41533 |  |  |  | TOWER B 201 PLUMBING WORK | TOWER B 201 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Tentative | 7.54 | 0 | 7.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 28564 |  |  |  | TOWER B 201 | TOWER B 201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40417 |  |  |  | TOWER B 201 ELECTRIC WORK | TOWER B 201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28566 |  |  |  | TOWER B 201 | TOWER B 201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38436 |  |  |  | TOWER B 201 FLOORING & DEDO WORK | TOWER B 201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 3350.16 |  | Tentative | 1436.16 | 1914 | 3350.16 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28569 |  |  |  | TOWER B 201 | TOWER B 201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40856 |  |  |  | TOWER B 201 CARPENTRY WORK | TOWER B 201 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28567 |  |  |  | TOWER B 201 | TOWER B 201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28568 |  |  |  | TOWER B 201 | TOWER B 201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28570 |  |  |  | TOWER B 201 | TOWER B 201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34921 |  |  |  | TOWER B 201 | TOWER B 201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34922 |  |  |  | TOWER B 201 COMMON WORK | TOWER B 201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34923 |  |  |  | TOWER B 201 COMMON WORK | TOWER B 201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34924 |  |  |  | TOWER B 201 COMMON WORK | TOWER B 201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28580 |  |  |  | TOWER B 2ND FLOOR | TOWER B 202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28572 |  |  |  | TOWER B 202 | TOWER B 202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40332 |  |  |  | TOWER B 202 WATERPROOFING WORK | TOWER B 202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28574 |  |  |  | TOWER B 202 | TOWER B 202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41119 |  |  |  | TOWER B 202 PLUMBING WORK | TOWER B 202 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Tentative | 511.18 | 0 | 511.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41534 |  |  |  | TOWER B 202 PLUMBING WORK | TOWER B 202 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Tentative | 7.54 | 0 | 7.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 28573 |  |  |  | TOWER B 202 | TOWER B 202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40418 |  |  |  | TOWER B 202 ELECTRIC WORK | TOWER B 202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28575 |  |  |  | TOWER B 202 | TOWER B 202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41707 |  |  |  | TOWER B 202 FLOORING & DEDO WORK | TOWER B 202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 3350.16 |  | Tentative | 1436.16 | 1914 | 3350.16 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28578 |  |  |  | TOWER B 202 | TOWER B 202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40857 |  |  |  | TOWER B 202 CARPENTRY WORK | TOWER B 202 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28576 |  |  |  | TOWER B 202 | TOWER B 202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28577 |  |  |  | TOWER B 202 | TOWER B 202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28579 |  |  |  | TOWER B 202 | TOWER B 202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34925 |  |  |  | TOWER B 202 | TOWER B 202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34926 |  |  |  | TOWER B 202 COMMON WORK | TOWER B 202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34927 |  |  |  | TOWER B 202 COMMON WORK | TOWER B 202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34928 |  |  |  | TOWER B 202 COMMON WORK | TOWER B 202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28589 |  |  |  | TOWER B 2ND FLOOR | TOWER B 203 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28581 |  |  |  | TOWER B 203 | TOWER B 203 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40333 |  |  |  | TOWER B 203 WATERPROOFING WORK | TOWER B 203 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 69992.3 | 69992.3 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | WATERPROOFING WORK
Group | 5 | 28583 |  |  |  | TOWER B 203 | TOWER B 203 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40178 |  |  |  | TOWER B 203 PLUMBING WORK | TOWER B 203 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 94.06 |  | Started | 94.06 | 0 | 94.06 | 0 | 0.09 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | CP & SANITARY FITTINGS
Task | 6 | 40605 |  |  |  | TOWER B 203 PLUMBING WORK | TOWER B 203 PLUMBING WORK | 1 | NOS | 1 | NOS | 792.3 |  | Started | 792.3 | 0 | 792.3 | 0 | 0.79 | 0 | 22612 | 22612 | 17 Mar 2020 |  | 20 Aug 2024 |  | - | - | 1618 | - | PLUMBING WORK
Group | 5 | 28582 |  |  |  | TOWER B 203 | TOWER B 203 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40412 |  |  |  | TOWER B 203 ELECTRIC WORK | TOWER B 203 ELECTRIC WORK | 1 | NOS | 1 | NOS | 239.42 |  | Started | 239.42 | 0 | 239.42 | 0 | 0.24 | 0 | 0 | 0 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28584 |  |  |  | TOWER B 203 | TOWER B 203 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40606 |  |  |  | TOWER B 203 FLOORING & DEDO WORK | TOWER B 203 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 6677.838 |  | Started | 4255.84 | 2422 | 6677.84 | 0 | 6.68 | 0 | 145452.23 | 145452.23 | 17 Mar 2020 |  | 20 Aug 2024 |  | - | - | 1618 | - | FLOORING & DEDO
Group | 5 | 28587 |  |  |  | TOWER B 203 | TOWER B 203 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40858 |  |  |  | TOWER B 203 CARPENTRY WORK | TOWER B 203 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28585 |  |  |  | TOWER B 203 | TOWER B 203 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40841 |  |  |  | TOWER B 203 ALUMINIUM DOOR & WINDOW | TOWER B 203 ALUMINIUM WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 272994.74 | 272994.74 | 17 Mar 2020 |  | 20 Aug 2024 |  | - | - | 1618 | - | ALUMINUM WINDOW WORK
Group | 5 | 28586 |  |  |  | TOWER B 203 | TOWER B 203 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40913 |  |  |  | TOWER B 203 PAINT WORK | TOWER B 203 PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PAINT WORK
Group | 5 | 28588 |  |  |  | TOWER B 203 | TOWER B 203 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41817 | ABC |  |  | TOWER B 203 HVAC WORK | TOWER B 203 HVAC WORK | 1 | NOS | 1 | NOS | 22.7 |  | Started | 22.7 | 0 | 22.7 | 0 | 0.02 | 0 | 8319 | 8319 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | HVAC INSTALLATION
Group | 5 | 34929 |  |  |  | TOWER B 203 | TOWER B 203 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34930 |  |  |  | TOWER B 203 COMMON WORK | TOWER B 203 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Started | 0 | 8960 | 8960 | 0 | 8.96 | 0 | 73921.1 | 73921.1 | 17 Mar 2020 |  | 14 Jun 2024 |  | - | - | 1551 | - | BALCONY RAILING
Task | 6 | 34931 |  |  |  | TOWER B 203 COMMON WORK | TOWER B 203 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 82.6 |  | Tentative | 0 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34932 |  |  |  | TOWER B 203 COMMON WORK | TOWER B 203 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 18337.2 | 18337.2 | 17 Mar 2020 |  | 06 Jul 2024 |  | - | - | 1573 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 39305 |  |  |  | TOWER B 203 COMMON WORK | TOWER B 203 COMMON WORK CONSULTANCY CHARGES | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 41400 | 41400 | 17 Mar 2020 |  | 15 Feb 2024 |  | - | - | 1431 | - | CONSULTANCY CHARGES
Task | 6 | 40389 |  |  |  | TOWER B 203 COMMON WORK | TOWER B 203 COMMON WORK ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 4137 |  | Tentative | 0 | 4137 | 4137 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 28598 |  |  |  | TOWER B 2ND FLOOR | TOWER B 204 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28590 |  |  |  | TOWER B 204 | TOWER B 204 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40334 |  |  |  | TOWER B 204 WATERPROOFING WORK | TOWER B 204 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28592 |  |  |  | TOWER B 204 | TOWER B 204 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41120 |  |  |  | TOWER B 204 PLUMBING WORK | TOWER B 204 PLUMBING WORK | 1 | NOS | 1 | NOS | 511.18 |  | Tentative | 511.18 | 0 | 511.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41535 |  |  |  | TOWER B 204 PLUMBING WORK | TOWER B 204 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 7.54 |  | Tentative | 7.54 | 0 | 7.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 28591 |  |  |  | TOWER B 204 | TOWER B 204 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40419 |  |  |  | TOWER B 204 ELECTRIC WORK | TOWER B 204 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28593 |  |  |  | TOWER B 204 | TOWER B 204 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41708 |  |  |  | TOWER B 204 FLOORING & DEDO WORK | TOWER B 204 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 3350.16 |  | Tentative | 1436.16 | 1914 | 3350.16 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28596 |  |  |  | TOWER B 204 | TOWER B 204 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40859 |  |  |  | TOWER B 204 CARPENTRY WORK | TOWER B 204 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28594 |  |  |  | TOWER B 204 | TOWER B 204 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28595 |  |  |  | TOWER B 204 | TOWER B 204 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28597 |  |  |  | TOWER B 204 | TOWER B 204 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34933 |  |  |  | TOWER B 204 | TOWER B 204 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34934 |  |  |  | TOWER B 204 COMMON WORK | TOWER B 204 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34935 |  |  |  | TOWER B 204 COMMON WORK | TOWER B 204 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34936 |  |  |  | TOWER B 204 COMMON WORK | TOWER B 204 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29216 |  |  |  | TOWER B 2ND FLOOR | TOWER B 2ND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Apr 2023 |  | - | - | 1135 | -
Group | 5 | 29219 |  |  |  | TOWER B 2ND FLOOR COMMON WORK | TOWER B 2ND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39283 |  |  |  | TOWER B 2ND FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 2ND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29217 |  |  |  | TOWER B 2ND FLOOR COMMON WORK | TOWER B 2ND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41920 |  |  |  | TOWER B 2ND FLOOR COMMON FLOORING WORK | TOWER B 2ND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 1889.534 |  | Tentative | 1889.53 | 0 | 1889.53 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29218 |  |  |  | TOWER B 2ND FLOOR COMMON WORK | TOWER B 2ND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29220 |  |  |  | TOWER B 2ND FLOOR COMMON WORK | TOWER B 2ND FLOOR FALSE CEILING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42053 |  |  |  | TOWER B 2ND FLOOR FALSE CEILING WORK | TOWER B 2ND FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29476 |  |  |  | TOWER B 2ND FLOOR COMMON WORK | TOWER B 2ND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Apr 2023 |  | - | - | 1135 | -
Task | 6 | 33058 |  |  |  | TOWER B 2ND FLOOR COMMON ELECTRIC WORK | TOWER B 2ND FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 35.4 |  | Started | 35.4 | 0 | 35.4 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 25 Apr 2023 |  | - | - | 1135 | - | SLAB CONDUTE
Group | 5 | 42291 |  |  |  | TOWER B 2ND FLOOR COMMON WORK | TOWER B 2ND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42292 |  |  |  | TOWER B 2ND FLOOR WPC PANNELING WORK | TOWER B 2ND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24344 |  |  |  | TOWER B | TOWER B 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Group | 4 | 24345 |  |  |  | TOWER B 3RD FLOOR | TOWER B 3RD FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Group | 5 | 24346 |  |  |  | TOWER B 3RD FLOOR CIVIL WORK | TOWER B 3RD FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24349 |  |  |  | TOWER B 3RD FLOOR RCC WORK | TOWER B 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 54586.16 |  | Started | 54586.16 | 0 | 54586.16 | 8.71 | 475455.82 | 0 | 1649168 | 1649168 |  |  | 01 Aug 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33648 |  |  |  | TOWER B 3RD FLOOR RCC WORK | TOWER B 3RD FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 108724.62 | 108724.62 | 17 Mar 2020 |  | 20 Sep 2023 |  | - | - | 1283 | - | THREADING
Task | 6 | 38770 |  |  |  | TOWER B 3RD FLOOR RCC WORK | TOWER B 3RD FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 672 |  | Started | 672 | 0 | 672 | 0 | 0.67 | 0 | 199425.84 | 199425.84 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | SAFETY NET FIXING
Group | 5 | 24347 |  |  |  | TOWER B 3RD FLOOR CIVIL WORK | TOWER B 3RD FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24350 |  |  |  | TOWER B 3RD FLOOR MASONRY WORK | TOWER B 3RD FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 565369.7 |  | Tentative | 565369.7 | 0 | 565369.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39360 |  |  |  | TOWER B 3RD FLOOR MASONRY WORK | TOWER B 3RD FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 16 Feb 2024 |  | - | - | 1432 | - | REBARING WORK
Group | 5 | 24348 |  |  |  | TOWER B 3RD FLOOR CIVIL WORK | TOWER B 3RD FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24351 |  |  |  | TOWER B 3RD FLOOR PLASTER WORK | TOWER B 3RD FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28607 |  |  |  | TOWER B 3RD FLOOR | TOWER B 301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28599 |  |  |  | TOWER B 301 | TOWER B 301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40335 |  |  |  | TOWER B 301 WATERPROOFING WORK | TOWER B 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28601 |  |  |  | TOWER B 301 | TOWER B 301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41121 |  |  |  | TOWER B 301 PLUMBING WORK | TOWER B 301 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41536 |  |  |  | TOWER B 301 PLUMBING WORK | TOWER B 301 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 28600 |  |  |  | TOWER B 301 | TOWER B 301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40420 |  |  |  | TOWER B 301 ELECTRIC WORK | TOWER B 301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28602 |  |  |  | TOWER B 301 | TOWER B 301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41709 |  |  |  | TOWER B 301 FLOORING & DEDO WORK | TOWER B 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 2115.19 |  | Tentative | 201.19 | 1914 | 2115.19 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28605 |  |  |  | TOWER B 301 | TOWER B 301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40860 |  |  |  | TOWER B 301 CARPENTRY WORK | TOWER B 301 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28603 |  |  |  | TOWER B 301 | TOWER B 301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28604 |  |  |  | TOWER B 301 | TOWER B 301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28606 |  |  |  | TOWER B 301 | TOWER B 301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34937 |  |  |  | TOWER B 301 | TOWER B 301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34938 |  |  |  | TOWER B 301 COMMON WORK | TOWER B 301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34939 |  |  |  | TOWER B 301 COMMON WORK | TOWER B 301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34940 |  |  |  | TOWER B 301 COMMON WORK | TOWER B 301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28616 |  |  |  | TOWER B 3RD FLOOR | TOWER B 302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28608 |  |  |  | TOWER B 302 | TOWER B 302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40336 |  |  |  | TOWER B 302 WATERPROOFING WORK | TOWER B 302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28610 |  |  |  | TOWER B 302 | TOWER B 302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41122 |  |  |  | TOWER B 302 PLUMBING WORK | TOWER B 302 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41537 |  |  |  | TOWER B 302 PLUMBING WORK | TOWER B 302 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 28609 |  |  |  | TOWER B 302 | TOWER B 302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40421 |  |  |  | TOWER B 302 ELECTRIC WORK | TOWER B 302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28611 |  |  |  | TOWER B 302 | TOWER B 302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41710 |  |  |  | TOWER B 302 FLOORING & DEDO WORK | TOWER B 302 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 2115.19 |  | Tentative | 201.19 | 1914 | 2115.19 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28614 |  |  |  | TOWER B 302 | TOWER B 302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40861 |  |  |  | TOWER B 302 CARPENTRY WORK | TOWER B 302 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28612 |  |  |  | TOWER B 302 | TOWER B 302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28613 |  |  |  | TOWER B 302 | TOWER B 302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28615 |  |  |  | TOWER B 302 | TOWER B 302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34941 |  |  |  | TOWER B 302 | TOWER B 302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34942 |  |  |  | TOWER B 302 COMMON WORK | TOWER B 302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34943 |  |  |  | TOWER B 302 COMMON WORK | TOWER B 302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34944 |  |  |  | TOWER B 302 COMMON WORK | TOWER B 302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28625 |  |  |  | TOWER B 3RD FLOOR | TOWER B 303 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28617 |  |  |  | TOWER B 303 | TOWER B 303 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40337 |  |  |  | TOWER B 303 WATERPROOFING WORK | TOWER B 303 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28619 |  |  |  | TOWER B 303 | TOWER B 303 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40179 |  |  |  | TOWER B 303 PLUMBING WORK | TOWER B 303 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 87.7 |  | Tentative | 87.7 | 0 | 87.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Task | 6 | 40971 |  |  |  | TOWER B 303 PLUMBING WORK | TOWER B 303 PLUMBING WORK | 1 | NOS | 1 | NOS | 787.58 |  | Tentative | 787.58 | 0 | 787.58 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28618 |  |  |  | TOWER B 303 | TOWER B 303 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40422 |  |  |  | TOWER B 303 ELECTRIC WORK | TOWER B 303 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 35031.26 | 35031.26 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28620 |  |  |  | TOWER B 303 | TOWER B 303 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41711 |  |  |  | TOWER B 303 FLOORING & DEDO WORK | TOWER B 303 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 2115.19 |  | Tentative | 201.19 | 1914 | 2115.19 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28623 |  |  |  | TOWER B 303 | TOWER B 303 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40862 |  |  |  | TOWER B 303 CARPENTRY WORK | TOWER B 303 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28621 |  |  |  | TOWER B 303 | TOWER B 303 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28622 |  |  |  | TOWER B 303 | TOWER B 303 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28624 |  |  |  | TOWER B 303 | TOWER B 303 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34945 |  |  |  | TOWER B 303 | TOWER B 303 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34946 |  |  |  | TOWER B 303 COMMON WORK | TOWER B 303 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34947 |  |  |  | TOWER B 303 COMMON WORK | TOWER B 303 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34948 |  |  |  | TOWER B 303 COMMON WORK | TOWER B 303 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28634 |  |  |  | TOWER B 3RD FLOOR | TOWER B 304 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28626 |  |  |  | TOWER B 304 | TOWER B 304 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40338 |  |  |  | TOWER B 304 WATERPROOFING WORK | TOWER B 304 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28628 |  |  |  | TOWER B 304 | TOWER B 304 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41123 |  |  |  | TOWER B 304 PLUMBING WORK | TOWER B 304 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41538 |  |  |  | TOWER B 304 PLUMBING WORK | TOWER B 304 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 28627 |  |  |  | TOWER B 304 | TOWER B 304 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40423 |  |  |  | TOWER B 304 ELECTRIC WORK | TOWER B 304 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28629 |  |  |  | TOWER B 304 | TOWER B 304 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41712 |  |  |  | TOWER B 304 FLOORING & DEDO WORK | TOWER B 304 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 2115.19 |  | Tentative | 201.19 | 1914 | 2115.19 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28632 |  |  |  | TOWER B 304 | TOWER B 304 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40863 |  |  |  | TOWER B 304 CARPENTRY WORK | TOWER B 304 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28630 |  |  |  | TOWER B 304 | TOWER B 304 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28631 |  |  |  | TOWER B 304 | TOWER B 304 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28633 |  |  |  | TOWER B 304 | TOWER B 304 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34949 |  |  |  | TOWER B 304 | TOWER B 304 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34950 |  |  |  | TOWER B 304 COMMON WORK | TOWER B 304 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34951 |  |  |  | TOWER B 304 COMMON WORK | TOWER B 304 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34952 |  |  |  | TOWER B 304 COMMON WORK | TOWER B 304 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29221 |  |  |  | TOWER B 3RD FLOOR | TOWER B 3RD FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Group | 5 | 29224 |  |  |  | TOWER B 3RD FLOOR COMMON WORK | TOWER B 3RD FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39284 |  |  |  | TOWER B 3RD FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 3RD FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29222 |  |  |  | TOWER B 3RD FLOOR COMMON WORK | TOWER B 3RD FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41946 |  |  |  | TOWER B 3RD FLOOR COMMON FLOORING WORK | TOWER B 3RD FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 1653.534 |  | Tentative | 1653.53 | 0 | 1653.53 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29223 |  |  |  | TOWER B 3RD FLOOR COMMON WORK | TOWER B 3RD FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29225 |  |  |  | TOWER B 3RD FLOOR COMMON WORK | TOWER B 3RD FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42054 |  |  |  | TOWER B 3RD FLOOR COMMON FALSE CEILING WORK | TOWER B 3RD FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29477 |  |  |  | TOWER B 3RD FLOOR COMMON WORK | TOWER B 3RD FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Task | 6 | 33059 |  |  |  | TOWER B 3RD FLOOR COMMON ELECTRIC WORK | TOWER B 3RD FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | - | SLAB CONDUTE
Group | 5 | 42293 |  |  |  | TOWER B 3RD FLOOR COMMON WORK | TOWER B 3RD FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42294 |  |  |  | TOWER B 3RD FLOOR WPC PANNELING WORK | TOWER B 3RD FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24352 |  |  |  | TOWER B | TOWER B 4TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 Sep 2023 |  | - | - | - | -
Group | 4 | 24353 |  |  |  | TOWER B 4TH FLOOR | TOWER B 4TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 Sep 2023 |  | - | - | - | -
Group | 5 | 24354 |  |  |  | TOWER B 4TH FLOOR CIVIL WORK | TOWER B 4TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 Sep 2023 |  | - | - | - | -
Task | 6 | 24357 |  |  |  | TOWER B 4TH FLOOR RCC WORK | TOWER B 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 56725.7 |  | Started | 56725.7 | 0 | 56725.7 | 0 | 56.73 | 0 | 1649168 | 1649168 |  |  | 13 Sep 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33649 |  |  |  | TOWER B 4TH FLOOR RCC WORK | TOWER B 4TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 84116.3 | 84116.3 | 17 Mar 2020 |  | 20 Sep 2023 |  | - | - | 1283 | - | THREADING
Group | 5 | 24355 |  |  |  | TOWER B 4TH FLOOR CIVIL WORK | TOWER B 4TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24358 |  |  |  | TOWER B 4TH FLOOR MASONRY WORK | TOWER B 4TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 616368.2 |  | Tentative | 616368.2 | 0 | 616368.2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39361 |  |  |  | TOWER B 4TH FLOOR MASONRY WORK | TOWER B 4TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21948 | 21948 | 17 Mar 2020 |  | 16 Feb 2024 |  | - | - | 1432 | - | REBARING WORK
Group | 5 | 24356 |  |  |  | TOWER B 4TH FLOOR CIVIL WORK | TOWER B 4TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24359 |  |  |  | TOWER B 4TH FLOOR PLASTER WORK | TOWER B 4TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28643 |  |  |  | TOWER B 4TH FLOOR | TOWER B 401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28635 |  |  |  | TOWER B 401 | TOWER B 401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40339 |  |  |  | TOWER B 401 WATERPROOFING WORK | TOWER B 401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28637 |  |  |  | TOWER B 401 | TOWER B 401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41124 |  |  |  | TOWER B 401 PLUMBING WORK | TOWER B 401 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28636 |  |  |  | TOWER B 401 | TOWER B 401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40424 |  |  |  | TOWER B 401 ELECTRIC WORK | TOWER B 401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28638 |  |  |  | TOWER B 401 | TOWER B 401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41713 |  |  |  | TOWER B 401 FLOORING & DEDO WORK | TOWER B 401 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28641 |  |  |  | TOWER B 401 | TOWER B 401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40864 |  |  |  | TOWER B 401 CARPENTRY WORK | TOWER B 401 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28639 |  |  |  | TOWER B 401 | TOWER B 401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28640 |  |  |  | TOWER B 401 | TOWER B 401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28642 |  |  |  | TOWER B 401 | TOWER B 401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34953 |  |  |  | TOWER B 401 | TOWER B 401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34954 |  |  |  | TOWER B 401 COMMON WORK | TOWER B 401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34955 |  |  |  | TOWER B 401 COMMON WORK | TOWER B 401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34956 |  |  |  | TOWER B 401 COMMON WORK | TOWER B 401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28652 |  |  |  | TOWER B 4TH FLOOR | TOWER B 402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28644 |  |  |  | TOWER B 402 | TOWER B 402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40340 |  |  |  | TOWER B 402 WATERPROOFING WORK | TOWER B 402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28646 |  |  |  | TOWER B 402 | TOWER B 402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41125 |  |  |  | TOWER B 402 PLUMBING WORK | TOWER B 402 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28645 |  |  |  | TOWER B 402 | TOWER B 402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40425 |  |  |  | TOWER B 402 ELECTRIC WORK | TOWER B 402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28647 |  |  |  | TOWER B 402 | TOWER B 402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41714 |  |  |  | TOWER B 402 FLOORING & DEDO WORK | TOWER B 402 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28650 |  |  |  | TOWER B 402 | TOWER B 402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40865 |  |  |  | TOWER B 402 CARPENTRY WORK | TOWER B 402 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28648 |  |  |  | TOWER B 402 | TOWER B 402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28649 |  |  |  | TOWER B 402 | TOWER B 402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28651 |  |  |  | TOWER B 402 | TOWER B 402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34957 |  |  |  | TOWER B 402 | TOWER B 402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34958 |  |  |  | TOWER B 402 COMMON WORK | TOWER B 402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34959 |  |  |  | TOWER B 402 COMMON WORK | TOWER B 402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34960 |  |  |  | TOWER B 402 COMMON WORK | TOWER B 402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28661 |  |  |  | TOWER B 4TH FLOOR | TOWER B 403 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28653 |  |  |  | TOWER B 403 | TOWER B 403 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40341 |  |  |  | TOWER B 403 WATERPROOFING WORK | TOWER B 403 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28655 |  |  |  | TOWER B 403 | TOWER B 403 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41126 |  |  |  | TOWER B 403 PLUMBING WORK | TOWER B 403 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28654 |  |  |  | TOWER B 403 | TOWER B 403 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40426 |  |  |  | TOWER B 403 ELECTRIC WORK | TOWER B 403 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28656 |  |  |  | TOWER B 403 | TOWER B 403 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41715 |  |  |  | TOWER B 403 FLOORING & DEDO WORK | TOWER B 403 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28659 |  |  |  | TOWER B 403 | TOWER B 403 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40866 |  |  |  | TOWER B 403 CARPENTRY WORK | TOWER B 403 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28657 |  |  |  | TOWER B 403 | TOWER B 403 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28658 |  |  |  | TOWER B 403 | TOWER B 403 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28660 |  |  |  | TOWER B 403 | TOWER B 403 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34961 |  |  |  | TOWER B 403 | TOWER B 403 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34962 |  |  |  | TOWER B 403 COMMON WORK | TOWER B 403 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34963 |  |  |  | TOWER B 403 COMMON WORK | TOWER B 403 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34964 |  |  |  | TOWER B 403 COMMON WORK | TOWER B 403 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28670 |  |  |  | TOWER B 4TH FLOOR | TOWER B 404 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28662 |  |  |  | TOWER B 404 | TOWER B 404 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40342 |  |  |  | TOWER B 404 WATERPROOFING WORK | TOWER B 404 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28664 |  |  |  | TOWER B 404 | TOWER B 404 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41127 |  |  |  | TOWER B 404 PLUMBING WORK | TOWER B 404 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28663 |  |  |  | TOWER B 404 | TOWER B 404 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40427 |  |  |  | TOWER B 404 ELECTRIC WORK | TOWER B 404 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28665 |  |  |  | TOWER B 404 | TOWER B 404 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41716 |  |  |  | TOWER B 404 FLOORING & DEDO WORK | TOWER B 404 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28668 |  |  |  | TOWER B 404 | TOWER B 404 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40867 |  |  |  | TOWER B 404 CARPENTRY WORK | TOWER B 404 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28666 |  |  |  | TOWER B 404 | TOWER B 404 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28667 |  |  |  | TOWER B 404 | TOWER B 404 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28669 |  |  |  | TOWER B 404 | TOWER B 404 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34965 |  |  |  | TOWER B 404 | TOWER B 404 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34966 |  |  |  | TOWER B 404 COMMON WORK | TOWER B 404 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34967 |  |  |  | TOWER B 404 COMMON WORK | TOWER B 404 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34968 |  |  |  | TOWER B 404 COMMON WORK | TOWER B 404 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29226 |  |  |  | TOWER B 4TH FLOOR | TOWER B 4TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Group | 5 | 29229 |  |  |  | TOWER B 4TH FLOOR COMMON WORK | TOWER B 4TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39285 |  |  |  | TOWER B 4TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 4TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29227 |  |  |  | TOWER B 4TH FLOOR COMMON WORK | TOWER B 4TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41965 |  |  |  | TOWER B 4TH FLOOR COMMON FLOORING WORK | TOWER B 4TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29228 |  |  |  | TOWER B 4TH FLOOR COMMON WORK | TOWER B 4TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29230 |  |  |  | TOWER B 4TH FLOOR COMMON WORK | TOWER B 4TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42055 |  |  |  | TOWER B 4TH FLOOR COMMON FALSE CEILING WORK | TOWER B 4TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29478 |  |  |  | TOWER B 4TH FLOOR COMMON WORK | TOWER B 4TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Task | 6 | 33060 |  |  |  | TOWER B 4TH FLOOR COMMON ELECTRIC WORK | TOWER B 4TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | - | SLAB CONDUTE
Group | 5 | 42295 |  |  |  | TOWER B 4TH FLOOR COMMON WORK | TOWER B 4TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42296 |  |  |  | TOWER B 4TH FLOOR WPC PANNELING WORK | TOWER B 4TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24360 |  |  |  | TOWER B | TOWER B 5TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Oct 2023 |  | - | - | - | -
Group | 4 | 24361 |  |  |  | TOWER B 5TH FLOOR | TOWER B 5TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Oct 2023 |  | - | - | - | -
Group | 5 | 24362 |  |  |  | TOWER B 5TH FLOOR CIVIL WORK | TOWER B 5TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Oct 2023 |  | - | - | - | -
Task | 6 | 24365 |  |  |  | TOWER B 5TH FLOOR RCC WORK | TOWER B 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 51087.1 |  | Started | 51087.1 | 0 | 51087.1 | 0 | 51.09 | 0 | 1644448 | 1644448 |  |  | 17 Oct 2023 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33650 |  |  |  | TOWER B 5TH FLOOR RCC WORK | TOWER B 5TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 96760 | 96760 | 17 Mar 2020 |  | 17 Oct 2023 |  | - | - | 1310 | - | THREADING
Task | 6 | 39377 |  |  |  | TOWER B 5TH FLOOR RCC WORK | TOWER B 5TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 50152.36 | 50152.36 | 17 Mar 2020 |  | 10 Jan 2024 |  | - | - | 1395 | - | SAFETY NET FIXING
Group | 5 | 24363 |  |  |  | TOWER B 5TH FLOOR CIVIL WORK | TOWER B 5TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24366 |  |  |  | TOWER B 5TH FLOOR MASONRY WORK | TOWER B 5TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39362 |  |  |  | TOWER B 5TH FLOOR MASONRY WORK | TOWER B 5TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24364 |  |  |  | TOWER B 5TH FLOOR CIVIL WORK | TOWER B 5TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24367 |  |  |  | TOWER B 5TH FLOOR PLASTER WORK | TOWER B 5TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28679 |  |  |  | TOWER B 5TH FLOOR | TOWER B 501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28671 |  |  |  | TOWER B 501 | TOWER B 501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40343 |  |  |  | TOWER B 501 WATERPROOFING WORK | TOWER B 501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28673 |  |  |  | TOWER B 501 | TOWER B 501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41128 |  |  |  | TOWER B 501 PLUMBING WORK | TOWER B 501 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28672 |  |  |  | TOWER B 501 | TOWER B 501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40428 |  |  |  | TOWER B 501 ELECTRIC WORK | TOWER B 501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28674 |  |  |  | TOWER B 501 | TOWER B 501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41717 |  |  |  | TOWER B 501 FLOORING & DEDO WORK | TOWER B 501 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28677 |  |  |  | TOWER B 501 | TOWER B 501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40868 |  |  |  | TOWER B 501 CARPENTRY WORK | TOWER B 501 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28675 |  |  |  | TOWER B 501 | TOWER B 501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28676 |  |  |  | TOWER B 501 | TOWER B 501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28678 |  |  |  | TOWER B 501 | TOWER B 501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34969 |  |  |  | TOWER B 501 | TOWER B 501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34970 |  |  |  | TOWER B 501 COMMON WORK | TOWER B 501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34971 |  |  |  | TOWER B 501 COMMON WORK | TOWER B 501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34972 |  |  |  | TOWER B 501 COMMON WORK | TOWER B 501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28688 |  |  |  | TOWER B 5TH FLOOR | TOWER B 502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28680 |  |  |  | TOWER B 502 | TOWER B 502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40344 |  |  |  | TOWER B 502 WATERPROOFING WORK | TOWER B 502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28682 |  |  |  | TOWER B 502 | TOWER B 502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41129 |  |  |  | TOWER B 502 PLUMBING WORK | TOWER B 502 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28681 |  |  |  | TOWER B 502 | TOWER B 502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40429 |  |  |  | TOWER B 502 ELECTRIC WORK | TOWER B 502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28683 |  |  |  | TOWER B 502 | TOWER B 502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41718 |  |  |  | TOWER B 502 FLOORING & DEDO WORK | TOWER B 502 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28686 |  |  |  | TOWER B 502 | TOWER B 502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40869 |  |  |  | TOWER B 502 CARPENTRY WORK | TOWER B 502 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28684 |  |  |  | TOWER B 502 | TOWER B 502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28685 |  |  |  | TOWER B 502 | TOWER B 502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28687 |  |  |  | TOWER B 502 | TOWER B 502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34973 |  |  |  | TOWER B 502 | TOWER B 502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34974 |  |  |  | TOWER B 502 COMMON WORK | TOWER B 502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34975 |  |  |  | TOWER B 502 COMMON WORK | TOWER B 502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34976 |  |  |  | TOWER B 502 COMMON WORK | TOWER B 502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28697 |  |  |  | TOWER B 5TH FLOOR | TOWER B 503 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28689 |  |  |  | TOWER B 503 | TOWER B 503 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40345 |  |  |  | TOWER B 503 WATERPROOFING WORK | TOWER B 503 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28691 |  |  |  | TOWER B 503 | TOWER B 503 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41130 |  |  |  | TOWER B 503 PLUMBING WORK | TOWER B 503 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28690 |  |  |  | TOWER B 503 | TOWER B 503 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40430 |  |  |  | TOWER B 503 ELECTRIC WORK | TOWER B 503 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28692 |  |  |  | TOWER B 503 | TOWER B 503 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41719 |  |  |  | TOWER B 503 FLOORING & DEDO WORK | TOWER B 503 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28695 |  |  |  | TOWER B 503 | TOWER B 503 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40870 |  |  |  | TOWER B 503 CARPENTRY WORK | TOWER B 503 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28693 |  |  |  | TOWER B 503 | TOWER B 503 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28694 |  |  |  | TOWER B 503 | TOWER B 503 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28696 |  |  |  | TOWER B 503 | TOWER B 503 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34977 |  |  |  | TOWER B 503 | TOWER B 503 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34978 |  |  |  | TOWER B 503 COMMON WORK | TOWER B 503 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34979 |  |  |  | TOWER B 503 COMMON WORK | TOWER B 503 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34980 |  |  |  | TOWER B 503 COMMON WORK | TOWER B 503 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28706 |  |  |  | TOWER B 5TH FLOOR | TOWER B 504 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28698 |  |  |  | TOWER B 504 | TOWER B 504 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40346 |  |  |  | TOWER B 504 WATERPROOFING WORK | TOWER B 504 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28700 |  |  |  | TOWER B 504 | TOWER B 504 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41131 |  |  |  | TOWER B 504 PLUMBING WORK | TOWER B 504 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28699 |  |  |  | TOWER B 504 | TOWER B 504 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40431 |  |  |  | TOWER B 504 ELECTRIC WORK | TOWER B 504 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28701 |  |  |  | TOWER B 504 | TOWER B 504 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41720 |  |  |  | TOWER B 504 FLOORING & DEDO WORK | TOWER B 504 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28704 |  |  |  | TOWER B 504 | TOWER B 504 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40871 |  |  |  | TOWER B 504 CARPENTRY WORK | TOWER B 504 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28702 |  |  |  | TOWER B 504 | TOWER B 504 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28703 |  |  |  | TOWER B 504 | TOWER B 504 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28705 |  |  |  | TOWER B 504 | TOWER B 504 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34981 |  |  |  | TOWER B 504 | TOWER B 504 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34982 |  |  |  | TOWER B 504 COMMON WORK | TOWER B 504 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34983 |  |  |  | TOWER B 504 COMMON WORK | TOWER B 504 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34984 |  |  |  | TOWER B 504 COMMON WORK | TOWER B 504 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29231 |  |  |  | TOWER B 5TH FLOOR | TOWER B 5TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Oct 2023 |  | - | - | 1310 | -
Group | 5 | 29234 |  |  |  | TOWER B 5TH FLOOR COMMON WORK | TOWER B 5TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39286 |  |  |  | TOWER B 5TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 5TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29232 |  |  |  | TOWER B 5TH FLOOR COMMON WORK | TOWER B 5TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41966 |  |  |  | TOWER B 5TH FLOOR COMMON FLOORING WORK | TOWER B 5TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29233 |  |  |  | TOWER B 5TH FLOOR COMMON WORK | TOWER B 5TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29235 |  |  |  | TOWER B 5TH FLOOR COMMON WORK | TOWER B 5TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42056 |  |  |  | TOWER B 5TH FLOOR COMMON FALSE CEILING WORK | TOWER B 5TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29479 |  |  |  | TOWER B 5TH FLOOR COMMON WORK | TOWER B 5TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Oct 2023 |  | - | - | 1310 | -
Task | 6 | 33061 |  |  |  | TOWER B 5TH FLOOR COMMON ELECTRIC WORK | TOWER B 5TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 17 Oct 2023 |  | - | - | 1310 | - | SLAB CONDUTE
Group | 5 | 42299 |  |  |  | TOWER B 5TH FLOOR COMMON WORK | TOWER B 5TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42300 |  |  |  | TOWER B 5TH FLOOR WPC PANNELING WORK | TOWER B 5TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24368 |  |  |  | TOWER B | TOWER B 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19 Oct 2023 |  | - | - | - | -
Group | 4 | 24369 |  |  |  | TOWER B 6TH FLOOR | TOWER B 6TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19 Oct 2023 |  | - | - | - | -
Group | 5 | 24370 |  |  |  | TOWER B 6TH FLOOR CIVIL WORK | TOWER B 6TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19 Oct 2023 |  | - | - | - | -
Task | 6 | 24373 |  |  |  | TOWER B 6TH FLOOR RCC WORK | TOWER B 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 44808.02 |  | Started | 44808.02 | 0 | 44808.02 | 0 | 44.81 | 0 | 2718478.1 | 2718478.1 |  |  | 04 Jan 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33651 |  |  |  | TOWER B 6TH FLOOR RCC WORK | TOWER B 6TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 71685 | 71685 | 17 Mar 2020 |  | 06 Dec 2023 |  | - | - | 1360 | - | THREADING
Group | 5 | 24371 |  |  |  | TOWER B 6TH FLOOR CIVIL WORK | TOWER B 6TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24374 |  |  |  | TOWER B 6TH FLOOR MASONRY WORK | TOWER B 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39363 |  |  |  | TOWER B 6TH FLOOR MASONRY WORK | TOWER B 6TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24372 |  |  |  | TOWER B 6TH FLOOR CIVIL WORK | TOWER B 6TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24375 |  |  |  | TOWER B 6TH FLOOR PLASTER WORK | TOWER B 6TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28715 |  |  |  | TOWER B 6TH FLOOR | TOWER B 601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28707 |  |  |  | TOWER B 601 | TOWER B 601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40347 |  |  |  | TOWER B 601 WATERPROOFING WORK | TOWER B 601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28709 |  |  |  | TOWER B 601 | TOWER B 601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41132 |  |  |  | TOWER B 601 PLUMBING WORK | TOWER B 601 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28708 |  |  |  | TOWER B 601 | TOWER B 601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40432 |  |  |  | TOWER B 601 ELECTRIC WORK | TOWER B 601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28710 |  |  |  | TOWER B 601 | TOWER B 601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41721 |  |  |  | TOWER B 601 FLOORING & DEDO WORK | TOWER B 601 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28713 |  |  |  | TOWER B 601 | TOWER B 601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40872 |  |  |  | TOWER B 601 CARPENTRY WORK | TOWER B 601 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28711 |  |  |  | TOWER B 601 | TOWER B 601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28712 |  |  |  | TOWER B 601 | TOWER B 601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28714 |  |  |  | TOWER B 601 | TOWER B 601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34985 |  |  |  | TOWER B 601 | TOWER B 601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34986 |  |  |  | TOWER B 601 COMMON WORK | TOWER B 601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34987 |  |  |  | TOWER B 601 COMMON WORK | TOWER B 601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34988 |  |  |  | TOWER B 601 COMMON WORK | TOWER B 601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28724 |  |  |  | TOWER B 6TH FLOOR | TOWER B 602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28716 |  |  |  | TOWER B 602 | TOWER B 602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40348 |  |  |  | TOWER B 602 WATERPROOFING WORK | TOWER B 602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28718 |  |  |  | TOWER B 602 | TOWER B 602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41133 |  |  |  | TOWER B 602 PLUMBING WORK | TOWER B 602 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28717 |  |  |  | TOWER B 602 | TOWER B 602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40433 |  |  |  | TOWER B 602 ELECTRIC WORK | TOWER B 602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28719 |  |  |  | TOWER B 602 | TOWER B 602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41722 |  |  |  | TOWER B 602 FLOORING & DEDO WORK | TOWER B 602 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28722 |  |  |  | TOWER B 602 | TOWER B 602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40873 |  |  |  | TOWER B 602 CARPENTRY WORK | TOWER B 602 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28720 |  |  |  | TOWER B 602 | TOWER B 602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28721 |  |  |  | TOWER B 602 | TOWER B 602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28723 |  |  |  | TOWER B 602 | TOWER B 602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34989 |  |  |  | TOWER B 602 | TOWER B 602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34990 |  |  |  | TOWER B 602 COMMON WORK | TOWER B 602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34991 |  |  |  | TOWER B 602 COMMON WORK | TOWER B 602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34992 |  |  |  | TOWER B 602 COMMON WORK | TOWER B 602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28733 |  |  |  | TOWER B 6TH FLOOR | TOWER B 603 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28725 |  |  |  | TOWER B 603 | TOWER B 603 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40349 |  |  |  | TOWER B 603 WATERPROOFING WORK | TOWER B 603 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28727 |  |  |  | TOWER B 603 | TOWER B 603 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41134 |  |  |  | TOWER B 603 PLUMBING WORK | TOWER B 603 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28726 |  |  |  | TOWER B 603 | TOWER B 603 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40434 |  |  |  | TOWER B 603 ELECTRIC WORK | TOWER B 603 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28728 |  |  |  | TOWER B 603 | TOWER B 603 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41723 |  |  |  | TOWER B 603 FLOORING & DEDO WORK | TOWER B 603 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28731 |  |  |  | TOWER B 603 | TOWER B 603 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40874 |  |  |  | TOWER B 603 CARPENTRY WORK | TOWER B 603 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28729 |  |  |  | TOWER B 603 | TOWER B 603 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28730 |  |  |  | TOWER B 603 | TOWER B 603 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28732 |  |  |  | TOWER B 603 | TOWER B 603 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34993 |  |  |  | TOWER B 603 | TOWER B 603 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34994 |  |  |  | TOWER B 603 COMMON WORK | TOWER B 603 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34995 |  |  |  | TOWER B 603 COMMON WORK | TOWER B 603 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34996 |  |  |  | TOWER B 603 COMMON WORK | TOWER B 603 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28742 |  |  |  | TOWER B 6TH FLOOR | TOWER B 604 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28734 |  |  |  | TOWER B 604 | TOWER B 604 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40350 |  |  |  | TOWER B 604 WATERPROOFING WORK | TOWER B 604 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28736 |  |  |  | TOWER B 604 | TOWER B 604 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41135 |  |  |  | TOWER B 604 PLUMBING WORK | TOWER B 604 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28735 |  |  |  | TOWER B 604 | TOWER B 604 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40435 |  |  |  | TOWER B 604 ELECTRIC WORK | TOWER B 604 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28737 |  |  |  | TOWER B 604 | TOWER B 604 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41724 |  |  |  | TOWER B 604 FLOORING & DEDO WORK | TOWER B 604 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28740 |  |  |  | TOWER B 604 | TOWER B 604 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40875 |  |  |  | TOWER B 604 CARPENTRY WORK | TOWER B 604 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28738 |  |  |  | TOWER B 604 | TOWER B 604 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28739 |  |  |  | TOWER B 604 | TOWER B 604 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28741 |  |  |  | TOWER B 604 | TOWER B 604 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34997 |  |  |  | TOWER B 604 | TOWER B 604 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34998 |  |  |  | TOWER B 604 COMMON WORK | TOWER B 604 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34999 |  |  |  | TOWER B 604 COMMON WORK | TOWER B 604 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35000 |  |  |  | TOWER B 604 COMMON WORK | TOWER B 604 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29236 |  |  |  | TOWER B 6TH FLOOR | TOWER B 6TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29239 |  |  |  | TOWER B 6TH FLOOR COMMON WORK | TOWER B 6TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39406 |  |  |  | TOWER B 6TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 6TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 2500 | 2500 | 17 Mar 2020 |  | 15 Sep 2024 |  | - | - | 1644 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29237 |  |  |  | TOWER B 6TH FLOOR COMMON WORK | TOWER B 6TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41967 |  |  |  | TOWER B 6TH FLOOR COMMON FLOORING WORK | TOWER B 6TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29238 |  |  |  | TOWER B 6TH FLOOR COMMON WORK | TOWER B 6TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29240 |  |  |  | TOWER B 6TH FLOOR COMMON WORK | TOWER B 6TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42057 |  |  |  | TOWER B 6TH FLOOR COMMON FALSE CEILING WORK | TOWER B 6TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29480 |  |  |  | TOWER B 6TH FLOOR COMMON WORK | TOWER B 6TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33062 |  |  |  | TOWER B 6TH FLOOR COMMON ELECTRIC WORK | TOWER B 6TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 03 Jan 2024 |  | - | - | 1388 | - | SLAB CONDUTE
Group | 5 | 42301 |  |  |  | TOWER B 6TH FLOOR COMMON WORK | TOWER B 6TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42302 |  |  |  | TOWER B 6TH FLOOR WPC PANNELING WORK | TOWER B 6TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24376 |  |  |  | TOWER B | TOWER B 7TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24377 |  |  |  | TOWER B 7TH FLOOR | TOWER B 7TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24378 |  |  |  | TOWER B 7TH FLOOR CIVIL WORK | TOWER B 7TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24381 |  |  |  | TOWER B 7TH FLOOR RCC WORK | TOWER B 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 242877.02 |  | Started | 242877.02 | 0 | 242877.02 | 0 | 242.88 | 0 | 1644448 | 1644448 |  |  | 07 Feb 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33652 |  |  |  | TOWER B 7TH FLOOR RCC WORK | TOWER B 7TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 66569.7 | 66569.7 | 17 Mar 2020 |  | 28 Jan 2024 |  | - | - | 1413 | - | THREADING
Group | 5 | 24379 |  |  |  | TOWER B 7TH FLOOR CIVIL WORK | TOWER B 7TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24382 |  |  |  | TOWER B 7TH FLOOR MASONRY WORK | TOWER B 7TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39364 |  |  |  | TOWER B 7TH FLOOR MASONRY WORK | TOWER B 7TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24380 |  |  |  | TOWER B 7TH FLOOR CIVIL WORK | TOWER B 7TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24383 |  |  |  | TOWER B 7TH FLOOR PLASTER WORK | TOWER B 7TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28751 |  |  |  | TOWER B 7TH FLOOR | TOWER B 701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28743 |  |  |  | TOWER B 701 | TOWER B 701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40351 |  |  |  | TOWER B 701 WATERPROOFING WORK | TOWER B 701 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28745 |  |  |  | TOWER B 701 | TOWER B 701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41136 |  |  |  | TOWER B 701 PLUMBING WORK | TOWER B 701 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28744 |  |  |  | TOWER B 701 | TOWER B 701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40436 |  |  |  | TOWER B 701 ELECTRIC WORK | TOWER B 701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28746 |  |  |  | TOWER B 701 | TOWER B 701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41725 |  |  |  | TOWER B 701 FLOORING & DEDO WORK | TOWER B 701 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28749 |  |  |  | TOWER B 701 | TOWER B 701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40876 |  |  |  | TOWER B 701 CARPENTRY WORK | TOWER B 701 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28747 |  |  |  | TOWER B 701 | TOWER B 701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28748 |  |  |  | TOWER B 701 | TOWER B 701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28750 |  |  |  | TOWER B 701 | TOWER B 701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35001 |  |  |  | TOWER B 701 | TOWER B 701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35002 |  |  |  | TOWER B 701 COMMON WORK | TOWER B 701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35003 |  |  |  | TOWER B 701 COMMON WORK | TOWER B 701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35004 |  |  |  | TOWER B 701 COMMON WORK | TOWER B 701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28760 |  |  |  | TOWER B 7TH FLOOR | TOWER B 702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28752 |  |  |  | TOWER B 702 | TOWER B 702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40352 |  |  |  | TOWER B 702 WATERPROOFING WORK | TOWER B 702 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28754 |  |  |  | TOWER B 702 | TOWER B 702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41137 |  |  |  | TOWER B 702 PLUMBING WORK | TOWER B 702 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28753 |  |  |  | TOWER B 702 | TOWER B 702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40437 |  |  |  | TOWER B 702 ELECTRIC WORK | TOWER B 702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28755 |  |  |  | TOWER B 702 | TOWER B 702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41726 |  |  |  | TOWER B 702 FLOORING & DEDO WORK | TOWER B 702 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28758 |  |  |  | TOWER B 702 | TOWER B 702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40877 |  |  |  | TOWER B 702 CARPENTRY WORK | TOWER B 702 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28756 |  |  |  | TOWER B 702 | TOWER B 702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28757 |  |  |  | TOWER B 702 | TOWER B 702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28759 |  |  |  | TOWER B 702 | TOWER B 702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35005 |  |  |  | TOWER B 702 | TOWER B 702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35006 |  |  |  | TOWER B 702 COMMON WORK | TOWER B 702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35007 |  |  |  | TOWER B 702 COMMON WORK | TOWER B 702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35008 |  |  |  | TOWER B 702 COMMON WORK | TOWER B 702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28769 |  |  |  | TOWER B 7TH FLOOR | TOWER B 703 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28761 |  |  |  | TOWER B 703 | TOWER B 703 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40353 |  |  |  | TOWER B 703 WATERPROOFING WORK | TOWER B 703 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28763 |  |  |  | TOWER B 703 | TOWER B 703 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41138 |  |  |  | TOWER B 703 PLUMBING WORK | TOWER B 703 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28762 |  |  |  | TOWER B 703 | TOWER B 703 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40438 |  |  |  | TOWER B 703 ELECTRIC WORK | TOWER B 703 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28764 |  |  |  | TOWER B 703 | TOWER B 703 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41727 |  |  |  | TOWER B 703 FLOORING & DEDO WORK | TOWER B 703 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28767 |  |  |  | TOWER B 703 | TOWER B 703 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40878 |  |  |  | TOWER B 703 CARPENTRY WORK | TOWER B 703 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28765 |  |  |  | TOWER B 703 | TOWER B 703 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28766 |  |  |  | TOWER B 703 | TOWER B 703 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28768 |  |  |  | TOWER B 703 | TOWER B 703 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35009 |  |  |  | TOWER B 703 | TOWER B 703 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35010 |  |  |  | TOWER B 703 COMMON WORK | TOWER B 703 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35011 |  |  |  | TOWER B 703 COMMON WORK | TOWER B 703 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35012 |  |  |  | TOWER B 703 COMMON WORK | TOWER B 703 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28778 |  |  |  | TOWER B 7TH FLOOR | TOWER B 704 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28770 |  |  |  | TOWER B 704 | TOWER B 704 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40354 |  |  |  | TOWER B 704 WATERPROOFING WORK | TOWER B 704 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28772 |  |  |  | TOWER B 704 | TOWER B 704 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41139 |  |  |  | TOWER B 704 PLUMBING WORK | TOWER B 704 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28771 |  |  |  | TOWER B 704 | TOWER B 704 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40439 |  |  |  | TOWER B 704 ELECTRIC WORK | TOWER B 704 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28773 |  |  |  | TOWER B 704 | TOWER B 704 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41728 |  |  |  | TOWER B 704 FLOORING & DEDO WORK | TOWER B 704 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28776 |  |  |  | TOWER B 704 | TOWER B 704 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40879 |  |  |  | TOWER B 704 CARPENTRY WORK | TOWER B 704 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28774 |  |  |  | TOWER B 704 | TOWER B 704 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28775 |  |  |  | TOWER B 704 | TOWER B 704 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28777 |  |  |  | TOWER B 704 | TOWER B 704 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35013 |  |  |  | TOWER B 704 | TOWER B 704 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35014 |  |  |  | TOWER B 704 COMMON WORK | TOWER B 704 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35015 |  |  |  | TOWER B 704 COMMON WORK | TOWER B 704 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35016 |  |  |  | TOWER B 704 COMMON WORK | TOWER B 704 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29241 |  |  |  | TOWER B 7TH FLOOR | TOWER B 7TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29244 |  |  |  | TOWER B 7TH FLOOR COMMON WORK | TOWER B 7TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39407 |  |  |  | TOWER B 7TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 7TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29242 |  |  |  | TOWER B 7TH FLOOR COMMON WORK | TOWER B 7TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41968 |  |  |  | TOWER B 7TH FLOOR COMMON FLOORING WORK | TOWER B 7TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29243 |  |  |  | TOWER B 7TH FLOOR COMMON WORK | TOWER B 7TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29245 |  |  |  | TOWER B 7TH FLOOR COMMON WORK | TOWER B 7TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42058 |  |  |  | TOWER B 7TH FLOOR COMMON FALSE CEILING WORK | TOWER B 7TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29481 |  |  |  | TOWER B 7TH FLOOR COMMON WORK | TOWER B 7TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33063 |  |  |  | TOWER B 7TH FLOOR COMMON ELECTRIC WORK | TOWER B 7TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 28 Jan 2024 |  | - | - | 1413 | - | SLAB CONDUTE
Group | 5 | 42303 |  |  |  | TOWER B 7TH FLOOR COMMON WORK | TOWER B 7TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42304 |  |  |  | TOWER B 7TH FLOOR WPC PANNELING WORK | TOWER B 7TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24384 |  |  |  | TOWER B | TOWER B 8TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24385 |  |  |  | TOWER B 8TH FLOOR | TOWER B 8TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24386 |  |  |  | TOWER B 8TH FLOOR CIVIL WORK | TOWER B 8TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24389 |  |  |  | TOWER B 8TH FLOOR RCC WORK | TOWER B 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 54556.02 |  | Started | 54556.02 | 0 | 54556.02 | 0 | 54.56 | 0 | 1644448 | 1644448 |  |  | 09 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33653 |  |  |  | TOWER B 8TH FLOOR RCC WORK | TOWER B 8TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 67112.5 | 67112.5 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Task | 6 | 41568 |  |  |  | TOWER B 8TH FLOOR RCC WORK | TOWER B 8TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 46978.16 | 46978.16 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | SAFETY NET FIXING
Group | 5 | 24387 |  |  |  | TOWER B 8TH FLOOR CIVIL WORK | TOWER B 8TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24390 |  |  |  | TOWER B 8TH FLOOR MASONRY WORK | TOWER B 8TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39365 |  |  |  | TOWER B 8TH FLOOR MASONRY WORK | TOWER B 8TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24388 |  |  |  | TOWER B 8TH FLOOR CIVIL WORK | TOWER B 8TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24391 |  |  |  | TOWER B 8TH FLOOR PLASTER WORK | TOWER B 8TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28787 |  |  |  | TOWER B 8TH FLOOR | TOWER B 801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28779 |  |  |  | TOWER B 801 | TOWER B 801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40355 |  |  |  | TOWER B 801 WATERPROOFING WORK | TOWER B 801 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28781 |  |  |  | TOWER B 801 | TOWER B 801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41140 |  |  |  | TOWER B 801 PLUMBING WORK | TOWER B 801 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28780 |  |  |  | TOWER B 801 | TOWER B 801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40440 |  |  |  | TOWER B 801 ELECTRIC WORK | TOWER B 801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28782 |  |  |  | TOWER B 801 | TOWER B 801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41729 |  |  |  | TOWER B 801 FLOORING & DEDO WORK | TOWER B 801 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28785 |  |  |  | TOWER B 801 | TOWER B 801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40880 |  |  |  | TOWER B 801 CARPENTRY WORK | TOWER B 801 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28783 |  |  |  | TOWER B 801 | TOWER B 801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28784 |  |  |  | TOWER B 801 | TOWER B 801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28786 |  |  |  | TOWER B 801 | TOWER B 801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35017 |  |  |  | TOWER B 801 | TOWER B 801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35018 |  |  |  | TOWER B 801 COMMON WORK | TOWER B 801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35019 |  |  |  | TOWER B 801 COMMON WORK | TOWER B 801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35020 |  |  |  | TOWER B 801 COMMON WORK | TOWER B 801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28796 |  |  |  | TOWER B 8TH FLOOR | TOWER B 802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28788 |  |  |  | TOWER B 802 | TOWER B 802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40356 |  |  |  | TOWER B 802 WATERPROOFING WORK | TOWER B 802 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28790 |  |  |  | TOWER B 802 | TOWER B 802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41141 |  |  |  | TOWER B 802 PLUMBING WORK | TOWER B 802 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28789 |  |  |  | TOWER B 802 | TOWER B 802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40441 |  |  |  | TOWER B 802 ELECTRIC WORK | TOWER B 802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28791 |  |  |  | TOWER B 802 | TOWER B 802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41730 |  |  |  | TOWER B 802 FLOORING & DEDO WORK | TOWER B 802 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28794 |  |  |  | TOWER B 802 | TOWER B 802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40881 |  |  |  | TOWER B 802 CARPENTRY WORK | TOWER B 802 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28792 |  |  |  | TOWER B 802 | TOWER B 802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28793 |  |  |  | TOWER B 802 | TOWER B 802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28795 |  |  |  | TOWER B 802 | TOWER B 802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35021 |  |  |  | TOWER B 802 | TOWER B 802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35022 |  |  |  | TOWER B 802 COMMON WORK | TOWER B 802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35023 |  |  |  | TOWER B 802 COMMON WORK | TOWER B 802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35024 |  |  |  | TOWER B 802 COMMON WORK | TOWER B 802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28805 |  |  |  | TOWER B 8TH FLOOR | TOWER B 803 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28797 |  |  |  | TOWER B 803 | TOWER B 803 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40357 |  |  |  | TOWER B 803 WATERPROOFING WORK | TOWER B 803 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28799 |  |  |  | TOWER B 803 | TOWER B 803 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41142 |  |  |  | TOWER B 803 PLUMBING WORK | TOWER B 803 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28798 |  |  |  | TOWER B 803 | TOWER B 803 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40442 |  |  |  | TOWER B 803 ELECTRIC WORK | TOWER B 803 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28800 |  |  |  | TOWER B 803 | TOWER B 803 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41731 |  |  |  | TOWER B 803 FLOORING & DEDO WORK | TOWER B 803 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28803 |  |  |  | TOWER B 803 | TOWER B 803 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40882 |  |  |  | TOWER B 803 CARPENTRY WORK | TOWER B 803 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28801 |  |  |  | TOWER B 803 | TOWER B 803 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28802 |  |  |  | TOWER B 803 | TOWER B 803 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28804 |  |  |  | TOWER B 803 | TOWER B 803 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35025 |  |  |  | TOWER B 803 | TOWER B 803 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35026 |  |  |  | TOWER B 803 COMMON WORK | TOWER B 803 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35027 |  |  |  | TOWER B 803 COMMON WORK | TOWER B 803 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35028 |  |  |  | TOWER B 803 COMMON WORK | TOWER B 803 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28814 |  |  |  | TOWER B 8TH FLOOR | TOWER B 804 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28806 |  |  |  | TOWER B 804 | TOWER B 804 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40358 |  |  |  | TOWER B 804 WATERPROOFING WORK | TOWER B 804 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28808 |  |  |  | TOWER B 804 | TOWER B 804 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41143 |  |  |  | TOWER B 804 PLUMBING WORK | TOWER B 804 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28807 |  |  |  | TOWER B 804 | TOWER B 804 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40443 |  |  |  | TOWER B 804 ELECTRIC WORK | TOWER B 804 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28809 |  |  |  | TOWER B 804 | TOWER B 804 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41732 |  |  |  | TOWER B 804 FLOORING & DEDO WORK | TOWER B 804 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28812 |  |  |  | TOWER B 804 | TOWER B 804 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40883 |  |  |  | TOWER B 804 CARPENTRY WORK | TOWER B 804 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28810 |  |  |  | TOWER B 804 | TOWER B 804 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28811 |  |  |  | TOWER B 804 | TOWER B 804 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28813 |  |  |  | TOWER B 804 | TOWER B 804 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35029 |  |  |  | TOWER B 804 | TOWER B 804 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35030 |  |  |  | TOWER B 804 COMMON WORK | TOWER B 804 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35031 |  |  |  | TOWER B 804 COMMON WORK | TOWER B 804 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35032 |  |  |  | TOWER B 804 COMMON WORK | TOWER B 804 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29246 |  |  |  | TOWER B 8TH FLOOR | TOWER B 8TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29249 |  |  |  | TOWER B 8TH FLOOR COMMON WORK | TOWER B 8TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39408 |  |  |  | TOWER B 8TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 8TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29247 |  |  |  | TOWER B 8TH FLOOR COMMON WORK | TOWER B 8TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41969 |  |  |  | TOWER B 8TH FLOOR COMMON FLOORING WORK | TOWER B 8TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29248 |  |  |  | TOWER B 8TH FLOOR COMMON WORK | TOWER B 8TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29250 |  |  |  | TOWER B 8TH FLOOR COMMON WORK | TOWER B 8TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42059 |  |  |  | TOWER B 8TH FLOOR COMMON FALSE CEILING WORK | TOWER B 8TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29482 |  |  |  | TOWER B 8TH FLOOR COMMON WORK | TOWER B 8TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33064 |  |  |  | TOWER B 8TH FLOOR COMMON ELECTRIC WORK | TOWER B 8TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 15 Mar 2024 |  | - | - | 1460 | - | SLAB CONDUTE
Group | 5 | 42305 |  |  |  | TOWER B 8TH FLOOR COMMON WORK | TOWER B 8TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42306 |  |  |  | TOWER B 8TH FLOOR WPC PANNELING WORK | TOWER B 8TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24392 |  |  |  | TOWER B | TOWER B 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24393 |  |  |  | TOWER B 9TH FLOOR | TOWER B 9TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24394 |  |  |  | TOWER B 9TH FLOOR CIVIL WORK | TOWER B 9TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24397 |  |  |  | TOWER B 9TH FLOOR RCC WORK | TOWER B 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 52659.56 |  | Started | 52659.56 | 0 | 52659.56 | 0 | 52.66 | 0 | 1644448 | 1644448 |  |  | 22 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33654 |  |  |  | TOWER B 9TH FLOOR RCC WORK | TOWER B 9TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 66670 | 66670 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | THREADING
Task | 6 | 41834 |  |  |  | TOWER B 9TH FLOOR RCC WORK | TOWER B 9TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 91513.8 | 91513.8 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | SAFETY NET FIXING
Group | 5 | 24395 |  |  |  | TOWER B 9TH FLOOR CIVIL WORK | TOWER B 9TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24398 |  |  |  | TOWER B 9TH FLOOR MASONRY WORK | TOWER B 9TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39366 |  |  |  | TOWER B 9TH FLOOR MASONRY WORK | TOWER B 9TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24396 |  |  |  | TOWER B 9TH FLOOR CIVIL WORK | TOWER B 9TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24399 |  |  |  | TOWER B 9TH FLOOR PLASTER WORK | TOWER B 9TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28823 |  |  |  | TOWER B 9TH FLOOR | TOWER B 901 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28815 |  |  |  | TOWER B 901 | TOWER B 901 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40359 |  |  |  | TOWER B 901 WATERPROOFING WORK | TOWER B 901 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28817 |  |  |  | TOWER B 901 | TOWER B 901 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41144 |  |  |  | TOWER B 901 PLUMBING WORK | TOWER B 901 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28816 |  |  |  | TOWER B 901 | TOWER B 901 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40444 |  |  |  | TOWER B 901 ELECTRIC WORK | TOWER B 901 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28818 |  |  |  | TOWER B 901 | TOWER B 901 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41733 |  |  |  | TOWER B 901 FLOORING & DEDO WORK | TOWER B 901 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28821 |  |  |  | TOWER B 901 | TOWER B 901 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40884 |  |  |  | TOWER B 901 CARPENTRY WORK | TOWER B 901 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28819 |  |  |  | TOWER B 901 | TOWER B 901 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28820 |  |  |  | TOWER B 901 | TOWER B 901 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28822 |  |  |  | TOWER B 901 | TOWER B 901 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35033 |  |  |  | TOWER B 901 | TOWER B 901 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35034 |  |  |  | TOWER B 901 COMMON WORK | TOWER B 901 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35035 |  |  |  | TOWER B 901 COMMON WORK | TOWER B 901 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35036 |  |  |  | TOWER B 901 COMMON WORK | TOWER B 901 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28832 |  |  |  | TOWER B 9TH FLOOR | TOWER B 902 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28824 |  |  |  | TOWER B 902 | TOWER B 902 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40360 |  |  |  | TOWER B 902 WATERPROOFING WORK | TOWER B 902 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28826 |  |  |  | TOWER B 902 | TOWER B 902 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41145 |  |  |  | TOWER B 902 PLUMBING WORK | TOWER B 902 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28825 |  |  |  | TOWER B 902 | TOWER B 902 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40445 |  |  |  | TOWER B 902 ELECTRIC WORK | TOWER B 902 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28827 |  |  |  | TOWER B 902 | TOWER B 902 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41734 |  |  |  | TOWER B 902 FLOORING & DEDO WORK | TOWER B 902 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28830 |  |  |  | TOWER B 902 | TOWER B 902 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40885 |  |  |  | TOWER B 902 CARPENTRY WORK | TOWER B 902 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28828 |  |  |  | TOWER B 902 | TOWER B 902 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28829 |  |  |  | TOWER B 902 | TOWER B 902 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28831 |  |  |  | TOWER B 902 | TOWER B 902 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35037 |  |  |  | TOWER B 902 | TOWER B 902 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35038 |  |  |  | TOWER B 902 COMMON WORK | TOWER B 902 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35039 |  |  |  | TOWER B 902 COMMON WORK | TOWER B 902 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35040 |  |  |  | TOWER B 902 COMMON WORK | TOWER B 902 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28841 |  |  |  | TOWER B 9TH FLOOR | TOWER B 903 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28833 |  |  |  | TOWER B 903 | TOWER B 903 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40361 |  |  |  | TOWER B 903 WATERPROOFING WORK | TOWER B 903 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28835 |  |  |  | TOWER B 903 | TOWER B 903 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41146 |  |  |  | TOWER B 903 PLUMBING WORK | TOWER B 903 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28834 |  |  |  | TOWER B 903 | TOWER B 903 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40446 |  |  |  | TOWER B 903 ELECTRIC WORK | TOWER B 903 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28836 |  |  |  | TOWER B 903 | TOWER B 903 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41735 |  |  |  | TOWER B 903 FLOORING & DEDO WORK | TOWER B 903 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28839 |  |  |  | TOWER B 903 | TOWER B 903 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40886 |  |  |  | TOWER B 903 CARPENTRY WORK | TOWER B 903 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28837 |  |  |  | TOWER B 903 | TOWER B 903 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28838 |  |  |  | TOWER B 903 | TOWER B 903 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28840 |  |  |  | TOWER B 903 | TOWER B 903 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35041 |  |  |  | TOWER B 903 | TOWER B 903 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35042 |  |  |  | TOWER B 903 COMMON WORK | TOWER B 903 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35043 |  |  |  | TOWER B 903 COMMON WORK | TOWER B 903 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35044 |  |  |  | TOWER B 903 COMMON WORK | TOWER B 903 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28850 |  |  |  | TOWER B 9TH FLOOR | TOWER B 904 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28842 |  |  |  | TOWER B 904 | TOWER B 904 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40362 |  |  |  | TOWER B 904 WATERPROOFING WORK | TOWER B 904 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28844 |  |  |  | TOWER B 904 | TOWER B 904 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41147 |  |  |  | TOWER B 904 PLUMBING WORK | TOWER B 904 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28843 |  |  |  | TOWER B 904 | TOWER B 904 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40447 |  |  |  | TOWER B 904 ELECTRIC WORK | TOWER B 904 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28845 |  |  |  | TOWER B 904 | TOWER B 904 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41736 |  |  |  | TOWER B 904 FLOORING & DEDO WORK | TOWER B 904 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28848 |  |  |  | TOWER B 904 | TOWER B 904 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40887 |  |  |  | TOWER B 904 CARPENTRY WORK | TOWER B 904 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28846 |  |  |  | TOWER B 904 | TOWER B 904 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28847 |  |  |  | TOWER B 904 | TOWER B 904 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28849 |  |  |  | TOWER B 904 | TOWER B 904 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35045 |  |  |  | TOWER B 904 | TOWER B 904 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35046 |  |  |  | TOWER B 904 COMMON WORK | TOWER B 904 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35047 |  |  |  | TOWER B 904 COMMON WORK | TOWER B 904 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35048 |  |  |  | TOWER B 904 COMMON WORK | TOWER B 904 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29251 |  |  |  | TOWER B 9TH FLOOR | TOWER B 9TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29254 |  |  |  | TOWER B 9TH FLOOR COMMON WORK | TOWER B 9TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39409 |  |  |  | TOWER B 9TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 9TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29252 |  |  |  | TOWER B 9TH FLOOR COMMON WORK | TOWER B 9TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41970 |  |  |  | TOWER B 9TH FLOOR COMMON FLOORING WORK | TOWER B 9TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29253 |  |  |  | TOWER B 9TH FLOOR COMMON WORK | TOWER B 9TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29255 |  |  |  | TOWER B 9TH FLOOR COMMON WORK | TOWER B 9TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42060 |  |  |  | TOWER B 9TH FLOOR COMMON FALSE CEILING WORK | TOWER B 9TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29483 |  |  |  | TOWER B 9TH FLOOR COMMON WORK | TOWER B 9TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33065 |  |  |  | TOWER B 9TH FLOOR COMMON ELECTRIC WORK | TOWER B 9TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 80771 | 80771 | 17 Mar 2020 |  | 15 May 2024 |  | - | - | 1521 | - | SLAB CONDUTE
Group | 5 | 42307 |  |  |  | TOWER B 9TH FLOOR COMMON WORK | TOWER B 9TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42308 |  |  |  | TOWER B 9TH FLOOR WPC PANNELING WORK | TOWER B 9TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24400 |  |  |  | TOWER B | TOWER B 10TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24401 |  |  |  | TOWER B 10TH FLOOR | TOWER B 10TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24402 |  |  |  | TOWER B 10TH FLOOR CIVIL WORK | TOWER B 10TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24405 |  |  |  | TOWER B 10TH FLOOR RCC WORK | TOWER B 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 53123.2 |  | Started | 53123.2 | 0 | 53123.2 | 0 | 53.12 | 0 | 1644448 | 1644448 |  |  | 04 Oct 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33655 |  |  |  | TOWER B 10TH FLOOR RCC WORK | TOWER B 10TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 55064.7 | 55064.7 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | THREADING
Group | 5 | 24403 |  |  |  | TOWER B 10TH FLOOR CIVIL WORK | TOWER B 10TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24406 |  |  |  | TOWER B 10TH FLOOR MASONRY WORK | TOWER B 10TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39367 |  |  |  | TOWER B 10TH FLOOR MASONRY WORK | TOWER B 10TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24404 |  |  |  | TOWER B 10TH FLOOR CIVIL WORK | TOWER B 10TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24407 |  |  |  | TOWER B 10TH FLOOR PLASTER WORK | TOWER B 10TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28859 |  |  |  | TOWER B 10TH FLOOR | TOWER B 1001 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28851 |  |  |  | TOWER B 1001 | TOWER B 1001 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40363 |  |  |  | TOWER B 1001 WATERPROOFING WORK | TOWER B 1001 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28853 |  |  |  | TOWER B 1001 | TOWER B 1001 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41148 |  |  |  | TOWER B 1001 PLUMBING WORK | TOWER B 1001 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28852 |  |  |  | TOWER B 1001 | TOWER B 1001 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40448 |  |  |  | TOWER B 1001 ELECTRIC WORK | TOWER B 1001 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 28025 | 28025 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28854 |  |  |  | TOWER B 1001 | TOWER B 1001 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41737 |  |  |  | TOWER B 1001 FLOORING & DEDO WORK | TOWER B 1001 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28857 |  |  |  | TOWER B 1001 | TOWER B 1001 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40888 |  |  |  | TOWER B 1001 CARPENTRY WORK | TOWER B 1001 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28855 |  |  |  | TOWER B 1001 | TOWER B 1001 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28856 |  |  |  | TOWER B 1001 | TOWER B 1001 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28858 |  |  |  | TOWER B 1001 | TOWER B 1001 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35049 |  |  |  | TOWER B 1001 | TOWER B 1001 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35050 |  |  |  | TOWER B 1001 COMMON WORK | TOWER B 1001 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35051 |  |  |  | TOWER B 1001 COMMON WORK | TOWER B 1001 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35052 |  |  |  | TOWER B 1001 COMMON WORK | TOWER B 1001 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28868 |  |  |  | TOWER B 10TH FLOOR | TOWER B 1002 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28860 |  |  |  | TOWER B 1002 | TOWER B 1002 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40364 |  |  |  | TOWER B 1002 WATERPROOFING WORK | TOWER B 1002 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28862 |  |  |  | TOWER B 1002 | TOWER B 1002 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41149 |  |  |  | TOWER B 1002 PLUMBING WORK | TOWER B 1002 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28861 |  |  |  | TOWER B 1002 | TOWER B 1002 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40449 |  |  |  | TOWER B 1002 ELECTRIC WORK | TOWER B 1002 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 28025 | 28025 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28863 |  |  |  | TOWER B 1002 | TOWER B 1002 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41738 |  |  |  | TOWER B 1002 FLOORING & DEDO WORK | TOWER B 1002 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28866 |  |  |  | TOWER B 1002 | TOWER B 1002 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40889 |  |  |  | TOWER B 1002 CARPENTRY WORK | TOWER B 1002 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28864 |  |  |  | TOWER B 1002 | TOWER B 1002 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28865 |  |  |  | TOWER B 1002 | TOWER B 1002 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28867 |  |  |  | TOWER B 1002 | TOWER B 1002 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35053 |  |  |  | TOWER B 1002 | TOWER B 1002 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35054 |  |  |  | TOWER B 1002 COMMON WORK | TOWER B 1002 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35055 |  |  |  | TOWER B 1002 COMMON WORK | TOWER B 1002 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35056 |  |  |  | TOWER B 1002 COMMON WORK | TOWER B 1002 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28877 |  |  |  | TOWER B 10TH FLOOR | TOWER B 1003 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28869 |  |  |  | TOWER B 1003 | TOWER B 1003 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40365 |  |  |  | TOWER B 1003 WATERPROOFING WORK | TOWER B 1003 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28871 |  |  |  | TOWER B 1003 | TOWER B 1003 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41150 |  |  |  | TOWER B 1003 PLUMBING WORK | TOWER B 1003 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28870 |  |  |  | TOWER B 1003 | TOWER B 1003 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40450 |  |  |  | TOWER B 1003 ELECTRIC WORK | TOWER B 1003 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 28025 | 28025 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28872 |  |  |  | TOWER B 1003 | TOWER B 1003 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41739 |  |  |  | TOWER B 1003 FLOORING & DEDO WORK | TOWER B 1003 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28875 |  |  |  | TOWER B 1003 | TOWER B 1003 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40890 |  |  |  | TOWER B 1003 CARPENTRY WORK | TOWER B 1003 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28873 |  |  |  | TOWER B 1003 | TOWER B 1003 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28874 |  |  |  | TOWER B 1003 | TOWER B 1003 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28876 |  |  |  | TOWER B 1003 | TOWER B 1003 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35057 |  |  |  | TOWER B 1003 | TOWER B 1003 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35058 |  |  |  | TOWER B 1003 COMMON WORK | TOWER B 1003 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35059 |  |  |  | TOWER B 1003 COMMON WORK | TOWER B 1003 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35060 |  |  |  | TOWER B 1003 COMMON WORK | TOWER B 1003 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28886 |  |  |  | TOWER B 10TH FLOOR | TOWER B 1004 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28878 |  |  |  | TOWER B 1004 | TOWER B 1004 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40366 |  |  |  | TOWER B 1004 WATERPROOFING WORK | TOWER B 1004 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28880 |  |  |  | TOWER B 1004 | TOWER B 1004 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41151 |  |  |  | TOWER B 1004 PLUMBING WORK | TOWER B 1004 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28879 |  |  |  | TOWER B 1004 | TOWER B 1004 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40452 |  |  |  | TOWER B 1004 ELECTRIC WORK | TOWER B 1004 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Started | 256.06 | 0 | 256.06 | 0 | 0.26 | 0 | 28025 | 28025 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 28881 |  |  |  | TOWER B 1004 | TOWER B 1004 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41740 |  |  |  | TOWER B 1004 FLOORING & DEDO WORK | TOWER B 1004 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28884 |  |  |  | TOWER B 1004 | TOWER B 1004 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40891 |  |  |  | TOWER B 1004 CARPENTRY WORK | TOWER B 1004 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28882 |  |  |  | TOWER B 1004 | TOWER B 1004 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28883 |  |  |  | TOWER B 1004 | TOWER B 1004 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28885 |  |  |  | TOWER B 1004 | TOWER B 1004 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35061 |  |  |  | TOWER B 1004 | TOWER B 1004 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35062 |  |  |  | TOWER B 1004 COMMON WORK | TOWER B 1004 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35063 |  |  |  | TOWER B 1004 COMMON WORK | TOWER B 1004 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35064 |  |  |  | TOWER B 1004 COMMON WORK | TOWER B 1004 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29256 |  |  |  | TOWER B 10TH FLOOR | TOWER B 10TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29259 |  |  |  | TOWER B 10TH FLOOR COMMON WORK | TOWER B 10TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39410 |  |  |  | TOWER B 10TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER B 10TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Tentative | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29257 |  |  |  | TOWER B 10TH FLOOR COMMON WORK | TOWER B 10TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41971 |  |  |  | TOWER B 10TH FLOOR COMMON FLOORING WORK | TOWER B 10TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29258 |  |  |  | TOWER B 10TH FLOOR COMMON WORK | TOWER B 10TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29260 |  |  |  | TOWER B 10TH FLOOR COMMON WORK | TOWER B 10TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42061 |  |  |  | TOWER B 10TH FLOOR COMMON FALSE CEILING WORK | TOWER B 10TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29484 |  |  |  | TOWER B 10TH FLOOR COMMON WORK | TOWER B 10TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33066 |  |  |  | TOWER B 10TH FLOOR COMMON ELECTRIC WORK | TOWER B 10TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42309 |  |  |  | TOWER B 10TH FLOOR COMMON WORK | TOWER B 10TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42310 |  |  |  | TOWER B 10TH FLOOR WPC PANNELING WORK | TOWER B 10TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24408 |  |  |  | TOWER B | TOWER B 11TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24409 |  |  |  | TOWER B 11TH FLOOR | TOWER B 11TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24410 |  |  |  | TOWER B 11TH FLOOR CIVIL WORK | TOWER B 11TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24413 |  |  |  | TOWER B 11TH FLOOR RCC WORK | TOWER B 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 48346.9 |  | Tentative | 48346.9 | 0 | 48346.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33656 |  |  |  | TOWER B 11TH FLOOR RCC WORK | TOWER B 11TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 49666.2 | 49666.2 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | THREADING
Group | 5 | 24411 |  |  |  | TOWER B 11TH FLOOR CIVIL WORK | TOWER B 11TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24414 |  |  |  | TOWER B 11TH FLOOR MASONRY WORK | TOWER B 11TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39368 |  |  |  | TOWER B 11TH FLOOR MASONRY WORK | TOWER B 11TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24412 |  |  |  | TOWER B 11TH FLOOR CIVIL WORK | TOWER B 11TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24415 |  |  |  | TOWER B 11TH FLOOR PLASTER WORK | TOWER B 11TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28895 |  |  |  | TOWER B 11TH FLOOR | TOWER B 1101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28887 |  |  |  | TOWER B 1101 | TOWER B 1101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40367 |  |  |  | TOWER B 1101 WATERPROOFING WORK | TOWER B 1101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28889 |  |  |  | TOWER B 1101 | TOWER B 1101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41152 |  |  |  | TOWER B 1101 PLUMBING WORK | TOWER B 1101 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28888 |  |  |  | TOWER B 1101 | TOWER B 1101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40453 |  |  |  | TOWER B 1101 ELECTRIC WORK | TOWER B 1101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28890 |  |  |  | TOWER B 1101 | TOWER B 1101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41741 |  |  |  | TOWER B 1101 FLOORING & DEDO WORK | TOWER B 1101 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28893 |  |  |  | TOWER B 1101 | TOWER B 1101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40892 |  |  |  | TOWER B 1101 CARPENTRY WORK | TOWER B 1101 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28891 |  |  |  | TOWER B 1101 | TOWER B 1101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28892 |  |  |  | TOWER B 1101 | TOWER B 1101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28894 |  |  |  | TOWER B 1101 | TOWER B 1101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35065 |  |  |  | TOWER B 1101 | TOWER B 1101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35066 |  |  |  | TOWER B 1101 COMMON WORK | TOWER B 1101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35067 |  |  |  | TOWER B 1101 COMMON WORK | TOWER B 1101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35068 |  |  |  | TOWER B 1101 COMMON WORK | TOWER B 1101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28904 |  |  |  | TOWER B 11TH FLOOR | TOWER B 1102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28896 |  |  |  | TOWER B 1102 | TOWER B 1102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40368 |  |  |  | TOWER B 1102 WATERPROOFING WORK | TOWER B 1102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28898 |  |  |  | TOWER B 1102 | TOWER B 1102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41153 |  |  |  | TOWER B 1102 PLUMBING WORK | TOWER B 1102 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28897 |  |  |  | TOWER B 1102 | TOWER B 1102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40454 |  |  |  | TOWER B 1102 ELECTRIC WORK | TOWER B 1102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28899 |  |  |  | TOWER B 1102 | TOWER B 1102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41742 |  |  |  | TOWER B 1102 FLOORING & DEDO WORK | TOWER B 1102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28902 |  |  |  | TOWER B 1102 | TOWER B 1102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40893 |  |  |  | TOWER B 1102 CARPENTRY WORK | TOWER B 1102 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28900 |  |  |  | TOWER B 1102 | TOWER B 1102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28901 |  |  |  | TOWER B 1102 | TOWER B 1102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28903 |  |  |  | TOWER B 1102 | TOWER B 1102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35069 |  |  |  | TOWER B 1102 | TOWER B 1102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35070 |  |  |  | TOWER B 1102 COMMON WORK | TOWER B 1102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35071 |  |  |  | TOWER B 1102 COMMON WORK | TOWER B 1102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35072 |  |  |  | TOWER B 1102 COMMON WORK | TOWER B 1102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28913 |  |  |  | TOWER B 11TH FLOOR | TOWER B 1103 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28905 |  |  |  | TOWER B 1103 | TOWER B 1103 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40369 |  |  |  | TOWER B 1103 WATERPROOFING WORK | TOWER B 1103 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28907 |  |  |  | TOWER B 1103 | TOWER B 1103 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41154 |  |  |  | TOWER B 1103 PLUMBING WORK | TOWER B 1103 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28906 |  |  |  | TOWER B 1103 | TOWER B 1103 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40455 |  |  |  | TOWER B 1103 ELECTRIC WORK | TOWER B 1103 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28908 |  |  |  | TOWER B 1103 | TOWER B 1103 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41743 |  |  |  | TOWER B 1103 FLOORING & DEDO WORK | TOWER B 1103 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28911 |  |  |  | TOWER B 1103 | TOWER B 1103 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40894 |  |  |  | TOWER B 1103 CARPENTRY WORK | TOWER B 1103 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28909 |  |  |  | TOWER B 1103 | TOWER B 1103 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28910 |  |  |  | TOWER B 1103 | TOWER B 1103 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28912 |  |  |  | TOWER B 1103 | TOWER B 1103 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35073 |  |  |  | TOWER B 1103 | TOWER B 1103 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35074 |  |  |  | TOWER B 1103 COMMON WORK | TOWER B 1103 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35075 |  |  |  | TOWER B 1103 COMMON WORK | TOWER B 1103 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35076 |  |  |  | TOWER B 1103 COMMON WORK | TOWER B 1103 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28922 |  |  |  | TOWER B 11TH FLOOR | TOWER B 1104 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28914 |  |  |  | TOWER B 1104 | TOWER B 1104 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40370 |  |  |  | TOWER B 1104 WATERPROOFING WORK | TOWER B 1104 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28916 |  |  |  | TOWER B 1104 | TOWER B 1104 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41155 |  |  |  | TOWER B 1104 PLUMBING WORK | TOWER B 1104 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28915 |  |  |  | TOWER B 1104 | TOWER B 1104 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40456 |  |  |  | TOWER B 1104 ELECTRIC WORK | TOWER B 1104 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28917 |  |  |  | TOWER B 1104 | TOWER B 1104 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41744 |  |  |  | TOWER B 1104 FLOORING & DEDO WORK | TOWER B 1104 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28920 |  |  |  | TOWER B 1104 | TOWER B 1104 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40895 |  |  |  | TOWER B 1104 CARPENTRY WORK | TOWER B 1104 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28918 |  |  |  | TOWER B 1104 | TOWER B 1104 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28919 |  |  |  | TOWER B 1104 | TOWER B 1104 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28921 |  |  |  | TOWER B 1104 | TOWER B 1104 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35077 |  |  |  | TOWER B 1104 | TOWER B 1104 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35078 |  |  |  | TOWER B 1104 COMMON WORK | TOWER B 1104 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35079 |  |  |  | TOWER B 1104 COMMON WORK | TOWER B 1104 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35080 |  |  |  | TOWER B 1104 COMMON WORK | TOWER B 1104 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29261 |  |  |  | TOWER B 11TH FLOOR | TOWER B 11TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29264 |  |  |  | TOWER B 11TH FLOOR COMMON WORK | TOWER B 11TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29262 |  |  |  | TOWER B 11TH FLOOR COMMON WORK | TOWER B 11TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41972 |  |  |  | TOWER B 11TH FLOOR COMMON FLOORING WORK | TOWER B 11TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29263 |  |  |  | TOWER B 11TH FLOOR COMMON WORK | TOWER B 11TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29265 |  |  |  | TOWER B 11TH FLOOR COMMON WORK | TOWER B 11TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42062 |  |  |  | TOWER B 11TH FLOOR COMMON FALSE CEILING WORK | TOWER B 11TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29485 |  |  |  | TOWER B 11TH FLOOR COMMON WORK | TOWER B 11TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33067 |  |  |  | TOWER B 11TH FLOOR COMMON ELECTRIC WORK | TOWER B 11TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42311 |  |  |  | TOWER B 11TH FLOOR COMMON WORK | TOWER B 11TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42312 |  |  |  | TOWER B 11TH FLOOR WPC PANNELING WORK | TOWER B 11TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24416 |  |  |  | TOWER B | TOWER B 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24417 |  |  |  | TOWER B 12TH FLOOR | TOWER B 12TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24418 |  |  |  | TOWER B 12TH FLOOR CIVIL WORK | TOWER B 12TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24421 |  |  |  | TOWER B 12TH FLOOR RCC WORK | TOWER B 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34573.5 |  | Tentative | 34573.5 | 0 | 34573.5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24419 |  |  |  | TOWER B 12TH FLOOR CIVIL WORK | TOWER B 12TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24422 |  |  |  | TOWER B 12TH FLOOR MASONRY WORK | TOWER B 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39369 |  |  |  | TOWER B 12TH FLOOR MASONRY WORK | TOWER B 12TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24420 |  |  |  | TOWER B 12TH FLOOR CIVIL WORK | TOWER B 12TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24423 |  |  |  | TOWER B 12TH FLOOR PLASTER WORK | TOWER B 12TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28931 |  |  |  | TOWER B 12TH FLOOR | TOWER B 1201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28923 |  |  |  | TOWER B 1201 | TOWER B 1201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40371 |  |  |  | TOWER B 1201 WATERPROOFING WORK | TOWER B 1201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28925 |  |  |  | TOWER B 1201 | TOWER B 1201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41156 |  |  |  | TOWER B 1201 PLUMBING WORK | TOWER B 1201 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28924 |  |  |  | TOWER B 1201 | TOWER B 1201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40457 |  |  |  | TOWER B 1201 ELECTRIC WORK | TOWER B 1201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28926 |  |  |  | TOWER B 1201 | TOWER B 1201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41745 |  |  |  | TOWER B 1201 FLOORING & DEDO WORK | TOWER B 1201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28929 |  |  |  | TOWER B 1201 | TOWER B 1201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40896 |  |  |  | TOWER B 1201 CARPENTRY WORK | TOWER B 1201 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28927 |  |  |  | TOWER B 1201 | TOWER B 1201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28928 |  |  |  | TOWER B 1201 | TOWER B 1201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28930 |  |  |  | TOWER B 1201 | TOWER B 1201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35081 |  |  |  | TOWER B 1201 | TOWER B 1201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35082 |  |  |  | TOWER B 1201 COMMON WORK | TOWER B 1201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35083 |  |  |  | TOWER B 1201 COMMON WORK | TOWER B 1201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35084 |  |  |  | TOWER B 1201 COMMON WORK | TOWER B 1201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28940 |  |  |  | TOWER B 12TH FLOOR | TOWER B 1202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28932 |  |  |  | TOWER B 1202 | TOWER B 1202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40372 |  |  |  | TOWER B 1202 WATERPROOFING WORK | TOWER B 1202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28934 |  |  |  | TOWER B 1202 | TOWER B 1202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41157 |  |  |  | TOWER B 1202 PLUMBING WORK | TOWER B 1202 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28933 |  |  |  | TOWER B 1202 | TOWER B 1202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40458 |  |  |  | TOWER B 1202 ELECTRIC WORK | TOWER B 1202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28935 |  |  |  | TOWER B 1202 | TOWER B 1202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41746 |  |  |  | TOWER B 1202 FLOORING & DEDO WORK | TOWER B 1202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28938 |  |  |  | TOWER B 1202 | TOWER B 1202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40897 |  |  |  | TOWER B 1202 CARPENTRY WORK | TOWER B 1202 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28936 |  |  |  | TOWER B 1202 | TOWER B 1202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28937 |  |  |  | TOWER B 1202 | TOWER B 1202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28939 |  |  |  | TOWER B 1202 | TOWER B 1202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35085 |  |  |  | TOWER B 1202 | TOWER B 1202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35086 |  |  |  | TOWER B 1202 COMMON WORK | TOWER B 1202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35087 |  |  |  | TOWER B 1202 COMMON WORK | TOWER B 1202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35088 |  |  |  | TOWER B 1202 COMMON WORK | TOWER B 1202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28949 |  |  |  | TOWER B 12TH FLOOR | TOWER B 1203 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28941 |  |  |  | TOWER B 1203 | TOWER B 1203 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40373 |  |  |  | TOWER B 1203 WATERPROOFING WORK | TOWER B 1203 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28943 |  |  |  | TOWER B 1203 | TOWER B 1203 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41158 |  |  |  | TOWER B 1203 PLUMBING WORK | TOWER B 1203 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28942 |  |  |  | TOWER B 1203 | TOWER B 1203 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40459 |  |  |  | TOWER B 1203 ELECTRIC WORK | TOWER B 1203 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28944 |  |  |  | TOWER B 1203 | TOWER B 1203 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41747 |  |  |  | TOWER B 1203 FLOORING & DEDO WORK | TOWER B 1203 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28947 |  |  |  | TOWER B 1203 | TOWER B 1203 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40898 |  |  |  | TOWER B 1203 CARPENTRY WORK | TOWER B 1203 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28945 |  |  |  | TOWER B 1203 | TOWER B 1203 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28946 |  |  |  | TOWER B 1203 | TOWER B 1203 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28948 |  |  |  | TOWER B 1203 | TOWER B 1203 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35089 |  |  |  | TOWER B 1203 | TOWER B 1203 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35090 |  |  |  | TOWER B 1203 COMMON WORK | TOWER B 1203 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35091 |  |  |  | TOWER B 1203 COMMON WORK | TOWER B 1203 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35092 |  |  |  | TOWER B 1203 COMMON WORK | TOWER B 1203 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28958 |  |  |  | TOWER B 12TH FLOOR | TOWER B 1204 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28950 |  |  |  | TOWER B 1204 | TOWER B 1204 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40374 |  |  |  | TOWER B 1204 WATERPROOFING WORK | TOWER B 1204 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28952 |  |  |  | TOWER B 1204 | TOWER B 1204 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41159 |  |  |  | TOWER B 1204 PLUMBING WORK | TOWER B 1204 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28951 |  |  |  | TOWER B 1204 | TOWER B 1204 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40460 |  |  |  | TOWER B 1204 ELECTRIC WORK | TOWER B 1204 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28953 |  |  |  | TOWER B 1204 | TOWER B 1204 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41748 |  |  |  | TOWER B 1204 FLOORING & DEDO WORK | TOWER B 1204 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28956 |  |  |  | TOWER B 1204 | TOWER B 1204 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40899 |  |  |  | TOWER B 1204 CARPENTRY WORK | TOWER B 1204 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28954 |  |  |  | TOWER B 1204 | TOWER B 1204 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28955 |  |  |  | TOWER B 1204 | TOWER B 1204 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28957 |  |  |  | TOWER B 1204 | TOWER B 1204 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35093 |  |  |  | TOWER B 1204 | TOWER B 1204 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35094 |  |  |  | TOWER B 1204 COMMON WORK | TOWER B 1204 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35095 |  |  |  | TOWER B 1204 COMMON WORK | TOWER B 1204 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35096 |  |  |  | TOWER B 1204 COMMON WORK | TOWER B 1204 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29266 |  |  |  | TOWER B 12TH FLOOR | TOWER B 12TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29269 |  |  |  | TOWER B 12TH FLOOR COMMON WORK | TOWER B 12TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29267 |  |  |  | TOWER B 12TH FLOOR COMMON WORK | TOWER B 12TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41973 |  |  |  | TOWER B 12TH FLOOR COMMON FLOORING WORK | TOWER B 12TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29268 |  |  |  | TOWER B 12TH FLOOR COMMON WORK | TOWER B 12TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29270 |  |  |  | TOWER B 12TH FLOOR COMMON WORK | TOWER B 12TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42063 |  |  |  | TOWER B 12TH FLOOR COMMON FALSE CEILING WORK | TOWER B 12TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29486 |  |  |  | TOWER B 12TH FLOOR COMMON WORK | TOWER B 12TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33068 |  |  |  | TOWER B 12TH FLOOR COMMON ELECTRIC WORK | TOWER B 12TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42313 |  |  |  | TOWER B 12TH FLOOR COMMON WORK | TOWER B 12TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42314 |  |  |  | TOWER B 12TH FLOOR WPC PANNELING WORK | TOWER B 12TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24424 |  |  |  | TOWER B | TOWER B 13TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24425 |  |  |  | TOWER B 13TH FLOOR | TOWER B 13TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24426 |  |  |  | TOWER B 13TH FLOOR CIVIL WORK | TOWER B 13TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24429 |  |  |  | TOWER B 13TH FLOOR RCC WORK | TOWER B 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24427 |  |  |  | TOWER B 13TH FLOOR CIVIL WORK | TOWER B 13TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24430 |  |  |  | TOWER B 13TH FLOOR MASONRY WORK | TOWER B 13TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39370 |  |  |  | TOWER B 13TH FLOOR MASONRY WORK | TOWER B 13TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24428 |  |  |  | TOWER B 13TH FLOOR CIVIL WORK | TOWER B 13TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24431 |  |  |  | TOWER B 13TH FLOOR PLASTER WORK | TOWER B 13TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 28967 |  |  |  | TOWER B 13TH FLOOR | TOWER B 1301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28959 |  |  |  | TOWER B 1301 | TOWER B 1301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40375 |  |  |  | TOWER B 1301 WATERPROOFING WORK | TOWER B 1301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28961 |  |  |  | TOWER B 1301 | TOWER B 1301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41160 |  |  |  | TOWER B 1301 PLUMBING WORK | TOWER B 1301 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28960 |  |  |  | TOWER B 1301 | TOWER B 1301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40461 |  |  |  | TOWER B 1301 ELECTRIC WORK | TOWER B 1301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28962 |  |  |  | TOWER B 1301 | TOWER B 1301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41749 |  |  |  | TOWER B 1301 FLOORING & DEDO WORK | TOWER B 1301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28965 |  |  |  | TOWER B 1301 | TOWER B 1301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40900 |  |  |  | TOWER B 1301 CARPENTRY WORK | TOWER B 1301 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28963 |  |  |  | TOWER B 1301 | TOWER B 1301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28964 |  |  |  | TOWER B 1301 | TOWER B 1301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28966 |  |  |  | TOWER B 1301 | TOWER B 1301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35097 |  |  |  | TOWER B 1301 | TOWER B 1301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35098 |  |  |  | TOWER B 1301 COMMON WORK | TOWER B 1301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35099 |  |  |  | TOWER B 1301 COMMON WORK | TOWER B 1301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35100 |  |  |  | TOWER B 1301 COMMON WORK | TOWER B 1301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28976 |  |  |  | TOWER B 13TH FLOOR | TOWER B 1302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28968 |  |  |  | TOWER B 1302 | TOWER B 1302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40376 |  |  |  | TOWER B 1302 WATERPROOFING WORK | TOWER B 1302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28970 |  |  |  | TOWER B 1302 | TOWER B 1302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41161 |  |  |  | TOWER B 1302 PLUMBING WORK | TOWER B 1302 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28969 |  |  |  | TOWER B 1302 | TOWER B 1302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40462 |  |  |  | TOWER B 1302 ELECTRIC WORK | TOWER B 1302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28971 |  |  |  | TOWER B 1302 | TOWER B 1302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41750 |  |  |  | TOWER B 1302 FLOORING & DEDO WORK | TOWER B 1302 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28974 |  |  |  | TOWER B 1302 | TOWER B 1302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40901 |  |  |  | TOWER B 1302 CARPENTRY WORK | TOWER B 1302 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28972 |  |  |  | TOWER B 1302 | TOWER B 1302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28973 |  |  |  | TOWER B 1302 | TOWER B 1302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28975 |  |  |  | TOWER B 1302 | TOWER B 1302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35101 |  |  |  | TOWER B 1302 | TOWER B 1302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35102 |  |  |  | TOWER B 1302 COMMON WORK | TOWER B 1302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35103 |  |  |  | TOWER B 1302 COMMON WORK | TOWER B 1302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35104 |  |  |  | TOWER B 1302 COMMON WORK | TOWER B 1302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28985 |  |  |  | TOWER B 13TH FLOOR | TOWER B 1303 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28977 |  |  |  | TOWER B 1303 | TOWER B 1303 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40377 |  |  |  | TOWER B 1303 WATERPROOFING WORK | TOWER B 1303 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28979 |  |  |  | TOWER B 1303 | TOWER B 1303 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41162 |  |  |  | TOWER B 1303 PLUMBING WORK | TOWER B 1303 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28978 |  |  |  | TOWER B 1303 | TOWER B 1303 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40463 |  |  |  | TOWER B 1303 ELECTRIC WORK | TOWER B 1303 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28980 |  |  |  | TOWER B 1303 | TOWER B 1303 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41751 |  |  |  | TOWER B 1303 FLOORING & DEDO WORK | TOWER B 1303 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28983 |  |  |  | TOWER B 1303 | TOWER B 1303 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40902 |  |  |  | TOWER B 1303 CARPENTRY WORK | TOWER B 1303 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28981 |  |  |  | TOWER B 1303 | TOWER B 1303 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28982 |  |  |  | TOWER B 1303 | TOWER B 1303 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28984 |  |  |  | TOWER B 1303 | TOWER B 1303 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35105 |  |  |  | TOWER B 1303 | TOWER B 1303 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35106 |  |  |  | TOWER B 1303 COMMON WORK | TOWER B 1303 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35107 |  |  |  | TOWER B 1303 COMMON WORK | TOWER B 1303 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35108 |  |  |  | TOWER B 1303 COMMON WORK | TOWER B 1303 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 28994 |  |  |  | TOWER B 13TH FLOOR | TOWER B 1304 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28986 |  |  |  | TOWER B 1304 | TOWER B 1304 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40378 |  |  |  | TOWER B 1304 WATERPROOFING WORK | TOWER B 1304 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28988 |  |  |  | TOWER B 1304 | TOWER B 1304 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41163 |  |  |  | TOWER B 1304 PLUMBING WORK | TOWER B 1304 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28987 |  |  |  | TOWER B 1304 | TOWER B 1304 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40464 |  |  |  | TOWER B 1304 ELECTRIC WORK | TOWER B 1304 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28989 |  |  |  | TOWER B 1304 | TOWER B 1304 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41752 |  |  |  | TOWER B 1304 FLOORING & DEDO WORK | TOWER B 1304 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 28992 |  |  |  | TOWER B 1304 | TOWER B 1304 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40903 |  |  |  | TOWER B 1304 CARPENTRY WORK | TOWER B 1304 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28990 |  |  |  | TOWER B 1304 | TOWER B 1304 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28991 |  |  |  | TOWER B 1304 | TOWER B 1304 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28993 |  |  |  | TOWER B 1304 | TOWER B 1304 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35109 |  |  |  | TOWER B 1304 | TOWER B 1304 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35110 |  |  |  | TOWER B 1304 COMMON WORK | TOWER B 1304 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35111 |  |  |  | TOWER B 1304 COMMON WORK | TOWER B 1304 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35112 |  |  |  | TOWER B 1304 COMMON WORK | TOWER B 1304 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29271 |  |  |  | TOWER B 13TH FLOOR | TOWER B 13TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29274 |  |  |  | TOWER B 13TH FLOOR COMMON WORK | TOWER B 13TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29272 |  |  |  | TOWER B 13TH FLOOR COMMON WORK | TOWER B 13TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41974 |  |  |  | TOWER B 13TH FLOOR COMMON FLOORING WORK | TOWER B 13TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29273 |  |  |  | TOWER B 13TH FLOOR COMMON WORK | TOWER B 13TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29275 |  |  |  | TOWER B 13TH FLOOR COMMON WORK | TOWER B 13TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42064 |  |  |  | TOWER B 13TH FLOOR COMMON FALSE CEILING WORK | TOWER B 13TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29487 |  |  |  | TOWER B 13TH FLOOR COMMON WORK | TOWER B 13TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33069 |  |  |  | TOWER B 13TH FLOOR COMMON ELECTRIC WORK | TOWER B 13TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42315 |  |  |  | TOWER B 13TH FLOOR COMMON WORK | TOWER B 13TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42316 |  |  |  | TOWER B 13TH FLOOR WPC PANNELING WORK | TOWER B 13TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24432 |  |  |  | TOWER B | TOWER B 14TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24433 |  |  |  | TOWER B 14TH FLOOR | TOWER B 14TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24434 |  |  |  | TOWER B 14TH FLOOR CIVIL WORK | TOWER B 14TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24437 |  |  |  | TOWER B 14TH FLOOR RCC WORK | TOWER B 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24435 |  |  |  | TOWER B 14TH FLOOR CIVIL WORK | TOWER B 14TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24438 |  |  |  | TOWER B 14TH FLOOR MASONRY WORK | TOWER B 14TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39371 |  |  |  | TOWER B 14TH FLOOR MASONRY WORK | TOWER B 14TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24436 |  |  |  | TOWER B 14TH FLOOR CIVIL WORK | TOWER B 14TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24439 |  |  |  | TOWER B 14TH FLOOR PLASTER WORK | TOWER B 14TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29003 |  |  |  | TOWER B 14TH FLOOR | TOWER B 1401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 28995 |  |  |  | TOWER B 1401 | TOWER B 1401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40379 |  |  |  | TOWER B 1401 WATERPROOFING WORK | TOWER B 1401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 28997 |  |  |  | TOWER B 1401 | TOWER B 1401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41164 |  |  |  | TOWER B 1401 PLUMBING WORK | TOWER B 1401 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 28996 |  |  |  | TOWER B 1401 | TOWER B 1401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40465 |  |  |  | TOWER B 1401 ELECTRIC WORK | TOWER B 1401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 28998 |  |  |  | TOWER B 1401 | TOWER B 1401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41753 |  |  |  | TOWER B 1401 FLOORING & DEDO WORK | TOWER B 1401 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29001 |  |  |  | TOWER B 1401 | TOWER B 1401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40904 |  |  |  | TOWER B 1401 CARPENTRY WORK | TOWER B 1401 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 28999 |  |  |  | TOWER B 1401 | TOWER B 1401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29000 |  |  |  | TOWER B 1401 | TOWER B 1401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29002 |  |  |  | TOWER B 1401 | TOWER B 1401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35113 |  |  |  | TOWER B 1401 | TOWER B 1401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35114 |  |  |  | TOWER B 1401 COMMON WORK | TOWER B 1401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35115 |  |  |  | TOWER B 1401 COMMON WORK | TOWER B 1401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35116 |  |  |  | TOWER B 1401 COMMON WORK | TOWER B 1401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29012 |  |  |  | TOWER B 14TH FLOOR | TOWER B 1402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29004 |  |  |  | TOWER B 1402 | TOWER B 1402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40380 |  |  |  | TOWER B 1402 WATERPROOFING WORK | TOWER B 1402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29006 |  |  |  | TOWER B 1402 | TOWER B 1402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41165 |  |  |  | TOWER B 1402 PLUMBING WORK | TOWER B 1402 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29005 |  |  |  | TOWER B 1402 | TOWER B 1402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40466 |  |  |  | TOWER B 1402 ELECTRIC WORK | TOWER B 1402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29007 |  |  |  | TOWER B 1402 | TOWER B 1402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41754 |  |  |  | TOWER B 1402 FLOORING & DEDO WORK | TOWER B 1402 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29010 |  |  |  | TOWER B 1402 | TOWER B 1402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40905 |  |  |  | TOWER B 1402 CARPENTRY WORK | TOWER B 1402 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29008 |  |  |  | TOWER B 1402 | TOWER B 1402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29009 |  |  |  | TOWER B 1402 | TOWER B 1402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29011 |  |  |  | TOWER B 1402 | TOWER B 1402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35117 |  |  |  | TOWER B 1402 | TOWER B 1402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35118 |  |  |  | TOWER B 1402 COMMON WORK | TOWER B 1402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35119 |  |  |  | TOWER B 1402 COMMON WORK | TOWER B 1402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35120 |  |  |  | TOWER B 1402 COMMON WORK | TOWER B 1402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29021 |  |  |  | TOWER B 14TH FLOOR | TOWER B 1403 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29013 |  |  |  | TOWER B 1403 | TOWER B 1403 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40381 |  |  |  | TOWER B 1403 WATERPROOFING WORK | TOWER B 1403 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29015 |  |  |  | TOWER B 1403 | TOWER B 1403 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41166 |  |  |  | TOWER B 1403 PLUMBING WORK | TOWER B 1403 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29014 |  |  |  | TOWER B 1403 | TOWER B 1403 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40467 |  |  |  | TOWER B 1403 ELECTRIC WORK | TOWER B 1403 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29016 |  |  |  | TOWER B 1403 | TOWER B 1403 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41755 |  |  |  | TOWER B 1403 FLOORING & DEDO WORK | TOWER B 1403 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29019 |  |  |  | TOWER B 1403 | TOWER B 1403 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40906 |  |  |  | TOWER B 1403 CARPENTRY WORK | TOWER B 1403 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29017 |  |  |  | TOWER B 1403 | TOWER B 1403 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29018 |  |  |  | TOWER B 1403 | TOWER B 1403 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29020 |  |  |  | TOWER B 1403 | TOWER B 1403 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35121 |  |  |  | TOWER B 1403 | TOWER B 1403 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35122 |  |  |  | TOWER B 1403 COMMON WORK | TOWER B 1403 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35123 |  |  |  | TOWER B 1403 COMMON WORK | TOWER B 1403 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35124 |  |  |  | TOWER B 1403 COMMON WORK | TOWER B 1403 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29030 |  |  |  | TOWER B 14TH FLOOR | TOWER B 1404 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29022 |  |  |  | TOWER B 1404 | TOWER B 1404 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40382 |  |  |  | TOWER B 1404 WATERPROOFING WORK | TOWER B 1404 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29024 |  |  |  | TOWER B 1404 | TOWER B 1404 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41167 |  |  |  | TOWER B 1404 PLUMBING WORK | TOWER B 1404 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29023 |  |  |  | TOWER B 1404 | TOWER B 1404 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40468 |  |  |  | TOWER B 1404 ELECTRIC WORK | TOWER B 1404 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29025 |  |  |  | TOWER B 1404 | TOWER B 1404 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41756 |  |  |  | TOWER B 1404 FLOORING & DEDO WORK | TOWER B 1404 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29028 |  |  |  | TOWER B 1404 | TOWER B 1404 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40907 |  |  |  | TOWER B 1404 CARPENTRY WORK | TOWER B 1404 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29026 |  |  |  | TOWER B 1404 | TOWER B 1404 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29027 |  |  |  | TOWER B 1404 | TOWER B 1404 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29029 |  |  |  | TOWER B 1404 | TOWER B 1404 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35125 |  |  |  | TOWER B 1404 | TOWER B 1404 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35126 |  |  |  | TOWER B 1404 COMMON WORK | TOWER B 1404 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35127 |  |  |  | TOWER B 1404 COMMON WORK | TOWER B 1404 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35128 |  |  |  | TOWER B 1404 COMMON WORK | TOWER B 1404 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29276 |  |  |  | TOWER B 14TH FLOOR | TOWER B 14TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29279 |  |  |  | TOWER B 14TH FLOOR COMMON WORK | TOWER B 14TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29277 |  |  |  | TOWER B 14TH FLOOR COMMON WORK | TOWER B 14TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41975 |  |  |  | TOWER B 14TH FLOOR COMMON FLOORING WORK | TOWER B 14TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29278 |  |  |  | TOWER B 14TH FLOOR COMMON WORK | TOWER B 14TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29280 |  |  |  | TOWER B 14TH FLOOR COMMON WORK | TOWER B 14TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42065 |  |  |  | TOWER B 14TH FLOOR COMMON FALSE CEILING WORK | TOWER B 14TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29488 |  |  |  | TOWER B 14TH FLOOR COMMON WORK | TOWER B 14TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33070 |  |  |  | TOWER B 14TH FLOOR COMMON ELECTRIC WORK | TOWER B 14TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42317 |  |  |  | TOWER B 14TH FLOOR COMMON WORK | TOWER B 14TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42318 |  |  |  | TOWER B 14TH FLOOR WPC PANNELING WORK | TOWER B 14TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24440 |  |  |  | TOWER B | TOWER B 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24441 |  |  |  | TOWER B 15TH FLOOR | TOWER B 15TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24442 |  |  |  | TOWER B 15TH FLOOR CIVIL WORK | TOWER B 15TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24445 |  |  |  | TOWER B 15TH FLOOR RCC WORK | TOWER B 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24443 |  |  |  | TOWER B 15TH FLOOR CIVIL WORK | TOWER B 15TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24446 |  |  |  | TOWER B 15TH FLOOR MASONRY WORK | TOWER B 15TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Task | 6 | 39372 |  |  |  | TOWER B 15TH FLOOR MASONRY WORK | TOWER B 15TH FLOOR MASONRY WORK REBARING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | REBARING WORK
Group | 5 | 24444 |  |  |  | TOWER B 15TH FLOOR CIVIL WORK | TOWER B 15TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24447 |  |  |  | TOWER B 15TH FLOOR PLASTER WORK | TOWER B 15TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29039 |  |  |  | TOWER B 15TH FLOOR | TOWER B 1501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29031 |  |  |  | TOWER B 1501 | TOWER B 1501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40383 |  |  |  | TOWER B 1501 WATERPROOFING WORK | TOWER B 1501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29033 |  |  |  | TOWER B 1501 | TOWER B 1501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41168 |  |  |  | TOWER B 1501 PLUMBING WORK | TOWER B 1501 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29032 |  |  |  | TOWER B 1501 | TOWER B 1501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40469 |  |  |  | TOWER B 1501 ELECTRIC WORK | TOWER B 1501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29034 |  |  |  | TOWER B 1501 | TOWER B 1501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41757 |  |  |  | TOWER B 1501 FLOORING & DEDO WORK | TOWER B 1501 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29037 |  |  |  | TOWER B 1501 | TOWER B 1501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40908 |  |  |  | TOWER B 1501 CARPENTRY WORK | TOWER B 1501 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29035 |  |  |  | TOWER B 1501 | TOWER B 1501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29036 |  |  |  | TOWER B 1501 | TOWER B 1501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29038 |  |  |  | TOWER B 1501 | TOWER B 1501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35129 |  |  |  | TOWER B 1501 | TOWER B 1501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35130 |  |  |  | TOWER B 1501 COMMON WORK | TOWER B 1501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35131 |  |  |  | TOWER B 1501 COMMON WORK | TOWER B 1501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35132 |  |  |  | TOWER B 1501 COMMON WORK | TOWER B 1501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29048 |  |  |  | TOWER B 15TH FLOOR | TOWER B 1502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29040 |  |  |  | TOWER B 1502 | TOWER B 1502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40384 |  |  |  | TOWER B 1502 WATERPROOFING WORK | TOWER B 1502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29042 |  |  |  | TOWER B 1502 | TOWER B 1502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41169 |  |  |  | TOWER B 1502 PLUMBING WORK | TOWER B 1502 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29041 |  |  |  | TOWER B 1502 | TOWER B 1502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40470 |  |  |  | TOWER B 1502 ELECTRIC WORK | TOWER B 1502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29043 |  |  |  | TOWER B 1502 | TOWER B 1502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41758 |  |  |  | TOWER B 1502 FLOORING & DEDO WORK | TOWER B 1502 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29046 |  |  |  | TOWER B 1502 | TOWER B 1502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40909 |  |  |  | TOWER B 1502 CARPENTRY WORK | TOWER B 1502 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29044 |  |  |  | TOWER B 1502 | TOWER B 1502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29045 |  |  |  | TOWER B 1502 | TOWER B 1502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29047 |  |  |  | TOWER B 1502 | TOWER B 1502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35133 |  |  |  | TOWER B 1502 | TOWER B 1502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35134 |  |  |  | TOWER B 1502 COMMON WORK | TOWER B 1502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35135 |  |  |  | TOWER B 1502 COMMON WORK | TOWER B 1502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35136 |  |  |  | TOWER B 1502 COMMON WORK | TOWER B 1502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29057 |  |  |  | TOWER B 15TH FLOOR | TOWER B 1503 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29049 |  |  |  | TOWER B 1503 | TOWER B 1503 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40385 |  |  |  | TOWER B 1503 WATERPROOFING WORK | TOWER B 1503 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29051 |  |  |  | TOWER B 1503 | TOWER B 1503 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41170 |  |  |  | TOWER B 1503 PLUMBING WORK | TOWER B 1503 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29050 |  |  |  | TOWER B 1503 | TOWER B 1503 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40471 |  |  |  | TOWER B 1503 ELECTRIC WORK | TOWER B 1503 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29052 |  |  |  | TOWER B 1503 | TOWER B 1503 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41759 |  |  |  | TOWER B 1503 FLOORING & DEDO WORK | TOWER B 1503 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29055 |  |  |  | TOWER B 1503 | TOWER B 1503 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40910 |  |  |  | TOWER B 1503 CARPENTRY WORK | TOWER B 1503 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29053 |  |  |  | TOWER B 1503 | TOWER B 1503 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29054 |  |  |  | TOWER B 1503 | TOWER B 1503 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29056 |  |  |  | TOWER B 1503 | TOWER B 1503 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35137 |  |  |  | TOWER B 1503 | TOWER B 1503 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35138 |  |  |  | TOWER B 1503 COMMON WORK | TOWER B 1503 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35139 |  |  |  | TOWER B 1503 COMMON WORK | TOWER B 1503 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35140 |  |  |  | TOWER B 1503 COMMON WORK | TOWER B 1503 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29066 |  |  |  | TOWER B 15TH FLOOR | TOWER B 1504 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29058 |  |  |  | TOWER B 1504 | TOWER B 1504 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40386 |  |  |  | TOWER B 1504 WATERPROOFING WORK | TOWER B 1504 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29060 |  |  |  | TOWER B 1504 | TOWER B 1504 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41171 |  |  |  | TOWER B 1504 PLUMBING WORK | TOWER B 1504 PLUMBING WORK | 1 | NOS | 1 | NOS | 508.68 |  | Tentative | 508.68 | 0 | 508.68 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29059 |  |  |  | TOWER B 1504 | TOWER B 1504 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40472 |  |  |  | TOWER B 1504 ELECTRIC WORK | TOWER B 1504 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29061 |  |  |  | TOWER B 1504 | TOWER B 1504 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41760 |  |  |  | TOWER B 1504 FLOORING & DEDO WORK | TOWER B 1504 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 1914 |  | Tentative | 0 | 1914 | 1914 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29064 |  |  |  | TOWER B 1504 | TOWER B 1504 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40911 |  |  |  | TOWER B 1504 CARPENTRY WORK | TOWER B 1504 CARPENTRY WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29062 |  |  |  | TOWER B 1504 | TOWER B 1504 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29063 |  |  |  | TOWER B 1504 | TOWER B 1504 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29065 |  |  |  | TOWER B 1504 | TOWER B 1504 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35141 |  |  |  | TOWER B 1504 | TOWER B 1504 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35142 |  |  |  | TOWER B 1504 COMMON WORK | TOWER B 1504 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 8960 |  | Tentative | 0 | 8960 | 8960 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35143 |  |  |  | TOWER B 1504 COMMON WORK | TOWER B 1504 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35144 |  |  |  | TOWER B 1504 COMMON WORK | TOWER B 1504 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29281 |  |  |  | TOWER B 15TH FLOOR | TOWER B 15TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29284 |  |  |  | TOWER B 15TH FLOOR COMMON WORK | TOWER B 15TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29282 |  |  |  | TOWER B 15TH FLOOR COMMON WORK | TOWER B 15TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41976 |  |  |  | TOWER B 15TH FLOOR COMMON FLOORING WORK | TOWER B 15TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29283 |  |  |  | TOWER B 15TH FLOOR COMMON WORK | TOWER B 15TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29285 |  |  |  | TOWER B 15TH FLOOR COMMON WORK | TOWER B 15TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42066 |  |  |  | TOWER B 15TH FLOOR COMMON FALSE CEILING WORK | TOWER B 15TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29489 |  |  |  | TOWER B 15TH FLOOR COMMON WORK | TOWER B 15TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33071 |  |  |  | TOWER B 15TH FLOOR COMMON ELECTRIC WORK | TOWER B 15TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42319 |  |  |  | TOWER B 15TH FLOOR COMMON WORK | TOWER B 15TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42320 |  |  |  | TOWER B 15TH FLOOR WPC PANNELING WORK | TOWER B 15TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24448 |  |  |  | TOWER B | TOWER B 16TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24449 |  |  |  | TOWER B 16TH FLOOR | TOWER B 16TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24450 |  |  |  | TOWER B 16TH FLOOR CIVIL WORK | TOWER B 16TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24453 |  |  |  | TOWER B 16TH FLOOR RCC WORK | TOWER B 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24451 |  |  |  | TOWER B 16TH FLOOR CIVIL WORK | TOWER B 16TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24454 |  |  |  | TOWER B 16TH FLOOR MASONRY WORK | TOWER B 16TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24452 |  |  |  | TOWER B 16TH FLOOR CIVIL WORK | TOWER B 16TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24455 |  |  |  | TOWER B 16TH FLOOR PLASTER WORK | TOWER B 16TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29075 |  |  |  | TOWER B 16TH FLOOR | TOWER B 1601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29068 |  |  |  | TOWER B 1601 | TOWER B 1601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40473 |  |  |  | TOWER B 1601 ELECTRIC WORK | TOWER B 1601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 42120 |  |  |  | TOWER B 1601 | TOWER B 1601 CARPENTRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42121 |  |  |  | TOWER B 1601 CARPENTRY WORK | TOWER B 1601 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 4 | 29084 |  |  |  | TOWER B 16TH FLOOR | TOWER B 1602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29077 |  |  |  | TOWER B 1602 | TOWER B 1602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40474 |  |  |  | TOWER B 1602 ELECTRIC WORK | TOWER B 1602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 42122 |  |  |  | TOWER B 1602 | TOWER B 1602 CARPENTRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42123 |  |  |  | TOWER B 1602 CARPENTRY WORK | TOWER B 1602 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 4 | 29093 |  |  |  | TOWER B 16TH FLOOR | TOWER B 1603 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29086 |  |  |  | TOWER B 1603 | TOWER B 1603 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40475 |  |  |  | TOWER B 1603 ELECTRIC WORK | TOWER B 1603 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 4 | 29102 |  |  |  | TOWER B 16TH FLOOR | TOWER B 1604 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29095 |  |  |  | TOWER B 1604 | TOWER B 1604 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40476 |  |  |  | TOWER B 1604 ELECTRIC WORK | TOWER B 1604 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 4 | 29286 |  |  |  | TOWER B 16TH FLOOR | TOWER B 16TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29287 |  |  |  | TOWER B 16TH FLOOR COMMON WORK | TOWER B 16TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41977 |  |  |  | TOWER B 16TH FLOOR COMMON FLOORING WORK | TOWER B 16TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29288 |  |  |  | TOWER B 16TH FLOOR COMMON WORK | TOWER B 16TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29290 |  |  |  | TOWER B 16TH FLOOR COMMON WORK | TOWER B 16TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42067 |  |  |  | TOWER B 16TH FLOOR COMMON FALSE CEILING WORK | TOWER B 16TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29490 |  |  |  | TOWER B 16TH FLOOR COMMON WORK | TOWER B 16TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33072 |  |  |  | TOWER B 16TH FLOOR COMMON ELECTRIC WORK | TOWER B 16TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42321 |  |  |  | TOWER B 16TH FLOOR COMMON WORK | TOWER B 16TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42322 |  |  |  | TOWER B 16TH FLOOR WPC PANNELING WORK | TOWER B 16TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24456 |  |  |  | TOWER B | TOWER B 17TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24457 |  |  |  | TOWER B 17TH FLOOR | TOWER B 17TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24458 |  |  |  | TOWER B 17TH FLOOR CIVIL WORK | TOWER B 17TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24461 |  |  |  | TOWER B 17TH FLOOR RCC WORK | TOWER B 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24459 |  |  |  | TOWER B 17TH FLOOR CIVIL WORK | TOWER B 17TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24462 |  |  |  | TOWER B 17TH FLOOR MASONRY WORK | TOWER B 17TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24460 |  |  |  | TOWER B 17TH FLOOR CIVIL WORK | TOWER B 17TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24463 |  |  |  | TOWER B 17TH FLOOR PLASTER WORK | TOWER B 17TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29111 |  |  |  | TOWER B 17TH FLOOR | TOWER B 1701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29103 |  |  |  | TOWER B 1701 | TOWER B 1701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29105 |  |  |  | TOWER B 1701 | TOWER B 1701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29104 |  |  |  | TOWER B 1701 | TOWER B 1701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40477 |  |  |  | TOWER B 1701 ELECTRIC WORK | TOWER B 1701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29106 |  |  |  | TOWER B 1701 | TOWER B 1701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29109 |  |  |  | TOWER B 1701 | TOWER B 1701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42124 |  |  |  | TOWER B 1701 CARPENTRY WORK | TOWER B 1701 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29107 |  |  |  | TOWER B 1701 | TOWER B 1701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29108 |  |  |  | TOWER B 1701 | TOWER B 1701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29110 |  |  |  | TOWER B 1701 | TOWER B 1701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35161 |  |  |  | TOWER B 1701 | TOWER B 1701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35162 |  |  |  | TOWER B 1701 COMMON WORK | TOWER B 1701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35163 |  |  |  | TOWER B 1701 COMMON WORK | TOWER B 1701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35164 |  |  |  | TOWER B 1701 COMMON WORK | TOWER B 1701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29120 |  |  |  | TOWER B 17TH FLOOR | TOWER B 1702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29112 |  |  |  | TOWER B 1702 | TOWER B 1702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29114 |  |  |  | TOWER B 1702 | TOWER B 1702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29113 |  |  |  | TOWER B 1702 | TOWER B 1702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40478 |  |  |  | TOWER B 1702 ELECTRIC WORK | TOWER B 1702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29115 |  |  |  | TOWER B 1702 | TOWER B 1702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29118 |  |  |  | TOWER B 1702 | TOWER B 1702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42125 |  |  |  | TOWER B 1702 CARPENTRY WORK | TOWER B 1702 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29116 |  |  |  | TOWER B 1702 | TOWER B 1702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29117 |  |  |  | TOWER B 1702 | TOWER B 1702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29119 |  |  |  | TOWER B 1702 | TOWER B 1702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35165 |  |  |  | TOWER B 1702 | TOWER B 1702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35166 |  |  |  | TOWER B 1702 COMMON WORK | TOWER B 1702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35167 |  |  |  | TOWER B 1702 COMMON WORK | TOWER B 1702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35168 |  |  |  | TOWER B 1702 COMMON WORK | TOWER B 1702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29129 |  |  |  | TOWER B 17TH FLOOR | TOWER B 1703 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29121 |  |  |  | TOWER B 1703 | TOWER B 1703 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29123 |  |  |  | TOWER B 1703 | TOWER B 1703 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29122 |  |  |  | TOWER B 1703 | TOWER B 1703 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40479 |  |  |  | TOWER B 1703 ELECTRIC WORK | TOWER B 1703 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29124 |  |  |  | TOWER B 1703 | TOWER B 1703 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29127 |  |  |  | TOWER B 1703 | TOWER B 1703 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42126 |  |  |  | TOWER B 1703 CARPENTRY WORK | TOWER B 1703 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29125 |  |  |  | TOWER B 1703 | TOWER B 1703 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29126 |  |  |  | TOWER B 1703 | TOWER B 1703 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29128 |  |  |  | TOWER B 1703 | TOWER B 1703 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35169 |  |  |  | TOWER B 1703 | TOWER B 1703 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35170 |  |  |  | TOWER B 1703 COMMON WORK | TOWER B 1703 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35171 |  |  |  | TOWER B 1703 COMMON WORK | TOWER B 1703 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35172 |  |  |  | TOWER B 1703 COMMON WORK | TOWER B 1703 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29138 |  |  |  | TOWER B 17TH FLOOR | TOWER B 1704 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29130 |  |  |  | TOWER B 1704 | TOWER B 1704 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29132 |  |  |  | TOWER B 1704 | TOWER B 1704 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29131 |  |  |  | TOWER B 1704 | TOWER B 1704 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40481 |  |  |  | TOWER B 1704 ELECTRIC WORK | TOWER B 1704 ELECTRIC WORK | 1 | NOS | 1 | NOS | 256.06 |  | Tentative | 256.06 | 0 | 256.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29133 |  |  |  | TOWER B 1704 | TOWER B 1704 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29136 |  |  |  | TOWER B 1704 | TOWER B 1704 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42127 |  |  |  | TOWER B 1704 CARPENTRY WORK | TOWER B 1704 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29134 |  |  |  | TOWER B 1704 | TOWER B 1704 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29135 |  |  |  | TOWER B 1704 | TOWER B 1704 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29137 |  |  |  | TOWER B 1704 | TOWER B 1704 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35173 |  |  |  | TOWER B 1704 | TOWER B 1704 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35174 |  |  |  | TOWER B 1704 COMMON WORK | TOWER B 1704 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35175 |  |  |  | TOWER B 1704 COMMON WORK | TOWER B 1704 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35176 |  |  |  | TOWER B 1704 COMMON WORK | TOWER B 1704 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29291 |  |  |  | TOWER B 17TH FLOOR | TOWER B 17TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29294 |  |  |  | TOWER B 17TH FLOOR COMMON WORK | TOWER B 17TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29292 |  |  |  | TOWER B 17TH FLOOR COMMON WORK | TOWER B 17TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41978 |  |  |  | TOWER B 17TH FLOOR COMMON FLOORING WORK | TOWER B 17TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29293 |  |  |  | TOWER B 17TH FLOOR COMMON WORK | TOWER B 17TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29295 |  |  |  | TOWER B 17TH FLOOR COMMON WORK | TOWER B 17TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42068 |  |  |  | TOWER B 17TH FLOOR COMMON FALSE CEILING WORK | TOWER B 17TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29491 |  |  |  | TOWER B 17TH FLOOR COMMON WORK | TOWER B 17TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33073 |  |  |  | TOWER B 17TH FLOOR COMMON ELECTRIC WORK | TOWER B 17TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42323 |  |  |  | TOWER B 17TH FLOOR COMMON WORK | TOWER B 17TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42324 |  |  |  | TOWER B 17TH FLOOR WPC PANNELING WORK | TOWER B 17TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24464 |  |  |  | TOWER B | TOWER B 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24465 |  |  |  | TOWER B 18TH FLOOR | TOWER B 18TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24466 |  |  |  | TOWER B 18TH FLOOR CIVIL WORK | TOWER B 18TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24469 |  |  |  | TOWER B 18TH FLOOR RCC WORK | TOWER B 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24467 |  |  |  | TOWER B 18TH FLOOR CIVIL WORK | TOWER B 18TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24470 |  |  |  | TOWER B 18TH FLOOR MASONRY WORK | TOWER B 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24468 |  |  |  | TOWER B 18TH FLOOR CIVIL WORK | TOWER B 18TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24471 |  |  |  | TOWER B 18TH FLOOR PLASTER WORK | TOWER B 18TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Tentative | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29147 |  |  |  | TOWER B 18TH FLOOR | TOWER B 1801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29139 |  |  |  | TOWER B 1801 | TOWER B 1801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29141 |  |  |  | TOWER B 1801 | TOWER B 1801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29140 |  |  |  | TOWER B 1801 | TOWER B 1801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40482 |  |  |  | TOWER B 1801 ELECTRIC WORK | TOWER B 1801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29142 |  |  |  | TOWER B 1801 | TOWER B 1801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29145 |  |  |  | TOWER B 1801 | TOWER B 1801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42128 |  |  |  | TOWER B 1801 CARPENTRY WORK | TOWER B 1801 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29143 |  |  |  | TOWER B 1801 | TOWER B 1801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29144 |  |  |  | TOWER B 1801 | TOWER B 1801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29146 |  |  |  | TOWER B 1801 | TOWER B 1801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35177 |  |  |  | TOWER B 1801 | TOWER B 1801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35178 |  |  |  | TOWER B 1801 COMMON WORK | TOWER B 1801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35179 |  |  |  | TOWER B 1801 COMMON WORK | TOWER B 1801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35180 |  |  |  | TOWER B 1801 COMMON WORK | TOWER B 1801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29156 |  |  |  | TOWER B 18TH FLOOR | TOWER B 1802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29148 |  |  |  | TOWER B 1802 | TOWER B 1802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29150 |  |  |  | TOWER B 1802 | TOWER B 1802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29149 |  |  |  | TOWER B 1802 | TOWER B 1802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40483 |  |  |  | TOWER B 1802 ELECTRIC WORK | TOWER B 1802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29151 |  |  |  | TOWER B 1802 | TOWER B 1802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29154 |  |  |  | TOWER B 1802 | TOWER B 1802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42129 |  |  |  | TOWER B 1802 CARPENTRY WORK | TOWER B 1802 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29152 |  |  |  | TOWER B 1802 | TOWER B 1802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29153 |  |  |  | TOWER B 1802 | TOWER B 1802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29155 |  |  |  | TOWER B 1802 | TOWER B 1802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35181 |  |  |  | TOWER B 1802 | TOWER B 1802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35182 |  |  |  | TOWER B 1802 COMMON WORK | TOWER B 1802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35183 |  |  |  | TOWER B 1802 COMMON WORK | TOWER B 1802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35184 |  |  |  | TOWER B 1802 COMMON WORK | TOWER B 1802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29165 |  |  |  | TOWER B 18TH FLOOR | TOWER B 1803 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29157 |  |  |  | TOWER B 1803 | TOWER B 1803 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29159 |  |  |  | TOWER B 1803 | TOWER B 1803 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29158 |  |  |  | TOWER B 1803 | TOWER B 1803 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40484 |  |  |  | TOWER B 1803 ELECTRIC WORK | TOWER B 1803 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29160 |  |  |  | TOWER B 1803 | TOWER B 1803 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29163 |  |  |  | TOWER B 1803 | TOWER B 1803 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42130 |  |  |  | TOWER B 1803 CARPENTRY WORK | TOWER B 1803 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29161 |  |  |  | TOWER B 1803 | TOWER B 1803 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29162 |  |  |  | TOWER B 1803 | TOWER B 1803 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29164 |  |  |  | TOWER B 1803 | TOWER B 1803 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35185 |  |  |  | TOWER B 1803 | TOWER B 1803 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35186 |  |  |  | TOWER B 1803 COMMON WORK | TOWER B 1803 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35187 |  |  |  | TOWER B 1803 COMMON WORK | TOWER B 1803 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35188 |  |  |  | TOWER B 1803 COMMON WORK | TOWER B 1803 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29174 |  |  |  | TOWER B 18TH FLOOR | TOWER B 1804 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29166 |  |  |  | TOWER B 1804 | TOWER B 1804 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29168 |  |  |  | TOWER B 1804 | TOWER B 1804 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29167 |  |  |  | TOWER B 1804 | TOWER B 1804 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40485 |  |  |  | TOWER B 1804 ELECTRIC WORK | TOWER B 1804 ELECTRIC WORK | 1 | NOS | 1 | NOS | 254.88 |  | Tentative | 254.88 | 0 | 254.88 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29169 |  |  |  | TOWER B 1804 | TOWER B 1804 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29172 |  |  |  | TOWER B 1804 | TOWER B 1804 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42131 |  |  |  | TOWER B 1804 CARPENTRY WORK | TOWER B 1804 CARPENTRY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INTERNAL CARPENTRY WORK
Group | 5 | 29170 |  |  |  | TOWER B 1804 | TOWER B 1804 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29171 |  |  |  | TOWER B 1804 | TOWER B 1804 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29173 |  |  |  | TOWER B 1804 | TOWER B 1804 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 35189 |  |  |  | TOWER B 1804 | TOWER B 1804 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 35190 |  |  |  | TOWER B 1804 COMMON WORK | TOWER B 1804 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 35191 |  |  |  | TOWER B 1804 COMMON WORK | TOWER B 1804 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 35192 |  |  |  | TOWER B 1804 COMMON WORK | TOWER B 1804 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 29296 |  |  |  | TOWER B 18TH FLOOR | TOWER B 18TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29299 |  |  |  | TOWER B 18TH FLOOR COMMON WORK | TOWER B 18TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29297 |  |  |  | TOWER B 18TH FLOOR COMMON WORK | TOWER B 18TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41979 |  |  |  | TOWER B 18TH FLOOR COMMON FLOORING WORK | TOWER B 18TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29298 |  |  |  | TOWER B 18TH FLOOR COMMON WORK | TOWER B 18TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29300 |  |  |  | TOWER B 18TH FLOOR COMMON WORK | TOWER B 18TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42069 |  |  |  | TOWER B 18TH FLOOR COMMON FALSE CEILING WORK | TOWER B 18TH FLOOR FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FALSE CEILING WORK
Group | 5 | 29492 |  |  |  | TOWER B 18TH FLOOR COMMON WORK | TOWER B 18TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33074 |  |  |  | TOWER B 18TH FLOOR COMMON ELECTRIC WORK | TOWER B 18TH FLOOR COMMON ELECTRIC WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | SLAB CONDUTE
Group | 5 | 42325 |  |  |  | TOWER B 18TH FLOOR COMMON WORK | TOWER B 18TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42326 |  |  |  | TOWER B 18TH FLOOR WPC PANNELING WORK | TOWER B 18TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 41493 |  |  |  | TOWER B | TOWER B TERRACE | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41494 |  |  |  | TOWER B TERRACE | TOWER B TERRACE CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41495 |  |  |  | TOWER B TERRACE CIVIL WORK | TOWER B TERRACE RCC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41498 |  |  |  | TOWER B TERRACE RCC WORK | TOWER B TERRACE RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 41496 |  |  |  | TOWER B TERRACE CIVIL WORK | TOWER B TERRACE MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41499 |  |  |  | TOWER B TERRACE MASONRY WORK | TOWER B TERRACE MASONRY WORK | 1 | SQFT | 1 | SQFT | 640621.7 |  | Tentative | 640621.7 | 0 | 640621.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 41497 |  |  |  | TOWER B TERRACE CIVIL WORK | TOWER B TERRACE PLASTER WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41500 |  |  |  | TOWER B TERRACE PLASTER WORK | TOWER B TERRACE PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 41444 |  |  |  | TOWER B | TOWER B COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41445 |  |  |  | TOWER B COMMON WORK | TOWER B COMMON PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41453 |  |  |  | TOWER B COMMON PLUMBING WORK | TOWER B COMMON DUCT PLUMBING WORK | 1 | NOS | 1 | NOS | 586.46 |  | Tentative | 586.46 | 0 | 586.46 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING DUCT-PVC-SWR DRAINAGE PIPING WO
Group | 4 | 41475 |  |  |  | TOWER B COMMON WORK | TOWER B COMMON ELECTRIC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41476 |  |  |  | TOWER B COMMON ELECTRIC WORK | TOWER B COMMON ELECTRIC WORK | 1 | POINT | 1 | POINT | 217.9 | ELECTRIC WORK | Tentative | 217.9 | 0 | 217.9 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | TOWER COMMON ELECTRIC WORK
Group | 4 | 42151 | Block/Building/Tower/Wing |  | Externall Plaster | TOWER B COMMON WORK | TOWER B EXTERNAL PAINT WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 42152 |  |  |  | TOWER B EXTERNAL PAINT WORK | TOWER B EXTERNAL PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | EXTERNAL PAINT WORK
Group | 2 | 24078 |  |  |  |  | TOWER C | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 3 | 24100 |  |  |  | TOWER C | TOWER C BASEMENT | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24101 |  |  |  | TOWER C BASEMENT | TOWER C BASEMENT CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24102 |  |  |  | TOWER C BASEMENT CIVIL WORK | TOWER C BASEMENT RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24104 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 251167.09 |  | Started | 251167.09 | 0 | 251167.09 | 19.74 | 4958426.41 | 16019148.98 | 5596136.43 | 21615285.41 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 25356 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 52298.8 | 52298.8 | 17 Mar 2020 |  | 16 Jul 2021 |  | - | - | 487 | - | THREADING
Task | 6 | 26043 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 178 |  | Started | 0 | 178 | 178 | 0 | 0.18 | 0 | 179489.8 | 179489.8 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | REBARING WORK
Task | 6 | 25601 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT CIVIL WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | COMMON WORK
Group | 5 | 24103 |  |  |  | TOWER C BASEMENT CIVIL WORK | TOWER C BASEMENT PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24105 |  |  |  | TOWER C BASEMENT PLASTER WORK | TOWER C BASEMENT PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Started | 500 | 0 | 500 | 19.74 | 9870.77 | 0 | 1152572.37 | 1152572.37 |  |  | 21 Mar 2024 |  | - | - | - | - | PLASTER WORK
Group | 5 | 38137 |  |  |  | TOWER C BASEMENT CIVIL WORK | TOWER C BASEMENT MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 May 2023 |  | - | - | 1171 | -
Task | 6 | 38138 |  |  |  | TOWER C BASEMENT MASONRY WORK | TOWER C BASEMENT MASONRY WORK | 1 | SQFT | 1 | SQFT | 15200 |  | Started | 15200 | 0 | 15200 | 0 | 15.2 | 0 | 4248 | 4248 | 17 Mar 2020 |  | 31 May 2023 |  | - | - | 1171 | - | MASONRY WORK
Group | 4 | 24860 |  |  |  | TOWER C BASEMENT | TOWER C BASEMENT FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | -
Group | 5 | 24871 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | -
Task | 6 | 24861 |  |  |  | TOWER C BASEMENT WATERPROOFING WORK | TOWER C BASEMENT WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 9.5 | 0 | 0 | 226020 | 226020 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | - | WATERPROOFING WORK
Group | 5 | 29316 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29317 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29318 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29319 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29320 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29321 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 25600 |  |  |  | TOWER C BASEMENT | TOWER C BASEMENT COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 29322 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29323 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29324 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29856 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 25894 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 25895 |  |  |  | TOWER C BASEMENT COMMON ELECTRIC WORK | TOWER C BASEMENT COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 46079 | 46079 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | ELECTRIC WORK
Group | 3 | 24121 |  |  |  | TOWER C | TOWER C GROUND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24122 |  |  |  | TOWER C GROUND FLOOR | TOWER C GROUND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24123 |  |  |  | TOWER C GROUND FLOOR CIVIL WORK | TOWER C GROUND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24126 |  |  |  | TOWER C GROUND FLOOR RCC WORK | TOWER C GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 42126.44 |  | Started | 42126.44 | 0 | 42126.44 | 5.72 | 240937.03 | 3238983.74 | 1090159.53 | 4329143.27 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 25980 |  |  |  | TOWER C GROUND FLOOR RCC WORK | TOWER C GROUND FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 65822.24 | 65822.24 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Group | 5 | 24124 |  |  |  | TOWER C GROUND FLOOR CIVIL WORK | TOWER C GROUND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24127 |  |  |  | TOWER C GROUND FLOOR MASONRY WORK | TOWER C GROUND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 17000 |  | Tentative | 17000 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24125 |  |  |  | TOWER C GROUND FLOOR CIVIL WORK | TOWER C GROUND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 09 Feb 2023 |  | - | - | - | -
Task | 6 | 24128 |  |  |  | TOWER C GROUND FLOOR PLASTER WORK | TOWER C GROUND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 920 |  | Started | 920 | 0 | 920 | 5.77 | 5310.04 | 0 | 208898.06 | 208898.06 |  |  | 09 Feb 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 30337 |  |  |  | TOWER C GROUND FLOOR | TOWER C GROUND FLOOR FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30339 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 30338 |  |  |  | TOWER C GROUND FLOOR WATERPROOFING WORK | TOWER C GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30342 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30340 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 30341 |  |  |  | TOWER C GROUND FLOOR ELECTRIC WORK | TOWER C GROUND FLOOR ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30343 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30346 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30344 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30345 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32906 |  |  |  | TOWER C GROUND FLOOR PAINT WORK | TOWER C GROUND FLOOR PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PAINT WORK
Group | 5 | 30347 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 29326 |  |  |  | TOWER C GROUND FLOOR | TOWER C GROUND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Nov 2021 |  | - | - | 614 | -
Group | 5 | 29329 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32589 |  |  |  | TOWER C GROUND FLOOR COMMON DEBRISH CHUTE WORK | TOWER C GROUND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29327 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29328 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29330 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26453 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Nov 2021 |  | - | - | 614 | -
Task | 6 | 26454 |  |  |  | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Nov 2021 |  | - | - | 614 | - | ELECTRIC WORK
Group | 3 | 24280 |  |  |  | TOWER C | TOWER C 1ST FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24281 |  |  |  | TOWER C 1ST FLOOR | TOWER C 1ST FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24282 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24285 |  |  |  | TOWER C 1ST FLOOR RCC WORK | TOWER C 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 42840.96 |  | Started | 42840.96 | 0 | 42840.96 | 5.77 | 247268.6 | 2820372.19 | 1114945.21 | 3935317.4 |  |  | 01 Nov 2021 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 26644 |  |  |  | TOWER C 1ST FLOOR RCC WORK | TOWER C 1ST FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 25390.8 | 25390.8 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 31077 |  |  |  | TOWER C 1ST FLOOR RCC WORK | TOWER C 1ST FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 525 |  | Started | 525 | 0 | 525 | 0 | 0.53 | 0 | 135529.64 | 135529.64 | 17 Mar 2020 |  | 20 Apr 2022 |  | - | - | 765 | - | FIRE AND SAFETY WORK
Group | 5 | 24283 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 Jul 2022 |  | - | - | - | -
Task | 6 | 24286 |  |  |  | TOWER C 1ST FLOOR MASONRY WORK | TOWER C 1ST FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 341125.5 |  | Started | 341125.5 | 0 | 341125.5 | 5.77 | 1968901.34 | 0 | 299750.24 | 299750.24 |  |  | 13 Jul 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24284 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15 Apr 2023 |  | - | - | - | -
Task | 6 | 24287 |  |  |  | TOWER C 1ST FLOOR PLASTER WORK | TOWER C 1ST FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.77 | 15543.4 | 0 | 284882.24 | 284882.24 |  |  | 15 Apr 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39317 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR EXTRA CIVIL WOK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39318 |  |  |  | TOWER C 1ST FLOOR EXTRA CIVIL WOK | TOWER C 1ST FLOOR EXTRA CIVIL WOK MASONRY WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 5524.28 | 5524.28 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29504 |  |  |  | TOWER C 1ST FLOOR | TOWER C 101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29496 |  |  |  | TOWER C 101 | TOWER C 101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33572 |  |  |  | TOWER C 101 WATERPROOFING WORK | TOWER C 101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38633 |  |  |  | TOWER C 101 WATERPROOFING WORK | TOWER C 101 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29498 |  |  |  | TOWER C 101 | TOWER C 101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33000 |  |  |  | TOWER C 101 PLUMBING WORK | TOWER C 101 PLUMBING WORK | 1 | NOS | 0 | NOS | 773.94 |  | Tentative | 773.94 | 0 | 773.94 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41539 |  |  |  | TOWER C 101 PLUMBING WORK | TOWER C 101 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29497 |  |  |  | TOWER C 101 | TOWER C 101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33812 |  |  |  | TOWER C 101 ELECTRIC WORK | TOWER C 101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29499 |  |  |  | TOWER C 101 | TOWER C 101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41020 |  |  |  | TOWER C 101 FLOORING & DEDO WORK | TOWER C 101 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4252.436 |  | Started | 1172.44 | 3080 | 4252.44 | 0 | 4.25 | 0 | 16000 | 16000 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29502 |  |  |  | TOWER C 101 | TOWER C 101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33100 |  |  |  | TOWER C 101 CARPENTRY WORK | TOWER C 101 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29500 |  |  |  | TOWER C 101 | TOWER C 101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29501 |  |  |  | TOWER C 101 | TOWER C 101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29503 |  |  |  | TOWER C 101 | TOWER C 101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34325 |  |  |  | TOWER C 101 | TOWER C 101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34326 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34327 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | PVC FALSE CEILING
Task | 6 | 34328 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40277 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29513 |  |  |  | TOWER C 1ST FLOOR | TOWER C 102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29505 |  |  |  | TOWER C 102 | TOWER C 102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33573 |  |  |  | TOWER C 102 WATERPROOFING WORK | TOWER C 102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38634 |  |  |  | TOWER C 102 WATERPROOFING WORK | TOWER C 102 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29507 |  |  |  | TOWER C 102 | TOWER C 102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33001 |  |  |  | TOWER C 102 PLUMBING WORK | TOWER C 102 PLUMBING WORK | 1 | NOS | 0 | NOS | 773.94 |  | Tentative | 773.94 | 0 | 773.94 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41540 |  |  |  | TOWER C 102 PLUMBING WORK | TOWER C 102 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29506 |  |  |  | TOWER C 102 | TOWER C 102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33813 |  |  |  | TOWER C 102 ELECTRIC WORK | TOWER C 102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29508 |  |  |  | TOWER C 102 | TOWER C 102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41021 |  |  |  | TOWER C 102 FLOORING & DEDO WORK | TOWER C 102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4252.436 |  | Started | 1172.44 | 3080 | 4252.44 | 0 | 4.25 | 0 | 34728.05 | 34728.05 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29511 |  |  |  | TOWER C 102 | TOWER C 102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33101 |  |  |  | TOWER C 102 CARPENTRY WORK | TOWER C 102 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29509 |  |  |  | TOWER C 102 | TOWER C 102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29510 |  |  |  | TOWER C 102 | TOWER C 102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29512 |  |  |  | TOWER C 102 | TOWER C 102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34329 |  |  |  | TOWER C 102 | TOWER C 102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34330 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34331 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34332 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40278 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29339 |  |  |  | TOWER C 1ST FLOOR | TOWER C 1ST FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 29342 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32591 |  |  |  | TOWER C 1ST FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 1ST FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29340 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41980 |  |  |  | TOWER C 1ST FLOOR COMMON FLOORING WORK | TOWER C 1ST FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29341 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29343 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26456 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 26457 |  |  |  | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40972 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40973 |  |  |  | TOWER C 1ST FLOOR WPC PANNELING WORK | TOWER C 1ST FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24288 |  |  |  | TOWER C | TOWER C 2ND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24289 |  |  |  | TOWER C 2ND FLOOR | TOWER C 2ND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24290 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24293 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 36146.76 |  | Started | 36146.76 | 0 | 36146.76 | 5.77 | 208631.15 | 2467366.21 | 1084020.21 | 3551386.42 |  |  | 01 Nov 2021 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 27047 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 35264.5 | 35264.5 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 38389 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6726 | 6726 | 17 Mar 2020 |  | 16 Jul 2023 |  | - | - | 1217 | - | SAFETY NET FIXING
Task | 6 | 42050 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 50 |  | Started | 0 | 50 | 50 | 0 | 0.05 | 0 | 16425.6 | 16425.6 | 17 Mar 2020 |  | 24 Oct 2024 |  | - | - | 1683 | - | REBARING WORK
Group | 5 | 24291 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2022 |  | - | - | - | -
Task | 6 | 24294 |  |  |  | TOWER C 2ND FLOOR MASONRY WORK | TOWER C 2ND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 313936.3 |  | Started | 313936.3 | 0 | 313936.3 | 5.77 | 1811971.26 | 0 | 291069.73 | 291069.73 |  |  | 01 Aug 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24292 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24295 |  |  |  | TOWER C 2ND FLOOR PLASTER WORK | TOWER C 2ND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.77 | 15543.4 | 0 | 276202.4 | 276202.4 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39319 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR EXTRA CIVIL WOK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39320 |  |  |  | TOWER C 2ND FLOOR EXTRA CIVIL WOK | TOWER C 2ND FLOOR EXTRA CIVIL WOK MASONRY WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 5524.28 | 5524.28 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29522 |  |  |  | TOWER C 2ND FLOOR | TOWER C 201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29514 |  |  |  | TOWER C 201 | TOWER C 201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33574 |  |  |  | TOWER C 201 WATERPROOFING WORK | TOWER C 201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38635 |  |  |  | TOWER C 201 WATERPROOFING WORK | TOWER C 201 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29516 |  |  |  | TOWER C 201 | TOWER C 201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33002 |  |  |  | TOWER C 201 PLUMBING WORK | TOWER C 201 PLUMBING WORK | 1 | NOS | 0 | NOS | 699.06 |  | Tentative | 699.06 | 0 | 699.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41541 |  |  |  | TOWER C 201 PLUMBING WORK | TOWER C 201 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29515 |  |  |  | TOWER C 201 | TOWER C 201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33814 |  |  |  | TOWER C 201 ELECTRIC WORK | TOWER C 201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29517 |  |  |  | TOWER C 201 | TOWER C 201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41770 |  |  |  | TOWER C 201 FLOORING & DEDO WORK | TOWER C 201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4012.436 |  | Started | 932.44 | 3080 | 4012.44 | 0 | 4.01 | 0 | 29430 | 29430 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29520 |  |  |  | TOWER C 201 | TOWER C 201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33102 |  |  |  | TOWER C 201 CARPENTRY WORK | TOWER C 201 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29518 |  |  |  | TOWER C 201 | TOWER C 201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29519 |  |  |  | TOWER C 201 | TOWER C 201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29521 |  |  |  | TOWER C 201 | TOWER C 201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34333 |  |  |  | TOWER C 201 | TOWER C 201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34334 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34335 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34336 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40279 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29531 |  |  |  | TOWER C 2ND FLOOR | TOWER C 202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29523 |  |  |  | TOWER C 202 | TOWER C 202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33575 |  |  |  | TOWER C 202 WATERPROOFING WORK | TOWER C 202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38636 |  |  |  | TOWER C 202 WATERPROOFING WORK | TOWER C 202 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29525 |  |  |  | TOWER C 202 | TOWER C 202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33003 |  |  |  | TOWER C 202 PLUMBING WORK | TOWER C 202 PLUMBING WORK | 1 | NOS | 0 | NOS | 699.06 |  | Tentative | 699.06 | 0 | 699.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41542 |  |  |  | TOWER C 202 PLUMBING WORK | TOWER C 202 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29524 |  |  |  | TOWER C 202 | TOWER C 202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33815 |  |  |  | TOWER C 202 ELECTRIC WORK | TOWER C 202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29526 |  |  |  | TOWER C 202 | TOWER C 202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41771 |  |  |  | TOWER C 202 FLOORING & DEDO WORK | TOWER C 202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4012.436 |  | Started | 932.44 | 3080 | 4012.44 | 0 | 4.01 | 0 | 0 | 0 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29529 |  |  |  | TOWER C 202 | TOWER C 202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33103 |  |  |  | TOWER C 202 CARPENTRY WORK | TOWER C 202 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29527 |  |  |  | TOWER C 202 | TOWER C 202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29528 |  |  |  | TOWER C 202 | TOWER C 202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29530 |  |  |  | TOWER C 202 | TOWER C 202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34337 |  |  |  | TOWER C 202 | TOWER C 202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34338 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34339 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34340 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40280 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29345 |  |  |  | TOWER C 2ND FLOOR | TOWER C 2ND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Group | 5 | 29348 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32590 |  |  |  | TOWER C 2ND FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 2ND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29346 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41981 |  |  |  | TOWER C 2ND FLOOR COMMON FLOORING WORK | TOWER C 2ND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29347 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29349 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26459 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 26460 |  |  |  | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40974 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40975 |  |  |  | TOWER C 2ND FLOOR WPC PANNELING WORK | TOWER C 2ND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24296 |  |  |  | TOWER C | TOWER C 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24297 |  |  |  | TOWER C 3RD FLOOR | TOWER C 3RD FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24298 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24301 |  |  |  | TOWER C 3RD FLOOR RCC WORK | TOWER C 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 37081.14 |  | Started | 37081.14 | 0 | 37081.14 | 5.72 | 212239.1 | 2458506.6 | 1081070.11 | 3539576.71 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 31084 |  |  |  | TOWER C 3RD FLOOR RCC WORK | TOWER C 3RD FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 43769.16 | 43769.16 | 17 Mar 2020 |  | 30 Mar 2022 |  | - | - | 744 | - | THREADING
Task | 6 | 39268 |  |  |  | TOWER C 3RD FLOOR RCC WORK | TOWER C 3RD FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FIRE AND SAFETY WORK
Group | 5 | 24299 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 06 Sep 2022 |  | - | - | - | -
Task | 6 | 24302 |  |  |  | TOWER C 3RD FLOOR MASONRY WORK | TOWER C 3RD FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 325825.95 |  | Started | 325825.95 | 0 | 325825.95 | 5.72 | 1863521.77 | 0 | 291069.73 | 291069.73 |  |  | 06 Sep 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24300 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24303 |  |  |  | TOWER C 3RD FLOOR PLASTER WORK | TOWER C 3RD FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.72 | 15402.28 | 0 | 271924.9 | 271924.9 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39321 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR EXTRA CIVIL WOK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39322 |  |  |  | TOWER C 3RD FLOOR EXTRA CIVIL WOK | TOWER C 3RD FLOOR EXTRA CIVIL WOK MASONRY WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 5524.28 | 5524.28 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29540 |  |  |  | TOWER C 3RD FLOOR | TOWER C 301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29532 |  |  |  | TOWER C 301 | TOWER C 301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33576 |  |  |  | TOWER C 301 WATERPROOFING WORK | TOWER C 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38637 |  |  |  | TOWER C 301 WATERPROOFING WORK | TOWER C 301 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29534 |  |  |  | TOWER C 301 | TOWER C 301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33004 |  |  |  | TOWER C 301 PLUMBING WORK | TOWER C 301 PLUMBING WORK | 1 | NOS | 0 | NOS | 696.7 |  | Tentative | 696.7 | 0 | 696.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41543 |  |  |  | TOWER C 301 PLUMBING WORK | TOWER C 301 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29533 |  |  |  | TOWER C 301 | TOWER C 301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33816 |  |  |  | TOWER C 301 ELECTRIC WORK | TOWER C 301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29535 |  |  |  | TOWER C 301 | TOWER C 301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29538 |  |  |  | TOWER C 301 | TOWER C 301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33104 |  |  |  | TOWER C 301 CARPENTRY WORK | TOWER C 301 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29536 |  |  |  | TOWER C 301 | TOWER C 301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29537 |  |  |  | TOWER C 301 | TOWER C 301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29539 |  |  |  | TOWER C 301 | TOWER C 301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34341 |  |  |  | TOWER C 301 | TOWER C 301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34342 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34343 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34344 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40281 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29549 |  |  |  | TOWER C 3RD FLOOR | TOWER C 302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29541 |  |  |  | TOWER C 302 | TOWER C 302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33577 |  |  |  | TOWER C 302 WATERPROOFING WORK | TOWER C 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38638 |  |  |  | TOWER C 302 WATERPROOFING WORK | TOWER C 302 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29543 |  |  |  | TOWER C 302 | TOWER C 302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33005 |  |  |  | TOWER C 302 PLUMBING WORK | TOWER C 302 PLUMBING WORK | 1 | NOS | 0 | NOS | 696.7 |  | Tentative | 696.7 | 0 | 696.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41544 |  |  |  | TOWER C 302 PLUMBING WORK | TOWER C 302 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29542 |  |  |  | TOWER C 302 | TOWER C 302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33817 |  |  |  | TOWER C 302 ELECTRIC WORK | TOWER C 302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29544 |  |  |  | TOWER C 302 | TOWER C 302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29547 |  |  |  | TOWER C 302 | TOWER C 302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33105 |  |  |  | TOWER C 302 CARPENTRY WORK | TOWER C 302 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29545 |  |  |  | TOWER C 302 | TOWER C 302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29546 |  |  |  | TOWER C 302 | TOWER C 302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29548 |  |  |  | TOWER C 302 | TOWER C 302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34345 |  |  |  | TOWER C 302 | TOWER C 302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34346 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34347 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34348 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40282 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29351 |  |  |  | TOWER C 3RD FLOOR | TOWER C 3RD FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Apr 2022 |  | - | - | 768 | -
Group | 5 | 29354 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32592 |  |  |  | TOWER C 3RD FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 3RD FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29352 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41982 |  |  |  | TOWER C 3RD FLOOR COMMON FLOORING WORK | TOWER C 3RD FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29353 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29355 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26462 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Apr 2022 |  | - | - | 768 | -
Task | 6 | 26463 |  |  |  | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 23 Apr 2022 |  | - | - | 768 | - | ELECTRIC WORK
Group | 5 | 40976 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40977 |  |  |  | TOWER C 3RD FLOOR WPC PANNELING WORK | TOWER C 3RD FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24304 |  |  |  | TOWER C | TOWER C 4TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24305 |  |  |  | TOWER C 4TH FLOOR | TOWER C 4TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24306 |  |  |  | TOWER C 4TH FLOOR CIVIL WORK | TOWER C 4TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24309 |  |  |  | TOWER C 4TH FLOOR RCC WORK | TOWER C 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 40410.32 |  | Started | 40410.32 | 0 | 40410.32 | 5.72 | 231294.12 | 986622.2 | 1081939.43 | 2068561.63 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 31085 |  |  |  | TOWER C 4TH FLOOR RCC WORK | TOWER C 4TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 38161.2 | 38161.2 | 17 Mar 2020 |  | 07 Sep 2022 |  | - | - | 905 | - | THREADING
Task | 6 | 38390 |  |  |  | TOWER C 4TH FLOOR RCC WORK | TOWER C 4TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 32737.92 | 32737.92 | 17 Mar 2020 |  | 16 Jul 2023 |  | - | - | 1217 | - | SAFETY NET FIXING
Group | 5 | 24307 |  |  |  | TOWER C 4TH FLOOR CIVIL WORK | TOWER C 4TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22 Dec 2022 |  | - | - | - | -
Task | 6 | 24310 |  |  |  | TOWER C 4TH FLOOR MASONRY WORK | TOWER C 4TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 332628.75 |  | Started | 332628.75 | 0 | 332628.75 | 5.72 | 1902429.55 | 0 | 291070.27 | 291070.27 |  |  | 22 Dec 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24308 |  |  |  | TOWER C 4TH FLOOR CIVIL WORK | TOWER C 4TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24311 |  |  |  | TOWER C 4TH FLOOR PLASTER WORK | TOWER C 4TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.72 | 15402.28 | 0 | 262172.21 | 262172.21 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29558 |  |  |  | TOWER C 4TH FLOOR | TOWER C 401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29550 |  |  |  | TOWER C 401 | TOWER C 401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33578 |  |  |  | TOWER C 401 WATERPROOFING WORK | TOWER C 401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38639 |  |  |  | TOWER C 401 WATERPROOFING WORK | TOWER C 401 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29552 |  |  |  | TOWER C 401 | TOWER C 401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33007 |  |  |  | TOWER C 401 PLUMBING WORK | TOWER C 401 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29551 |  |  |  | TOWER C 401 | TOWER C 401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33818 |  |  |  | TOWER C 401 ELECTRIC WORK | TOWER C 401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29553 |  |  |  | TOWER C 401 | TOWER C 401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29556 |  |  |  | TOWER C 401 | TOWER C 401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39382 |  |  |  | TOWER C 401 CARPENTRY WORK | TOWER C 401 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29554 |  |  |  | TOWER C 401 | TOWER C 401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29555 |  |  |  | TOWER C 401 | TOWER C 401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29557 |  |  |  | TOWER C 401 | TOWER C 401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34349 |  |  |  | TOWER C 401 | TOWER C 401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34350 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34351 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34352 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40283 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29567 |  |  |  | TOWER C 4TH FLOOR | TOWER C 402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29559 |  |  |  | TOWER C 402 | TOWER C 402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33579 |  |  |  | TOWER C 402 WATERPROOFING WORK | TOWER C 402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38640 |  |  |  | TOWER C 402 WATERPROOFING WORK | TOWER C 402 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29561 |  |  |  | TOWER C 402 | TOWER C 402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33008 |  |  |  | TOWER C 402 PLUMBING WORK | TOWER C 402 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29560 |  |  |  | TOWER C 402 | TOWER C 402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33819 |  |  |  | TOWER C 402 ELECTRIC WORK | TOWER C 402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29562 |  |  |  | TOWER C 402 | TOWER C 402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29565 |  |  |  | TOWER C 402 | TOWER C 402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39383 |  |  |  | TOWER C 402 CARPENTRY WORK | TOWER C 402 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29563 |  |  |  | TOWER C 402 | TOWER C 402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29564 |  |  |  | TOWER C 402 | TOWER C 402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29566 |  |  |  | TOWER C 402 | TOWER C 402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34353 |  |  |  | TOWER C 402 | TOWER C 402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34354 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34355 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34356 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40284 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29357 |  |  |  | TOWER C 4TH FLOOR | TOWER C 4TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2022 |  | - | - | 898 | -
Group | 5 | 29360 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32593 |  |  |  | TOWER C 4TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 4TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29358 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41983 |  |  |  | TOWER C 4TH FLOOR COMMON FLOORING WORK | TOWER C 4TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29359 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29361 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29362 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2022 |  | - | - | 898 | -
Task | 6 | 31331 |  |  |  | TOWER C 4TH FLOOR COMMON ELECTRIC WORK | TOWER C 4TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 31 Aug 2022 |  | - | - | 898 | - | ELECTRIC WORK
Group | 5 | 40978 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40979 |  |  |  | TOWER C 4TH FLOOR WPC PANNELING WORK | TOWER C 4TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24312 |  |  |  | TOWER C | TOWER C 5TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24313 |  |  |  | TOWER C 5TH FLOOR | TOWER C 5TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24314 |  |  |  | TOWER C 5TH FLOOR CIVIL WORK | TOWER C 5TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24317 |  |  |  | TOWER C 5TH FLOOR RCC WORK | TOWER C 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 133413.41 |  | Started | 133413.41 | 0 | 133413.41 | 5.72 | 763610.33 | 0 | 1079559.71 | 1079559.71 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 32568 |  |  |  | TOWER C 5TH FLOOR RCC WORK | TOWER C 5TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 27358.9 | 27358.9 | 17 Mar 2020 |  | 17 Oct 2022 |  | - | - | 945 | - | THREADING
Task | 6 | 35227 |  |  |  | TOWER C 5TH FLOOR RCC WORK | TOWER C 5TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Apr 2023 |  | - | - | 1121 | - | SAFETY NET FIXING
Group | 5 | 24315 |  |  |  | TOWER C 5TH FLOOR CIVIL WORK | TOWER C 5TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 Feb 2023 |  | - | - | - | -
Task | 6 | 24318 |  |  |  | TOWER C 5TH FLOOR MASONRY WORK | TOWER C 5TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307129.5 |  | Started | 307129.5 | 0 | 307129.5 | 5.72 | 1756589.71 | 0 | 291070.27 | 291070.27 |  |  | 16 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24316 |  |  |  | TOWER C 5TH FLOOR CIVIL WORK | TOWER C 5TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24319 |  |  |  | TOWER C 5TH FLOOR PLASTER WORK | TOWER C 5TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.72 | 15402.28 | 0 | 271924.9 | 271924.9 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29576 |  |  |  | TOWER C 5TH FLOOR | TOWER C 501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29568 |  |  |  | TOWER C 501 | TOWER C 501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33580 |  |  |  | TOWER C 501 WATERPROOFING WORK | TOWER C 501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38641 |  |  |  | TOWER C 501 WATERPROOFING WORK | TOWER C 501 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29570 |  |  |  | TOWER C 501 | TOWER C 501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33009 |  |  |  | TOWER C 501 PLUMBING WORK | TOWER C 501 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29569 |  |  |  | TOWER C 501 | TOWER C 501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33820 |  |  |  | TOWER C 501 ELECTRIC WORK | TOWER C 501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29571 |  |  |  | TOWER C 501 | TOWER C 501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29574 |  |  |  | TOWER C 501 | TOWER C 501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39384 |  |  |  | TOWER C 501 CARPENTRY WORK | TOWER C 501 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29572 |  |  |  | TOWER C 501 | TOWER C 501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29573 |  |  |  | TOWER C 501 | TOWER C 501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29575 |  |  |  | TOWER C 501 | TOWER C 501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34361 |  |  |  | TOWER C 501 | TOWER C 501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34362 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34363 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34364 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40285 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29585 |  |  |  | TOWER C 5TH FLOOR | TOWER C 502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29577 |  |  |  | TOWER C 502 | TOWER C 502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33581 |  |  |  | TOWER C 502 WATERPROOFING WORK | TOWER C 502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38642 |  |  |  | TOWER C 502 WATERPROOFING WORK | TOWER C 502 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29579 |  |  |  | TOWER C 502 | TOWER C 502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33010 |  |  |  | TOWER C 502 PLUMBING WORK | TOWER C 502 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29578 |  |  |  | TOWER C 502 | TOWER C 502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33821 |  |  |  | TOWER C 502 ELECTRIC WORK | TOWER C 502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29580 |  |  |  | TOWER C 502 | TOWER C 502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29583 |  |  |  | TOWER C 502 | TOWER C 502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39385 |  |  |  | TOWER C 502 CARPENTRY WORK | TOWER C 502 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29581 |  |  |  | TOWER C 502 | TOWER C 502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29582 |  |  |  | TOWER C 502 | TOWER C 502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29584 |  |  |  | TOWER C 502 | TOWER C 502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34365 |  |  |  | TOWER C 502 | TOWER C 502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34366 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34367 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34368 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40286 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29363 |  |  |  | TOWER C 5TH FLOOR | TOWER C 5TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | -
Group | 5 | 29366 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32594 |  |  |  | TOWER C 5TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 5TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29364 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41984 |  |  |  | TOWER C 5TH FLOOR COMMON FLOORING WORK | TOWER C 5TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29365 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29367 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29879 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | -
Task | 6 | 31332 |  |  |  | TOWER C 5TH FLOOR COMMON ELECTRIC WORK | TOWER C 5TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | - | ELECTRIC WORK
Group | 5 | 40980 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40981 |  |  |  | TOWER C 5TH FLOOR WPC PANNELING WORK | TOWER C 5TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24320 |  |  |  | TOWER C | TOWER C 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 4 | 24321 |  |  |  | TOWER C 6TH FLOOR | TOWER C 6TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 5 | 24322 |  |  |  | TOWER C 6TH FLOOR CIVIL WORK | TOWER C 6TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Task | 6 | 24325 |  |  |  | TOWER C 6TH FLOOR RCC WORK | TOWER C 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135783.34 |  | Started | 135783.34 | 0 | 135783.34 | 5.72 | 777174.96 | 0 | 1079561.68 | 1079561.68 |  |  | 16 Dec 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33091 |  |  |  | TOWER C 6TH FLOOR RCC WORK | TOWER C 6TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21349.74 | 21349.74 | 17 Mar 2020 |  | 27 Nov 2022 |  | - | - | 986 | - | THREADING
Task | 6 | 33710 |  |  |  | TOWER C 6TH FLOOR RCC WORK | TOWER C 6TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 625 |  | Started | 625 | 0 | 625 | 0 | 0.63 | 0 | 70179.1 | 70179.1 | 17 Mar 2020 |  | 02 Feb 2023 |  | - | - | 1053 | - | FIRE AND SAFETY WORK
Group | 5 | 24323 |  |  |  | TOWER C 6TH FLOOR CIVIL WORK | TOWER C 6TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24326 |  |  |  | TOWER C 6TH FLOOR MASONRY WORK | TOWER C 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 409126.5 |  | Started | 409126.5 | 0 | 409126.5 | 5.72 | 2339949.1 | 0 | 291070.4 | 291070.4 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24324 |  |  |  | TOWER C 6TH FLOOR CIVIL WORK | TOWER C 6TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24327 |  |  |  | TOWER C 6TH FLOOR PLASTER WORK | TOWER C 6TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 0 | 2.69 | 0 | 444413.85 | 444413.85 |  |  | 04 Jan 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29594 |  |  |  | TOWER C 6TH FLOOR | TOWER C 601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29586 |  |  |  | TOWER C 601 | TOWER C 601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33582 |  |  |  | TOWER C 601 WATERPROOFING WORK | TOWER C 601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38643 |  |  |  | TOWER C 601 WATERPROOFING WORK | TOWER C 601 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29588 |  |  |  | TOWER C 601 | TOWER C 601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33011 |  |  |  | TOWER C 601 PLUMBING WORK | TOWER C 601 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29587 |  |  |  | TOWER C 601 | TOWER C 601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33822 |  |  |  | TOWER C 601 ELECTRIC WORK | TOWER C 601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29589 |  |  |  | TOWER C 601 | TOWER C 601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29592 |  |  |  | TOWER C 601 | TOWER C 601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39386 |  |  |  | TOWER C 601 CARPENTRY WORK | TOWER C 601 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29590 |  |  |  | TOWER C 601 | TOWER C 601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29591 |  |  |  | TOWER C 601 | TOWER C 601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29593 |  |  |  | TOWER C 601 | TOWER C 601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34369 |  |  |  | TOWER C 601 | TOWER C 601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34370 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34371 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34372 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40287 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29603 |  |  |  | TOWER C 6TH FLOOR | TOWER C 602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29595 |  |  |  | TOWER C 602 | TOWER C 602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33583 |  |  |  | TOWER C 602 WATERPROOFING WORK | TOWER C 602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38644 |  |  |  | TOWER C 602 WATERPROOFING WORK | TOWER C 602 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29597 |  |  |  | TOWER C 602 | TOWER C 602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33012 |  |  |  | TOWER C 602 PLUMBING WORK | TOWER C 602 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29596 |  |  |  | TOWER C 602 | TOWER C 602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33823 |  |  |  | TOWER C 602 ELECTRIC WORK | TOWER C 602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29598 |  |  |  | TOWER C 602 | TOWER C 602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29601 |  |  |  | TOWER C 602 | TOWER C 602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39387 |  |  |  | TOWER C 602 CARPENTRY WORK | TOWER C 602 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29599 |  |  |  | TOWER C 602 | TOWER C 602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29600 |  |  |  | TOWER C 602 | TOWER C 602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29602 |  |  |  | TOWER C 602 | TOWER C 602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34373 |  |  |  | TOWER C 602 | TOWER C 602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34374 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34375 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34376 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40288 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29369 |  |  |  | TOWER C 6TH FLOOR | TOWER C 6TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Dec 2022 |  | - | - | 996 | -
Group | 5 | 29372 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34025 |  |  |  | TOWER C 6TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 6TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29370 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41985 |  |  |  | TOWER C 6TH FLOOR COMMON FLOORING WORK | TOWER C 6TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29371 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29373 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29374 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Dec 2022 |  | - | - | 996 | -
Task | 6 | 31333 |  |  |  | TOWER C 6TH FLOOR COMMON ELECTRIC WORK | TOWER C 6TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 07 Dec 2022 |  | - | - | 996 | - | ELECTRIC WORK
Group | 5 | 40982 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40983 |  |  |  | TOWER C 6TH FLOOR WPC PANNELING WORK | TOWER C 6TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24480 |  |  |  | TOWER C | TOWER C 7TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 4 | 24481 |  |  |  | TOWER C 7TH FLOOR | TOWER C 7TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 5 | 24482 |  |  |  | TOWER C 7TH FLOOR CIVIL WORK | TOWER C 7TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Task | 6 | 24485 |  |  |  | TOWER C 7TH FLOOR RCC WORK | TOWER C 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 140077.34 |  | Started | 140077.34 | 0 | 140077.34 | 5.72 | 801752.27 | 0 | 1079136.88 | 1079136.88 |  |  | 22 Dec 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33092 |  |  |  | TOWER C 7TH FLOOR RCC WORK | TOWER C 7TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 49200.1 | 49200.1 | 17 Mar 2020 |  | 27 Nov 2022 |  | - | - | 986 | - | THREADING
Task | 6 | 38611 |  |  |  | TOWER C 7TH FLOOR RCC WORK | TOWER C 7TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 38331.12 | 38331.12 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | FIRE AND SAFETY WORK
Group | 5 | 24483 |  |  |  | TOWER C 7TH FLOOR CIVIL WORK | TOWER C 7TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 08 Sep 2023 |  | - | - | - | -
Task | 6 | 24486 |  |  |  | TOWER C 7TH FLOOR MASONRY WORK | TOWER C 7TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 277040.2 | 277040.2 |  |  | 08 Sep 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24484 |  |  |  | TOWER C 7TH FLOOR CIVIL WORK | TOWER C 7TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24487 |  |  |  | TOWER C 7TH FLOOR PLASTER WORK | TOWER C 7TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 0 | 2.69 | 0 | 262172.2 | 262172.2 |  |  | 04 Oct 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29612 |  |  |  | TOWER C 7TH FLOOR | TOWER C 701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29604 |  |  |  | TOWER C 701 | TOWER C 701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33584 |  |  |  | TOWER C 701 WATERPROOFING WORK | TOWER C 701 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38645 |  |  |  | TOWER C 701 WATERPROOFING WORK | TOWER C 701 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29606 |  |  |  | TOWER C 701 | TOWER C 701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33013 |  |  |  | TOWER C 701 PLUMBING WORK | TOWER C 701 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29605 |  |  |  | TOWER C 701 | TOWER C 701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33824 |  |  |  | TOWER C 701 ELECTRIC WORK | TOWER C 701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 29607 |  |  |  | TOWER C 701 | TOWER C 701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29610 |  |  |  | TOWER C 701 | TOWER C 701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39388 |  |  |  | TOWER C 701 CARPENTRY WORK | TOWER C 701 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29608 |  |  |  | TOWER C 701 | TOWER C 701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29609 |  |  |  | TOWER C 701 | TOWER C 701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29611 |  |  |  | TOWER C 701 | TOWER C 701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34377 |  |  |  | TOWER C 701 | TOWER C 701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34378 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34379 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34380 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40289 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29621 |  |  |  | TOWER C 7TH FLOOR | TOWER C 702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29613 |  |  |  | TOWER C 702 | TOWER C 702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33585 |  |  |  | TOWER C 702 WATERPROOFING WORK | TOWER C 702 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38646 |  |  |  | TOWER C 702 WATERPROOFING WORK | TOWER C 702 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29615 |  |  |  | TOWER C 702 | TOWER C 702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33014 |  |  |  | TOWER C 702 PLUMBING WORK | TOWER C 702 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29614 |  |  |  | TOWER C 702 | TOWER C 702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33825 |  |  |  | TOWER C 702 ELECTRIC WORK | TOWER C 702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 29616 |  |  |  | TOWER C 702 | TOWER C 702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29619 |  |  |  | TOWER C 702 | TOWER C 702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39389 |  |  |  | TOWER C 702 CARPENTRY WORK | TOWER C 702 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29617 |  |  |  | TOWER C 702 | TOWER C 702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29618 |  |  |  | TOWER C 702 | TOWER C 702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29620 |  |  |  | TOWER C 702 | TOWER C 702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34381 |  |  |  | TOWER C 702 | TOWER C 702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34382 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34383 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34384 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40290 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29375 |  |  |  | TOWER C 7TH FLOOR | TOWER C 7TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29378 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34026 |  |  |  | TOWER C 7TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 7TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29376 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41986 |  |  |  | TOWER C 7TH FLOOR COMMON FLOORING WORK | TOWER C 7TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29377 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29379 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29380 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 31471 |  |  |  | TOWER C 7TH FLOOR COMMON ELECTRIC WORK | TOWER C 7TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 40984 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40985 |  |  |  | TOWER C 7TH FLOOR WPC PANNELING WORK | TOWER C 7TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24488 |  |  |  | TOWER C | TOWER C 8TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 4 | 24489 |  |  |  | TOWER C 8TH FLOOR | TOWER C 8TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 5 | 24490 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Task | 6 | 24493 |  |  |  | TOWER C 8TH FLOOR RCC WORK | TOWER C 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135791.42 |  | Started | 135791.42 | 0 | 135791.42 | 5.72 | 777221.2 | 0 | 1137162.16 | 1137162.16 |  |  | 25 Aug 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33093 |  |  |  | TOWER C 8TH FLOOR RCC WORK | TOWER C 8TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 31801 | 31801 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | THREADING
Task | 6 | 38773 |  |  |  | TOWER C 8TH FLOOR RCC WORK | TOWER C 8TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 625 |  | Started | 625 | 0 | 625 | 0 | 0.63 | 0 | 2063.24 | 2063.24 | 17 Mar 2020 |  | 12 Jan 2024 |  | - | - | 1397 | - | SAFETY NET FIXING
Group | 5 | 24491 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24494 |  |  |  | TOWER C 8TH FLOOR MASONRY WORK | TOWER C 8TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 277040.2 | 277040.2 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24492 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24495 |  |  |  | TOWER C 8TH FLOOR PLASTER WORK | TOWER C 8TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 5 | 37471 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 09 Feb 2023 |  | - | - | 1060 | -
Task | 6 | 37472 |  |  |  | TOWER C 8TH FLOOR CIVIL EXTRA WORK | TOWER C 8TH FLOOR CIVIL EXTRA WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 128325 | 128325 | 17 Mar 2020 |  | 09 Feb 2023 |  | - | - | 1060 | - | CIVIL EXTRA WORK
Group | 4 | 29639 |  |  |  | TOWER C 8TH FLOOR | TOWER C 801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29631 |  |  |  | TOWER C 801 | TOWER C 801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33586 |  |  |  | TOWER C 801 WATERPROOFING WORK | TOWER C 801 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38647 |  |  |  | TOWER C 801 WATERPROOFING WORK | TOWER C 801 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29633 |  |  |  | TOWER C 801 | TOWER C 801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33015 |  |  |  | TOWER C 801 PLUMBING WORK | TOWER C 801 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29632 |  |  |  | TOWER C 801 | TOWER C 801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33826 |  |  |  | TOWER C 801 ELECTRIC WORK | TOWER C 801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 21461.26 | 21461.26 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29634 |  |  |  | TOWER C 801 | TOWER C 801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29637 |  |  |  | TOWER C 801 | TOWER C 801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39390 |  |  |  | TOWER C 801 CARPENTRY WORK | TOWER C 801 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29635 |  |  |  | TOWER C 801 | TOWER C 801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29636 |  |  |  | TOWER C 801 | TOWER C 801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29638 |  |  |  | TOWER C 801 | TOWER C 801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34385 |  |  |  | TOWER C 801 | TOWER C 801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34386 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34387 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34388 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40291 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29630 |  |  |  | TOWER C 8TH FLOOR | TOWER C 802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29622 |  |  |  | TOWER C 802 | TOWER C 802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33587 |  |  |  | TOWER C 802 WATERPROOFING WORK | TOWER C 802 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38648 |  |  |  | TOWER C 802 WATERPROOFING WORK | TOWER C 802 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29624 |  |  |  | TOWER C 802 | TOWER C 802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33016 |  |  |  | TOWER C 802 PLUMBING WORK | TOWER C 802 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29623 |  |  |  | TOWER C 802 | TOWER C 802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33827 |  |  |  | TOWER C 802 ELECTRIC WORK | TOWER C 802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 24337.5 | 24337.5 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29625 |  |  |  | TOWER C 802 | TOWER C 802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29628 |  |  |  | TOWER C 802 | TOWER C 802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39391 |  |  |  | TOWER C 802 CARPENTRY WORK | TOWER C 802 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29626 |  |  |  | TOWER C 802 | TOWER C 802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29627 |  |  |  | TOWER C 802 | TOWER C 802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29629 |  |  |  | TOWER C 802 | TOWER C 802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34389 |  |  |  | TOWER C 802 | TOWER C 802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34390 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34391 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34392 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40292 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29381 |  |  |  | TOWER C 8TH FLOOR | TOWER C 8TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 22 Apr 2023 |  | - | - | 1132 | -
Group | 5 | 29384 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34027 |  |  |  | TOWER C 8TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 8TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29382 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41987 |  |  |  | TOWER C 8TH FLOOR COMMON FLOORING WORK | TOWER C 8TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29383 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29385 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29386 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 22 Apr 2023 |  | - | - | 1132 | -
Task | 6 | 31472 |  |  |  | TOWER C 8TH FLOOR COMMON ELECTRIC WORK | TOWER C 8TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 22 Apr 2023 |  | - | - | 1132 | - | ELECTRIC WORK
Group | 5 | 40986 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40987 |  |  |  | TOWER C 8TH FLOOR WPC PANNELING WORK | TOWER C 8TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24496 |  |  |  | TOWER C | TOWER C 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 4 | 24497 |  |  |  | TOWER C 9TH FLOOR | TOWER C 9TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 5 | 24498 |  |  |  | TOWER C 9TH FLOOR CIVIL WORK | TOWER C 9TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Task | 6 | 24501 |  |  |  | TOWER C 9TH FLOOR RCC WORK | TOWER C 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 38225.24 |  | Started | 38225.24 | 0 | 38225.24 | 5.72 | 218787.51 | 0 | 1077862.96 | 1077862.96 |  |  | 17 Nov 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33456 |  |  |  | TOWER C 9TH FLOOR RCC WORK | TOWER C 9TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 30916 | 30916 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | THREADING
Task | 6 | 38920 |  |  |  | TOWER C 9TH FLOOR RCC WORK | TOWER C 9TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 83248.18 | 83248.18 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | SAFETY NET FIXING
Group | 5 | 24499 |  |  |  | TOWER C 9TH FLOOR CIVIL WORK | TOWER C 9TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24502 |  |  |  | TOWER C 9TH FLOOR MASONRY WORK | TOWER C 9TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 273641.51 | 273641.51 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24500 |  |  |  | TOWER C 9TH FLOOR CIVIL WORK | TOWER C 9TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24503 |  |  |  | TOWER C 9TH FLOOR PLASTER WORK | TOWER C 9TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29648 |  |  |  | TOWER C 9TH FLOOR | TOWER C 901 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29640 |  |  |  | TOWER C 901 | TOWER C 901 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33589 |  |  |  | TOWER C 901 WATERPROOFING WORK | TOWER C 901 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38649 |  |  |  | TOWER C 901 WATERPROOFING WORK | TOWER C 901 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29642 |  |  |  | TOWER C 901 | TOWER C 901 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33017 |  |  |  | TOWER C 901 PLUMBING WORK | TOWER C 901 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29641 |  |  |  | TOWER C 901 | TOWER C 901 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33828 |  |  |  | TOWER C 901 ELECTRIC WORK | TOWER C 901 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 24337.5 | 24337.5 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29643 |  |  |  | TOWER C 901 | TOWER C 901 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29646 |  |  |  | TOWER C 901 | TOWER C 901 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39392 |  |  |  | TOWER C 901 CARPENTRY WORK | TOWER C 901 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29644 |  |  |  | TOWER C 901 | TOWER C 901 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29645 |  |  |  | TOWER C 901 | TOWER C 901 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29647 |  |  |  | TOWER C 901 | TOWER C 901 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34393 |  |  |  | TOWER C 901 | TOWER C 901 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34394 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34395 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34396 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40293 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29657 |  |  |  | TOWER C 9TH FLOOR | TOWER C 902 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29649 |  |  |  | TOWER C 902 | TOWER C 902 WATERPROOFING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33608 |  |  |  | TOWER C 902 WATERPROOFING WORK | TOWER C 902 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38650 |  |  |  | TOWER C 902 WATERPROOFING WORK | TOWER C 902 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29651 |  |  |  | TOWER C 902 | TOWER C 902 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33018 |  |  |  | TOWER C 902 PLUMBING WORK | TOWER C 902 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29650 |  |  |  | TOWER C 902 | TOWER C 902 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33829 |  |  |  | TOWER C 902 ELECTRIC WORK | TOWER C 902 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 24337.5 | 24337.5 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29652 |  |  |  | TOWER C 902 | TOWER C 902 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29655 |  |  |  | TOWER C 902 | TOWER C 902 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39393 |  |  |  | TOWER C 902 CARPENTRY WORK | TOWER C 902 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29653 |  |  |  | TOWER C 902 | TOWER C 902 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29654 |  |  |  | TOWER C 902 | TOWER C 902 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29656 |  |  |  | TOWER C 902 | TOWER C 902 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34397 |  |  |  | TOWER C 902 | TOWER C 902 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34398 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34399 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34400 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40294 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29387 |  |  |  | TOWER C 9TH FLOOR | TOWER C 9TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Group | 5 | 29390 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34028 |  |  |  | TOWER C 9TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 9TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 3.36 |  | Started | 2.36 | 1 | 3.36 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29388 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41988 |  |  |  | TOWER C 9TH FLOOR COMMON FLOORING WORK | TOWER C 9TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29389 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29391 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29392 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Task | 6 | 31473 |  |  |  | TOWER C 9TH FLOOR COMMON ELECTRIC WORK | TOWER C 9TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | - | ELECTRIC WORK
Group | 5 | 40988 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40989 |  |  |  | TOWER C 9TH FLOOR WPC PANNELING WORK | TOWER C 9TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24504 |  |  |  | TOWER C | TOWER C 10TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 4 | 24505 |  |  |  | TOWER C 10TH FLOOR | TOWER C 10TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 5 | 24506 |  |  |  | TOWER C 10TH FLOOR CIVIL WORK | TOWER C 10TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Task | 6 | 24509 |  |  |  | TOWER C 10TH FLOOR RCC WORK | TOWER C 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35747.21 |  | Started | 35747.21 | 0 | 35747.21 | 0 | 35.75 | 0 | 1714225.85 | 1714225.85 |  |  | 04 Jan 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24507 |  |  |  | TOWER C 10TH FLOOR CIVIL WORK | TOWER C 10TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24510 |  |  |  | TOWER C 10TH FLOOR MASONRY WORK | TOWER C 10TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 271992 |  | Started | 271992 | 0 | 271992 | 5.72 | 1555625.06 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24508 |  |  |  | TOWER C 10TH FLOOR CIVIL WORK | TOWER C 10TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24511 |  |  |  | TOWER C 10TH FLOOR PLASTER WORK | TOWER C 10TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29666 |  |  |  | TOWER C 10TH FLOOR | TOWER C 1001 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29658 |  |  |  | TOWER C 1001 | TOWER C 1001 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33611 |  |  |  | TOWER C 1001 WATERPROOFING WORK | TOWER C 1001 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29660 |  |  |  | TOWER C 1001 | TOWER C 1001 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33019 |  |  |  | TOWER C 1001 PLUMBING WORK | TOWER C 1001 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29659 |  |  |  | TOWER C 1001 | TOWER C 1001 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33830 |  |  |  | TOWER C 1001 ELECTRIC WORK | TOWER C 1001 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29661 |  |  |  | TOWER C 1001 | TOWER C 1001 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29664 |  |  |  | TOWER C 1001 | TOWER C 1001 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39394 |  |  |  | TOWER C 1001 CARPENTRY WORK | TOWER C 1001 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29662 |  |  |  | TOWER C 1001 | TOWER C 1001 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29663 |  |  |  | TOWER C 1001 | TOWER C 1001 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29665 |  |  |  | TOWER C 1001 | TOWER C 1001 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34401 |  |  |  | TOWER C 1001 | TOWER C 1001 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34402 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34403 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34404 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40295 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29675 |  |  |  | TOWER C 10TH FLOOR | TOWER C 1002 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29667 |  |  |  | TOWER C 1002 | TOWER C 1002 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33622 |  |  |  | TOWER C 1002 WATERPROOFING WORK | TOWER C 1002 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29669 |  |  |  | TOWER C 1002 | TOWER C 1002 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33020 |  |  |  | TOWER C 1002 PLUMBING WORK | TOWER C 1002 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29668 |  |  |  | TOWER C 1002 | TOWER C 1002 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33831 |  |  |  | TOWER C 1002 ELECTRIC WORK | TOWER C 1002 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29670 |  |  |  | TOWER C 1002 | TOWER C 1002 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29673 |  |  |  | TOWER C 1002 | TOWER C 1002 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39395 |  |  |  | TOWER C 1002 CARPENTRY WORK | TOWER C 1002 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29671 |  |  |  | TOWER C 1002 | TOWER C 1002 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29672 |  |  |  | TOWER C 1002 | TOWER C 1002 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29674 |  |  |  | TOWER C 1002 | TOWER C 1002 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34405 |  |  |  | TOWER C 1002 | TOWER C 1002 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34406 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34407 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34408 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40296 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29393 |  |  |  | TOWER C 10TH FLOOR | TOWER C 10TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29396 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34029 |  |  |  | TOWER C 10TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 10TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 3.36 |  | Started | 2.36 | 1 | 3.36 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29394 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41989 |  |  |  | TOWER C 10TH FLOOR COMMON FLOORING WORK | TOWER C 10TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29395 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29397 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29398 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 31474 |  |  |  | TOWER C 10TH FLOOR COMMON ELECTRIC WORK | TOWER C 10TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40990 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40991 |  |  |  | TOWER C 10TH FLOOR WPC PANNELING WORK | TOWER C 10TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24512 |  |  |  | TOWER C | TOWER C 11TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24513 |  |  |  | TOWER C 11TH FLOOR | TOWER C 11TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24514 |  |  |  | TOWER C 11TH FLOOR CIVIL WORK | TOWER C 11TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24517 |  |  |  | TOWER C 11TH FLOOR RCC WORK | TOWER C 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35533.18 |  | Started | 35533.18 | 0 | 35533.18 | 0 | 35.53 | 0 | 1049424.96 | 1049424.96 |  |  | 04 Feb 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24515 |  |  |  | TOWER C 11TH FLOOR CIVIL WORK | TOWER C 11TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24518 |  |  |  | TOWER C 11TH FLOOR MASONRY WORK | TOWER C 11TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 271992 |  | Tentative | 271992 | 0 | 271992 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24516 |  |  |  | TOWER C 11TH FLOOR CIVIL WORK | TOWER C 11TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24519 |  |  |  | TOWER C 11TH FLOOR PLASTER WORK | TOWER C 11TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29684 |  |  |  | TOWER C 11TH FLOOR | TOWER C 1101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29676 |  |  |  | TOWER C 1101 | TOWER C 1101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33624 |  |  |  | TOWER C 1101 WATERPROOFING WORK | TOWER C 1101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29678 |  |  |  | TOWER C 1101 | TOWER C 1101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33021 |  |  |  | TOWER C 1101 PLUMBING WORK | TOWER C 1101 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29677 |  |  |  | TOWER C 1101 | TOWER C 1101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33832 |  |  |  | TOWER C 1101 ELECTRIC WORK | TOWER C 1101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29679 |  |  |  | TOWER C 1101 | TOWER C 1101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29682 |  |  |  | TOWER C 1101 | TOWER C 1101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29680 |  |  |  | TOWER C 1101 | TOWER C 1101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29681 |  |  |  | TOWER C 1101 | TOWER C 1101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29683 |  |  |  | TOWER C 1101 | TOWER C 1101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34409 |  |  |  | TOWER C 1101 | TOWER C 1101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34410 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34411 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34412 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40297 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29693 |  |  |  | TOWER C 11TH FLOOR | TOWER C 1102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29685 |  |  |  | TOWER C 1102 | TOWER C 1102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33625 |  |  |  | TOWER C 1102 WATERPROOFING WORK | TOWER C 1102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29687 |  |  |  | TOWER C 1102 | TOWER C 1102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33022 |  |  |  | TOWER C 1102 PLUMBING WORK | TOWER C 1102 PLUMBING WORK | 1 | NOS | 1 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29686 |  |  |  | TOWER C 1102 | TOWER C 1102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33833 |  |  |  | TOWER C 1102 ELECTRIC WORK | TOWER C 1102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29688 |  |  |  | TOWER C 1102 | TOWER C 1102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29691 |  |  |  | TOWER C 1102 | TOWER C 1102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29689 |  |  |  | TOWER C 1102 | TOWER C 1102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29690 |  |  |  | TOWER C 1102 | TOWER C 1102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29692 |  |  |  | TOWER C 1102 | TOWER C 1102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34413 |  |  |  | TOWER C 1102 | TOWER C 1102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34414 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34415 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34416 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40298 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29399 |  |  |  | TOWER C 11TH FLOOR | TOWER C 11TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29402 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34030 |  |  |  | TOWER C 11TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 11TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29400 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41990 |  |  |  | TOWER C 11TH FLOOR COMMON FLOORING WORK | TOWER C 11TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29401 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29403 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29404 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 31475 |  |  |  | TOWER C 11TH FLOOR COMMON ELECTRIC WORK | TOWER C 11TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40992 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40993 |  |  |  | TOWER C 11TH FLOOR WPC PANNELING WORK | TOWER C 11TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24520 |  |  |  | TOWER C | TOWER C 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24521 |  |  |  | TOWER C 12TH FLOOR | TOWER C 12TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24522 |  |  |  | TOWER C 12TH FLOOR CIVIL WORK | TOWER C 12TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24525 |  |  |  | TOWER C 12TH FLOOR RCC WORK | TOWER C 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35094.18 |  | Started | 35094.18 | 0 | 35094.18 | 0 | 35.09 | 0 | 1023110.96 | 1023110.96 |  |  | 04 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 39526 |  |  |  | TOWER C 12TH FLOOR RCC WORK | TOWER C 12TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21712 | 21712 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Task | 6 | 40088 |  |  |  | TOWER C 12TH FLOOR RCC WORK | TOWER C 12TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6884.72 | 6884.72 | 17 Mar 2020 |  | 23 Jul 2024 |  | - | - | 1590 | - | SAFETY NET FIXING
Group | 5 | 24523 |  |  |  | TOWER C 12TH FLOOR CIVIL WORK | TOWER C 12TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24526 |  |  |  | TOWER C 12TH FLOOR MASONRY WORK | TOWER C 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24524 |  |  |  | TOWER C 12TH FLOOR CIVIL WORK | TOWER C 12TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24527 |  |  |  | TOWER C 12TH FLOOR PLASTER WORK | TOWER C 12TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29702 |  |  |  | TOWER C 12TH FLOOR | TOWER C 1201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29694 |  |  |  | TOWER C 1201 | TOWER C 1201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33627 |  |  |  | TOWER C 1201 WATERPROOFING WORK | TOWER C 1201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29696 |  |  |  | TOWER C 1201 | TOWER C 1201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33023 |  |  |  | TOWER C 1201 PLUMBING WORK | TOWER C 1201 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29695 |  |  |  | TOWER C 1201 | TOWER C 1201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33834 |  |  |  | TOWER C 1201 ELECTRIC WORK | TOWER C 1201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29697 |  |  |  | TOWER C 1201 | TOWER C 1201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29700 |  |  |  | TOWER C 1201 | TOWER C 1201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29698 |  |  |  | TOWER C 1201 | TOWER C 1201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29699 |  |  |  | TOWER C 1201 | TOWER C 1201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29701 |  |  |  | TOWER C 1201 | TOWER C 1201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34417 |  |  |  | TOWER C 1201 | TOWER C 1201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34418 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34419 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34420 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40299 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29711 |  |  |  | TOWER C 12TH FLOOR | TOWER C 1202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29703 |  |  |  | TOWER C 1202 | TOWER C 1202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33628 |  |  |  | TOWER C 1202 WATERPROOFING WORK | TOWER C 1202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29705 |  |  |  | TOWER C 1202 | TOWER C 1202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33024 |  |  |  | TOWER C 1202 PLUMBING WORK | TOWER C 1202 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29704 |  |  |  | TOWER C 1202 | TOWER C 1202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33835 |  |  |  | TOWER C 1202 ELECTRIC WORK | TOWER C 1202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29706 |  |  |  | TOWER C 1202 | TOWER C 1202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29709 |  |  |  | TOWER C 1202 | TOWER C 1202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29707 |  |  |  | TOWER C 1202 | TOWER C 1202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29708 |  |  |  | TOWER C 1202 | TOWER C 1202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29710 |  |  |  | TOWER C 1202 | TOWER C 1202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34421 |  |  |  | TOWER C 1202 | TOWER C 1202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34422 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34423 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34424 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40300 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29405 |  |  |  | TOWER C 12TH FLOOR | TOWER C 12TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29408 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34031 |  |  |  | TOWER C 12TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 12TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Tentative | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29406 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41991 |  |  |  | TOWER C 12TH FLOOR COMMON FLOORING WORK | TOWER C 12TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29407 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29409 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29410 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38759 |  |  |  | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40994 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40995 |  |  |  | TOWER C 12TH FLOOR WPC PANNELING WORK | TOWER C 12TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24528 |  |  |  | TOWER C | TOWER C 13TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24529 |  |  |  | TOWER C 13TH FLOOR | TOWER C 13TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24530 |  |  |  | TOWER C 13TH FLOOR CIVIL WORK | TOWER C 13TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24533 |  |  |  | TOWER C 13TH FLOOR RCC WORK | TOWER C 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34581.3 |  | Started | 34581.3 | 0 | 34581.3 | 0 | 34.58 | 0 | 1604142.96 | 1604142.96 |  |  | 22 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 39527 |  |  |  | TOWER C 13TH FLOOR RCC WORK | TOWER C 13TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 18880 | 18880 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Group | 5 | 24531 |  |  |  | TOWER C 13TH FLOOR CIVIL WORK | TOWER C 13TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24534 |  |  |  | TOWER C 13TH FLOOR MASONRY WORK | TOWER C 13TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24532 |  |  |  | TOWER C 13TH FLOOR CIVIL WORK | TOWER C 13TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24535 |  |  |  | TOWER C 13TH FLOOR PLASTER WORK | TOWER C 13TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29729 |  |  |  | TOWER C 13TH FLOOR | TOWER C 1301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29721 |  |  |  | TOWER C 1301 | TOWER C 1301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33629 |  |  |  | TOWER C 1301 WATERPROOFING WORK | TOWER C 1301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29723 |  |  |  | TOWER C 1301 | TOWER C 1301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33025 |  |  |  | TOWER C 1301 PLUMBING WORK | TOWER C 1301 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29722 |  |  |  | TOWER C 1301 | TOWER C 1301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33836 |  |  |  | TOWER C 1301 ELECTRIC WORK | TOWER C 1301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 19 Apr 2024 |  | - | - | 1495 | - | ELECTRIC WORK
Group | 5 | 29724 |  |  |  | TOWER C 1301 | TOWER C 1301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29727 |  |  |  | TOWER C 1301 | TOWER C 1301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29725 |  |  |  | TOWER C 1301 | TOWER C 1301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29726 |  |  |  | TOWER C 1301 | TOWER C 1301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29728 |  |  |  | TOWER C 1301 | TOWER C 1301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34425 |  |  |  | TOWER C 1301 | TOWER C 1301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34426 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34427 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34428 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40301 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29720 |  |  |  | TOWER C 13TH FLOOR | TOWER C 1302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29712 |  |  |  | TOWER C 1302 | TOWER C 1302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33630 |  |  |  | TOWER C 1302 WATERPROOFING WORK | TOWER C 1302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29714 |  |  |  | TOWER C 1302 | TOWER C 1302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33026 |  |  |  | TOWER C 1302 PLUMBING WORK | TOWER C 1302 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29713 |  |  |  | TOWER C 1302 | TOWER C 1302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33837 |  |  |  | TOWER C 1302 ELECTRIC WORK | TOWER C 1302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 19 Apr 2024 |  | - | - | 1495 | - | ELECTRIC WORK
Group | 5 | 29715 |  |  |  | TOWER C 1302 | TOWER C 1302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29718 |  |  |  | TOWER C 1302 | TOWER C 1302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29716 |  |  |  | TOWER C 1302 | TOWER C 1302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29717 |  |  |  | TOWER C 1302 | TOWER C 1302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29719 |  |  |  | TOWER C 1302 | TOWER C 1302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34429 |  |  |  | TOWER C 1302 | TOWER C 1302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34430 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34431 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34432 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40302 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29411 |  |  |  | TOWER C 13TH FLOOR | TOWER C 13TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29414 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29412 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41992 |  |  |  | TOWER C 13TH FLOOR COMMON FLOORING WORK | TOWER C 13TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29413 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29415 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29416 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38760 |  |  |  | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40996 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40997 |  |  |  | TOWER C 13TH FLOOR WPC PANNELING WORK | TOWER C 13TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24536 |  |  |  | TOWER C | TOWER C 14TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24537 |  |  |  | TOWER C 14TH FLOOR | TOWER C 14TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24538 |  |  |  | TOWER C 14TH FLOOR CIVIL WORK | TOWER C 14TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24541 |  |  |  | TOWER C 14TH FLOOR RCC WORK | TOWER C 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34397.44 |  | Started | 34397.44 | 0 | 34397.44 | 0 | 34.4 | 0 | 1023110.96 | 1023110.96 |  |  | 07 Oct 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41017 |  |  |  | TOWER C 14TH FLOOR RCC WORK | TOWER C 14TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 18113 | 18113 | 17 Mar 2020 |  | 15 May 2024 |  | - | - | 1521 | - | THREADING
Group | 5 | 24539 |  |  |  | TOWER C 14TH FLOOR CIVIL WORK | TOWER C 14TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24542 |  |  |  | TOWER C 14TH FLOOR MASONRY WORK | TOWER C 14TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24540 |  |  |  | TOWER C 14TH FLOOR CIVIL WORK | TOWER C 14TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24543 |  |  |  | TOWER C 14TH FLOOR PLASTER WORK | TOWER C 14TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29738 |  |  |  | TOWER C 14TH FLOOR | TOWER C 1401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29730 |  |  |  | TOWER C 1401 | TOWER C 1401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33631 |  |  |  | TOWER C 1401 WATERPROOFING WORK | TOWER C 1401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29732 |  |  |  | TOWER C 1401 | TOWER C 1401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33027 |  |  |  | TOWER C 1401 PLUMBING WORK | TOWER C 1401 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29731 |  |  |  | TOWER C 1401 | TOWER C 1401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33838 |  |  |  | TOWER C 1401 ELECTRIC WORK | TOWER C 1401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 29733 |  |  |  | TOWER C 1401 | TOWER C 1401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29736 |  |  |  | TOWER C 1401 | TOWER C 1401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29734 |  |  |  | TOWER C 1401 | TOWER C 1401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29735 |  |  |  | TOWER C 1401 | TOWER C 1401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29737 |  |  |  | TOWER C 1401 | TOWER C 1401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34433 |  |  |  | TOWER C 1401 | TOWER C 1401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34434 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34435 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34436 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40303 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29747 |  |  |  | TOWER C 14TH FLOOR | TOWER C 1402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29739 |  |  |  | TOWER C 1402 | TOWER C 1402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33632 |  |  |  | TOWER C 1402 WATERPROOFING WORK | TOWER C 1402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29741 |  |  |  | TOWER C 1402 | TOWER C 1402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33028 |  |  |  | TOWER C 1402 PLUMBING WORK | TOWER C 1402 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29740 |  |  |  | TOWER C 1402 | TOWER C 1402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33839 |  |  |  | TOWER C 1402 ELECTRIC WORK | TOWER C 1402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 29742 |  |  |  | TOWER C 1402 | TOWER C 1402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29745 |  |  |  | TOWER C 1402 | TOWER C 1402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29743 |  |  |  | TOWER C 1402 | TOWER C 1402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29744 |  |  |  | TOWER C 1402 | TOWER C 1402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29746 |  |  |  | TOWER C 1402 | TOWER C 1402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34437 |  |  |  | TOWER C 1402 | TOWER C 1402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34438 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34439 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34440 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40304 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29417 |  |  |  | TOWER C 14TH FLOOR | TOWER C 14TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29420 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29418 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41993 |  |  |  | TOWER C 14TH FLOOR COMMON FLOORING WORK | TOWER C 14TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29419 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29421 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29422 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38761 |  |  |  | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 40998 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40999 |  |  |  | TOWER C 14TH FLOOR WPC PANNELING WORK | TOWER C 14TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24544 |  |  |  | TOWER C | TOWER C 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24545 |  |  |  | TOWER C 15TH FLOOR | TOWER C 15TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24546 |  |  |  | TOWER C 15TH FLOOR CIVIL WORK | TOWER C 15TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24549 |  |  |  | TOWER C 15TH FLOOR RCC WORK | TOWER C 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135527.9 |  | Tentative | 135527.9 | 0 | 135527.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41018 |  |  |  | TOWER C 15TH FLOOR RCC WORK | TOWER C 15TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24547 |  |  |  | TOWER C 15TH FLOOR CIVIL WORK | TOWER C 15TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24550 |  |  |  | TOWER C 15TH FLOOR MASONRY WORK | TOWER C 15TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24548 |  |  |  | TOWER C 15TH FLOOR CIVIL WORK | TOWER C 15TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24551 |  |  |  | TOWER C 15TH FLOOR PLASTER WORK | TOWER C 15TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29756 |  |  |  | TOWER C 15TH FLOOR | TOWER C 1501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29748 |  |  |  | TOWER C 1501 | TOWER C 1501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33633 |  |  |  | TOWER C 1501 WATERPROOFING WORK | TOWER C 1501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29750 |  |  |  | TOWER C 1501 | TOWER C 1501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33029 |  |  |  | TOWER C 1501 PLUMBING WORK | TOWER C 1501 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29749 |  |  |  | TOWER C 1501 | TOWER C 1501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33841 |  |  |  | TOWER C 1501 ELECTRIC WORK | TOWER C 1501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29751 |  |  |  | TOWER C 1501 | TOWER C 1501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29754 |  |  |  | TOWER C 1501 | TOWER C 1501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29752 |  |  |  | TOWER C 1501 | TOWER C 1501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29753 |  |  |  | TOWER C 1501 | TOWER C 1501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29755 |  |  |  | TOWER C 1501 | TOWER C 1501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34441 |  |  |  | TOWER C 1501 | TOWER C 1501 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34442 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34443 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34444 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40305 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29765 |  |  |  | TOWER C 15TH FLOOR | TOWER C 1502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29757 |  |  |  | TOWER C 1502 | TOWER C 1502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33634 |  |  |  | TOWER C 1502 WATERPROOFING WORK | TOWER C 1502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29759 |  |  |  | TOWER C 1502 | TOWER C 1502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33030 |  |  |  | TOWER C 1502 PLUMBING WORK | TOWER C 1502 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29758 |  |  |  | TOWER C 1502 | TOWER C 1502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33842 |  |  |  | TOWER C 1502 ELECTRIC WORK | TOWER C 1502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29760 |  |  |  | TOWER C 1502 | TOWER C 1502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29763 |  |  |  | TOWER C 1502 | TOWER C 1502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29761 |  |  |  | TOWER C 1502 | TOWER C 1502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29762 |  |  |  | TOWER C 1502 | TOWER C 1502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29764 |  |  |  | TOWER C 1502 | TOWER C 1502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34445 |  |  |  | TOWER C 1502 | TOWER C 1502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34446 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34447 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34448 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40306 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29423 |  |  |  | TOWER C 15TH FLOOR | TOWER C 15TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29426 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29424 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41994 |  |  |  | TOWER C 15TH FLOOR COMMON FLOORING WORK | TOWER C 15TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29425 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29427 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29428 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38762 |  |  |  | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 41000 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41001 |  |  |  | TOWER C 15TH FLOOR WPC PANNELING WORK | TOWER C 15TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24552 |  |  |  | TOWER C | TOWER C 16TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24553 |  |  |  | TOWER C 16TH FLOOR | TOWER C 16TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24554 |  |  |  | TOWER C 16TH FLOOR CIVIL WORK | TOWER C 16TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24557 |  |  |  | TOWER C 16TH FLOOR RCC WORK | TOWER C 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 18765.9 |  | Tentative | 18765.9 | 0 | 18765.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41019 |  |  |  | TOWER C 16TH FLOOR RCC WORK | TOWER C 16TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24555 |  |  |  | TOWER C 16TH FLOOR CIVIL WORK | TOWER C 16TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24558 |  |  |  | TOWER C 16TH FLOOR MASONRY WORK | TOWER C 16TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24556 |  |  |  | TOWER C 16TH FLOOR CIVIL WORK | TOWER C 16TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24559 |  |  |  | TOWER C 16TH FLOOR PLASTER WORK | TOWER C 16TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29774 |  |  |  | TOWER C 16TH FLOOR | TOWER C 1601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29766 |  |  |  | TOWER C 1601 | TOWER C 1601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33635 |  |  |  | TOWER C 1601 WATERPROOFING WORK | TOWER C 1601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29768 |  |  |  | TOWER C 1601 | TOWER C 1601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33031 |  |  |  | TOWER C 1601 PLUMBING WORK | TOWER C 1601 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29767 |  |  |  | TOWER C 1601 | TOWER C 1601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33843 |  |  |  | TOWER C 1601 ELECTRIC WORK | TOWER C 1601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29769 |  |  |  | TOWER C 1601 | TOWER C 1601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29772 |  |  |  | TOWER C 1601 | TOWER C 1601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29770 |  |  |  | TOWER C 1601 | TOWER C 1601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29771 |  |  |  | TOWER C 1601 | TOWER C 1601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29773 |  |  |  | TOWER C 1601 | TOWER C 1601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34449 |  |  |  | TOWER C 1601 | TOWER C 1601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34450 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34451 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34452 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40307 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29783 |  |  |  | TOWER C 16TH FLOOR | TOWER C 1602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29775 |  |  |  | TOWER C 1602 | TOWER C 1602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33636 |  |  |  | TOWER C 1602 WATERPROOFING WORK | TOWER C 1602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29777 |  |  |  | TOWER C 1602 | TOWER C 1602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33032 |  |  |  | TOWER C 1602 PLUMBING WORK | TOWER C 1602 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29776 |  |  |  | TOWER C 1602 | TOWER C 1602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33844 |  |  |  | TOWER C 1602 ELECTRIC WORK | TOWER C 1602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29778 |  |  |  | TOWER C 1602 | TOWER C 1602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29781 |  |  |  | TOWER C 1602 | TOWER C 1602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29779 |  |  |  | TOWER C 1602 | TOWER C 1602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29780 |  |  |  | TOWER C 1602 | TOWER C 1602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29782 |  |  |  | TOWER C 1602 | TOWER C 1602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34453 |  |  |  | TOWER C 1602 | TOWER C 1602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34454 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34455 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34456 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40308 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29429 |  |  |  | TOWER C 16TH FLOOR | TOWER C 16TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29432 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29430 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41995 |  |  |  | TOWER C 16TH FLOOR COMMON FLOORING WORK | TOWER C 16TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29431 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29433 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29434 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38763 |  |  |  | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 41002 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41003 |  |  |  | TOWER C 16TH FLOOR WPC PANNELING WORK | TOWER C 16TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24560 |  |  |  | TOWER C | TOWER C 17TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24561 |  |  |  | TOWER C 17TH FLOOR | TOWER C 17TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24562 |  |  |  | TOWER C 17TH FLOOR CIVIL WORK | TOWER C 17TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24565 |  |  |  | TOWER C 17TH FLOOR RCC WORK | TOWER C 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 3437.9 |  | Tentative | 3437.9 | 0 | 3437.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24563 |  |  |  | TOWER C 17TH FLOOR CIVIL WORK | TOWER C 17TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24566 |  |  |  | TOWER C 17TH FLOOR MASONRY WORK | TOWER C 17TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24564 |  |  |  | TOWER C 17TH FLOOR CIVIL WORK | TOWER C 17TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24567 |  |  |  | TOWER C 17TH FLOOR PLASTER WORK | TOWER C 17TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29792 |  |  |  | TOWER C 17TH FLOOR | TOWER C 1701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29784 |  |  |  | TOWER C 1701 | TOWER C 1701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29786 |  |  |  | TOWER C 1701 | TOWER C 1701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33033 |  |  |  | TOWER C 1701 PLUMBING WORK | TOWER C 1701 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29785 |  |  |  | TOWER C 1701 | TOWER C 1701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40396 |  |  |  | TOWER C 1701 ELECTRIC WORK | TOWER C 1701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29787 |  |  |  | TOWER C 1701 | TOWER C 1701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29790 |  |  |  | TOWER C 1701 | TOWER C 1701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29788 |  |  |  | TOWER C 1701 | TOWER C 1701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29789 |  |  |  | TOWER C 1701 | TOWER C 1701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29791 |  |  |  | TOWER C 1701 | TOWER C 1701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34457 |  |  |  | TOWER C 1701 | TOWER C 1701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34458 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34459 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34460 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40309 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5778 |  | Tentative | 0 | 5778 | 5778 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29801 |  |  |  | TOWER C 17TH FLOOR | TOWER C 1702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29793 |  |  |  | TOWER C 1702 | TOWER C 1702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29795 |  |  |  | TOWER C 1702 | TOWER C 1702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33034 |  |  |  | TOWER C 1702 PLUMBING WORK | TOWER C 1702 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29794 |  |  |  | TOWER C 1702 | TOWER C 1702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40397 |  |  |  | TOWER C 1702 ELECTRIC WORK | TOWER C 1702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29796 |  |  |  | TOWER C 1702 | TOWER C 1702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29799 |  |  |  | TOWER C 1702 | TOWER C 1702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29797 |  |  |  | TOWER C 1702 | TOWER C 1702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29798 |  |  |  | TOWER C 1702 | TOWER C 1702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29800 |  |  |  | TOWER C 1702 | TOWER C 1702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34461 |  |  |  | TOWER C 1702 | TOWER C 1702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34462 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34463 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34464 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40310 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5778 |  | Tentative | 0 | 5778 | 5778 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29435 |  |  |  | TOWER C 17TH FLOOR | TOWER C 17TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29438 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29436 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41996 |  |  |  | TOWER C 17TH FLOOR COMMON FLOORING WORK | TOWER C 17TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29437 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29439 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29440 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41004 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41005 |  |  |  | TOWER C 17TH FLOOR WPC PANNELING WORK | TOWER C 17TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 24568 |  |  |  | TOWER C | TOWER C 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24569 |  |  |  | TOWER C 18TH FLOOR | TOWER C 18TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24570 |  |  |  | TOWER C 18TH FLOOR CIVIL WORK | TOWER C 18TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24573 |  |  |  | TOWER C 18TH FLOOR RCC WORK | TOWER C 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 227.74 |  | Tentative | 227.74 | 0 | 227.74 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24571 |  |  |  | TOWER C 18TH FLOOR CIVIL WORK | TOWER C 18TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24574 |  |  |  | TOWER C 18TH FLOOR MASONRY WORK | TOWER C 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24572 |  |  |  | TOWER C 18TH FLOOR CIVIL WORK | TOWER C 18TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24575 |  |  |  | TOWER C 18TH FLOOR PLASTER WORK | TOWER C 18TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29828 |  |  |  | TOWER C 18TH FLOOR | TOWER C 1801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29820 |  |  |  | TOWER C 1801 | TOWER C 1801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29822 |  |  |  | TOWER C 1801 | TOWER C 1801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33035 |  |  |  | TOWER C 1801 PLUMBING WORK | TOWER C 1801 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29821 |  |  |  | TOWER C 1801 | TOWER C 1801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40398 |  |  |  | TOWER C 1801 ELECTRIC WORK | TOWER C 1801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29823 |  |  |  | TOWER C 1801 | TOWER C 1801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29826 |  |  |  | TOWER C 1801 | TOWER C 1801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29824 |  |  |  | TOWER C 1801 | TOWER C 1801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29825 |  |  |  | TOWER C 1801 | TOWER C 1801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29827 |  |  |  | TOWER C 1801 | TOWER C 1801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34465 |  |  |  | TOWER C 1801 | TOWER C 1801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34466 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34467 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34468 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40311 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 3813 |  | Tentative | 0 | 3813 | 3813 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29837 |  |  |  | TOWER C 18TH FLOOR | TOWER C 1802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29829 |  |  |  | TOWER C 1802 | TOWER C 1802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29831 |  |  |  | TOWER C 1802 | TOWER C 1802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33036 |  |  |  | TOWER C 1802 PLUMBING WORK | TOWER C 1802 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29830 |  |  |  | TOWER C 1802 | TOWER C 1802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40399 |  |  |  | TOWER C 1802 ELECTRIC WORK | TOWER C 1802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29832 |  |  |  | TOWER C 1802 | TOWER C 1802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29835 |  |  |  | TOWER C 1802 | TOWER C 1802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29833 |  |  |  | TOWER C 1802 | TOWER C 1802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29834 |  |  |  | TOWER C 1802 | TOWER C 1802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29836 |  |  |  | TOWER C 1802 | TOWER C 1802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34469 |  |  |  | TOWER C 1802 | TOWER C 1802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34470 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34471 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34472 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40312 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 3813 |  | Tentative | 0 | 3813 | 3813 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29441 |  |  |  | TOWER C 18TH FLOOR | TOWER C 18TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29444 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29442 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41997 |  |  |  | TOWER C 18TH FLOOR COMMON FLOORING WORK | TOWER C 18TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29443 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29445 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29446 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41006 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41007 |  |  |  | TOWER C 18TH FLOOR WPC PANNELING WORK | TOWER C 18TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 3 | 41501 |  |  |  | TOWER C | TOWER C TERRACE | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41502 |  |  |  | TOWER C TERRACE | TOWER C TERRACE CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41503 |  |  |  | TOWER C TERRACE CIVIL WORK | TOWER C TERRACE RCC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41506 |  |  |  | TOWER C TERRACE RCC WORK | TOWER C TERRACE RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 41504 |  |  |  | TOWER C TERRACE CIVIL WORK | TOWER C TERRACE MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41507 |  |  |  | TOWER C TERRACE MASONRY WORK | TOWER C TERRACE MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 41505 |  |  |  | TOWER C TERRACE CIVIL WORK | TOWER C TERRACE PLASTER WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41508 |  |  |  | TOWER C TERRACE PLASTER WORK | TOWER C TERRACE PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 41447 |  |  |  | TOWER C | TOWER C COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41448 |  |  |  | TOWER C COMMON WORK | TOWER C COMMON PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41449 |  |  |  | TOWER C COMMON PLUMBING WORK | TOWER C COMMON DUCT PLUMBING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING DUCT-PVC-SWR DRAINAGE PIPING WO
Group | 4 | 41477 |  |  |  | TOWER C COMMON WORK | TOWER C COMMON ELECTRIC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41478 |  |  |  | TOWER C COMMON ELECTRIC WORK | TOWER C COMMON ELECTRIC WORK | 1 | POINT | 1 | POINT | 0 | ELECTRIC WORK | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | TOWER COMMON ELECTRIC WORK
Group | 4 | 42153 | Block/Building/Tower/Wing |  | Externall Plaster | TOWER C COMMON WORK | TOWER C EXTERNAL PAINT WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 42154 |  |  |  | TOWER C EXTERNAL PAINT WORK | TOWER C EXTERNAL PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | EXTERNAL PAINT WORK
Group | 2 | 24028 |  |  |  |  | TOWER D | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 3 | 24029 |  |  |  | TOWER D | TOWER D BASEMENT | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | -
Group | 4 | 24072 |  |  |  | TOWER D BASEMENT | TOWER D BASEMENT CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 16 Jul 2021 |  | - | - | 487 | -
Group | 5 | 24073 |  |  |  | TOWER D BASEMENT CIVIL WORK | TOWER D BASEMENT RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 16 Jul 2021 |  | - | - | 487 | -
Task | 6 | 24030 |  |  |  | TOWER D BASEMENT RCC WORK | TOWER D BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 261196.6 |  | Started | 232696.6 | 28500 | 261196.6 | 16.05 | 4192732.79 | 8400848.68 | 4815872.19 | 13216720.87 | 17 Mar 2020 |  | 20 Oct 2021 |  | - | - | 583 | - | RCC WORK
Task | 6 | 25357 |  |  |  | TOWER D BASEMENT RCC WORK | TOWER D BASEMENT THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 49866.82 | 49866.82 |  |  | 16 Jul 2021 |  | - | - | - | - | THREADING
Task | 6 | 26044 |  |  |  | TOWER D BASEMENT RCC WORK | TOWER D BASEMENT RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 5595 |  | Started | 0 | 5595 | 5595 | 0 | 5.6 | 0 | 22608.8 | 22608.8 | 17 Mar 2020 |  | 26 Mar 2022 |  | - | - | 740 | - | REBARING WORK
Group | 5 | 24074 |  |  |  | TOWER D BASEMENT CIVIL WORK | TOWER D BASEMENT PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 24075 |  |  |  | TOWER D BASEMENT PLASTER WORK | TOWER D BASEMENT PLASTER WORK | 1 | SQFT | 1 | SQFT | 900 |  | Started | 900 | 0 | 900 | 16.05 | 14446.82 | 0 | 1604660.68 | 1604660.68 | 17 Mar 2020 |  | 23 Feb 2024 |  | - | - | 1439 | - | PLASTER WORK
Group | 5 | 25737 |  |  |  | TOWER D BASEMENT CIVIL WORK | TOWER D BASEMENT CIVIL WORK REBARING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 13 Sep 2021 |  | - | - | 546 | -
Task | 6 | 25740 |  |  |  | TOWER D BASEMENT CIVIL WORK REBARING WORK | TOWER D BASEMENT CIVIL WORK REBARING WORK | 1 | NOS | 1 | NOS | 21332 |  | Started | 0 | 21332 | 21332 | 0 | 21.33 | 0 | 226513.98 | 226513.98 | 17 Mar 2020 |  | 13 Sep 2021 |  | - | - | 546 | - | REBARING WORK
Group | 5 | 37100 |  |  |  | TOWER D BASEMENT CIVIL WORK | TOWER D BASEMENT MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 May 2023 |  | - | - | 1171 | -
Task | 6 | 37101 |  |  |  | TOWER D BASEMENT MASONRY WORK | TOWER D BASEMENT MASONRY WORK | 1 | SQFT | 1 | SQFT | 15100 |  | Started | 15100 | 0 | 15100 | 0 | 15.1 | 0 | 4248 | 4248 | 17 Mar 2020 |  | 31 May 2023 |  | - | - | 1171 | - | MASONRY WORK
Group | 4 | 24862 |  |  |  | TOWER D BASEMENT | TOWER D BASEMENT FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Jul 2021 |  | - | - | - | -
Group | 5 | 24872 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | -
Task | 6 | 24863 |  |  |  | TOWER D BASEMENT WATERPROOFING WORK | TOWER D BASEMENT WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 9.5 | 0 | 0 | 223420 | 223420 |  |  | 07 Jul 2021 |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29857 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29878 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29859 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29860 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29861 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29862 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29863 |  |  |  | TOWER D BASEMENT FINISHING WORK | TOWER D BASEMENT FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 29864 |  |  |  | TOWER D BASEMENT | TOWER D BASEMENT COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Sep 2021 |  | - | - | 539 | -
Group | 5 | 29867 |  |  |  | TOWER D BASEMENT COMMON WORK | TOWER D BASEMENT COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29868 |  |  |  | TOWER D BASEMENT COMMON WORK | TOWER D BASEMENT COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29869 |  |  |  | TOWER D BASEMENT COMMON WORK | TOWER D BASEMENT COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29870 |  |  |  | TOWER D BASEMENT COMMON WORK | TOWER D BASEMENT COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 25896 |  |  |  | TOWER D BASEMENT COMMON WORK | TOWER D BASEMENT COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Sep 2021 |  | - | - | 539 | -
Task | 6 | 25897 |  |  |  | TOWER D BASEMENT COMMON ELECTRIC WORK | TOWER D BASEMENT COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 106179.36 | 106179.36 | 17 Mar 2020 |  | 06 Sep 2021 |  | - | - | 539 | - | ELECTRIC WORK
Group | 3 | 24584 |  |  |  | TOWER D | TOWER D GROUND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24585 |  |  |  | TOWER D GROUND FLOOR | TOWER D GROUND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24586 |  |  |  | TOWER D GROUND FLOOR CIVIL WORK | TOWER D GROUND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24589 |  |  |  | TOWER D GROUND FLOOR RCC WORK | TOWER D GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 41079.44 |  | Started | 41079.44 | 0 | 41079.44 | 5.72 | 234948.85 | 2364667.64 | 1090159.55 | 3454827.19 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 25959 |  |  |  | TOWER D GROUND FLOOR RCC WORK | TOWER D GROUND FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 52569 | 52569 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 42019 |  |  |  | TOWER D GROUND FLOOR RCC WORK | TOWER D GROUND FLOOR PUNNING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | APPLYING PUNNING WORK
Group | 5 | 24587 |  |  |  | TOWER D GROUND FLOOR CIVIL WORK | TOWER D GROUND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24590 |  |  |  | TOWER D GROUND FLOOR MASONRY WORK | TOWER D GROUND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 256128.5 |  | Tentative | 256128.5 | 0 | 256128.5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24588 |  |  |  | TOWER D GROUND FLOOR CIVIL WORK | TOWER D GROUND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 09 Feb 2023 |  | - | - | - | -
Task | 6 | 24591 |  |  |  | TOWER D GROUND FLOOR PLASTER WORK | TOWER D GROUND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2741.18 |  | Started | 2741.18 | 0 | 2741.18 | 5.77 | 15821.49 | 0 | 486301.37 | 486301.37 |  |  | 09 Feb 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 30348 |  |  |  | TOWER D GROUND FLOOR | TOWER D GROUND FLOOR FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30350 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 30349 |  |  |  | TOWER D GROUND FLOOR WATERPROOFING WORK | TOWER D GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30353 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30351 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 30352 |  |  |  | TOWER D GROUND FLOOR ELECTRIC WORK | TOWER D GROUND FLOOR ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30354 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41562 |  |  |  | TOWER D GROUND FLOOR FLOORING & DEDO WORK | TOWER D GROUND FLOOR FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 30357 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30355 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30356 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32905 |  |  |  | TOWER D GROUND FLOOR PAINT WORK | TOWER D GROUND FLOOR PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 103518.48 | 103518.48 | 17 Mar 2020 |  | 16 Aug 2024 |  | - | - | 1614 | - | PAINT WORK
Group | 5 | 30358 |  |  |  | TOWER D GROUND FLOOR FINISHING WORK | TOWER D GROUND FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 29871 |  |  |  | TOWER D GROUND FLOOR | TOWER D GROUND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 29874 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32600 |  |  |  | TOWER D GROUND FLOOR COMMON DEBRISH CHUTE WORK | TOWER D GROUND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29875 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40602 |  |  |  | TOWER D GROUND FLOOR COMMON FLOORING WORK | TOWER D GROUND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 212.4 |  | Tentative | 212.4 | 0 | 212.4 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29876 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41399 |  |  |  | TOWER D GROUND FLOOR COMMON RAILING WORK | TOWER D GROUND FLOOR COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 15 Jul 2024 |  | - | - | 1582 | - | SS RAILING FOR STAIR
Group | 5 | 29877 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41413 |  |  |  | TOWER D GROUND FLOOR COMMON FALSE CEILING WORK | TOWER D GROUND FLOOR COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 16496.4 | 16496.4 | 17 Mar 2020 |  | 24 Oct 2024 |  | - | - | 1683 | - | PVC FALSE CEILING
Group | 5 | 26465 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 26466 |  |  |  | TOWER D GROUND FLOOR COMMON ELECTRIC WORK | TOWER D GROUND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 4.72 |  | Started | 4.72 | 0 | 4.72 | 0 | 0 | 0 | 67632.89 | 67632.89 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 41389 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR GLASS WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41390 |  |  |  | TOWER D GROUND FLOOR GLASS WORK | TOWER D GROUND FLOOR GLASS WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 36224.53 | 36224.53 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | GLASS FIXING WORK
Group | 5 | 41434 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR COMMON ALUMINUM WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41435 |  |  |  | TOWER D GROUND FLOOR COMMON ALUMINUM WORK | TOWER D GROUND FLOOR COMMON ALUMINUM WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 125698.32 | 125698.32 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ALUMINIUM FINS
Group | 5 | 41774 |  |  |  | TOWER D GROUND FLOOR COMMON WORK | TOWER D GROUND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41775 |  |  |  | TOWER D GROUND FLOOR WPC PANNELING WORK | TOWER D GROUND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 223167.5 | 223167.5 | 17 Mar 2020 |  | 15 Oct 2024 |  | - | - | 1674 | - | WPC PANNELING WORK
Group | 3 | 24592 |  |  |  | TOWER D | TOWER D 1ST FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24593 |  |  |  | TOWER D 1ST FLOOR | TOWER D 1ST FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24594 |  |  |  | TOWER D 1ST FLOOR CIVIL WORK | TOWER D 1ST FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24597 |  |  |  | TOWER D 1ST FLOOR RCC WORK | TOWER D 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 43382.96 |  | Started | 43382.96 | 0 | 43382.96 | 5.77 | 250396.9 | 2756880.3 | 1114945.21 | 3871825.51 |  |  | 01 Nov 2021 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 26643 |  |  |  | TOWER D 1ST FLOOR RCC WORK | TOWER D 1ST FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 40865.72 | 40865.72 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 31076 |  |  |  | TOWER D 1ST FLOOR RCC WORK | TOWER D 1ST FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 525 |  | Started | 525 | 0 | 525 | 0 | 0.53 | 0 | 111514.64 | 111514.64 | 17 Mar 2020 |  | 20 Apr 2022 |  | - | - | 765 | - | FIRE AND SAFETY WORK
Task | 6 | 42020 |  |  |  | TOWER D 1ST FLOOR RCC WORK | TOWER D 1ST FLOOR PUNNING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | APPLYING PUNNING WORK
Group | 5 | 24595 |  |  |  | TOWER D 1ST FLOOR CIVIL WORK | TOWER D 1ST FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 08 Jul 2022 |  | - | - | - | -
Task | 6 | 24598 |  |  |  | TOWER D 1ST FLOOR MASONRY WORK | TOWER D 1ST FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 345810.1 |  | Started | 345810.1 | 0 | 345810.1 | 5.77 | 1995939.82 | 0 | 305697.44 | 305697.44 |  |  | 08 Jul 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24596 |  |  |  | TOWER D 1ST FLOOR CIVIL WORK | TOWER D 1ST FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14 Dec 2022 |  | - | - | - | -
Task | 6 | 24599 |  |  |  | TOWER D 1ST FLOOR PLASTER WORK | TOWER D 1ST FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 6926.54 |  | Started | 6926.54 | 0 | 6926.54 | 5.77 | 39978.47 | 0 | 568946.58 | 568946.58 |  |  | 14 Dec 2022 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39307 |  |  |  | TOWER D 1ST FLOOR CIVIL WORK | TOWER D 1ST FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39308 |  |  |  | TOWER D 1ST FLOOR CIVIL EXTRA WORK | TOWER D 1ST FLOOR CIVIL EXTRA WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 22573.4 | 22573.4 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29907 |  |  |  | TOWER D 1ST FLOOR | TOWER D 101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Group | 5 | 29901 |  |  |  | TOWER D 101 | TOWER D 101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Jul 2023 |  | - | - | 1207 | -
Task | 6 | 32801 |  |  |  | TOWER D 101 PLUMBING WORK | TOWER D 101 PLUMBING WORK | 1 | NOS | 1 | NOS | 727.5 |  | Started | 727.5 | 0 | 727.5 | 0 | 0.73 | 0 | 21854 | 21854 | 17 Mar 2020 |  | 06 Jul 2023 |  | - | - | 1207 | - | PLUMBING WORK
Group | 5 | 29900 |  |  |  | TOWER D 101 | TOWER D 101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Task | 6 | 32751 |  |  |  | TOWER D 101 ELECTRIC WORK | TOWER D 101 ELECTRIC WORK | 1 | NOS | 0 | NOS | 9.36 |  | Started | 9.36 | 0 | 9.36 | 0 | 0.01 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | - | ELECTRIC WORK
Group | 5 | 29902 |  |  |  | TOWER D 101 | TOWER D 101 FLOORING &AMP; DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 28 Aug 2023 |  | - | - | 1260 | -
Task | 6 | 33038 |  |  |  | TOWER D 101 FLOORING &AMP; DEDO WORK | TOWER D 101 FLOORING & DEDO WORK | 1 | SQFT | 0 | SQFT | 3435.84 |  | Started | 575.84 | 2860 | 3435.84 | 0 | 3.44 | 0 | 0 | 0 | 17 Mar 2020 |  | 28 Aug 2023 |  | - | - | 1260 | - | FLOORING & DEDO
Group | 5 | 29905 |  |  |  | TOWER D 101 | TOWER D 101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33094 |  |  |  | TOWER D 101 CARPENTRY WORK | TOWER D 101 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 10006.4 | 10006.4 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 38847 |  |  |  | TOWER D 101 | TOWER D 101WATERPROOFING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Oct 2023 |  | - | - | 1318 | -
Task | 6 | 38848 |  |  |  | TOWER D 101WATERPROOFING WORK | TOWER D 101WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 15 |  | Started | 15 | 0 | 15 | 0 | 0.02 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Oct 2023 |  | - | - | 1318 | - | WATERPROOFING WORK
Group | 4 | 38260 |  |  |  | TOWER D 1ST FLOOR | TOWER D 101 SH | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 18 Aug 2023 |  | - | - | 1250 | -
Group | 5 | 38261 |  |  |  | TOWER D 101 SH | TOWER D 101 SH PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38262 |  |  |  | TOWER D 101 SH PLUMBING WORK | TOWER D 101 SH CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 110.66 |  | Tentative | 110.66 | 0 | 110.66 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Task | 6 | 38328 |  |  |  | TOWER D 101 SH PLUMBING WORK | TOWER D 101 SH PLUMBING WORK | 1 | NOS | 1 | NOS | 489.7 |  | Tentative | 489.7 | 0 | 489.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 38283 |  |  |  | TOWER D 101 SH | TOWER D 101 SH CONSULTANCY CHARGES | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 18 Aug 2023 |  | - | - | 1250 | -
Task | 6 | 38284 |  |  |  | TOWER D 101 SH CONSULTANCY CHARGES | TOWER D 101 SH CONSULTANCY CHARGES | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 118000 | 118000 | 17 Mar 2020 |  | 18 Aug 2023 |  | - | - | 1250 | - | CONSULTANCY CHARGES
Group | 5 | 38290 |  |  |  | TOWER D 101 SH | TOWER D 101 SH PUNNING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38291 |  |  |  | TOWER D 101 SH PUNNING WORK | TOWER D 101 SH PUNNING WORK | 1 | SQFT | 1 | SQFT | 200 |  | Tentative | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | APPLYING PUNNING WORK
Group | 5 | 38300 |  |  |  | TOWER D 101 SH | TOWER D 101 SH ELECTRIC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Oct 2023 |  | - | - | 1313 | -
Task | 6 | 38301 |  |  |  | TOWER D 101 SH ELECTRIC WORK | TOWER D 101 SH ELECTRIC WORK | 1 | NOS | 1 | NOS | 860.44 |  | Started | 860.44 | 0 | 860.44 | 0 | 0 | 0 | 94152.2 | 94152.2 | 17 Mar 2020 |  | 20 Oct 2023 |  | - | - | 1313 | - | ELECTRIC WORK
Group | 5 | 38326 |  |  |  | TOWER D 101 SH | TOWER D 101 SH FLOORING & DEDO WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 28 Aug 2023 |  | - | - | 1260 | -
Task | 6 | 38327 |  |  |  | TOWER D 101 SH FLOORING & DEDO WORK | TOWER D 101 SH FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 38219.39 |  | Started | 35067.9 | 3151.49 | 38219.39 | 0 | 38.22 | 0 | 590394.79 | 590394.79 | 17 Mar 2020 |  | 28 Aug 2023 |  | - | - | 1260 | - | FLOORING & DEDO
Group | 5 | 38374 |  |  |  | TOWER D 101 SH | TOWER D 101 SH HVAC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Oct 2023 |  | - | - | 1299 | -
Task | 6 | 38375 |  |  |  | TOWER D 101 SH HVAC WORK | TOWER D 101 SH HVAC WORK | 1 | NOS | 1 | NOS | 349.38 |  | Started | 349.38 | 0 | 349.38 | 0 | 0.35 | 0 | 16649.8 | 16649.8 | 17 Mar 2020 |  | 06 Oct 2023 |  | - | - | 1299 | - | HVAC INSTALLATION
Group | 5 | 38376 |  |  |  | TOWER D 101 SH | TOWER D 101 SH COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40095 |  |  |  | TOWER D 101 SH COMMON WORK | TOWER D 101 SH COMMON MISC WORK | 1 | NOS | 1 | NOS | 94.4 |  | Started | 94.4 | 0 | 94.4 | 0 | 0.09 | 0 | 20060 | 20060 | 17 Mar 2020 |  | 11 Jul 2024 |  | - | - | 1578 | - | MISCELLANEOUS WORK
Group | 5 | 38439 |  |  |  | TOWER D 101 SH | TOWER D 101 SH FURNITURE WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Sep 2023 |  | - | - | 1264 | -
Task | 6 | 38440 |  |  |  | TOWER D 101 SH FURNITURE WORK | TOWER D 101 SH FURNITURE WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 2846786.6 | 2846786.6 | 17 Mar 2020 |  | 01 Sep 2023 |  | - | - | 1264 | - | INTERNAL CARPENTRY WORK
Group | 5 | 38668 |  |  |  | TOWER D 101 SH | TOWER D 101 SH WATERPROOFING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2023 |  | - | - | 1263 | -
Task | 6 | 38669 |  |  |  | TOWER D 101 SH WATERPROOFING WORK | TOWER D 101 SH DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2023 |  | - | - | 1263 | - | DRILLING WORK
Task | 6 | 38735 |  |  |  | TOWER D 101 SH WATERPROOFING WORK | TOWER D 101 SH WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 85382.44 | 85382.44 | 17 Mar 2020 |  | 04 Sep 2023 |  | - | - | 1267 | - | WATERPROOFING WORK
Group | 5 | 38674 |  |  |  | TOWER D 101 SH | TOWER D 101 SH AUTOMATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38675 |  |  |  | TOWER D 101 SH AUTOMATION WORK | TOWER D 101 SH AUTOMATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 507834.24 | 507834.24 | 17 Mar 2020 |  | 15 Oct 2024 |  | - | - | 1674 | - | ELECTRIC AUTOMATION
Group | 5 | 39262 |  |  |  | TOWER D 101 SH | TOWER D 101 SH PAINT WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39263 |  |  |  | TOWER D 101 SH PAINT WORK | TOWER D 101 SH PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 03 Sep 2024 |  | - | - | 1632 | - | PAINT WORK
Task | 6 | 39683 |  |  |  | TOWER D 101 SH PAINT WORK | TOWER D 101 SH TEXTURE WORK | 1 | SQFT | 1 | SQFT | 329.338 | INTERIOR WORK | Tentative | 329.34 | 0 | 329.34 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | TEXTURE WORK
Group | 5 | 40208 |  |  |  | TOWER D 101 SH | TOWER D 101 SH ALUMINIUM DOOR & WINDOW | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40209 |  |  |  | TOWER D 101 SH ALUMINIUM DOOR & WINDOW | TOWER D 101 SH ALUMINIUM WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 356080.1 | 356080.1 | 17 Mar 2020 |  | 31 May 2024 |  | - | - | 1537 | - | ALUMINUM WINDOW WORK
Group | 5 | 41318 |  |  |  | TOWER D 101 SH | TOWER D 101 SH KITCHEN APPLIANCES | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41319 |  |  |  | TOWER D 101 SH KITCHEN APPLIANCES | TOWER D 101 SH KITCHEN APPLIANCES | 1 | NOS | 1 | NOS | 5.72 |  | Tentative | 5.72 | 0 | 5.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | INSTALLATION OF MODULAR KITCHEN
Group | 5 | 41374 |  |  |  | TOWER D 101 SH | TOWER D 101 SH GLASS WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41375 |  |  |  | TOWER D 101 SH GLASS WORK | TOWER D 101 SH GLASS WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 48041.34 | 48041.34 | 17 Mar 2020 |  | 20 Jun 2024 |  | - | - | 1557 | - | GLASS FIXING WORK
Group | 5 | 41454 |  |  |  | TOWER D 101 SH | TOWER D 101 SH CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41455 |  |  |  | TOWER D 101 SH CIVIL WORK | TOWER D 101 SH CIVIL WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 33821.2 | 33821.2 | 17 Mar 2020 |  | 04 Aug 2024 |  | - | - | 1602 | - | CIVIL EXTRA WORK
Group | 5 | 41459 |  |  |  | TOWER D 101 SH | TOWER D 101 SH PLANTATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41460 |  |  |  | TOWER D 101 SH PLANTATION WORK | TOWER D 101 SH PLANTATION WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 32940 | 32940 | 17 Mar 2020 |  | 30 Jul 2024 |  | - | - | 1597 | - | GARDENING WORK
Group | 5 | 38377 |  |  |  | TOWER D 101 SH | TOWER D 101 SH ANTITERMITE WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38378 |  |  |  | TOWER D 101 SH ANTITERMITE WORK | TOWER D 101 SH ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5880 |  | Tentative | 0 | 5880 | 5880 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 5 | 39373 |  |  |  | TOWER D 101 SH | TOWER D 101 SH RAILING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39374 |  |  |  | TOWER D 101 SH RAILING WORK | TOWER D 101 SH RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 122891.1 | 122891.1 | 17 Mar 2020 |  | 12 Feb 2024 |  | - | - | 1428 | - | BALCONY RAILING
Group | 5 | 39375 |  |  |  | TOWER D 101 SH | TOWER D 101 SH FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39376 |  |  |  | TOWER D 101 SH FABRICATION WORK | TOWER D 101 SH FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 51841.5 | 51841.5 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | MISCELLANEOUS FABRICATION WORK
Group | 5 | 41471 |  |  |  | TOWER D 101 SH | TOWER D 101 SH CURTAIN & MATTRESSES | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41472 |  |  |  | TOWER D 101 SH CURTAIN & MATTRESSES | TOWER D 101 SH CURTAIN & MATTRESSES | 1 | SQFT | 1 | SQFT | 17135.575 | INTERIOR WORK | Started | 17135.58 | 0 | 17135.58 | 0 | 17.14 | 0 | 11550 | 11550 | 17 Mar 2020 |  | 12 Sep 2024 |  | - | - | 1641 | - | CURTAIN & MATTRESSES
Group | 4 | 29916 |  |  |  | TOWER D 1ST FLOOR | TOWER D 102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Oct 2022 |  | - | - | 943 | -
Group | 5 | 29908 |  |  |  | TOWER D 102 | TOWER D 102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2023 |  | - | - | 1263 | -
Task | 6 | 33590 |  |  |  | TOWER D 102 WATERPROOFING WORK | TOWER D 102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 15 |  | Started | 15 | 0 | 15 | 0 | 0.02 | 0 | 116076.6 | 116076.6 | 17 Mar 2020 |  | 31 Aug 2023 |  | - | - | 1263 | - | WATERPROOFING WORK
Task | 6 | 38651 |  |  |  | TOWER D 102 WATERPROOFING WORK | TOWER D 102 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 531 | 531 | 17 Mar 2020 |  | 04 Sep 2023 |  | - | - | 1267 | - | DRILLING WORK
Group | 5 | 29910 |  |  |  | TOWER D 102 | TOWER D 102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | -
Task | 6 | 32803 |  |  |  | TOWER D 102 PLUMBING WORK | TOWER D 102 PLUMBING WORK | 1 | NOS | 1 | NOS | 981.36 |  | Started | 981.36 | 0 | 981.36 | 0 | 0.98 | 0 | 29138 | 29138 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | PLUMBING WORK
Task | 6 | 38716 |  |  |  | TOWER D 102 PLUMBING WORK | TOWER D 102 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 205.3 |  | Tentative | 205.3 | 0 | 205.3 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29909 |  |  |  | TOWER D 102 | TOWER D 102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 15 Oct 2022 |  | - | - | 943 | -
Task | 6 | 32750 |  |  |  | TOWER D 102 ELECTRIC WORK | TOWER D 102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 2872.05 |  | Started | 2872.05 | 0 | 2872.05 | 0 | 2.87 | 0 | 28320 | 28320 | 17 Mar 2020 |  | 15 Oct 2022 |  | - | - | 943 | - | ELECTRIC WORK
Group | 5 | 29911 |  |  |  | TOWER D 102 | TOWER D 102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 May 2023 |  | - | - | 1166 | -
Task | 6 | 33037 |  |  |  | TOWER D 102 FLOORING & DEDO WORK | TOWER D 102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 14857.1704 |  | Started | 8342.17 | 6515 | 14857.17 | 0 | 14.86 | 0 | 232797.29 | 232797.29 | 17 Mar 2020 |  | 26 May 2023 |  | - | - | 1166 | - | FLOORING & DEDO
Group | 5 | 29914 |  |  |  | TOWER D 102 | TOWER D 102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33095 |  |  |  | TOWER D 102 CARPENTRY WORK | TOWER D 102 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 165876.14 | 165876.14 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29912 |  |  |  | TOWER D 102 | TOWER D 102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40210 |  |  |  | TOWER D 102 ALUMINIUM DOOR & WINDOW | TOWER D 102 ALUMINIUM WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 356080.1 | 356080.1 | 17 Mar 2020 |  | 31 May 2024 |  | - | - | 1537 | - | ALUMINUM WINDOW WORK
Group | 5 | 29913 |  |  |  | TOWER D 102 | TOWER D 102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39266 |  |  |  | TOWER D 102 PAINT WORK | TOWER D 102 PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 49259.54 | 49259.54 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | PAINT WORK
Group | 5 | 29915 |  |  |  | TOWER D 102 | TOWER D 102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38379 |  |  |  | TOWER D 102 HVAC WORK | TOWER D 102 HVAC WORK | 1 | NOS | 1 | NOS | 321.24 |  | Tentative | 321.24 | 0 | 321.24 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HVAC INSTALLATION
Group | 5 | 34477 |  |  |  | TOWER D 102 | TOWER D 102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 28 Mar 2023 |  | - | - | 1107 | -
Task | 6 | 34478 |  |  |  | TOWER D 102 COMMON WORK | TOWER D 102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 28480 |  | Started | 0 | 28480 | 28480 | 0 | 28.48 | 0 | 181380.16 | 181380.16 | 17 Mar 2020 |  | 28 Mar 2023 |  | - | - | 1107 | - | BALCONY RAILING
Task | 6 | 34479 |  |  |  | TOWER D 102 COMMON WORK | TOWER D 102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 146.02 |  | Tentative | 5.6 | 140.42 | 146.02 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34480 |  |  |  | TOWER D 102 COMMON WORK | TOWER D 102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 51841.5 | 51841.5 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 38719 |  |  |  | TOWER D 102 COMMON WORK | TOWER D 102 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29880 |  |  |  | TOWER D 1ST FLOOR | TOWER D 1ST FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Dec 2021 |  | - | - | 649 | -
Group | 5 | 29881 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32599 |  |  |  | TOWER D 1ST FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 1ST FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29882 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39696 |  |  |  | TOWER D 1ST FLOOR COMMON FLOORING WORK | TOWER D 1ST FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 1453.7128 |  | Tentative | 1453.71 | 0 | 1453.71 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29883 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29884 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40313 |  |  |  | TOWER D 1ST FLOOR COMMON FALSE CEILING WORK | TOWER D 1ST FLOOR COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 17513.2 | 17513.2 | 17 Mar 2020 |  | 24 Oct 2024 |  | - | - | 1683 | - | PVC FALSE CEILING
Group | 5 | 26468 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Dec 2021 |  | - | - | 649 | -
Task | 6 | 26469 |  |  |  | TOWER D 1ST FLOOR COMMON ELECTRIC WORK | TOWER D 1ST FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 4.72 |  | Started | 4.72 | 0 | 4.72 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 25 Dec 2021 |  | - | - | 649 | - | ELECTRIC WORK
Group | 5 | 40931 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40932 |  |  |  | TOWER D 1ST FLOOR WPC PANNELING WORK | TOWER D 1ST FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 72546.4 | 72546.4 | 17 Mar 2020 |  | 15 Oct 2024 |  | - | - | 1674 | - | WPC PANNELING WORK
Group | 5 | 41312 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41313 |  |  |  | TOWER D 1ST FLOOR COMMON PLUMBING WORK | TOWER D 1ST FLOOR COMMON PLUMBING WORK | 1 | NOS | 1 | NOS | 589.46 |  | Tentative | 589.46 | 0 | 589.46 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | EXTERNAL PLUMBING WORK
Group | 5 | 41436 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON ALUMINUM WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41437 |  |  |  | TOWER D 1ST FLOOR COMMON ALUMINUM WORK | TOWER D 1ST FLOOR COMMON ALUMINUM WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 96642 | 96642 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ALUMINIUM FINS
Group | 5 | 41778 |  |  |  | TOWER D 1ST FLOOR COMMON WORK | TOWER D 1ST FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41779 |  |  |  | TOWER D 1ST FLOOR COMMON FABRICATION WORK | TOWER D 1ST FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | FLOOR FABRICATION WORK
Group | 3 | 24600 |  |  |  | TOWER D | TOWER D 2ND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24601 |  |  |  | TOWER D 2ND FLOOR | TOWER D 2ND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24602 |  |  |  | TOWER D 2ND FLOOR CIVIL WORK | TOWER D 2ND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24605 |  |  |  | TOWER D 2ND FLOOR RCC WORK | TOWER D 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 36146.76 |  | Started | 36146.76 | 0 | 36146.76 | 5.77 | 208631.15 | 2593349.45 | 1081070.11 | 3674419.56 |  |  | 01 Nov 2021 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 27046 |  |  |  | TOWER D 2ND FLOOR RCC WORK | TOWER D 2ND FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 41013.72 | 41013.72 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 38388 |  |  |  | TOWER D 2ND FLOOR RCC WORK | TOWER D 2ND FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6726 | 6726 | 17 Mar 2020 |  | 16 Jul 2023 |  | - | - | 1217 | - | SAFETY NET FIXING
Task | 6 | 42021 |  |  |  | TOWER D 2ND FLOOR RCC WORK | TOWER D 2ND FLOOR PUNNING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | APPLYING PUNNING WORK
Group | 5 | 24603 |  |  |  | TOWER D 2ND FLOOR CIVIL WORK | TOWER D 2ND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2022 |  | - | - | - | -
Task | 6 | 24606 |  |  |  | TOWER D 2ND FLOOR MASONRY WORK | TOWER D 2ND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 318620.9 |  | Started | 318620.9 | 0 | 318620.9 | 5.77 | 1839009.74 | 0 | 291069.73 | 291069.73 |  |  | 01 Aug 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24604 |  |  |  | TOWER D 2ND FLOOR CIVIL WORK | TOWER D 2ND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14 Dec 2022 |  | - | - | - | -
Task | 6 | 24607 |  |  |  | TOWER D 2ND FLOOR PLASTER WORK | TOWER D 2ND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 6893 |  | Started | 6893 | 0 | 6893 | 5.77 | 39784.88 | 0 | 551163.48 | 551163.48 |  |  | 14 Dec 2022 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39309 |  |  |  | TOWER D 2ND FLOOR CIVIL WORK | TOWER D 2ND FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39310 |  |  |  | TOWER D 2ND FLOOR CIVIL EXTRA WORK | TOWER D 2ND FLOOR CIVIL EXTRA WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 22573.4 | 22573.4 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29925 |  |  |  | TOWER D 2ND FLOOR | TOWER D 201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Group | 5 | 29917 |  |  |  | TOWER D 201 | TOWER D 201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33591 |  |  |  | TOWER D 201 WATERPROOFING WORK | TOWER D 201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 7.5 |  | Tentative | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38652 |  |  |  | TOWER D 201 WATERPROOFING WORK | TOWER D 201 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29919 |  |  |  | TOWER D 201 | TOWER D 201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32966 |  |  |  | TOWER D 201 PLUMBING WORK | TOWER D 201 PLUMBING WORK | 1 | NOS | 0 | NOS | 961.94 |  | Started | 961.94 | 0 | 961.94 | 0 | 0.96 | 0 | 26904 | 26904 | 17 Mar 2020 |  | 18 Jan 2024 |  | - | - | 1403 | - | PLUMBING WORK
Task | 6 | 39325 |  |  |  | TOWER D 201 PLUMBING WORK | TOWER D 201 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 80.52 |  | Tentative | 80.52 | 0 | 80.52 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29918 |  |  |  | TOWER D 201 | TOWER D 201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Task | 6 | 33845 |  |  |  | TOWER D 201 ELECTRIC WORK | TOWER D 201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 34633 | 34633 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | - | ELECTRIC WORK
Group | 5 | 29920 |  |  |  | TOWER D 201 | TOWER D 201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38429 |  |  |  | TOWER D 201 FLOORING & DEDO WORK | TOWER D 201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 6574.0152 |  | Tentative | 3494.02 | 3080 | 6574.02 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29923 |  |  |  | TOWER D 201 | TOWER D 201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33096 |  |  |  | TOWER D 201 CARPENTRY WORK | TOWER D 201 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29921 |  |  |  | TOWER D 201 | TOWER D 201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29922 |  |  |  | TOWER D 201 | TOWER D 201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29924 |  |  |  | TOWER D 201 | TOWER D 201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38380 |  |  |  | TOWER D 201 HVAC WORK | TOWER D 201 HVAC WORK | 1 | NOS | 1 | NOS | 321.24 |  | Started | 321.24 | 0 | 321.24 | 0 | 0.32 | 0 | 7009.2 | 7009.2 | 17 Mar 2020 |  | 09 Sep 2024 |  | - | - | 1638 | - | HVAC INSTALLATION
Group | 5 | 34481 |  |  |  | TOWER D 201 | TOWER D 201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34482 |  |  |  | TOWER D 201 COMMON WORK | TOWER D 201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 110754.8 | 110754.8 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34483 |  |  |  | TOWER D 201 COMMON WORK | TOWER D 201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 140.42 |  | Tentative | 0 | 140.42 | 140.42 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34484 |  |  |  | TOWER D 201 COMMON WORK | TOWER D 201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 20449.5 | 20449.5 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40211 |  |  |  | TOWER D 201 COMMON WORK | TOWER D 201 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29934 |  |  |  | TOWER D 2ND FLOOR | TOWER D 202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Group | 5 | 29926 |  |  |  | TOWER D 202 | TOWER D 202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 13 Apr 2023 |  | - | - | 1123 | -
Task | 6 | 33593 |  |  |  | TOWER D 202 WATERPROOFING WORK | TOWER D 202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 7.5 |  | Started | 7.5 | 0 | 7.5 | 0 | 0.01 | 0 | 7731.36 | 7731.36 | 17 Mar 2020 |  | 13 Apr 2023 |  | - | - | 1123 | - | WATERPROOFING WORK
Task | 6 | 38653 |  |  |  | TOWER D 202 WATERPROOFING WORK | TOWER D 202 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29928 |  |  |  | TOWER D 202 | TOWER D 202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32967 |  |  |  | TOWER D 202 PLUMBING WORK | TOWER D 202 PLUMBING WORK | 1 | NOS | 0 | NOS | 974.92 |  | Started | 974.92 | 0 | 974.92 | 0 | 0.97 | 0 | 26904 | 26904 | 17 Mar 2020 |  | 18 Jan 2024 |  | - | - | 1403 | - | PLUMBING WORK
Task | 6 | 39326 |  |  |  | TOWER D 202 PLUMBING WORK | TOWER D 202 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 81.7 |  | Tentative | 81.7 | 0 | 81.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29927 |  |  |  | TOWER D 202 | TOWER D 202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Task | 6 | 33846 |  |  |  | TOWER D 202 ELECTRIC WORK | TOWER D 202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 34633 | 34633 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | - | ELECTRIC WORK
Group | 5 | 29929 |  |  |  | TOWER D 202 | TOWER D 202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38430 |  |  |  | TOWER D 202 FLOORING & DEDO WORK | TOWER D 202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 8519.2352 |  | Tentative | 5439.24 | 3080 | 8519.24 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29932 |  |  |  | TOWER D 202 | TOWER D 202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33097 |  |  |  | TOWER D 202 CARPENTRY WORK | TOWER D 202 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29930 |  |  |  | TOWER D 202 | TOWER D 202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29931 |  |  |  | TOWER D 202 | TOWER D 202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29933 |  |  |  | TOWER D 202 | TOWER D 202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38381 |  |  |  | TOWER D 202 HVAC WORK | TOWER D 202 HVAC WORK | 1 | NOS | 1 | NOS | 321.24 |  | Started | 321.24 | 0 | 321.24 | 0 | 0.32 | 0 | 7009.2 | 7009.2 | 17 Mar 2020 |  | 09 Sep 2024 |  | - | - | 1638 | - | HVAC INSTALLATION
Group | 5 | 34485 |  |  |  | TOWER D 202 | TOWER D 202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34486 |  |  |  | TOWER D 202 COMMON WORK | TOWER D 202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34487 |  |  |  | TOWER D 202 COMMON WORK | TOWER D 202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | PVC FALSE CEILING
Task | 6 | 34488 |  |  |  | TOWER D 202 COMMON WORK | TOWER D 202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 36136.5 | 36136.5 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40213 |  |  |  | TOWER D 202 COMMON WORK | TOWER D 202 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29887 |  |  |  | TOWER D 2ND FLOOR | TOWER D 2ND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 29888 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32598 |  |  |  | TOWER D 2ND FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 2ND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29889 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41457 |  |  |  | TOWER D 2ND FLOOR COMMON FLOORING WORK | TOWER D 2ND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 649 |  | Tentative | 649 | 0 | 649 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29890 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29891 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26471 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 26472 |  |  |  | TOWER D 2ND FLOOR COMMON ELECTRIC WORK | TOWER D 2ND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40933 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40934 |  |  |  | TOWER D 2ND FLOOR WPC PANNELING WORK | TOWER D 2ND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 10608.2 | 10608.2 | 17 Mar 2020 |  | 15 Oct 2024 |  | - | - | 1674 | - | WPC PANNELING WORK
Group | 5 | 41780 |  |  |  | TOWER D 2ND FLOOR COMMON WORK | TOWER D 2ND FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41781 |  |  |  | TOWER D 2ND FLOOR COMMON FABRICATION WORK | TOWER D 2ND FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | FLOOR FABRICATION WORK
Group | 3 | 24608 |  |  |  | TOWER D | TOWER D 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24609 |  |  |  | TOWER D 3RD FLOOR | TOWER D 3RD FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24610 |  |  |  | TOWER D 3RD FLOOR CIVIL WORK | TOWER D 3RD FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24613 |  |  |  | TOWER D 3RD FLOOR RCC WORK | TOWER D 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 42135.46 |  | Started | 42135.46 | 0 | 42135.46 | 5.72 | 241168.2 | 2163316.81 | 1081070.11 | 3244386.92 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 31082 |  |  |  | TOWER D 3RD FLOOR RCC WORK | TOWER D 3RD FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 43841.74 | 43841.74 | 17 Mar 2020 |  | 30 Mar 2022 |  | - | - | 744 | - | THREADING
Task | 6 | 39267 |  |  |  | TOWER D 3RD FLOOR RCC WORK | TOWER D 3RD RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FIRE AND SAFETY WORK
Group | 5 | 24611 |  |  |  | TOWER D 3RD FLOOR CIVIL WORK | TOWER D 3RD FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30 Sep 2022 |  | - | - | - | -
Task | 6 | 24614 |  |  |  | TOWER D 3RD FLOOR MASONRY WORK | TOWER D 3RD FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 305011.3 |  | Started | 305011.3 | 0 | 305011.3 | 5.72 | 1744474.92 | 0 | 291069.73 | 291069.73 |  |  | 30 Sep 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24612 |  |  |  | TOWER D 3RD FLOOR CIVIL WORK | TOWER D 3RD FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14 Dec 2022 |  | - | - | - | -
Task | 6 | 24615 |  |  |  | TOWER D 3RD FLOOR PLASTER WORK | TOWER D 3RD FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 6893 |  | Started | 6893 | 0 | 6893 | 5.72 | 39423.67 | 0 | 551163.48 | 551163.48 |  |  | 14 Dec 2022 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39311 |  |  |  | TOWER D 3RD FLOOR CIVIL WORK | TOWER D 3RD FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39312 |  |  |  | TOWER D 3RD FLOOR CIVIL EXTRA WORK | TOWER D 3RD FLOOR CIVIL EXTRA WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 22573.4 | 22573.4 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29943 |  |  |  | TOWER D 3RD FLOOR | TOWER D 301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Group | 5 | 29935 |  |  |  | TOWER D 301 | TOWER D 301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33594 |  |  |  | TOWER D 301 WATERPROOFING WORK | TOWER D 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38654 |  |  |  | TOWER D 301 WATERPROOFING WORK | TOWER D 301 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29937 |  |  |  | TOWER D 301 | TOWER D 301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32968 |  |  |  | TOWER D 301 PLUMBING WORK | TOWER D 301 PLUMBING WORK | 1 | NOS | 0 | NOS | 559.32 |  | Tentative | 559.32 | 0 | 559.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 40407 |  |  |  | TOWER D 301 PLUMBING WORK | TOWER D 301 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29936 |  |  |  | TOWER D 301 | TOWER D 301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Task | 6 | 33847 |  |  |  | TOWER D 301 ELECTRIC WORK | TOWER D 301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | - | ELECTRIC WORK
Group | 5 | 29938 |  |  |  | TOWER D 301 | TOWER D 301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38437 |  |  |  | TOWER D 301 FLOORING & DEDO WORK | TOWER D 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 6002.376 |  | Tentative | 2922.38 | 3080 | 6002.38 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29941 |  |  |  | TOWER D 301 | TOWER D 301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33098 |  |  |  | TOWER D 301 CARPENTRY WORK | TOWER D 301 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29939 |  |  |  | TOWER D 301 | TOWER D 301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29940 |  |  |  | TOWER D 301 | TOWER D 301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29942 |  |  |  | TOWER D 301 | TOWER D 301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34489 |  |  |  | TOWER D 301 | TOWER D 301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34490 |  |  |  | TOWER D 301 COMMON WORK | TOWER D 301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34491 |  |  |  | TOWER D 301 COMMON WORK | TOWER D 301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34492 |  |  |  | TOWER D 301 COMMON WORK | TOWER D 301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40215 |  |  |  | TOWER D 301 COMMON WORK | TOWER D 301 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29952 |  |  |  | TOWER D 3RD FLOOR | TOWER D 302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Group | 5 | 29944 |  |  |  | TOWER D 302 | TOWER D 302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33595 |  |  |  | TOWER D 302 WATERPROOFING WORK | TOWER D 302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38655 |  |  |  | TOWER D 302 WATERPROOFING WORK | TOWER D 302 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29946 |  |  |  | TOWER D 302 | TOWER D 302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32969 |  |  |  | TOWER D 302 PLUMBING WORK | TOWER D 302 PLUMBING WORK | 1 | NOS | 0 | NOS | 606.44 |  | Tentative | 606.44 | 0 | 606.44 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 40408 |  |  |  | TOWER D 302 PLUMBING WORK | TOWER D 302 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29945 |  |  |  | TOWER D 302 | TOWER D 302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | -
Task | 6 | 33848 |  |  |  | TOWER D 302 ELECTRIC WORK | TOWER D 302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 26 Mar 2023 |  | - | - | 1105 | - | ELECTRIC WORK
Group | 5 | 29947 |  |  |  | TOWER D 302 | TOWER D 302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38438 |  |  |  | TOWER D 302 FLOORING & DEDO WORK | TOWER D 302 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 6002.376 |  | Tentative | 2922.38 | 3080 | 6002.38 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29950 |  |  |  | TOWER D 302 | TOWER D 302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33099 |  |  |  | TOWER D 302 CARPENTRY WORK | TOWER D 302 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29948 |  |  |  | TOWER D 302 | TOWER D 302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29949 |  |  |  | TOWER D 302 | TOWER D 302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29951 |  |  |  | TOWER D 302 | TOWER D 302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34493 |  |  |  | TOWER D 302 | TOWER D 302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34494 |  |  |  | TOWER D 302 COMMON WORK | TOWER D 302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34495 |  |  |  | TOWER D 302 COMMON WORK | TOWER D 302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | PVC FALSE CEILING
Task | 6 | 34496 |  |  |  | TOWER D 302 COMMON WORK | TOWER D 302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 15673.5 | 15673.5 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40216 |  |  |  | TOWER D 302 COMMON WORK | TOWER D 302 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29894 |  |  |  | TOWER D 3RD FLOOR | TOWER D 3RD FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Mar 2022 |  | - | - | 745 | -
Group | 5 | 29895 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32597 |  |  |  | TOWER D 3RD FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 3RD FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29896 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41998 |  |  |  | TOWER D 3RD FLOOR COMMON FLOORING WORK | TOWER D 3RD FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29897 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29898 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26474 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Mar 2022 |  | - | - | 745 | -
Task | 6 | 26475 |  |  |  | TOWER D 3RD FLOOR ELECTRIC WORK | TOWER D 3RD FLOOR ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 31 Mar 2022 |  | - | - | 745 | - | ELECTRIC WORK
Group | 5 | 40935 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40936 |  |  |  | TOWER D 3RD FLOOR WPC PANNELING WORK | TOWER D 3RD FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41782 |  |  |  | TOWER D 3RD FLOOR COMMON WORK | TOWER D 3RD FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41783 |  |  |  | TOWER D 3RD FLOOR COMMON FABRICATION WORK | TOWER D 3RD FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 13 Sep 2024 |  | - | - | 1642 | - | FLOOR FABRICATION WORK
Group | 3 | 24616 |  |  |  | TOWER D | TOWER D 4TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24617 |  |  |  | TOWER D 4TH FLOOR | TOWER D 4TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24618 |  |  |  | TOWER D 4TH FLOOR CIVIL WORK | TOWER D 4TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24621 |  |  |  | TOWER D 4TH FLOOR RCC WORK | TOWER D 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35283.32 |  | Started | 35283.32 | 0 | 35283.32 | 5.72 | 201949.02 | 694120.54 | 1081919.71 | 1776040.25 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 31083 |  |  |  | TOWER D 4TH FLOOR RCC WORK | TOWER D 4TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 38161.2 | 38161.2 | 17 Mar 2020 |  | 07 Sep 2022 |  | - | - | 905 | - | THREADING
Task | 6 | 38391 |  |  |  | TOWER D 4TH FLOOR RCC WORK | TOWER D 4TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 19816.92 | 19816.92 | 17 Mar 2020 |  | 20 Jul 2023 |  | - | - | 1221 | - | SAFETY NET FIXING
Group | 5 | 24619 |  |  |  | TOWER D 4TH FLOOR CIVIL WORK | TOWER D 4TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22 Dec 2022 |  | - | - | - | -
Task | 6 | 24622 |  |  |  | TOWER D 4TH FLOOR MASONRY WORK | TOWER D 4TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 305014.3 |  | Started | 305014.3 | 0 | 305014.3 | 5.72 | 1744492.08 | 0 | 291070.27 | 291070.27 |  |  | 22 Dec 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24620 |  |  |  | TOWER D 4TH FLOOR CIVIL WORK | TOWER D 4TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 31 Jul 2023 |  | - | - | - | -
Task | 6 | 24623 |  |  |  | TOWER D 4TH FLOOR PLASTER WORK | TOWER D 4TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2690 |  | Started | 2690 | 0 | 2690 | 5.72 | 15385.13 | 0 | 537133.29 | 537133.29 |  |  | 31 Jul 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39313 |  |  |  | TOWER D 4TH FLOOR CIVIL WORK | TOWER D 4TH FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39314 |  |  |  | TOWER D 4TH FLOOR CIVIL EXTRA WORK | TOWER D 4TH FLOOR CIVIL EXTRA WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 22573.4 | 22573.4 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29961 |  |  |  | TOWER D 4TH FLOOR | TOWER D 401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Group | 5 | 29953 |  |  |  | TOWER D 401 | TOWER D 401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33596 |  |  |  | TOWER D 401 WATERPROOFING WORK | TOWER D 401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38656 |  |  |  | TOWER D 401 WATERPROOFING WORK | TOWER D 401 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29955 |  |  |  | TOWER D 401 | TOWER D 401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32970 |  |  |  | TOWER D 401 PLUMBING WORK | TOWER D 401 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42102 |  |  |  | TOWER D 401 PLUMBING WORK | TOWER D 401 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29954 |  |  |  | TOWER D 401 | TOWER D 401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Task | 6 | 33849 |  |  |  | TOWER D 401 ELECTRIC WORK | TOWER D 401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | - | ELECTRIC WORK
Group | 5 | 29956 |  |  |  | TOWER D 401 | TOWER D 401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41835 |  |  |  | TOWER D 401 FLOORING & DEDO WORK | TOWER D 401 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 3601.196 |  | Tentative | 2921.2 | 680 | 3601.2 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29959 |  |  |  | TOWER D 401 | TOWER D 401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39411 |  |  |  | TOWER D 401 CARPENTRY WORK | TOWER D 401 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29957 |  |  |  | TOWER D 401 | TOWER D 401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29958 |  |  |  | TOWER D 401 | TOWER D 401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29960 |  |  |  | TOWER D 401 | TOWER D 401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34497 |  |  |  | TOWER D 401 | TOWER D 401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34498 |  |  |  | TOWER D 401 COMMON WORK | TOWER D 401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34499 |  |  |  | TOWER D 401 COMMON WORK | TOWER D 401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34500 |  |  |  | TOWER D 401 COMMON WORK | TOWER D 401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40217 |  |  |  | TOWER D 401 COMMON WORK | TOWER D 401 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29970 |  |  |  | TOWER D 4TH FLOOR | TOWER D 402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Group | 5 | 29962 |  |  |  | TOWER D 402 | TOWER D 402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33597 |  |  |  | TOWER D 402 WATERPROOFING WORK | TOWER D 402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38657 |  |  |  | TOWER D 402 WATERPROOFING WORK | TOWER D 402 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29964 |  |  |  | TOWER D 402 | TOWER D 402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32971 |  |  |  | TOWER D 402 PLUMBING WORK | TOWER D 402 PLUMBING WORK | 1 | NOS | 1 | NOS | 782.7 |  | Tentative | 782.7 | 0 | 782.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 40409 |  |  |  | TOWER D 402 PLUMBING WORK | TOWER D 402 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29963 |  |  |  | TOWER D 402 | TOWER D 402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Task | 6 | 33850 |  |  |  | TOWER D 402 ELECTRIC WORK | TOWER D 402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | - | ELECTRIC WORK
Group | 5 | 29965 |  |  |  | TOWER D 402 | TOWER D 402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41836 |  |  |  | TOWER D 402 FLOORING & DEDO WORK | TOWER D 402 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 3601.196 |  | Tentative | 2921.2 | 680 | 3601.2 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29968 |  |  |  | TOWER D 402 | TOWER D 402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39412 |  |  |  | TOWER D 402 CARPENTRY WORK | TOWER D 402 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29966 |  |  |  | TOWER D 402 | TOWER D 402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29967 |  |  |  | TOWER D 402 | TOWER D 402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29969 |  |  |  | TOWER D 402 | TOWER D 402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34501 |  |  |  | TOWER D 402 | TOWER D 402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34502 |  |  |  | TOWER D 402 COMMON WORK | TOWER D 402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | BALCONY RAILING
Task | 6 | 34503 |  |  |  | TOWER D 402 COMMON WORK | TOWER D 402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34504 |  |  |  | TOWER D 402 COMMON WORK | TOWER D 402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40218 |  |  |  | TOWER D 402 COMMON WORK | TOWER D 402 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30241 |  |  |  | TOWER D 4TH FLOOR | TOWER D 4TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 13 Jul 2022 |  | - | - | 849 | -
Group | 5 | 30244 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32596 |  |  |  | TOWER D 4TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 4TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30242 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41999 |  |  |  | TOWER D 4TH FLOOR COMMON FLOORING WORK | TOWER D 4TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30243 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30245 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30246 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 13 Jul 2022 |  | - | - | 849 | -
Task | 6 | 31328 |  |  |  | TOWER D 4TH FLOOR COMMON ELECTRIC WORK | TOWER D 4TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 13 Jul 2022 |  | - | - | 849 | - | ELECTRIC WORK
Group | 5 | 40937 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH COMMON WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40938 |  |  |  | TOWER D 4TH COMMON WPC PANNELING WORK | TOWER D 4TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41784 |  |  |  | TOWER D 4TH FLOOR COMMON WORK | TOWER D 4TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41785 |  |  |  | TOWER D 4TH FLOOR COMMON FABRICATION WORK | TOWER D 4TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | FLOOR FABRICATION WORK
Group | 3 | 24624 |  |  |  | TOWER D | TOWER D 5TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24625 |  |  |  | TOWER D 5TH FLOOR | TOWER D 5TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24626 |  |  |  | TOWER D 5TH FLOOR CIVIL WORK | TOWER D 5TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24629 |  |  |  | TOWER D 5TH FLOOR RCC WORK | TOWER D 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35106.38 |  | Started | 35106.38 | 0 | 35106.38 | 5.72 | 200936.28 | 0 | 1079579.43 | 1079579.43 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 32567 |  |  |  | TOWER D 5TH FLOOR RCC WORK | TOWER D 5TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 22185.18 | 22185.18 | 17 Mar 2020 |  | 07 Sep 2022 |  | - | - | 905 | - | THREADING
Task | 6 | 37060 |  |  |  | TOWER D 5TH FLOOR RCC WORK | TOWER D 5TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 13133.92 | 13133.92 | 17 Mar 2020 |  | 10 Apr 2023 |  | - | - | 1120 | - | SAFETY NET FIXING
Group | 5 | 24627 |  |  |  | TOWER D 5TH FLOOR CIVIL WORK | TOWER D 5TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22 Dec 2022 |  | - | - | - | -
Task | 6 | 24630 |  |  |  | TOWER D 5TH FLOOR MASONRY WORK | TOWER D 5TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 311814.1 |  | Started | 311814.1 | 0 | 311814.1 | 5.72 | 1783382.7 | 0 | 291070.27 | 291070.27 |  |  | 22 Dec 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24628 |  |  |  | TOWER D 5TH FLOOR CIVIL WORK | TOWER D 5TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 31 Jul 2023 |  | - | - | - | -
Task | 6 | 24631 |  |  |  | TOWER D 5TH FLOOR PLASTER WORK | TOWER D 5TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2690 |  | Started | 2690 | 0 | 2690 | 5.72 | 15385.13 | 0 | 276202.4 | 276202.4 |  |  | 31 Jul 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39315 |  |  |  | TOWER D 5TH FLOOR CIVIL WORK | TOWER D 5TH FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39316 |  |  |  | TOWER D 5TH FLOOR CIVIL EXTRA WORK | TOWER D 5TH FLOOR CIVIL EXTRA WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 22573.4 | 22573.4 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29979 |  |  |  | TOWER D 5TH FLOOR | TOWER D 501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Group | 5 | 29971 |  |  |  | TOWER D 501 | TOWER D 501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33598 |  |  |  | TOWER D 501 WATERPROOFING WORK | TOWER D 501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38658 |  |  |  | TOWER D 501 WATERPROOFING WORK | TOWER D 501 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29973 |  |  |  | TOWER D 501 | TOWER D 501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32972 |  |  |  | TOWER D 501 PLUMBING WORK | TOWER D 501 PLUMBING WORK | 1 | NOS | 1 | NOS | 782.7 |  | Tentative | 782.7 | 0 | 782.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 40410 |  |  |  | TOWER D 501 PLUMBING WORK | TOWER D 501 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29972 |  |  |  | TOWER D 501 | TOWER D 501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Task | 6 | 33851 |  |  |  | TOWER D 501 ELECTRIC WORK | TOWER D 501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | - | ELECTRIC WORK
Group | 5 | 29974 |  |  |  | TOWER D 501 | TOWER D 501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42016 |  |  |  | TOWER D 501 FLOORING & DEDO WORK | TOWER D 501 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 238.36 |  | Tentative | 238.36 | 0 | 238.36 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29977 |  |  |  | TOWER D 501 | TOWER D 501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39413 |  |  |  | TOWER D 501 CARPENTRY WORK | TOWER D 501 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29975 |  |  |  | TOWER D 501 | TOWER D 501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29976 |  |  |  | TOWER D 501 | TOWER D 501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29978 |  |  |  | TOWER D 501 | TOWER D 501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34505 |  |  |  | TOWER D 501 | TOWER D 501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34506 |  |  |  | TOWER D 501 COMMON WORK | TOWER D 501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34507 |  |  |  | TOWER D 501 COMMON WORK | TOWER D 501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34508 |  |  |  | TOWER D 501 COMMON WORK | TOWER D 501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40219 |  |  |  | TOWER D 501 COMMON WORK | TOWER D 501 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29988 |  |  |  | TOWER D 5TH FLOOR | TOWER D 502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Group | 5 | 29980 |  |  |  | TOWER D 502 | TOWER D 502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33599 |  |  |  | TOWER D 502 WATERPROOFING WORK | TOWER D 502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38659 |  |  |  | TOWER D 502 WATERPROOFING WORK | TOWER D 502 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29982 |  |  |  | TOWER D 502 | TOWER D 502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32973 |  |  |  | TOWER D 502 PLUMBING WORK | TOWER D 502 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42103 |  |  |  | TOWER D 502 PLUMBING WORK | TOWER D 502 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29981 |  |  |  | TOWER D 502 | TOWER D 502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Task | 6 | 33852 |  |  |  | TOWER D 502 ELECTRIC WORK | TOWER D 502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | - | ELECTRIC WORK
Group | 5 | 29983 |  |  |  | TOWER D 502 | TOWER D 502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42017 |  |  |  | TOWER D 502 FLOORING & DEDO WORK | TOWER D 502 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 238.36 |  | Tentative | 238.36 | 0 | 238.36 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29986 |  |  |  | TOWER D 502 | TOWER D 502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39414 |  |  |  | TOWER D 502 CARPENTRY WORK | TOWER D 502 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29984 |  |  |  | TOWER D 502 | TOWER D 502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29985 |  |  |  | TOWER D 502 | TOWER D 502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29987 |  |  |  | TOWER D 502 | TOWER D 502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34509 |  |  |  | TOWER D 502 | TOWER D 502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34510 |  |  |  | TOWER D 502 COMMON WORK | TOWER D 502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34511 |  |  |  | TOWER D 502 COMMON WORK | TOWER D 502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34512 |  |  |  | TOWER D 502 COMMON WORK | TOWER D 502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40220 |  |  |  | TOWER D 502 COMMON WORK | TOWER D 502 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30247 |  |  |  | TOWER D 5TH FLOOR | TOWER D 5TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Sep 2022 |  | - | - | 909 | -
Group | 5 | 30250 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32595 |  |  |  | TOWER D 5TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 5TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30248 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42000 |  |  |  | TOWER D 5TH FLOOR COMMON FLOORING WORK | TOWER D 5TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30249 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30251 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30252 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Sep 2022 |  | - | - | 909 | -
Task | 6 | 31329 |  |  |  | TOWER D 5TH FLOOR COMMON ELECTRIC WORK | TOWER D 5TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 11 Sep 2022 |  | - | - | 909 | - | ELECTRIC WORK
Group | 5 | 40939 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40940 |  |  |  | TOWER D 5TH FLOOR WPC PANNELING WORK | TOWER D 5TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41786 |  |  |  | TOWER D 5TH FLOOR COMMON WORK | TOWER D 5TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41787 |  |  |  | TOWER D 5TH FLOOR COMMON FABRICATION WORK | TOWER D 5TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | FLOOR FABRICATION WORK
Group | 3 | 24632 |  |  |  | TOWER D | TOWER D 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 4 | 24633 |  |  |  | TOWER D 6TH FLOOR | TOWER D 6TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 5 | 24634 |  |  |  | TOWER D 6TH FLOOR CIVIL WORK | TOWER D 6TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Task | 6 | 24637 |  |  |  | TOWER D 6TH FLOOR RCC WORK | TOWER D 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 132387.34 |  | Started | 132387.34 | 0 | 132387.34 | 5.72 | 757737.47 | 0 | 1079559.71 | 1079559.71 |  |  | 25 Aug 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33088 |  |  |  | TOWER D 6TH FLOOR RCC WORK | TOWER D 6TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 33276 | 33276 | 17 Mar 2020 |  | 27 Nov 2022 |  | - | - | 986 | - | THREADING
Task | 6 | 33711 |  |  |  | TOWER D 6TH FLOOR RCC WORK | TOWER D 6TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 625 |  | Started | 625 | 0 | 625 | 0 | 0.63 | 0 | 67861.58 | 67861.58 | 17 Mar 2020 |  | 18 Feb 2023 |  | - | - | 1069 | - | FIRE AND SAFETY WORK
Group | 5 | 24635 |  |  |  | TOWER D 6TH FLOOR CIVIL WORK | TOWER D 6TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 21 Feb 2023 |  | - | - | - | -
Task | 6 | 24638 |  |  |  | TOWER D 6TH FLOOR MASONRY WORK | TOWER D 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 413811.1 |  | Started | 413811.1 | 0 | 413811.1 | 5.72 | 2366742.1 | 0 | 291070.27 | 291070.27 |  |  | 21 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24636 |  |  |  | TOWER D 6TH FLOOR CIVIL WORK | TOWER D 6TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24639 |  |  |  | TOWER D 6TH FLOOR PLASTER WORK | TOWER D 6TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2690 |  | Started | 2690 | 0 | 2690 | 0 | 2.69 | 0 | 444413.85 | 444413.85 |  |  | 04 Jan 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29997 |  |  |  | TOWER D 6TH FLOOR | TOWER D 601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Group | 5 | 29989 |  |  |  | TOWER D 601 | TOWER D 601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33600 |  |  |  | TOWER D 601 WATERPROOFING WORK | TOWER D 601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38660 |  |  |  | TOWER D 601 WATERPROOFING WORK | TOWER D 601 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29991 |  |  |  | TOWER D 601 | TOWER D 601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32974 |  |  |  | TOWER D 601 PLUMBING WORK | TOWER D 601 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42104 |  |  |  | TOWER D 601 PLUMBING WORK | TOWER D 601 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29990 |  |  |  | TOWER D 601 | TOWER D 601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Task | 6 | 33853 |  |  |  | TOWER D 601 ELECTRIC WORK | TOWER D 601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | - | ELECTRIC WORK
Group | 5 | 29992 |  |  |  | TOWER D 601 | TOWER D 601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42018 |  |  |  | TOWER D 601 FLOORING & DEDO WORK | TOWER D 601 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 109.74 |  | Tentative | 109.74 | 0 | 109.74 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29995 |  |  |  | TOWER D 601 | TOWER D 601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39415 |  |  |  | TOWER D 601 CARPENTRY WORK | TOWER D 601 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29993 |  |  |  | TOWER D 601 | TOWER D 601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29994 |  |  |  | TOWER D 601 | TOWER D 601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29996 |  |  |  | TOWER D 601 | TOWER D 601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34513 |  |  |  | TOWER D 601 | TOWER D 601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34514 |  |  |  | TOWER D 601 COMMON WORK | TOWER D 601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34515 |  |  |  | TOWER D 601 COMMON WORK | TOWER D 601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34516 |  |  |  | TOWER D 601 COMMON WORK | TOWER D 601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40221 |  |  |  | TOWER D 601 COMMON WORK | TOWER D 601 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30006 |  |  |  | TOWER D 6TH FLOOR | TOWER D 602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Group | 5 | 29998 |  |  |  | TOWER D 602 | TOWER D 602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33601 |  |  |  | TOWER D 602 WATERPROOFING WORK | TOWER D 602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38661 |  |  |  | TOWER D 602 WATERPROOFING WORK | TOWER D 602 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30000 |  |  |  | TOWER D 602 | TOWER D 602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32975 |  |  |  | TOWER D 602 PLUMBING WORK | TOWER D 602 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42105 |  |  |  | TOWER D 602 PLUMBING WORK | TOWER D 602 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29999 |  |  |  | TOWER D 602 | TOWER D 602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | -
Task | 6 | 33854 |  |  |  | TOWER D 602 ELECTRIC WORK | TOWER D 602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 05 Jul 2023 |  | - | - | 1206 | - | ELECTRIC WORK
Group | 5 | 30001 |  |  |  | TOWER D 602 | TOWER D 602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30004 |  |  |  | TOWER D 602 | TOWER D 602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39416 |  |  |  | TOWER D 602 CARPENTRY WORK | TOWER D 602 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30002 |  |  |  | TOWER D 602 | TOWER D 602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30003 |  |  |  | TOWER D 602 | TOWER D 602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30005 |  |  |  | TOWER D 602 | TOWER D 602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34517 |  |  |  | TOWER D 602 | TOWER D 602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34518 |  |  |  | TOWER D 602 COMMON WORK | TOWER D 602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34519 |  |  |  | TOWER D 602 COMMON WORK | TOWER D 602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34520 |  |  |  | TOWER D 602 COMMON WORK | TOWER D 602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40222 |  |  |  | TOWER D 602 COMMON WORK | TOWER D 602 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30253 |  |  |  | TOWER D 6TH FLOOR | TOWER D 6TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | -
Group | 5 | 30256 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34032 |  |  |  | TOWER D 6TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 6TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30254 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42001 |  |  |  | TOWER D 6TH FLOOR COMMON FLOORING WORK | TOWER D 6TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30255 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30257 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30258 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | -
Task | 6 | 31330 |  |  |  | TOWER D 6TH FLOOR COMMON ELECTRIC WORK | TOWER D 6TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | - | ELECTRIC WORK
Group | 5 | 40941 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40942 |  |  |  | TOWER D 6TH FLOOR WPC PANNELING WORK | TOWER D 6TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41788 |  |  |  | TOWER D 6TH FLOOR COMMON WORK | TOWER D 6TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41789 |  |  |  | TOWER D 6TH FLOOR COMMON FABRICATION WORK | TOWER D 6TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | FLOOR FABRICATION WORK
Group | 3 | 24640 |  |  |  | TOWER D | TOWER D 7TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 4 | 24641 |  |  |  | TOWER D 7TH FLOOR | TOWER D 7TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 5 | 24642 |  |  |  | TOWER D 7TH FLOOR CIVIL WORK | TOWER D 7TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Task | 6 | 24645 |  |  |  | TOWER D 7TH FLOOR RCC WORK | TOWER D 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 139382.34 |  | Started | 139382.34 | 0 | 139382.34 | 5.72 | 797774.34 | 0 | 1077862.48 | 1077862.48 |  |  | 25 Aug 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33089 |  |  |  | TOWER D 7TH FLOOR RCC WORK | TOWER D 7TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 23249.54 | 23249.54 | 17 Mar 2020 |  | 27 Nov 2022 |  | - | - | 986 | - | THREADING
Task | 6 | 38612 |  |  |  | TOWER D 7TH FLOOR RCC WORK | TOWER D 7TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 14344.08 | 14344.08 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | FIRE AND SAFETY WORK
Group | 5 | 24643 |  |  |  | TOWER D 7TH FLOOR CIVIL WORK | TOWER D 7TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 Feb 2023 |  | - | - | - | -
Task | 6 | 24646 |  |  |  | TOWER D 7TH FLOOR MASONRY WORK | TOWER D 7TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 413808.1 |  | Started | 413808.1 | 0 | 413808.1 | 5.72 | 2366724.94 | 0 | 291070.4 | 291070.4 |  |  | 16 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24644 |  |  |  | TOWER D 7TH FLOOR CIVIL WORK | TOWER D 7TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24647 |  |  |  | TOWER D 7TH FLOOR PLASTER WORK | TOWER D 7TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 0 | 2.69 | 0 | 262172.2 | 262172.2 |  |  | 20 Sep 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 30015 |  |  |  | TOWER D 7TH FLOOR | TOWER D 701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30007 |  |  |  | TOWER D 701 | TOWER D 701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33602 |  |  |  | TOWER D 701 WATERPROOFING WORK | TOWER D 701 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38662 |  |  |  | TOWER D 701 WATERPROOFING WORK | TOWER D 701 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30009 |  |  |  | TOWER D 701 | TOWER D 701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32976 |  |  |  | TOWER D 701 PLUMBING WORK | TOWER D 701 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42106 |  |  |  | TOWER D 701 PLUMBING WORK | TOWER D 701 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 30008 |  |  |  | TOWER D 701 | TOWER D 701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33855 |  |  |  | TOWER D 701 ELECTRIC WORK | TOWER D 701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30010 |  |  |  | TOWER D 701 | TOWER D 701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30013 |  |  |  | TOWER D 701 | TOWER D 701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39417 |  |  |  | TOWER D 701 CARPENTRY WORK | TOWER D 701 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30011 |  |  |  | TOWER D 701 | TOWER D 701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30012 |  |  |  | TOWER D 701 | TOWER D 701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30014 |  |  |  | TOWER D 701 | TOWER D 701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34521 |  |  |  | TOWER D 701 | TOWER D 701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34522 |  |  |  | TOWER D 701 COMMON WORK | TOWER D 701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34523 |  |  |  | TOWER D 701 COMMON WORK | TOWER D 701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34524 |  |  |  | TOWER D 701 COMMON WORK | TOWER D 701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40223 |  |  |  | TOWER D 701 COMMON WORK | TOWER D 701 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30024 |  |  |  | TOWER D 7TH FLOOR | TOWER D 702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30016 |  |  |  | TOWER D 702 | TOWER D 702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33603 |  |  |  | TOWER D 702 WATERPROOFING WORK | TOWER D 702 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38663 |  |  |  | TOWER D 702 WATERPROOFING WORK | TOWER D 702 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30018 |  |  |  | TOWER D 702 | TOWER D 702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32977 |  |  |  | TOWER D 702 PLUMBING WORK | TOWER D 702 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42107 |  |  |  | TOWER D 702 PLUMBING WORK | TOWER D 702 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 30017 |  |  |  | TOWER D 702 | TOWER D 702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -