## Task Details638658826169245544_
Task Details
Project Name : GREENWOODS AARANYA
Task Name : All
Total Records: 5858 Records 5001 to 5858
Page 2 of 2
TaskType | Level | TaskNo | Identification1 | Identification2 | Identification3 | ParentTask | Task | VOLOFWORK M | M Unit | VOLOFWORK L | L Unit | Task Rate | Task Category 1 | Task Status | Estimated Mat Amt | Estimated Lab Amt | Estimated Task Amt | % Comp | Est Cost of Completion(BCWP) | Actual Cost Material | Actual Cost Labour | Actual Cost | Planned Start(PS) | Planned Finish(PF) | Actual Start(AS) | Actual Finish(AF) | Planned Duration=(PS)-(PF) Days | Actual Duration=(AS)-(AF) Days | Start Variance=(PS)-(AS) Days | Finish Variance=(PF)-(AF) Days | Library Task Name | Task Description
Task | 6 | 33856 |  |  |  | TOWER D 702 ELECTRIC WORK | TOWER D 702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30019 |  |  |  | TOWER D 702 | TOWER D 702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30022 |  |  |  | TOWER D 702 | TOWER D 702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39418 |  |  |  | TOWER D 702 CARPENTRY WORK | TOWER D 702 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30020 |  |  |  | TOWER D 702 | TOWER D 702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30021 |  |  |  | TOWER D 702 | TOWER D 702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30023 |  |  |  | TOWER D 702 | TOWER D 702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34525 |  |  |  | TOWER D 702 | TOWER D 702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34526 |  |  |  | TOWER D 702 COMMON WORK | TOWER D 702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34527 |  |  |  | TOWER D 702 COMMON WORK | TOWER D 702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34528 |  |  |  | TOWER D 702 COMMON WORK | TOWER D 702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40224 |  |  |  | TOWER D 702 COMMON WORK | TOWER D 702 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30259 |  |  |  | TOWER D 7TH FLOOR | TOWER D 7TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 08 Dec 2022 |  | - | - | 997 | -
Group | 5 | 30262 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34033 |  |  |  | TOWER D 7TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 7TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30260 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42002 |  |  |  | TOWER D 7TH FLOOR COMMON FLOORING WORK | TOWER D 7TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30261 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30263 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30264 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 08 Dec 2022 |  | - | - | 997 | -
Task | 6 | 31466 |  |  |  | TOWER D 7TH FLOOR COMMON ELECTRIC WORK | TOWER D 7TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 08 Dec 2022 |  | - | - | 997 | - | ELECTRIC WORK
Group | 5 | 40943 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40944 |  |  |  | TOWER D 7TH FLOOR WPC PANNELING WORK | TOWER D 7TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41790 |  |  |  | TOWER D 7TH FLOOR COMMON WORK | TOWER D 7TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41791 |  |  |  | TOWER D 7TH FLOOR COMMON FABRICATION WORK | TOWER D 7TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | FLOOR FABRICATION WORK
Group | 3 | 24648 |  |  |  | TOWER D | TOWER D 8TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 4 | 24649 |  |  |  | TOWER D 8TH FLOOR | TOWER D 8TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 5 | 24650 |  |  |  | TOWER D 8TH FLOOR CIVIL WORK | TOWER D 8TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Task | 6 | 24653 |  |  |  | TOWER D 8TH FLOOR RCC WORK | TOWER D 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135972.34 |  | Started | 135972.34 | 0 | 135972.34 | 5.72 | 778256.72 | 0 | 1077862.48 | 1077862.48 |  |  | 25 Aug 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33090 |  |  |  | TOWER D 8TH FLOOR RCC WORK | TOWER D 8TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 16048 | 16048 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | THREADING
Task | 6 | 38774 |  |  |  | TOWER D 8TH FLOOR RCC WORK | TOWER D 8TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 625 |  | Started | 625 | 0 | 625 | 0 | 0.63 | 0 | 1904.52 | 1904.52 | 17 Mar 2020 |  | 12 Jan 2024 |  | - | - | 1397 | - | SAFETY NET FIXING
Group | 5 | 24651 |  |  |  | TOWER D 8TH FLOOR CIVIL WORK | TOWER D 8TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Sep 2023 |  | - | - | - | -
Task | 6 | 24654 |  |  |  | TOWER D 8TH FLOOR MASONRY WORK | TOWER D 8TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 459281.85 | 459281.85 |  |  | 20 Sep 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24652 |  |  |  | TOWER D 8TH FLOOR CIVIL WORK | TOWER D 8TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24655 |  |  |  | TOWER D 8TH FLOOR PLASTER WORK | TOWER D 8TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30033 |  |  |  | TOWER D 8TH FLOOR | TOWER D 801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30025 |  |  |  | TOWER D 801 | TOWER D 801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33604 |  |  |  | TOWER D 801 WATERPROOFING WORK | TOWER D 801 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38664 |  |  |  | TOWER D 801 WATERPROOFING WORK | TOWER D 801 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30027 |  |  |  | TOWER D 801 | TOWER D 801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32978 |  |  |  | TOWER D 801 PLUMBING WORK | TOWER D 801 PLUMBING WORK | 1 | NOS | 0 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42108 |  |  |  | TOWER D 801 PLUMBING WORK | TOWER D 801 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 30026 |  |  |  | TOWER D 801 | TOWER D 801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33857 |  |  |  | TOWER D 801 ELECTRIC WORK | TOWER D 801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30028 |  |  |  | TOWER D 801 | TOWER D 801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30031 |  |  |  | TOWER D 801 | TOWER D 801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39419 |  |  |  | TOWER D 801 CARPENTRY WORK | TOWER D 801 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30029 |  |  |  | TOWER D 801 | TOWER D 801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30030 |  |  |  | TOWER D 801 | TOWER D 801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30032 |  |  |  | TOWER D 801 | TOWER D 801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34529 |  |  |  | TOWER D 801 | TOWER D 801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34530 |  |  |  | TOWER D 801 COMMON WORK | TOWER D 801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34531 |  |  |  | TOWER D 801 COMMON WORK | TOWER D 801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34532 |  |  |  | TOWER D 801 COMMON WORK | TOWER D 801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40225 |  |  |  | TOWER D 801 COMMON WORK | TOWER D 801 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30042 |  |  |  | TOWER D 8TH FLOOR | TOWER D 802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30034 |  |  |  | TOWER D 802 | TOWER D 802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33605 |  |  |  | TOWER D 802 WATERPROOFING WORK | TOWER D 802 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38665 |  |  |  | TOWER D 802 WATERPROOFING WORK | TOWER D 802 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30036 |  |  |  | TOWER D 802 | TOWER D 802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32979 |  |  |  | TOWER D 802 PLUMBING WORK | TOWER D 802 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42109 |  |  |  | TOWER D 802 PLUMBING WORK | TOWER D 802 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 30035 |  |  |  | TOWER D 802 | TOWER D 802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33858 |  |  |  | TOWER D 802 ELECTRIC WORK | TOWER D 802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 30037 |  |  |  | TOWER D 802 | TOWER D 802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30040 |  |  |  | TOWER D 802 | TOWER D 802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39420 |  |  |  | TOWER D 802 CARPENTRY WORK | TOWER D 802 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30038 |  |  |  | TOWER D 802 | TOWER D 802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30039 |  |  |  | TOWER D 802 | TOWER D 802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30041 |  |  |  | TOWER D 802 | TOWER D 802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34533 |  |  |  | TOWER D 802 | TOWER D 802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34534 |  |  |  | TOWER D 802 COMMON WORK | TOWER D 802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34535 |  |  |  | TOWER D 802 COMMON WORK | TOWER D 802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34536 |  |  |  | TOWER D 802 COMMON WORK | TOWER D 802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40226 |  |  |  | TOWER D 802 COMMON WORK | TOWER D 802 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30265 |  |  |  | TOWER D 8TH FLOOR | TOWER D 8TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 30268 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34034 |  |  |  | TOWER D 8TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 8TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30266 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42003 |  |  |  | TOWER D 8TH FLOOR COMMON FLOORING WORK | TOWER D 8TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30267 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30269 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30270 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 31467 |  |  |  | TOWER D 8TH FLOOR COMMON ELECTRIC WORK | TOWER D 8TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 40945 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40946 |  |  |  | TOWER D 8TH FLOOR WPC PANNELING WORK | TOWER D 8TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41792 |  |  |  | TOWER D 8TH FLOOR COMMON WORK | TOWER D 8TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41793 |  |  |  | TOWER D 8TH FLOOR COMMON FABRICATION WORK | TOWER D 8TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | FLOOR FABRICATION WORK
Group | 3 | 24656 |  |  |  | TOWER D | TOWER D 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 4 | 24657 |  |  |  | TOWER D 9TH FLOOR | TOWER D 9TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 5 | 24658 |  |  |  | TOWER D 9TH FLOOR CIVIL WORK | TOWER D 9TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Task | 6 | 24661 |  |  |  | TOWER D 9TH FLOOR RCC WORK | TOWER D 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 37861.51 |  | Started | 37861.51 | 0 | 37861.51 | 5.72 | 216705.65 | 0 | 1077862.96 | 1077862.96 |  |  | 17 Nov 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33457 |  |  |  | TOWER D 9TH FLOOR RCC WORK | TOWER D 9TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 30739 | 30739 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | THREADING
Task | 6 | 38919 |  |  |  | TOWER D 9TH FLOOR RCC WORK | TOWER D 9TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 63450.14 | 63450.14 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | SAFETY NET FIXING
Group | 5 | 24659 |  |  |  | TOWER D 9TH FLOOR CIVIL WORK | TOWER D 9TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24662 |  |  |  | TOWER D 9TH FLOOR MASONRY WORK | TOWER D 9TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 409123.5 |  | Started | 409123.5 | 0 | 409123.5 | 0 | 409.12 | 0 | 11894.4 | 11894.4 |  |  | 19 Sep 2024 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24660 |  |  |  | TOWER D 9TH FLOOR CIVIL WORK | TOWER D 9TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24663 |  |  |  | TOWER D 9TH FLOOR PLASTER WORK | TOWER D 9TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30051 |  |  |  | TOWER D 9TH FLOOR | TOWER D 901 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30043 |  |  |  | TOWER D 901 | TOWER D 901 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33606 |  |  |  | TOWER D 901 WATERPROOFING WORK | TOWER D 901 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38666 |  |  |  | TOWER D 901 WATERPROOFING WORK | TOWER D 901 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30045 |  |  |  | TOWER D 901 | TOWER D 901 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32980 |  |  |  | TOWER D 901 PLUMBING WORK | TOWER D 901 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42110 |  |  |  | TOWER D 901 PLUMBING WORK | TOWER D 901 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 30044 |  |  |  | TOWER D 901 | TOWER D 901 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33859 |  |  |  | TOWER D 901 ELECTRIC WORK | TOWER D 901 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30046 |  |  |  | TOWER D 901 | TOWER D 901 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30049 |  |  |  | TOWER D 901 | TOWER D 901 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39421 |  |  |  | TOWER D 901 CARPENTRY WORK | TOWER D 901 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30047 |  |  |  | TOWER D 901 | TOWER D 901 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30048 |  |  |  | TOWER D 901 | TOWER D 901 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30050 |  |  |  | TOWER D 901 | TOWER D 901 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34537 |  |  |  | TOWER D 901 | TOWER D 901 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34538 |  |  |  | TOWER D 901 COMMON WORK | TOWER D 901 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34539 |  |  |  | TOWER D 901 COMMON WORK | TOWER D 901 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34540 |  |  |  | TOWER D 901 COMMON WORK | TOWER D 901 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40227 |  |  |  | TOWER D 901 COMMON WORK | TOWER D 901 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30060 |  |  |  | TOWER D 9TH FLOOR | TOWER D 902 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30052 |  |  |  | TOWER D 902 | TOWER D 902 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33607 |  |  |  | TOWER D 902 WATERPROOFING WORK | TOWER D 902 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38667 |  |  |  | TOWER D 902 WATERPROOFING WORK | TOWER D 902 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 30054 |  |  |  | TOWER D 902 | TOWER D 902 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32981 |  |  |  | TOWER D 902 PLUMBING WORK | TOWER D 902 PLUMBING WORK | 1 | NOS | 1 | NOS | 720.26 |  | Tentative | 720.26 | 0 | 720.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 42111 |  |  |  | TOWER D 902 PLUMBING WORK | TOWER D 902 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 30053 |  |  |  | TOWER D 902 | TOWER D 902 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33860 |  |  |  | TOWER D 902 ELECTRIC WORK | TOWER D 902 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30055 |  |  |  | TOWER D 902 | TOWER D 902 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30058 |  |  |  | TOWER D 902 | TOWER D 902 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39422 |  |  |  | TOWER D 902 CARPENTRY WORK | TOWER D 902 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30056 |  |  |  | TOWER D 902 | TOWER D 902 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30057 |  |  |  | TOWER D 902 | TOWER D 902 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30059 |  |  |  | TOWER D 902 | TOWER D 902 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34541 |  |  |  | TOWER D 902 | TOWER D 902 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34542 |  |  |  | TOWER D 902 COMMON WORK | TOWER D 902 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34543 |  |  |  | TOWER D 902 COMMON WORK | TOWER D 902 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34544 |  |  |  | TOWER D 902 COMMON WORK | TOWER D 902 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40228 |  |  |  | TOWER D 902 COMMON WORK | TOWER D 902 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30271 |  |  |  | TOWER D 9TH FLOOR | TOWER D 9TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 02 May 2023 |  | - | - | 1142 | -
Group | 5 | 30274 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34035 |  |  |  | TOWER D 9TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 9TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 3.36 |  | Started | 2.36 | 1 | 3.36 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30272 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42004 |  |  |  | TOWER D 9TH FLOOR COMMON FLOORING WORK | TOWER D 9TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30273 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30275 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30276 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 02 May 2023 |  | - | - | 1142 | -
Task | 6 | 31468 |  |  |  | TOWER D 9TH FLOOR COMMON ELECTRIC WORK | TOWER D 9TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 02 May 2023 |  | - | - | 1142 | - | ELECTRIC WORK
Group | 5 | 40947 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40948 |  |  |  | TOWER D 9TH FLOOR WPC PANNELING WORK | TOWER D 9TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41794 |  |  |  | TOWER D 9TH FLOOR COMMON WORK | TOWER D 9TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41795 |  |  |  | TOWER D 9TH FLOOR COMMON FABRICATION WORK | TOWER D 9TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 4130 | 4130 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | FLOOR FABRICATION WORK
Group | 3 | 24664 |  |  |  | TOWER D | TOWER D 10TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 4 | 24665 |  |  |  | TOWER D 10TH FLOOR | TOWER D 10TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 5 | 24666 |  |  |  | TOWER D 10TH FLOOR CIVIL WORK | TOWER D 10TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Task | 6 | 24669 |  |  |  | TOWER D 10TH FLOOR RCC WORK | TOWER D 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 40575.54 |  | Started | 40575.54 | 0 | 40575.54 | 5.72 | 232239.78 | 0 | 1050638 | 1050638 |  |  | 17 Nov 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24667 |  |  |  | TOWER D 10TH FLOOR CIVIL WORK | TOWER D 10TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24670 |  |  |  | TOWER D 10TH FLOOR MASONRY WORK | TOWER D 10TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 0 | 307.13 | 0 | 0 | 0 |  |  | 07 Oct 2024 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24668 |  |  |  | TOWER D 10TH FLOOR CIVIL WORK | TOWER D 10TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24671 |  |  |  | TOWER D 10TH FLOOR PLASTER WORK | TOWER D 10TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30069 |  |  |  | TOWER D 10TH FLOOR | TOWER D 1001 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30061 |  |  |  | TOWER D 1001 | TOWER D 1001 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33609 |  |  |  | TOWER D 1001 WATERPROOFING WORK | TOWER D 1001 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30063 |  |  |  | TOWER D 1001 | TOWER D 1001 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32982 |  |  |  | TOWER D 1001 PLUMBING WORK | TOWER D 1001 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30062 |  |  |  | TOWER D 1001 | TOWER D 1001 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33861 |  |  |  | TOWER D 1001 ELECTRIC WORK | TOWER D 1001 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30064 |  |  |  | TOWER D 1001 | TOWER D 1001 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30067 |  |  |  | TOWER D 1001 | TOWER D 1001 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39423 |  |  |  | TOWER D 1001 CARPENTRY WORK | TOWER D 1001 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30065 |  |  |  | TOWER D 1001 | TOWER D 1001 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30066 |  |  |  | TOWER D 1001 | TOWER D 1001 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30068 |  |  |  | TOWER D 1001 | TOWER D 1001 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34545 |  |  |  | TOWER D 1001 | TOWER D 1001 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34546 |  |  |  | TOWER D 1001 COMMON WORK | TOWER D 1001 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34547 |  |  |  | TOWER D 1001 COMMON WORK | TOWER D 1001 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34548 |  |  |  | TOWER D 1001 COMMON WORK | TOWER D 1001 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40231 |  |  |  | TOWER D 1001 COMMON WORK | TOWER D 1001 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30078 |  |  |  | TOWER D 10TH FLOOR | TOWER D 1002 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30070 |  |  |  | TOWER D 1002 | TOWER D 1002 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33610 |  |  |  | TOWER D 1002 WATERPROOFING WORK | TOWER D 1002 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30072 |  |  |  | TOWER D 1002 | TOWER D 1002 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32983 |  |  |  | TOWER D 1002 PLUMBING WORK | TOWER D 1002 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30071 |  |  |  | TOWER D 1002 | TOWER D 1002 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33862 |  |  |  | TOWER D 1002 ELECTRIC WORK | TOWER D 1002 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30073 |  |  |  | TOWER D 1002 | TOWER D 1002 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30076 |  |  |  | TOWER D 1002 | TOWER D 1002 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39424 |  |  |  | TOWER D 1002 CARPENTRY WORK | TOWER D 1002 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 30074 |  |  |  | TOWER D 1002 | TOWER D 1002 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30075 |  |  |  | TOWER D 1002 | TOWER D 1002 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30077 |  |  |  | TOWER D 1002 | TOWER D 1002 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34549 |  |  |  | TOWER D 1002 | TOWER D 1002 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34550 |  |  |  | TOWER D 1002 COMMON WORK | TOWER D 1002 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34551 |  |  |  | TOWER D 1002 COMMON WORK | TOWER D 1002 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34552 |  |  |  | TOWER D 1002 COMMON WORK | TOWER D 1002 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40232 |  |  |  | TOWER D 1002 COMMON WORK | TOWER D 1002 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30277 |  |  |  | TOWER D 10TH FLOOR | TOWER D 10TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30280 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34036 |  |  |  | TOWER D 10TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 10TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 3.36 |  | Started | 2.36 | 1 | 3.36 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30278 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42005 |  |  |  | TOWER D 10TH FLOOR COMMON FLOORING WORK | TOWER D 10TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30279 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30281 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30282 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 31469 |  |  |  | TOWER D 10TH FLOOR COMMON ELECTRIC WORK | TOWER D 10TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 45748.71 | 45748.71 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | ELECTRIC WORK
Group | 5 | 40949 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40950 |  |  |  | TOWER D 10TH FLOOR WPC PANNELING WORK | TOWER D 10TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41796 |  |  |  | TOWER D 10TH FLOOR COMMON WORK | TOWER D 10TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41797 |  |  |  | TOWER D 10TH FLOOR COMMON FABRICATION WORK | TOWER D 10TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24672 |  |  |  | TOWER D | TOWER D 11TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19 Oct 2023 |  | - | - | - | -
Group | 4 | 24673 |  |  |  | TOWER D 11TH FLOOR | TOWER D 11TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19 Oct 2023 |  | - | - | - | -
Group | 5 | 24674 |  |  |  | TOWER D 11TH FLOOR CIVIL WORK | TOWER D 11TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19 Oct 2023 |  | - | - | - | -
Task | 6 | 24677 |  |  |  | TOWER D 11TH FLOOR RCC WORK | TOWER D 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35628.62 |  | Started | 35628.62 | 0 | 35628.62 | 0 | 35.63 | 0 | 1716169.31 | 1716169.31 |  |  | 04 Jan 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24675 |  |  |  | TOWER D 11TH FLOOR CIVIL WORK | TOWER D 11TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24678 |  |  |  | TOWER D 11TH FLOOR MASONRY WORK | TOWER D 11TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 271992 |  | Tentative | 271992 | 0 | 271992 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24676 |  |  |  | TOWER D 11TH FLOOR CIVIL WORK | TOWER D 11TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24679 |  |  |  | TOWER D 11TH FLOOR PLASTER WORK | TOWER D 11TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30087 |  |  |  | TOWER D 11TH FLOOR | TOWER D 1101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30079 |  |  |  | TOWER D 1101 | TOWER D 1101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33612 |  |  |  | TOWER D 1101 WATERPROOFING WORK | TOWER D 1101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30081 |  |  |  | TOWER D 1101 | TOWER D 1101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32984 |  |  |  | TOWER D 1101 PLUMBING WORK | TOWER D 1101 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30080 |  |  |  | TOWER D 1101 | TOWER D 1101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33863 |  |  |  | TOWER D 1101 ELECTRIC WORK | TOWER D 1101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30082 |  |  |  | TOWER D 1101 | TOWER D 1101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30085 |  |  |  | TOWER D 1101 | TOWER D 1101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30083 |  |  |  | TOWER D 1101 | TOWER D 1101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30084 |  |  |  | TOWER D 1101 | TOWER D 1101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30086 |  |  |  | TOWER D 1101 | TOWER D 1101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34553 |  |  |  | TOWER D 1101 | TOWER D 1101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34554 |  |  |  | TOWER D 1101 COMMON WORK | TOWER D 1101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34555 |  |  |  | TOWER D 1101 COMMON WORK | TOWER D 1101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34556 |  |  |  | TOWER D 1101 COMMON WORK | TOWER D 1101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40233 |  |  |  | TOWER D 1101 COMMON WORK | TOWER D 1101 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30096 |  |  |  | TOWER D 11TH FLOOR | TOWER D 1102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30088 |  |  |  | TOWER D 1102 | TOWER D 1102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33613 |  |  |  | TOWER D 1102 WATERPROOFING WORK | TOWER D 1102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30090 |  |  |  | TOWER D 1102 | TOWER D 1102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32985 |  |  |  | TOWER D 1102 PLUMBING WORK | TOWER D 1102 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30089 |  |  |  | TOWER D 1102 | TOWER D 1102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33864 |  |  |  | TOWER D 1102 ELECTRIC WORK | TOWER D 1102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30091 |  |  |  | TOWER D 1102 | TOWER D 1102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30094 |  |  |  | TOWER D 1102 | TOWER D 1102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30092 |  |  |  | TOWER D 1102 | TOWER D 1102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30093 |  |  |  | TOWER D 1102 | TOWER D 1102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30095 |  |  |  | TOWER D 1102 | TOWER D 1102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34557 |  |  |  | TOWER D 1102 | TOWER D 1102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34558 |  |  |  | TOWER D 1102 COMMON WORK | TOWER D 1102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34559 |  |  |  | TOWER D 1102 COMMON WORK | TOWER D 1102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34560 |  |  |  | TOWER D 1102 COMMON WORK | TOWER D 1102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40234 |  |  |  | TOWER D 1102 COMMON WORK | TOWER D 1102 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30283 |  |  |  | TOWER D 11TH FLOOR | TOWER D 11TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30286 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34037 |  |  |  | TOWER D 11TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 11TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30284 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42006 |  |  |  | TOWER D 11TH FLOOR COMMON FLOORING WORK | TOWER D 11TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30285 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30287 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30288 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 31470 |  |  |  | TOWER D 11TH FLOOR COMMON ELECTRIC WORK | TOWER D 11TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40951 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40952 |  |  |  | TOWER D 11TH FLOOR WPC PANNELING WORK | TOWER D 11TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41798 |  |  |  | TOWER D 11TH FLOOR COMMON WORK | TOWER D 11TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41799 |  |  |  | TOWER D 11TH FLOOR COMMON FABRICATION WORK | TOWER D 11TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24680 |  |  |  | TOWER D | TOWER D 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24681 |  |  |  | TOWER D 12TH FLOOR | TOWER D 12TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24682 |  |  |  | TOWER D 12TH FLOOR CIVIL WORK | TOWER D 12TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24685 |  |  |  | TOWER D 12TH FLOOR RCC WORK | TOWER D 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35094.18 |  | Started | 35094.18 | 0 | 35094.18 | 0 | 35.09 | 0 | 1023110.96 | 1023110.96 |  |  | 10 Feb 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 39525 |  |  |  | TOWER D 12TH FLOOR RCC WORK | TOWER D 12TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21712 | 21712 | 17 Mar 2020 |  | 06 Feb 2024 |  | - | - | 1422 | - | THREADING
Task | 6 | 40087 |  |  |  | TOWER D 12TH FLOOR RCC WORK | TOWER D 12TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 44235.64 | 44235.64 | 17 Mar 2020 |  | 23 Jul 2024 |  | - | - | 1590 | - | SAFETY NET FIXING
Group | 5 | 24683 |  |  |  | TOWER D 12TH FLOOR CIVIL WORK | TOWER D 12TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24686 |  |  |  | TOWER D 12TH FLOOR MASONRY WORK | TOWER D 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24684 |  |  |  | TOWER D 12TH FLOOR CIVIL WORK | TOWER D 12TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24687 |  |  |  | TOWER D 12TH FLOOR PLASTER WORK | TOWER D 12TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30105 |  |  |  | TOWER D 12TH FLOOR | TOWER D 1201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30097 |  |  |  | TOWER D 1201 | TOWER D 1201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33614 |  |  |  | TOWER D 1201 WATERPROOFING WORK | TOWER D 1201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30099 |  |  |  | TOWER D 1201 | TOWER D 1201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32986 |  |  |  | TOWER D 1201 PLUMBING WORK | TOWER D 1201 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30098 |  |  |  | TOWER D 1201 | TOWER D 1201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33865 |  |  |  | TOWER D 1201 ELECTRIC WORK | TOWER D 1201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30100 |  |  |  | TOWER D 1201 | TOWER D 1201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30103 |  |  |  | TOWER D 1201 | TOWER D 1201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30101 |  |  |  | TOWER D 1201 | TOWER D 1201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30102 |  |  |  | TOWER D 1201 | TOWER D 1201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30104 |  |  |  | TOWER D 1201 | TOWER D 1201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34561 |  |  |  | TOWER D 1201 | TOWER D 1201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34562 |  |  |  | TOWER D 1201 COMMON WORK | TOWER D 1201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34563 |  |  |  | TOWER D 1201 COMMON WORK | TOWER D 1201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34564 |  |  |  | TOWER D 1201 COMMON WORK | TOWER D 1201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40235 |  |  |  | TOWER D 1201 COMMON WORK | TOWER D 1201 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30114 |  |  |  | TOWER D 12TH FLOOR | TOWER D 1202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30106 |  |  |  | TOWER D 1202 | TOWER D 1202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33615 |  |  |  | TOWER D 1202 WATERPROOFING WORK | TOWER D 1202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30108 |  |  |  | TOWER D 1202 | TOWER D 1202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32987 |  |  |  | TOWER D 1202 PLUMBING WORK | TOWER D 1202 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30107 |  |  |  | TOWER D 1202 | TOWER D 1202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33866 |  |  |  | TOWER D 1202 ELECTRIC WORK | TOWER D 1202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30109 |  |  |  | TOWER D 1202 | TOWER D 1202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30112 |  |  |  | TOWER D 1202 | TOWER D 1202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30110 |  |  |  | TOWER D 1202 | TOWER D 1202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30111 |  |  |  | TOWER D 1202 | TOWER D 1202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30113 |  |  |  | TOWER D 1202 | TOWER D 1202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34565 |  |  |  | TOWER D 1202 | TOWER D 1202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34566 |  |  |  | TOWER D 1202 COMMON WORK | TOWER D 1202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34567 |  |  |  | TOWER D 1202 COMMON WORK | TOWER D 1202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34568 |  |  |  | TOWER D 1202 COMMON WORK | TOWER D 1202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40236 |  |  |  | TOWER D 1202 COMMON WORK | TOWER D 1202 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30289 |  |  |  | TOWER D 12TH FLOOR | TOWER D 12TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30292 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34038 |  |  |  | TOWER D 12TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER D 12TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 30290 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42007 |  |  |  | TOWER D 12TH FLOOR COMMON FLOORING WORK | TOWER D 12TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30291 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30293 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30294 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38764 |  |  |  | TOWER D 12TH FLOOR COMMON ELECTRIC WORK | TOWER D 12TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40953 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40954 |  |  |  | TOWER D 12TH FLOOR WPC PANNELING WORK | TOWER D 12TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41800 |  |  |  | TOWER D 12TH FLOOR COMMON WORK | TOWER D 12TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41801 |  |  |  | TOWER D 12TH FLOOR COMMON FABRICATION WORK | TOWER D 12TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24688 |  |  |  | TOWER D | TOWER D 13TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24689 |  |  |  | TOWER D 13TH FLOOR | TOWER D 13TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24690 |  |  |  | TOWER D 13TH FLOOR CIVIL WORK | TOWER D 13TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24693 |  |  |  | TOWER D 13TH FLOOR RCC WORK | TOWER D 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34561.3 |  | Started | 34561.3 | 0 | 34561.3 | 0 | 34.56 | 0 | 1023110.96 | 1023110.96 |  |  | 21 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 39528 |  |  |  | TOWER D 13TH FLOOR RCC WORK | TOWER D 13TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 18880 | 18880 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Group | 5 | 24691 |  |  |  | TOWER D 13TH FLOOR CIVIL WORK | TOWER D 13TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24694 |  |  |  | TOWER D 13TH FLOOR MASONRY WORK | TOWER D 13TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24692 |  |  |  | TOWER D 13TH FLOOR CIVIL WORK | TOWER D 13TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24695 |  |  |  | TOWER D 13TH FLOOR PLASTER WORK | TOWER D 13TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30123 |  |  |  | TOWER D 13TH FLOOR | TOWER D 1301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30115 |  |  |  | TOWER D 1301 | TOWER D 1301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33616 |  |  |  | TOWER D 1301 WATERPROOFING WORK | TOWER D 1301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30117 |  |  |  | TOWER D 1301 | TOWER D 1301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32988 |  |  |  | TOWER D 1301 PLUMBING WORK | TOWER D 1301 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30116 |  |  |  | TOWER D 1301 | TOWER D 1301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33867 |  |  |  | TOWER D 1301 ELECTRIC WORK | TOWER D 1301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 19 Apr 2024 |  | - | - | 1495 | - | ELECTRIC WORK
Group | 5 | 30118 |  |  |  | TOWER D 1301 | TOWER D 1301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30121 |  |  |  | TOWER D 1301 | TOWER D 1301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30119 |  |  |  | TOWER D 1301 | TOWER D 1301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30120 |  |  |  | TOWER D 1301 | TOWER D 1301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30122 |  |  |  | TOWER D 1301 | TOWER D 1301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34569 |  |  |  | TOWER D 1301 | TOWER D 1301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34570 |  |  |  | TOWER D 1301 COMMON WORK | TOWER D 1301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34571 |  |  |  | TOWER D 1301 COMMON WORK | TOWER D 1301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34572 |  |  |  | TOWER D 1301 COMMON WORK | TOWER D 1301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40237 |  |  |  | TOWER D 1301 COMMON WORK | TOWER D 1301 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30132 |  |  |  | TOWER D 13TH FLOOR | TOWER D 1302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30124 |  |  |  | TOWER D 1302 | TOWER D 1302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33617 |  |  |  | TOWER D 1302 WATERPROOFING WORK | TOWER D 1302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30126 |  |  |  | TOWER D 1302 | TOWER D 1302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32989 |  |  |  | TOWER D 1302 PLUMBING WORK | TOWER D 1302 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30125 |  |  |  | TOWER D 1302 | TOWER D 1302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33868 |  |  |  | TOWER D 1302 ELECTRIC WORK | TOWER D 1302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 19 Apr 2024 |  | - | - | 1495 | - | ELECTRIC WORK
Group | 5 | 30127 |  |  |  | TOWER D 1302 | TOWER D 1302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30130 |  |  |  | TOWER D 1302 | TOWER D 1302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30128 |  |  |  | TOWER D 1302 | TOWER D 1302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30129 |  |  |  | TOWER D 1302 | TOWER D 1302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30131 |  |  |  | TOWER D 1302 | TOWER D 1302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34573 |  |  |  | TOWER D 1302 | TOWER D 1302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34574 |  |  |  | TOWER D 1302 COMMON WORK | TOWER D 1302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34575 |  |  |  | TOWER D 1302 COMMON WORK | TOWER D 1302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34576 |  |  |  | TOWER D 1302 COMMON WORK | TOWER D 1302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40238 |  |  |  | TOWER D 1302 COMMON WORK | TOWER D 1302 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30295 |  |  |  | TOWER D 13TH FLOOR | TOWER D 13TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30298 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30296 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42008 |  |  |  | TOWER D 13TH FLOOR COMMON FLOORING WORK | TOWER D 13TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30297 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30299 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30300 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38765 |  |  |  | TOWER D 13TH FLOOR COMMON ELECTRIC WORK | TOWER D 13TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40955 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40956 |  |  |  | TOWER D 13TH FLOOR WPC PANNELING WORK | TOWER D 13TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41802 |  |  |  | TOWER D 13TH FLOOR COMMON WORK | TOWER D 13TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41803 |  |  |  | TOWER D 13TH FLOOR COMMON FABRICATION WORK | TOWER D 13TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24696 |  |  |  | TOWER D | TOWER D 14TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24697 |  |  |  | TOWER D 14TH FLOOR | TOWER D 14TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24698 |  |  |  | TOWER D 14TH FLOOR CIVIL WORK | TOWER D 14TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24701 |  |  |  | TOWER D 14TH FLOOR RCC WORK | TOWER D 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34503.64 |  | Started | 34503.64 | 0 | 34503.64 | 0 | 34.5 | 0 | 1023110.96 | 1023110.96 |  |  | 23 Aug 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41014 |  |  |  | TOWER D 14TH FLOOR RCC WORK | TOWER D 14TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 15104 | 15104 | 17 Mar 2020 |  | 15 May 2024 |  | - | - | 1521 | - | THREADING
Group | 5 | 24699 |  |  |  | TOWER D 14TH FLOOR CIVIL WORK | TOWER D 14TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24702 |  |  |  | TOWER D 14TH FLOOR MASONRY WORK | TOWER D 14TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24700 |  |  |  | TOWER D 14TH FLOOR CIVIL WORK | TOWER D 14TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24703 |  |  |  | TOWER D 14TH FLOOR PLASTER WORK | TOWER D 14TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30141 |  |  |  | TOWER D 14TH FLOOR | TOWER D 1401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30133 |  |  |  | TOWER D 1401 | TOWER D 1401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33618 |  |  |  | TOWER D 1401 WATERPROOFING WORK | TOWER D 1401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30135 |  |  |  | TOWER D 1401 | TOWER D 1401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32990 |  |  |  | TOWER D 1401 PLUMBING WORK | TOWER D 1401 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30134 |  |  |  | TOWER D 1401 | TOWER D 1401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33869 |  |  |  | TOWER D 1401 ELECTRIC WORK | TOWER D 1401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 20 May 2024 |  | - | - | 1526 | - | ELECTRIC WORK
Group | 5 | 30136 |  |  |  | TOWER D 1401 | TOWER D 1401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30139 |  |  |  | TOWER D 1401 | TOWER D 1401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30137 |  |  |  | TOWER D 1401 | TOWER D 1401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30138 |  |  |  | TOWER D 1401 | TOWER D 1401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30140 |  |  |  | TOWER D 1401 | TOWER D 1401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34577 |  |  |  | TOWER D 1401 | TOWER D 1401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34578 |  |  |  | TOWER D 1401 COMMON WORK | TOWER D 1401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34579 |  |  |  | TOWER D 1401 COMMON WORK | TOWER D 1401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34580 |  |  |  | TOWER D 1401 COMMON WORK | TOWER D 1401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40239 |  |  |  | TOWER D 1401 COMMON WORK | TOWER D 1401 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30150 |  |  |  | TOWER D 14TH FLOOR | TOWER D 1402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30142 |  |  |  | TOWER D 1402 | TOWER D 1402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33619 |  |  |  | TOWER D 1402 WATERPROOFING WORK | TOWER D 1402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30144 |  |  |  | TOWER D 1402 | TOWER D 1402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32991 |  |  |  | TOWER D 1402 PLUMBING WORK | TOWER D 1402 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30143 |  |  |  | TOWER D 1402 | TOWER D 1402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33870 |  |  |  | TOWER D 1402 ELECTRIC WORK | TOWER D 1402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 20 May 2024 |  | - | - | 1526 | - | ELECTRIC WORK
Group | 5 | 30145 |  |  |  | TOWER D 1402 | TOWER D 1402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30148 |  |  |  | TOWER D 1402 | TOWER D 1402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30146 |  |  |  | TOWER D 1402 | TOWER D 1402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30147 |  |  |  | TOWER D 1402 | TOWER D 1402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30149 |  |  |  | TOWER D 1402 | TOWER D 1402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34581 |  |  |  | TOWER D 1402 | TOWER D 1402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34582 |  |  |  | TOWER D 1402 COMMON WORK | TOWER D 1402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34583 |  |  |  | TOWER D 1402 COMMON WORK | TOWER D 1402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34584 |  |  |  | TOWER D 1402 COMMON WORK | TOWER D 1402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40240 |  |  |  | TOWER D 1402 COMMON WORK | TOWER D 1402 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30301 |  |  |  | TOWER D 14TH FLOOR | TOWER D 14TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30304 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30302 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42009 |  |  |  | TOWER D 14TH FLOOR COMMON FLOORING WORK | TOWER D 14TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30303 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30305 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30306 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38766 |  |  |  | TOWER D 14TH FLOOR COMMON ELECTRIC WORK | TOWER D 14TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 40957 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40958 |  |  |  | TOWER D 14TH FLOOR WPC PANNELING WORK | TOWER D 14TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41804 |  |  |  | TOWER D 14TH FLOOR COMMON WORK | TOWER D 14TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41805 |  |  |  | TOWER D 14TH FLOOR COMMON FABRICATION WORK | TOWER D 14TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24704 |  |  |  | TOWER D | TOWER D 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24705 |  |  |  | TOWER D 15TH FLOOR | TOWER D 15TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24706 |  |  |  | TOWER D 15TH FLOOR CIVIL WORK | TOWER D 15TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24709 |  |  |  | TOWER D 15TH FLOOR RCC WORK | TOWER D 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 133927.9 |  | Started | 133927.9 | 0 | 133927.9 | 0 | 133.93 | 0 | 1023110.96 | 1023110.96 |  |  | 20 Sep 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41015 |  |  |  | TOWER D 15TH FLOOR RCC WORK | TOWER D 15TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 13688 | 13688 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | THREADING
Group | 5 | 24707 |  |  |  | TOWER D 15TH FLOOR CIVIL WORK | TOWER D 15TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24710 |  |  |  | TOWER D 15TH FLOOR MASONRY WORK | TOWER D 15TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24708 |  |  |  | TOWER D 15TH FLOOR CIVIL WORK | TOWER D 15TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24711 |  |  |  | TOWER D 15TH FLOOR PLASTER WORK | TOWER D 15TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30159 |  |  |  | TOWER D 15TH FLOOR | TOWER D 1501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30151 |  |  |  | TOWER D 1501 | TOWER D 1501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33620 |  |  |  | TOWER D 1501 WATERPROOFING WORK | TOWER D 1501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30153 |  |  |  | TOWER D 1501 | TOWER D 1501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32992 |  |  |  | TOWER D 1501 PLUMBING WORK | TOWER D 1501 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30152 |  |  |  | TOWER D 1501 | TOWER D 1501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33871 |  |  |  | TOWER D 1501 ELECTRIC WORK | TOWER D 1501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 30154 |  |  |  | TOWER D 1501 | TOWER D 1501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30157 |  |  |  | TOWER D 1501 | TOWER D 1501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30155 |  |  |  | TOWER D 1501 | TOWER D 1501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30156 |  |  |  | TOWER D 1501 | TOWER D 1501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30158 |  |  |  | TOWER D 1501 | TOWER D 1501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34585 |  |  |  | TOWER D 1501 | TOWER D 1501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34586 |  |  |  | TOWER D 1501 COMMON WORK | TOWER D 1501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34587 |  |  |  | TOWER D 1501 COMMON WORK | TOWER D 1501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34588 |  |  |  | TOWER D 1501 COMMON WORK | TOWER D 1501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40241 |  |  |  | TOWER D 1501 COMMON WORK | TOWER D 1501 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30168 |  |  |  | TOWER D 15TH FLOOR | TOWER D 1502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30160 |  |  |  | TOWER D 1502 | TOWER D 1502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33621 |  |  |  | TOWER D 1502 WATERPROOFING WORK | TOWER D 1502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30162 |  |  |  | TOWER D 1502 | TOWER D 1502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32993 |  |  |  | TOWER D 1502 PLUMBING WORK | TOWER D 1502 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30161 |  |  |  | TOWER D 1502 | TOWER D 1502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33872 |  |  |  | TOWER D 1502 ELECTRIC WORK | TOWER D 1502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 30163 |  |  |  | TOWER D 1502 | TOWER D 1502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30166 |  |  |  | TOWER D 1502 | TOWER D 1502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30164 |  |  |  | TOWER D 1502 | TOWER D 1502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30165 |  |  |  | TOWER D 1502 | TOWER D 1502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30167 |  |  |  | TOWER D 1502 | TOWER D 1502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34589 |  |  |  | TOWER D 1502 | TOWER D 1502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34590 |  |  |  | TOWER D 1502 COMMON WORK | TOWER D 1502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34591 |  |  |  | TOWER D 1502 COMMON WORK | TOWER D 1502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34592 |  |  |  | TOWER D 1502 COMMON WORK | TOWER D 1502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40242 |  |  |  | TOWER D 1502 COMMON WORK | TOWER D 1502 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30307 |  |  |  | TOWER D 15TH FLOOR | TOWER D 15TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30310 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30308 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42010 |  |  |  | TOWER D 15TH FLOOR COMMON FLOORING WORK | TOWER D 15TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30309 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30311 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30312 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38767 |  |  |  | TOWER D 15TH FLOOR COMMON ELECTRIC WORK | TOWER D 15TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 40959 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40960 |  |  |  | TOWER D 15TH FLOOR COMMON WPC PANNELING WORK | TOWER D 15TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41806 |  |  |  | TOWER D 15TH FLOOR COMMON WORK | TOWER D 15TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41807 |  |  |  | TOWER D 15TH FLOOR COMMON FABRICATION WORK | TOWER D 15TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24712 |  |  |  | TOWER D | TOWER D 16TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24713 |  |  |  | TOWER D 16TH FLOOR | TOWER D 16TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24714 |  |  |  | TOWER D 16TH FLOOR CIVIL WORK | TOWER D 16TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24717 |  |  |  | TOWER D 16TH FLOOR RCC WORK | TOWER D 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 139976.9 |  | Started | 139976.9 | 0 | 139976.9 | 0 | 139.98 | 0 | 1023110.96 | 1023110.96 |  |  | 24 Oct 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41016 |  |  |  | TOWER D 16TH FLOOR RCC WORK | TOWER D 16TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24715 |  |  |  | TOWER D 16TH FLOOR CIVIL WORK | TOWER D 16TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24718 |  |  |  | TOWER D 16TH FLOOR MASONRY WORK | TOWER D 16TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24716 |  |  |  | TOWER D 16TH FLOOR CIVIL WORK | TOWER D 16TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24719 |  |  |  | TOWER D 16TH FLOOR PLASTER WORK | TOWER D 16TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30177 |  |  |  | TOWER D 16TH FLOOR | TOWER D 1601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30169 |  |  |  | TOWER D 1601 | TOWER D 1601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33623 |  |  |  | TOWER D 1601 WATERPROOFING WORK | TOWER D 1601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30171 |  |  |  | TOWER D 1601 | TOWER D 1601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32994 |  |  |  | TOWER D 1601 PLUMBING WORK | TOWER D 1601 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30170 |  |  |  | TOWER D 1601 | TOWER D 1601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33873 |  |  |  | TOWER D 1601 ELECTRIC WORK | TOWER D 1601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 30172 |  |  |  | TOWER D 1601 | TOWER D 1601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30175 |  |  |  | TOWER D 1601 | TOWER D 1601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30173 |  |  |  | TOWER D 1601 | TOWER D 1601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30174 |  |  |  | TOWER D 1601 | TOWER D 1601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30176 |  |  |  | TOWER D 1601 | TOWER D 1601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34593 |  |  |  | TOWER D 1601 | TOWER D 1601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34594 |  |  |  | TOWER D 1601 COMMON WORK | TOWER D 1601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34595 |  |  |  | TOWER D 1601 COMMON WORK | TOWER D 1601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34596 |  |  |  | TOWER D 1601 COMMON WORK | TOWER D 1601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40244 |  |  |  | TOWER D 1601 COMMON WORK | TOWER D 1601 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30186 |  |  |  | TOWER D 16TH FLOOR | TOWER D 1602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30178 |  |  |  | TOWER D 1602 | TOWER D 1602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33626 |  |  |  | TOWER D 1602 WATERPROOFING WORK | TOWER D 1602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30180 |  |  |  | TOWER D 1602 | TOWER D 1602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32995 |  |  |  | TOWER D 1602 PLUMBING WORK | TOWER D 1602 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30179 |  |  |  | TOWER D 1602 | TOWER D 1602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33874 |  |  |  | TOWER D 1602 ELECTRIC WORK | TOWER D 1602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 19 Oct 2024 |  | - | - | 1678 | - | ELECTRIC WORK
Group | 5 | 30181 |  |  |  | TOWER D 1602 | TOWER D 1602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30184 |  |  |  | TOWER D 1602 | TOWER D 1602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30182 |  |  |  | TOWER D 1602 | TOWER D 1602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30183 |  |  |  | TOWER D 1602 | TOWER D 1602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30185 |  |  |  | TOWER D 1602 | TOWER D 1602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34597 |  |  |  | TOWER D 1602 | TOWER D 1602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34598 |  |  |  | TOWER D 1602 COMMON WORK | TOWER D 1602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34599 |  |  |  | TOWER D 1602 COMMON WORK | TOWER D 1602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34600 |  |  |  | TOWER D 1602 COMMON WORK | TOWER D 1602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40245 |  |  |  | TOWER D 1602 COMMON WORK | TOWER D 1602 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30313 |  |  |  | TOWER D 16TH FLOOR | TOWER D 16TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30316 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30314 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42011 |  |  |  | TOWER D 16TH FLOOR COMMON FLOORING WORK | TOWER D 16TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30315 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30317 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30318 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38768 |  |  |  | TOWER D 16TH FLOOR COMMON ELECTRIC WORK | TOWER D 16TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40961 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40962 |  |  |  | TOWER D 16TH FLOOR WPC PANNELING WORK | TOWER D 16TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41808 |  |  |  | TOWER D 16TH FLOOR COMMON WORK | TOWER D 16TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41809 |  |  |  | TOWER D 16TH FLOOR COMMON FABRICATION WORK | TOWER D 16TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24720 |  |  |  | TOWER D | TOWER D 17TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24721 |  |  |  | TOWER D 17TH FLOOR | TOWER D 17TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24722 |  |  |  | TOWER D 17TH FLOOR CIVIL WORK | TOWER D 17TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24725 |  |  |  | TOWER D 17TH FLOOR RCC WORK | TOWER D 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 18353.9 |  | Tentative | 18353.9 | 0 | 18353.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24723 |  |  |  | TOWER D 17TH FLOOR CIVIL WORK | TOWER D 17TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24726 |  |  |  | TOWER D 17TH FLOOR MASONRY WORK | TOWER D 17TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24724 |  |  |  | TOWER D 17TH FLOOR CIVIL WORK | TOWER D 17TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24727 |  |  |  | TOWER D 17TH FLOOR PLASTER WORK | TOWER D 17TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30195 |  |  |  | TOWER D 17TH FLOOR | TOWER D 1701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30187 |  |  |  | TOWER D 1701 | TOWER D 1701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30189 |  |  |  | TOWER D 1701 | TOWER D 1701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32996 |  |  |  | TOWER D 1701 PLUMBING WORK | TOWER D 1701 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30188 |  |  |  | TOWER D 1701 | TOWER D 1701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40400 |  |  |  | TOWER D 1701 ELECTRIC WORK | TOWER D 1701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30190 |  |  |  | TOWER D 1701 | TOWER D 1701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30193 |  |  |  | TOWER D 1701 | TOWER D 1701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30191 |  |  |  | TOWER D 1701 | TOWER D 1701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30192 |  |  |  | TOWER D 1701 | TOWER D 1701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30194 |  |  |  | TOWER D 1701 | TOWER D 1701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34601 |  |  |  | TOWER D 1701 | TOWER D 1701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34602 |  |  |  | TOWER D 1701 COMMON WORK | TOWER D 1701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34603 |  |  |  | TOWER D 1701 COMMON WORK | TOWER D 1701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34604 |  |  |  | TOWER D 1701 COMMON WORK | TOWER D 1701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40247 |  |  |  | TOWER D 1701 COMMON WORK | TOWER D 1701 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5778 |  | Tentative | 0 | 5778 | 5778 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30204 |  |  |  | TOWER D 17TH FLOOR | TOWER D 1702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30196 |  |  |  | TOWER D 1702 | TOWER D 1702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30198 |  |  |  | TOWER D 1702 | TOWER D 1702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32997 |  |  |  | TOWER D 1702 PLUMBING WORK | TOWER D 1702 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30197 |  |  |  | TOWER D 1702 | TOWER D 1702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40401 |  |  |  | TOWER D 1702 ELECTRIC WORK | TOWER D 1702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30199 |  |  |  | TOWER D 1702 | TOWER D 1702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30202 |  |  |  | TOWER D 1702 | TOWER D 1702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30200 |  |  |  | TOWER D 1702 | TOWER D 1702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30201 |  |  |  | TOWER D 1702 | TOWER D 1702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30203 |  |  |  | TOWER D 1702 | TOWER D 1702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34605 |  |  |  | TOWER D 1702 | TOWER D 1702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34606 |  |  |  | TOWER D 1702 COMMON WORK | TOWER D 1702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34607 |  |  |  | TOWER D 1702 COMMON WORK | TOWER D 1702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34608 |  |  |  | TOWER D 1702 COMMON WORK | TOWER D 1702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40248 |  |  |  | TOWER D 1702 COMMON WORK | TOWER D 1702 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5778 |  | Tentative | 0 | 5778 | 5778 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30319 |  |  |  | TOWER D 17TH FLOOR | TOWER D 17TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30322 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30320 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42012 |  |  |  | TOWER D 17TH FLOOR COMMON FLOORING WORK | TOWER D 17TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30321 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30323 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30324 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 40963 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40964 |  |  |  | TOWER D 17TH FLOOR WPC PANNELING WORK | TOWER D 17TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41810 |  |  |  | TOWER D 17TH FLOOR COMMON WORK | TOWER D 17TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41811 |  |  |  | TOWER D 17TH FLOOR COMMON FABRICATION WORK | TOWER D 17TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24728 |  |  |  | TOWER D | TOWER D 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24729 |  |  |  | TOWER D 18TH FLOOR | TOWER D 18TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24730 |  |  |  | TOWER D 18TH FLOOR CIVIL WORK | TOWER D 18TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24733 |  |  |  | TOWER D 18TH FLOOR RCC WORK | TOWER D 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 227.74 |  | Tentative | 227.74 | 0 | 227.74 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24731 |  |  |  | TOWER D 18TH FLOOR CIVIL WORK | TOWER D 18TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24734 |  |  |  | TOWER D 18TH FLOOR MASONRY WORK | TOWER D 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24732 |  |  |  | TOWER D 18TH FLOOR CIVIL WORK | TOWER D 18TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24735 |  |  |  | TOWER D 18TH FLOOR PLASTER WORK | TOWER D 18TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 30213 |  |  |  | TOWER D 18TH FLOOR | TOWER D 1801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30205 |  |  |  | TOWER D 1801 | TOWER D 1801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30207 |  |  |  | TOWER D 1801 | TOWER D 1801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32998 |  |  |  | TOWER D 1801 PLUMBING WORK | TOWER D 1801 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30206 |  |  |  | TOWER D 1801 | TOWER D 1801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40402 |  |  |  | TOWER D 1801 ELECTRIC WORK | TOWER D 1801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30208 |  |  |  | TOWER D 1801 | TOWER D 1801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30211 |  |  |  | TOWER D 1801 | TOWER D 1801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30209 |  |  |  | TOWER D 1801 | TOWER D 1801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30210 |  |  |  | TOWER D 1801 | TOWER D 1801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30212 |  |  |  | TOWER D 1801 | TOWER D 1801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34609 |  |  |  | TOWER D 1801 | TOWER D 1801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34610 |  |  |  | TOWER D 1801 COMMON WORK | TOWER D 1801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34611 |  |  |  | TOWER D 1801 COMMON WORK | TOWER D 1801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34612 |  |  |  | TOWER D 1801 COMMON WORK | TOWER D 1801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40249 |  |  |  | TOWER D 1801 COMMON WORK | TOWER D 1801 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 3813 |  | Tentative | 0 | 3813 | 3813 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30222 |  |  |  | TOWER D 18TH FLOOR | TOWER D 1802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30214 |  |  |  | TOWER D 1802 | TOWER D 1802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30216 |  |  |  | TOWER D 1802 | TOWER D 1802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32999 |  |  |  | TOWER D 1802 PLUMBING WORK | TOWER D 1802 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 30215 |  |  |  | TOWER D 1802 | TOWER D 1802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40403 |  |  |  | TOWER D 1802 ELECTRIC WORK | TOWER D 1802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30217 |  |  |  | TOWER D 1802 | TOWER D 1802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30220 |  |  |  | TOWER D 1802 | TOWER D 1802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30218 |  |  |  | TOWER D 1802 | TOWER D 1802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30219 |  |  |  | TOWER D 1802 | TOWER D 1802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30221 |  |  |  | TOWER D 1802 | TOWER D 1802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34613 |  |  |  | TOWER D 1802 | TOWER D 1802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34614 |  |  |  | TOWER D 1802 COMMON WORK | TOWER D 1802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34615 |  |  |  | TOWER D 1802 COMMON WORK | TOWER D 1802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34616 |  |  |  | TOWER D 1802 COMMON WORK | TOWER D 1802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40250 |  |  |  | TOWER D 1802 COMMON WORK | TOWER D 1802 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 3813 |  | Tentative | 0 | 3813 | 3813 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 30325 |  |  |  | TOWER D 18TH FLOOR | TOWER D 18TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30328 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30326 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42013 |  |  |  | TOWER D 18TH FLOOR COMMON FLOORING WORK | TOWER D 18TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 30327 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30329 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30330 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 40965 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40966 |  |  |  | TOWER D 18TH FLOOR WPC PANNELING WORK | TOWER D 18TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 41812 |  |  |  | TOWER D 18TH FLOOR COMMON WORK | TOWER D 18TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41813 |  |  |  | TOWER D 18TH FLOOR COMMON FABRICATION WORK | TOWER D 18TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 41509 |  |  |  | TOWER D | TOWER D TERRACE | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41510 |  |  |  | TOWER D TERRACE | TOWER D TERRACE CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41511 |  |  |  | TOWER D TERRACE CIVIL WORK | TOWER D TERRACE RCC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41514 |  |  |  | TOWER D TERRACE RCC WORK | TOWER D TERRACE RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 41512 |  |  |  | TOWER D TERRACE CIVIL WORK | TOWER D TERRACE MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41515 |  |  |  | TOWER D TERRACE MASONRY WORK | TOWER D TERRACE MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 41513 |  |  |  | TOWER D TERRACE CIVIL WORK | TOWER D TERRACE PLASTER WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41516 |  |  |  | TOWER D TERRACE PLASTER WORK | TOWER D TERRACE PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 41450 |  |  |  | TOWER D | TOWER D COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41451 |  |  |  | TOWER D COMMON WORK | TOWER D COMMON PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41452 |  |  |  | TOWER D COMMON PLUMBING WORK | TOWER D COMMON DUCT PLUMBING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING DUCT-PVC-SWR DRAINAGE PIPING WO
Group | 4 | 41479 |  |  |  | TOWER D COMMON WORK | TOWER D COMMON ELECTRIC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41480 |  |  |  | TOWER D COMMON ELECTRIC WORK | TOWER D COMMON ELECTRIC WORK | 1 | POINT | 1 | POINT | 0 | ELECTRIC WORK | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | TOWER COMMON ELECTRIC WORK
Group | 4 | 42147 | Block/Building/Tower/Wing |  | Externall Plaster | TOWER D COMMON WORK | TOWER D EXTERNAL PAINT WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 42148 |  |  |  | TOWER D EXTERNAL PAINT WORK | TOWER D EXTERNAL PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | EXTERNAL PAINT WORK
Group | 2 | 30513 |  |  |  |  | CLUB HOUSE | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 30514 |  |  |  | CLUB HOUSE | CLUB HOUSE FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 4 | 41370 |  |  |  | CLUB HOUSE FLOORING WORK | CLUB HOUSE FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 37747.5 | 37747.5 | 17 Mar 2020 |  | 31 May 2024 |  | - | - | 1537 | - | FLOOR TILE
Group | 3 | 30515 |  |  |  | CLUB HOUSE | CLUB HOUSE EXTERNAL FACADE & WINDOWS WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 30516 |  |  |  | CLUB HOUSE | CLUB HOUSE PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 30517 |  |  |  | CLUB HOUSE | CLUB HOUSE ELECRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 30518 |  |  |  | CLUB HOUSE | CLUB HOUSE AIR CONDITIONING / HVAC | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 30519 |  |  |  | CLUB HOUSE | CLUB HOUSE MISCELLENEOUS | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 4 | 41563 |  |  |  | CLUB HOUSE MISCELLENEOUS | CLUB HOUSE MISCELLENEOUS | 1 | NOS | 1 | NOS | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS WORK
Group | 2 | 24913 |  |  |  |  | INFRA | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 27 Jan 2022 |  | - | - | 682 | -
Group | 3 | 24798 |  |  |  | INFRA | CONSULTANT CHARGES | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 27 Jan 2022 |  | - | - | 682 | -
Task | 4 | 24799 |  |  |  | CONSULTANT CHARGES | CONSULTANT CHARGES | 1 | NOS | 1 | NOS | 265004 |  | Started | 0 | 265004 | 265004 | 0 | 265 | 0 | 10676341.21 | 10676341.21 | 17 Mar 2020 |  | 27 Jan 2022 |  | - | - | 682 | - | HVAC CONSULTANT
Group | 3 | 30509 |  |  |  | INFRA | INFRA FIRE FIGHTINGS | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 30510 |  |  |  | INFRA | INFRA DG SET | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 2 | 24020 |  |  |  |  | COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 27 Mar 2021 |  | - | - | 376 | -
Group | 3 | 27659 |  |  |  | COMMON WORK | COMMOMN CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 09 Jun 2021 |  | - | - | 450 | -
Group | 4 | 25609 |  |  |  | COMMOMN CIVIL WORK | MATERIAL TESTING | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Oct 2021 |  | - | - | 568 | -
Task | 5 | 25611 |  |  |  | MATERIAL TESTING | TESTING OF MATERIALS | 1 | NOS | 1 | NOS | 6 |  | Started | 6 | 0 | 6 | 0 | 0.01 | 0 | 1405378.82 | 1405378.82 | 17 Mar 2020 |  | 05 Oct 2021 |  | - | - | 568 | - | TESTING OF MATERIALS
Group | 4 | 24912 |  |  |  | COMMOMN CIVIL WORK | COMMON BORE WELL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 09 Jun 2021 |  | - | - | 450 | -
Task | 5 | 24790 |  |  |  | COMMON BORE WELL WORK | COMMON BOREWELL WORK | 1 | NOS | 1 | NOS | 171391.2 |  | Started | 171391.2 | 0 | 171391.2 | 0 | 171.39 | 0 | 90290.8 | 90290.8 | 17 Mar 2020 |  | 09 Jun 2021 |  | - | - | 450 | - | BOREWELL WORK
Group | 4 | 24911 |  |  |  | COMMOMN CIVIL WORK | EXCAVATION & BACK FILLING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Sep 2021 |  | - | - | 556 | -
Task | 5 | 24746 |  |  |  | EXCAVATION & BACK FILLING WORK | EXCAVATION & BACKFILLING WORK | 1 | CMT | 1 | CMT | 2492345 |  | Started | 5 | 2492340 | 2492345 | 0 | 2492.35 | 0 | 8726573.59 | 8726573.59 | 17 Mar 2020 |  | 20 Mar 2024 |  | - | - | 1465 | - | EXCAVATION WORK
Group | 4 | 33693 |  |  |  | COMMOMN CIVIL WORK | COMMON CIVIL COMPOUND WALL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 01 Jan 2023 |  | - | - | 1021 | -
Task | 5 | 32804 |  |  |  | COMMON CIVIL COMPOUND WALL WORK | COMMON CIVIL COMPOUND WALL WORK | 1 | SQFT | 0 | SQFT | 192229.95 |  | Started | 192229.95 | 0 | 192229.95 | 0 | 192.23 | 0 | 980780.4 | 980780.4 | 17 Mar 2020 |  | 01 Jan 2023 |  | - | - | 1021 | - | DRESSING WORK
Group | 4 | 40916 |  |  |  | COMMOMN CIVIL WORK | COMMON CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 40917 |  |  |  | COMMON CIVIL EXTRA WORK | COMMON CIVIL EXTRA WORK | 1 | NOS | 1 | NOS | 15 |  | Started | 15 | 0 | 15 | 0 | 0.02 | 0 | 2380305.56 | 2380305.56 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | CIVIL EXTRA WORK
Group | 3 | 41049 |  |  |  | COMMON WORK | COMMON ESCALATOR / ELEVATOR | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 4 | 41050 |  |  |  | COMMON ESCALATOR / ELEVATOR | COMMON PASSENGER LIFT WORK | 1 | NOS | 1 | NOS | 103.18 |  | Started | 103.18 | 0 | 103.18 | 0 | 0.1 | 0 | 540204 | 540204 | 17 Mar 2020 |  | 19 Sep 2024 |  | - | - | 1648 | - | COMMON PASSENGER LIFT REAR (TOWER A-1)
Group | 3 | 24910 |  |  |  | COMMON WORK | COMMON PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 27 Mar 2021 |  | - | - | 376 | -
Task | 4 | 24021 |  |  |  | COMMON PLUMBING WORK | COMMON PLUMBING WORK | 1 | NOS | 1 | NOS | 58950.86 |  | Started | 58950.86 | 0 | 58950.86 | 0 | 58.95 | 0 | 36190.12 | 36190.12 | 17 Mar 2020 |  | 30 Jul 2024 |  | - | - | 1597 | - | PLUMBING
Group | 3 | 25752 |  |  |  | COMMON WORK | COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 4 | 25753 |  |  |  | COMMON ELECTRIC WORK | COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 4447.58 |  | Tentative | 4447.58 | 0 | 4447.58 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Task | 4 | 41380 |  |  |  | COMMON ELECTRIC WORK | COMPOUND WALL ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 14100 | 14100 | 17 Mar 2020 |  | 14 Jun 2024 |  | - | - | 1551 | - | ELECTRIC WORK
Task | 4 | 41484 |  |  |  | COMMON ELECTRIC WORK | COMMON CCTV WORK | 1 | NOS | 1 | NOS | 0 | ELECTRIC WORK | Started | 0 | 0 | 0 | 0 | 0 | 0 | 2666.8 | 2666.8 | 17 Mar 2020 |  | 30 Jul 2024 |  | - | - | 1597 | - | CCTV
Group | 3 | 30511 |  |  |  | COMMON WORK | COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 3 | 24793 |  |  |  | COMMON WORK | COMMON MISC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2021 |  | - | - | 476 | -
Group | 4 | 38441 |  |  |  | COMMON MISC WORK | COMMON SITE OFFICE | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 28 Aug 2023 |  | - | - | 1260 | -
Task | 5 | 38442 |  |  |  | COMMON SITE OFFICE | SITE OFFICE FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 5785 |  | Started | 4615 | 1170 | 5785 | 0 | 5.79 | 0 | 147534.93 | 147534.93 | 17 Mar 2020 |  | 20 Jan 2024 |  | - | - | 1405 | - | FLOORING & DEDO
Task | 5 | 38705 |  |  |  | COMMON SITE OFFICE | SITE OFFICE CIVIL WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 301124.47 | 301124.47 | 17 Mar 2020 |  | 30 Dec 2023 |  | - | - | 1384 | - | CIVIL EXTRA WORK
Task | 5 | 38806 |  |  |  | COMMON SITE OFFICE | SITE OFFICE ELECTRIC WORK | 1 | NOS | 1 | NOS | 3108.18 |  | Started | 3108.18 | 0 | 3108.18 | 0 | 3.11 | 0 | 457277.94 | 457277.94 | 17 Mar 2020 |  | 12 Dec 2023 |  | - | - | 1366 | - | ELECTRIC WORK
Task | 5 | 38807 |  |  |  | COMMON SITE OFFICE | SITE OFFICE PLUMBING WORK | 1 | NOS | 1 | NOS | 353.12 |  | Tentative | 351.32 | 0 | 351.32 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 5 | 38825 |  |  |  | COMMON SITE OFFICE | SITE OFFICE AC SYSTEM WORK | 1 | NOS | 1 | NOS | 58248.78 |  | Started | 50019.88 | 8228.9 | 58248.78 | 0 | 58.25 | 0 | 592348.2 | 592348.2 | 17 Mar 2020 |  | 10 Dec 2023 |  | - | - | 1364 | - | VRV INDOOR UNIT INSTALATION WORK
Task | 5 | 39244 |  |  |  | COMMON SITE OFFICE | SITE OFFICE FURNITURE WORK | 1 | NOS | 1 | NOS | 2542.54 |  | Started | 2542.54 | 0 | 2542.54 | 0 | 2.54 | 0 | 7221.6 | 7221.6 | 17 Mar 2020 |  | 01 Feb 2024 |  | - | - | 1417 | - | INTERNAL CARPENTRY WORK
Task | 5 | 39255 |  |  |  | COMMON SITE OFFICE | SITE OFFICE INTERIOR WORK | 1 | NOS | 1 | NOS | 39727.36 |  | Started | 2.36 | 39725 | 39727.36 | 0 | 39.73 | 0 | 138403.87 | 138403.87 | 17 Mar 2020 |  | 30 Dec 2023 |  | - | - | 1384 | - | INTERIOR WORK
Task | 5 | 39256 |  |  |  | COMMON SITE OFFICE | SITE OFFICE FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 93522.07 | 93522.07 | 17 Mar 2020 |  | 09 Mar 2024 |  | - | - | 1454 | - | PVC FALSE CEILING
Task | 5 | 39292 |  |  |  | COMMON SITE OFFICE | SITE OFFICE ALUMINUM WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 338446.44 | 338446.44 | 17 Mar 2020 |  | 28 Dec 2023 |  | - | - | 1382 | - | ALUMINUM WINDOW WORK
Task | 5 | 39327 |  |  |  | COMMON SITE OFFICE | SITE OFFICE GLASS WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6785 | 6785 | 17 Mar 2020 |  | 02 Jan 2024 |  | - | - | 1387 | - | GLASS FIXING WORK
Task | 5 | 39332 |  |  |  | COMMON SITE OFFICE | SITE OFFICE WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 17966.68 | 17966.68 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | WATERPROOFING WORK
Task | 5 | 39522 |  |  |  | COMMON SITE OFFICE | SITE OFFICE CLEANING WORK | 1 | HRS | 1 | HRS | 91.9 |  | Started | 91.9 | 0 | 91.9 | 0 | 0.09 | 0 | 5664 | 5664 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | CLEANING WORK
Task | 5 | 41465 |  |  |  | COMMON SITE OFFICE | COMMON SITE OFFICE CARTING EXPENCES | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CARTING EXPENCES
Task | 5 | 41466 |  |  |  | COMMON SITE OFFICE | COMMON SITE OFFICE CARTING EXPENCES | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CARTING EXPENCES
Task | 5 | 41467 |  |  |  | COMMON SITE OFFICE | SITE OFFICE STATIONARY WORK | 1 | NOS | 1 | NOS | 5524 |  | Tentative | 5524 | 0 | 5524 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | COMMON WORK
Task | 5 | 41645 |  |  |  | COMMON SITE OFFICE | COMMON SITE OFFICE PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 74783.5 | 74783.5 | 17 Mar 2020 |  | 16 Aug 2024 |  | - | - | 1614 | - | PAINT WORK
Group | 4 | 24800 |  |  |  | COMMON MISC WORK | LABOR COLONY | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Jul 2021 |  | - | - | 477 | -
Group | 5 | 24801 |  |  |  | LABOR COLONY | LABOR COLONY CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 24802 |  |  |  | LABOR COLONY CARPENTRY WORK | LABOR COLONY CARPENTRY WORK | 1 | NOS | 1 | NOS | 26.18 |  | Tentative | 26.18 | 0 | 26.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CARTING EXPENCES
Group | 5 | 24886 |  |  |  | LABOR COLONY | LABOR COLONY PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 Jul 2021 |  | - | - | 477 | -
Task | 6 | 24887 |  |  |  | LABOR COLONY PLUMBING WORK | LABOR COLONY PLUMBING WORK | 1 | NOS | 1 | NOS | 172 |  | Started | 170 | 2 | 172 | 0 | 0.17 | 0 | 43770 | 43770 | 17 Mar 2020 |  | 18 Sep 2024 |  | - | - | 1647 | - | PLUMBING
Group | 4 | 25602 |  |  |  | COMMON MISC WORK | COMMON CARTING EXPANSES | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Sep 2021 |  | - | - | 556 | -
Task | 5 | 25603 |  |  |  | COMMON CARTING EXPANSES | COMMON CARTING EXPANSES | 1 | NOS | 1 | NOS | 540000 |  | Started | 0 | 540000 | 540000 | 0 | 540 | 0 | 959250.96 | 959250.96 | 17 Mar 2020 |  | 11 Oct 2024 |  | - | - | 1670 | - | CARTING EXPENCES
Task | 4 | 24794 |  |  |  | COMMON MISC WORK | COMMON MISCELLANEOUS WORK | 1 | NOS | 1 | NOS | 15207.12 |  | Started | 7598.12 | 7609 | 15207.12 | 0 | 15.21 | 0 | 242913.84 | 242913.84 | 17 Mar 2020 |  | 30 Jun 2022 |  | - | - | 836 | - | MISCELLANEOUS WORK
Task | 4 | 24868 |  |  |  | COMMON MISC WORK | COMMON MISC PLUMBING WORK | 1 | NOS | 1 | NOS | 987.4 |  | Tentative | 987.4 | 0 | 987.4 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING
Task | 4 | 25360 |  |  |  | COMMON MISC WORK | COMMON MISC ELECTRIC WORK | 1 | NOS | 1 | NOS | 1862.9 |  | Started | 1862.9 | 0 | 1862.9 | 0 | 1.86 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 Jul 2021 |  | - | - | 476 | - | ELECTRIC WORK
Task | 4 | 24916 |  |  |  | COMMON MISC WORK | COMMON MISC FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 114626.18 | 114626.18 | 17 Mar 2020 |  | 05 Jul 2021 |  | - | - | 476 | - | MISCELLANEOUS FABRICATION WORK
Group | 4 | 41762 |  |  |  | COMMON MISC WORK | COMMON HOUSEKEEPING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41763 |  |  |  | COMMON HOUSEKEEPING WORK | COMMON HOUSEKEEPING WORK | 1 | NOS | 1 | NOS | 693.4 |  | Tentative | 693.4 | 0 | 693.4 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | HOUSEKEEPING
Group | 4 | 42075 |  |  |  | COMMON MISC WORK | FIRE WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 33720 |  |  |  | FIRE WORK | FIRE WORK | 1 | NOS | 1 | NOS | 293.82 |  | Tentative | 293.82 | 0 | 293.82 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FIRE AND SAFETY WORK
Group | 2 | 25719 |  |  |  |  | SALES & MARKETING | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Nov 2021 |  | - | - | 604 | -
Group | 3 | 25782 |  |  |  | SALES & MARKETING | SALES & MARKETING MISC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 06 May 2022 |  | - | - | 781 | -
Task | 4 | 25720 |  |  |  | SALES & MARKETING MISC WORK | SALES & MARKETING MISCELLANEOUS WORK | 1 | NOS | 1 | NOS | 991688.75 |  | Started | 991688.75 | 0 | 991688.75 | 0 | 0 | 0 | 7250113.6 | 7250113.6 | 17 Mar 2020 |  | 06 May 2022 |  | - | - | 781 | - | MISCELLANEOUS WORK
Group | 3 | 25783 |  |  |  | SALES & MARKETING | TOWER A | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 May 2022 |  | - | - | 780 | -
Group | 4 | 25829 |  |  |  | TOWER A | TOWER A UP TO PLINTH | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 May 2022 |  | - | - | 780 | -
Task | 5 | 25830 |  |  |  | TOWER A UP TO PLINTH | TOWER A UP TO PLINTH RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 May 2022 |  | - | - | 780 | - | RCC WORK FOR SLAB
Group | 4 | 25784 |  |  |  | TOWER A | TOWER A 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 May 2022 |  | - | - | 780 | -
Task | 5 | 25786 |  |  |  | TOWER A 3RD FLOOR | TOWER A 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 05 May 2022 | 19 Aug 2023 | - | 472 | 780 | - | RCC WORK FOR SLAB
Group | 4 | 25787 |  |  |  | TOWER A | TOWER A 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25788 |  |  |  | TOWER A 6TH FLOOR | TOWER A 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 25 Jan 2024 | 25 Jan 2024 | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25835 |  |  |  | TOWER A 6TH FLOOR | TOWER A 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25789 |  |  |  | TOWER A | TOWER A 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25790 |  |  |  | TOWER A 9TH FLOOR | TOWER A 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 22 Oct 2024 | 22 Oct 2024 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25791 |  |  |  | TOWER A | TOWER A 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25792 |  |  |  | TOWER A 12TH FLOOR | TOWER A 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25836 |  |  |  | TOWER A 12TH FLOOR | TOWER A 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25793 |  |  |  | TOWER A | TOWER A 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25794 |  |  |  | TOWER A 15TH FLOOR | TOWER A 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25795 |  |  |  | TOWER A | TOWER A 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25796 |  |  |  | TOWER A 18TH FLOOR | TOWER A 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25837 |  |  |  | TOWER A 18TH FLOOR | TOWER A 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25797 |  |  |  | TOWER A | TOWER A TERRACE FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25798 |  |  |  | TOWER A TERRACE FLOOR | TOWER A TERRACE FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25844 |  |  |  | TOWER A | TOWER A PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 25845 |  |  |  | TOWER A PLASTER WORK | TOWER A PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30855 |  |  |  | TOWER A PLASTER WORK | Tower A Plaster of apartment (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30859 |  |  |  | TOWER A PLASTER WORK | Tower A Plaster of apartment (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30863 |  |  |  | TOWER A PLASTER WORK | Tower A Plaster of apartment (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30867 |  |  |  | TOWER A PLASTER WORK | Tower A Plaster of apartment (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 25850 |  |  |  | TOWER A | TOWER A FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 25851 |  |  |  | TOWER A FINISHING WORK | TOWER A FINISHING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PRESSURE GROUTING
Task | 5 | 30871 |  |  |  | TOWER A FINISHING WORK | Tower A Finishing work (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30872 |  |  |  | TOWER A FINISHING WORK | Tower A Finishing work (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30874 |  |  |  | TOWER A FINISHING WORK | Tower A Finishing work (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30876 |  |  |  | TOWER A FINISHING WORK | Tower A Finishing work (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 25799 |  |  |  | SALES & MARKETING | TOWER B | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 25831 |  |  |  | TOWER B | TOWER B UP TO PLINTH | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 25832 |  |  |  | TOWER B UP TO PLINTH | TOWER B UP TO PLINTH RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  | 08 Jun 2022 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25800 |  |  |  | TOWER B | TOWER B 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25801 |  |  |  | TOWER B 3RD FLOOR | TOWER B 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 19 Aug 2023 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25802 |  |  |  | TOWER B | TOWER B 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25803 |  |  |  | TOWER B 6TH FLOOR | TOWER B 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 13 Mar 2024 | 13 Mar 2024 | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25838 |  |  |  | TOWER B 6TH FLOOR | TOWER B 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25804 |  |  |  | TOWER B | TOWER B 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25805 |  |  |  | TOWER B 9TH FLOOR | TOWER B 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 30 May 2024 | 30 May 2024 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25806 |  |  |  | TOWER B | TOWER B 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25807 |  |  |  | TOWER B 12TH FLOOR | TOWER B 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25839 |  |  |  | TOWER B 12TH FLOOR | TOWER B 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25808 |  |  |  | TOWER B | TOWER B 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25809 |  |  |  | TOWER B 15TH FLOOR | TOWER B 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25810 |  |  |  | TOWER B | TOWER B 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25811 |  |  |  | TOWER B 18TH FLOOR | TOWER B 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25840 |  |  |  | TOWER B 18TH FLOOR | TOWER B 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25812 |  |  |  | TOWER B | TOWER B TERRACE FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25813 |  |  |  | TOWER B TERRACE FLOOR | TOWER B TERRACE FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25846 |  |  |  | TOWER B | TOWER B PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 25848 |  |  |  | TOWER B PLASTER WORK | TOWER B PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30856 |  |  |  | TOWER B PLASTER WORK | Tower B Plaster of apartment (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30860 |  |  |  | TOWER B PLASTER WORK | Tower B Plaster of apartment (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30864 |  |  |  | TOWER B PLASTER WORK | Tower B Plaster of apartment (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30868 |  |  |  | TOWER B PLASTER WORK | Tower B Plaster of apartment (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 25852 |  |  |  | TOWER B | TOWER B FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25853 |  |  |  | TOWER B FINISHING WORK | TOWER B FINISHING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PRESSURE GROUTING
Task | 5 | 30879 |  |  |  | TOWER B FINISHING WORK | Tower B Finishing work (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30880 |  |  |  | TOWER B FINISHING WORK | Tower B Finishing work (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30881 |  |  |  | TOWER B FINISHING WORK | Tower B Finishing work (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30882 |  |  |  | TOWER B FINISHING WORK | Tower B Finishing work (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 25814 |  |  |  | SALES & MARKETING | TOWER C | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 25833 |  |  |  | TOWER C | TOWER C UP TO PLINTH | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 25834 |  |  |  | TOWER C UP TO PLINTH | TOWER C UP TO PLINTH RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  | 05 May 2022 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25815 |  |  |  | TOWER C | TOWER C 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25816 |  |  |  | TOWER C 3RD FLOOR | TOWER C 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 05 May 2022 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25817 |  |  |  | TOWER C | TOWER C 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25818 |  |  |  | TOWER C 6TH FLOOR | TOWER C 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 09 Dec 2022 | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25841 |  |  |  | TOWER C 6TH FLOOR | TOWER C 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Completed | 15 | 0 | 15 | 0.01 | 0.15 | 0 | 0 | 0 | 17 Mar 2020 |  |  | 01 Mar 2023 | - | - | - | - | MASONRY WORK
Group | 4 | 25819 |  |  |  | TOWER C | TOWER C 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25820 |  |  |  | TOWER C 9TH FLOOR | TOWER C 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 19 Aug 2023 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25821 |  |  |  | TOWER C | TOWER C 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25822 |  |  |  | TOWER C 12TH FLOOR | TOWER C 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 22 Feb 2024 | 22 Feb 2024 | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25842 |  |  |  | TOWER C 12TH FLOOR | TOWER C 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25823 |  |  |  | TOWER C | TOWER C 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25824 |  |  |  | TOWER C 15TH FLOOR | TOWER C 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25825 |  |  |  | TOWER C | TOWER C 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25826 |  |  |  | TOWER C 18TH FLOOR | TOWER C 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25843 |  |  |  | TOWER C 18TH FLOOR | TOWER C 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25827 |  |  |  | TOWER C | TOWER C TERRACE FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25828 |  |  |  | TOWER C TERRACE FLOOR | TOWER C TERRACE FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25847 |  |  |  | TOWER C | TOWER C PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 25849 |  |  |  | TOWER C PLASTER WORK | TOWER C PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30857 |  |  |  | TOWER C PLASTER WORK | Tower C Plaster of apartment (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  | 27 Jul 2023 | - | - | - | - | PLASTER WORK
Task | 5 | 30861 |  |  |  | TOWER C PLASTER WORK | Tower C Plaster of apartment (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30865 |  |  |  | TOWER C PLASTER WORK | Tower C Plaster of apartment (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30869 |  |  |  | TOWER C PLASTER WORK | Tower C Plaster of apartment (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 25854 |  |  |  | TOWER C | TOWER C FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25855 |  |  |  | TOWER C FINISHING WORK | TOWER C FINISHING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PRESSURE GROUTING
Task | 5 | 30883 |  |  |  | TOWER C FINISHING WORK | Tower C Finishing work (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30884 |  |  |  | TOWER C FINISHING WORK | Tower C Finishing work (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30885 |  |  |  | TOWER C FINISHING WORK | Tower C Finishing work (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30886 |  |  |  | TOWER C FINISHING WORK | Tower C Finishing work (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 25864 |  |  |  | SALES & MARKETING | TOWER D | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 Nov 2021 |  | - | - | - | -
Group | 4 | 25879 |  |  |  | TOWER D | TOWER D UP TO PLINTH | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 Nov 2021 |  | - | - | - | -
Task | 5 | 25880 |  |  |  | TOWER D UP TO PLINTH | TOWER D UP TO PLINTH RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 10 Nov 2021 | 10 Nov 2021 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25865 |  |  |  | TOWER D | TOWER D 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25866 |  |  |  | TOWER D 3RD FLOOR | TOWER D 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 05 May 2022 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25867 |  |  |  | TOWER D | TOWER D 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25868 |  |  |  | TOWER D 6TH FLOOR | TOWER D 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 03 Nov 2022 | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25881 |  |  |  | TOWER D 6TH FLOOR | TOWER D 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Completed | 15 | 0 | 15 | 0.01 | 0.15 | 0 | 0 | 0 |  |  |  | 01 Mar 2023 | - | - | - | - | MASONRY WORK
Group | 4 | 25869 |  |  |  | TOWER D | TOWER D 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25870 |  |  |  | TOWER D 9TH FLOOR | TOWER D 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  |  | 23 May 2023 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25871 |  |  |  | TOWER D | TOWER D 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25872 |  |  |  | TOWER D 12TH FLOOR | TOWER D 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 13 Mar 2024 | 13 Mar 2024 | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25882 |  |  |  | TOWER D 12TH FLOOR | TOWER D 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25873 |  |  |  | TOWER D | TOWER D 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25874 |  |  |  | TOWER D 15TH FLOOR | TOWER D 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 |  |  | 02 Oct 2024 | 02 Oct 2024 | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25875 |  |  |  | TOWER D | TOWER D 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25876 |  |  |  | TOWER D 18TH FLOOR | TOWER D 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 5 | 25883 |  |  |  | TOWER D 18TH FLOOR | TOWER D 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 15 |  | Tentative | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 4 | 25877 |  |  |  | TOWER D | TOWER D TERRACE FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25878 |  |  |  | TOWER D TERRACE FLOOR | TOWER D TERRACE FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 4 | 25884 |  |  |  | TOWER D | TOWER D PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25885 |  |  |  | TOWER D PLASTER WORK | TOWER D PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30858 |  |  |  | TOWER D PLASTER WORK | Tower D Plaster of apartment (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  | 27 Jul 2023 | - | - | - | - | PLASTER WORK
Task | 5 | 30862 |  |  |  | TOWER D PLASTER WORK | Tower D Plaster of apartment (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30866 |  |  |  | TOWER D PLASTER WORK | Tower D Plaster of apartment (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30870 |  |  |  | TOWER D PLASTER WORK | Tower D Plaster of apartment (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 25886 |  |  |  | TOWER D | TOWER D FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 5 | 25887 |  |  |  | TOWER D FINISHING WORK | TOWER D FINISHING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PRESSURE GROUTING
Task | 5 | 30887 |  |  |  | TOWER D FINISHING WORK | Tower D Finishing work (01st to 05th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30888 |  |  |  | TOWER D FINISHING WORK | Tower D Finishing work (06th to 10th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30889 |  |  |  | TOWER D FINISHING WORK | Tower D Finishing work (11th to 15th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Task | 5 | 30890 |  |  |  | TOWER D FINISHING WORK | Tower D Finishing work (16th to 18th Floor) | 0 | SQFT | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 2 | 32707 |  |  |  |  | ACCOUNTS | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Oct 2022 |  | - | - | 938 | -
Task | 3 | 32708 |  |  |  | ACCOUNTS | ACCOUNTS MISCELLANEOUS WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 22800 | 22800 | 17 Mar 2020 |  | 10 Oct 2022 |  | - | - | 938 | - | MISCELLANEOUS WORK