## Task Details638666582756373141_
Task Details
Project Name : GREENWOODS AARANYA
Task Name : TOWER C
Total Records: 1145 Records 1 to 1145
Page 1 of 1
TaskType | Level | TaskNo | Identification1 | Identification2 | Identification3 | ParentTask | Task | VOLOFWORK M | M Unit | VOLOFWORK L | L Unit | Task Rate | Task Category 1 | Task Status | Estimated Mat Amt | Estimated Lab Amt | Estimated Task Amt | % Comp | Est Cost of Completion(BCWP) | Actual Cost Material | Actual Cost Labour | Actual Cost | Planned Start(PS) | Planned Finish(PF) | Actual Start(AS) | Actual Finish(AF) | Planned Duration=(PS)-(PF) Days | Actual Duration=(AS)-(AF) Days | Start Variance=(PS)-(AS) Days | Finish Variance=(PF)-(AF) Days | Library Task Name | Task Description
Group | 2 | 24078 |  |  |  |  | TOWER C | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 3 | 24100 |  |  |  | TOWER C | TOWER C BASEMENT | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24101 |  |  |  | TOWER C BASEMENT | TOWER C BASEMENT CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24102 |  |  |  | TOWER C BASEMENT CIVIL WORK | TOWER C BASEMENT RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24104 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 251167.09 |  | Started | 251167.09 | 0 | 251167.09 | 19.74 | 4958426.41 | 16019148.98 | 5596136.43 | 21615285.41 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 25356 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 52298.8 | 52298.8 | 17 Mar 2020 |  | 16 Jul 2021 |  | - | - | 487 | - | THREADING
Task | 6 | 26043 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 178 |  | Started | 0 | 178 | 178 | 0 | 0.18 | 0 | 179489.8 | 179489.8 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | REBARING WORK
Task | 6 | 25601 |  |  |  | TOWER C BASEMENT RCC WORK | TOWER C BASEMENT CIVIL WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | COMMON WORK
Group | 5 | 24103 |  |  |  | TOWER C BASEMENT CIVIL WORK | TOWER C BASEMENT PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24105 |  |  |  | TOWER C BASEMENT PLASTER WORK | TOWER C BASEMENT PLASTER WORK | 1 | SQFT | 1 | SQFT | 500 |  | Started | 500 | 0 | 500 | 19.74 | 9870.77 | 0 | 1152572.37 | 1152572.37 |  |  | 21 Mar 2024 |  | - | - | - | - | PLASTER WORK
Group | 5 | 38137 |  |  |  | TOWER C BASEMENT CIVIL WORK | TOWER C BASEMENT MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 May 2023 |  | - | - | 1171 | -
Task | 6 | 38138 |  |  |  | TOWER C BASEMENT MASONRY WORK | TOWER C BASEMENT MASONRY WORK | 1 | SQFT | 1 | SQFT | 15200 |  | Started | 15200 | 0 | 15200 | 0 | 15.2 | 0 | 4248 | 4248 | 17 Mar 2020 |  | 31 May 2023 |  | - | - | 1171 | - | MASONRY WORK
Group | 4 | 24860 |  |  |  | TOWER C BASEMENT | TOWER C BASEMENT FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | -
Group | 5 | 24871 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | -
Task | 6 | 24861 |  |  |  | TOWER C BASEMENT WATERPROOFING WORK | TOWER C BASEMENT WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 9.5 | 0 | 0 | 226020 | 226020 | 17 Mar 2020 |  | 07 Jul 2021 |  | - | - | 478 | - | WATERPROOFING WORK
Group | 5 | 29316 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29317 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29318 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29319 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29320 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29321 |  |  |  | TOWER C BASEMENT FINISHING WORK | TOWER C BASEMENT FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 25600 |  |  |  | TOWER C BASEMENT | TOWER C BASEMENT COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 29322 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29323 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29324 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29856 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 25894 |  |  |  | TOWER C BASEMENT COMMON WORK | TOWER C BASEMENT COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 25895 |  |  |  | TOWER C BASEMENT COMMON ELECTRIC WORK | TOWER C BASEMENT COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 46079 | 46079 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | ELECTRIC WORK
Group | 3 | 24121 |  |  |  | TOWER C | TOWER C GROUND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24122 |  |  |  | TOWER C GROUND FLOOR | TOWER C GROUND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24123 |  |  |  | TOWER C GROUND FLOOR CIVIL WORK | TOWER C GROUND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24126 |  |  |  | TOWER C GROUND FLOOR RCC WORK | TOWER C GROUND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 42126.44 |  | Started | 42126.44 | 0 | 42126.44 | 5.72 | 240937.03 | 3238983.74 | 1090159.53 | 4329143.27 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 25980 |  |  |  | TOWER C GROUND FLOOR RCC WORK | TOWER C GROUND FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 65822.24 | 65822.24 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Group | 5 | 24124 |  |  |  | TOWER C GROUND FLOOR CIVIL WORK | TOWER C GROUND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24127 |  |  |  | TOWER C GROUND FLOOR MASONRY WORK | TOWER C GROUND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 17000 |  | Tentative | 17000 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24125 |  |  |  | TOWER C GROUND FLOOR CIVIL WORK | TOWER C GROUND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 09 Feb 2023 |  | - | - | - | -
Task | 6 | 24128 |  |  |  | TOWER C GROUND FLOOR PLASTER WORK | TOWER C GROUND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 920 |  | Started | 920 | 0 | 920 | 5.77 | 5310.04 | 0 | 208898.06 | 208898.06 |  |  | 09 Feb 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 30337 |  |  |  | TOWER C GROUND FLOOR | TOWER C GROUND FLOOR FINISHING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30339 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 30338 |  |  |  | TOWER C GROUND FLOOR WATERPROOFING WORK | TOWER C GROUND FLOOR WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 30342 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30340 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 30341 |  |  |  | TOWER C GROUND FLOOR ELECTRIC WORK | TOWER C GROUND FLOOR ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 30343 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30346 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30344 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 30345 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 32906 |  |  |  | TOWER C GROUND FLOOR PAINT WORK | TOWER C GROUND FLOOR PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PAINT WORK
Group | 5 | 30347 |  |  |  | TOWER C GROUND FLOOR FINISHING WORK | TOWER C GROUND FLOOR HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 29326 |  |  |  | TOWER C GROUND FLOOR | TOWER C GROUND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Nov 2021 |  | - | - | 614 | -
Group | 5 | 29329 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32589 |  |  |  | TOWER C GROUND FLOOR COMMON DEBRISH CHUTE WORK | TOWER C GROUND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29327 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29328 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29330 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26453 |  |  |  | TOWER C GROUND FLOOR COMMON WORK | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Nov 2021 |  | - | - | 614 | -
Task | 6 | 26454 |  |  |  | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Nov 2021 |  | - | - | 614 | - | ELECTRIC WORK
Group | 3 | 24280 |  |  |  | TOWER C | TOWER C 1ST FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24281 |  |  |  | TOWER C 1ST FLOOR | TOWER C 1ST FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24282 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24285 |  |  |  | TOWER C 1ST FLOOR RCC WORK | TOWER C 1ST FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 42840.96 |  | Started | 42840.96 | 0 | 42840.96 | 5.77 | 247268.6 | 2820372.19 | 1114945.21 | 3935317.4 |  |  | 01 Nov 2021 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 26644 |  |  |  | TOWER C 1ST FLOOR RCC WORK | TOWER C 1ST FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 25390.8 | 25390.8 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 31077 |  |  |  | TOWER C 1ST FLOOR RCC WORK | TOWER C 1ST FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 525 |  | Started | 525 | 0 | 525 | 0 | 0.53 | 0 | 135529.64 | 135529.64 | 17 Mar 2020 |  | 20 Apr 2022 |  | - | - | 765 | - | FIRE AND SAFETY WORK
Group | 5 | 24283 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 Jul 2022 |  | - | - | - | -
Task | 6 | 24286 |  |  |  | TOWER C 1ST FLOOR MASONRY WORK | TOWER C 1ST FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 341125.5 |  | Started | 341125.5 | 0 | 341125.5 | 5.77 | 1968901.34 | 0 | 299750.24 | 299750.24 |  |  | 13 Jul 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24284 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15 Apr 2023 |  | - | - | - | -
Task | 6 | 24287 |  |  |  | TOWER C 1ST FLOOR PLASTER WORK | TOWER C 1ST FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.77 | 15543.4 | 0 | 284882.24 | 284882.24 |  |  | 15 Apr 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39317 |  |  |  | TOWER C 1ST FLOOR CIVIL WORK | TOWER C 1ST FLOOR EXTRA CIVIL WOK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39318 |  |  |  | TOWER C 1ST FLOOR EXTRA CIVIL WOK | TOWER C 1ST FLOOR EXTRA CIVIL WOK MASONRY WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 5524.28 | 5524.28 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29504 |  |  |  | TOWER C 1ST FLOOR | TOWER C 101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29496 |  |  |  | TOWER C 101 | TOWER C 101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33572 |  |  |  | TOWER C 101 WATERPROOFING WORK | TOWER C 101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38633 |  |  |  | TOWER C 101 WATERPROOFING WORK | TOWER C 101 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29498 |  |  |  | TOWER C 101 | TOWER C 101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33000 |  |  |  | TOWER C 101 PLUMBING WORK | TOWER C 101 PLUMBING WORK | 1 | NOS | 0 | NOS | 773.94 |  | Tentative | 773.94 | 0 | 773.94 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41539 |  |  |  | TOWER C 101 PLUMBING WORK | TOWER C 101 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29497 |  |  |  | TOWER C 101 | TOWER C 101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33812 |  |  |  | TOWER C 101 ELECTRIC WORK | TOWER C 101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29499 |  |  |  | TOWER C 101 | TOWER C 101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41020 |  |  |  | TOWER C 101 FLOORING & DEDO WORK | TOWER C 101 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4452.436 |  | Started | 1172.44 | 3280 | 4452.44 | 0 | 4.45 | 0 | 16000 | 16000 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29502 |  |  |  | TOWER C 101 | TOWER C 101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33100 |  |  |  | TOWER C 101 CARPENTRY WORK | TOWER C 101 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29500 |  |  |  | TOWER C 101 | TOWER C 101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29501 |  |  |  | TOWER C 101 | TOWER C 101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29503 |  |  |  | TOWER C 101 | TOWER C 101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34325 |  |  |  | TOWER C 101 | TOWER C 101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34326 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34327 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | PVC FALSE CEILING
Task | 6 | 34328 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40277 |  |  |  | TOWER C 101 COMMON WORK | TOWER C 101 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29513 |  |  |  | TOWER C 1ST FLOOR | TOWER C 102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29505 |  |  |  | TOWER C 102 | TOWER C 102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33573 |  |  |  | TOWER C 102 WATERPROOFING WORK | TOWER C 102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38634 |  |  |  | TOWER C 102 WATERPROOFING WORK | TOWER C 102 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29507 |  |  |  | TOWER C 102 | TOWER C 102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33001 |  |  |  | TOWER C 102 PLUMBING WORK | TOWER C 102 PLUMBING WORK | 1 | NOS | 0 | NOS | 773.94 |  | Tentative | 773.94 | 0 | 773.94 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41540 |  |  |  | TOWER C 102 PLUMBING WORK | TOWER C 102 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29506 |  |  |  | TOWER C 102 | TOWER C 102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33813 |  |  |  | TOWER C 102 ELECTRIC WORK | TOWER C 102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29508 |  |  |  | TOWER C 102 | TOWER C 102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41021 |  |  |  | TOWER C 102 FLOORING & DEDO WORK | TOWER C 102 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4452.436 |  | Started | 1172.44 | 3280 | 4452.44 | 0 | 4.45 | 0 | 34728.05 | 34728.05 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29511 |  |  |  | TOWER C 102 | TOWER C 102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33101 |  |  |  | TOWER C 102 CARPENTRY WORK | TOWER C 102 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29509 |  |  |  | TOWER C 102 | TOWER C 102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29510 |  |  |  | TOWER C 102 | TOWER C 102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29512 |  |  |  | TOWER C 102 | TOWER C 102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34329 |  |  |  | TOWER C 102 | TOWER C 102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34330 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Started | 0 | 14720 | 14720 | 0 | 14.72 | 0 | 111183.14 | 111183.14 | 17 Mar 2020 |  | 20 Sep 2024 |  | - | - | 1649 | - | BALCONY RAILING
Task | 6 | 34331 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34332 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40278 |  |  |  | TOWER C 102 COMMON WORK | TOWER C 102 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29339 |  |  |  | TOWER C 1ST FLOOR | TOWER C 1ST FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 29342 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32591 |  |  |  | TOWER C 1ST FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 1ST FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29340 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41980 |  |  |  | TOWER C 1ST FLOOR COMMON FLOORING WORK | TOWER C 1ST FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29341 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29343 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26456 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 26457 |  |  |  | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40972 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40973 |  |  |  | TOWER C 1ST FLOOR WPC PANNELING WORK | TOWER C 1ST FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42330 |  |  |  | TOWER C 1ST FLOOR COMMON WORK | TOWER C 1ST FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42331 |  |  |  | TOWER C 1ST FLOOR COMMON FABRICATION WORK | TOWER C 1ST FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24288 |  |  |  | TOWER C | TOWER C 2ND FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 4 | 24289 |  |  |  | TOWER C 2ND FLOOR | TOWER C 2ND FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Group | 5 | 24290 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Mar 2020 |  | - | - | - | -
Task | 6 | 24293 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 36146.76 |  | Started | 36146.76 | 0 | 36146.76 | 5.77 | 208631.15 | 2467366.21 | 1084020.21 | 3551386.42 |  |  | 01 Nov 2021 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 27047 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 35264.5 | 35264.5 | 17 Mar 2020 |  | 17 Mar 2020 |  | - | - | - | - | THREADING
Task | 6 | 38389 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6726 | 6726 | 17 Mar 2020 |  | 16 Jul 2023 |  | - | - | 1217 | - | SAFETY NET FIXING
Task | 6 | 42050 |  |  |  | TOWER C 2ND FLOOR RCC WORK | TOWER C 2ND FLOOR RCC WORK REBARING WORK | 1 | NOS | 1 | NOS | 50 |  | Started | 0 | 50 | 50 | 0 | 0.05 | 0 | 16425.6 | 16425.6 | 17 Mar 2020 |  | 24 Oct 2024 |  | - | - | 1683 | - | REBARING WORK
Group | 5 | 24291 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2022 |  | - | - | - | -
Task | 6 | 24294 |  |  |  | TOWER C 2ND FLOOR MASONRY WORK | TOWER C 2ND FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 313936.3 |  | Started | 313936.3 | 0 | 313936.3 | 5.77 | 1811971.26 | 0 | 291069.73 | 291069.73 |  |  | 01 Aug 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24292 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24295 |  |  |  | TOWER C 2ND FLOOR PLASTER WORK | TOWER C 2ND FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.77 | 15543.4 | 0 | 276202.4 | 276202.4 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39319 |  |  |  | TOWER C 2ND FLOOR CIVIL WORK | TOWER C 2ND FLOOR EXTRA CIVIL WOK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39320 |  |  |  | TOWER C 2ND FLOOR EXTRA CIVIL WOK | TOWER C 2ND FLOOR EXTRA CIVIL WOK MASONRY WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 5524.28 | 5524.28 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29522 |  |  |  | TOWER C 2ND FLOOR | TOWER C 201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29514 |  |  |  | TOWER C 201 | TOWER C 201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33574 |  |  |  | TOWER C 201 WATERPROOFING WORK | TOWER C 201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38635 |  |  |  | TOWER C 201 WATERPROOFING WORK | TOWER C 201 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29516 |  |  |  | TOWER C 201 | TOWER C 201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33002 |  |  |  | TOWER C 201 PLUMBING WORK | TOWER C 201 PLUMBING WORK | 1 | NOS | 0 | NOS | 699.06 |  | Tentative | 699.06 | 0 | 699.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41541 |  |  |  | TOWER C 201 PLUMBING WORK | TOWER C 201 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29515 |  |  |  | TOWER C 201 | TOWER C 201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33814 |  |  |  | TOWER C 201 ELECTRIC WORK | TOWER C 201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29517 |  |  |  | TOWER C 201 | TOWER C 201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41770 |  |  |  | TOWER C 201 FLOORING & DEDO WORK | TOWER C 201 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4212.436 |  | Started | 932.44 | 3280 | 4212.44 | 0 | 4.21 | 0 | 29430 | 29430 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29520 |  |  |  | TOWER C 201 | TOWER C 201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33102 |  |  |  | TOWER C 201 CARPENTRY WORK | TOWER C 201 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29518 |  |  |  | TOWER C 201 | TOWER C 201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29519 |  |  |  | TOWER C 201 | TOWER C 201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29521 |  |  |  | TOWER C 201 | TOWER C 201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34333 |  |  |  | TOWER C 201 | TOWER C 201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34334 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34335 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34336 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40279 |  |  |  | TOWER C 201 COMMON WORK | TOWER C 201 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29531 |  |  |  | TOWER C 2ND FLOOR | TOWER C 202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29523 |  |  |  | TOWER C 202 | TOWER C 202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33575 |  |  |  | TOWER C 202 WATERPROOFING WORK | TOWER C 202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38636 |  |  |  | TOWER C 202 WATERPROOFING WORK | TOWER C 202 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29525 |  |  |  | TOWER C 202 | TOWER C 202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33003 |  |  |  | TOWER C 202 PLUMBING WORK | TOWER C 202 PLUMBING WORK | 1 | NOS | 0 | NOS | 699.06 |  | Tentative | 699.06 | 0 | 699.06 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41542 |  |  |  | TOWER C 202 PLUMBING WORK | TOWER C 202 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29524 |  |  |  | TOWER C 202 | TOWER C 202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 33815 |  |  |  | TOWER C 202 ELECTRIC WORK | TOWER C 202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 29526 |  |  |  | TOWER C 202 | TOWER C 202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41771 |  |  |  | TOWER C 202 FLOORING & DEDO WORK | TOWER C 202 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 4212.436 |  | Started | 932.44 | 3280 | 4212.44 | 0 | 4.21 | 0 | 0 | 0 | 17 Mar 2020 |  | 16 Oct 2024 |  | - | - | 1675 | - | FLOORING & DEDO
Group | 5 | 29529 |  |  |  | TOWER C 202 | TOWER C 202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33103 |  |  |  | TOWER C 202 CARPENTRY WORK | TOWER C 202 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29527 |  |  |  | TOWER C 202 | TOWER C 202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29528 |  |  |  | TOWER C 202 | TOWER C 202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29530 |  |  |  | TOWER C 202 | TOWER C 202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34337 |  |  |  | TOWER C 202 | TOWER C 202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34338 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34339 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34340 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40280 |  |  |  | TOWER C 202 COMMON WORK | TOWER C 202 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29345 |  |  |  | TOWER C 2ND FLOOR | TOWER C 2ND FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Group | 5 | 29348 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32590 |  |  |  | TOWER C 2ND FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 2ND FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29346 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41981 |  |  |  | TOWER C 2ND FLOOR COMMON FLOORING WORK | TOWER C 2ND FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29347 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29349 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26459 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 26460 |  |  |  | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40974 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40975 |  |  |  | TOWER C 2ND FLOOR WPC PANNELING WORK | TOWER C 2ND FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42332 |  |  |  | TOWER C 2ND FLOOR COMMON WORK | TOWER C 2ND FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42333 |  |  |  | TOWER C 2ND FLOOR COMMON FABRICATION WORK | TOWER C 2ND FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24296 |  |  |  | TOWER C | TOWER C 3RD FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24297 |  |  |  | TOWER C 3RD FLOOR | TOWER C 3RD FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24298 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24301 |  |  |  | TOWER C 3RD FLOOR RCC WORK | TOWER C 3RD FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 37081.14 |  | Started | 37081.14 | 0 | 37081.14 | 5.72 | 212239.1 | 2458506.6 | 1081070.11 | 3539576.71 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 31084 |  |  |  | TOWER C 3RD FLOOR RCC WORK | TOWER C 3RD FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 43769.16 | 43769.16 | 17 Mar 2020 |  | 30 Mar 2022 |  | - | - | 744 | - | THREADING
Task | 6 | 39268 |  |  |  | TOWER C 3RD FLOOR RCC WORK | TOWER C 3RD FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FIRE AND SAFETY WORK
Group | 5 | 24299 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 06 Sep 2022 |  | - | - | - | -
Task | 6 | 24302 |  |  |  | TOWER C 3RD FLOOR MASONRY WORK | TOWER C 3RD FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 325825.95 |  | Started | 325825.95 | 0 | 325825.95 | 5.72 | 1863521.77 | 0 | 291069.73 | 291069.73 |  |  | 06 Sep 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24300 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24303 |  |  |  | TOWER C 3RD FLOOR PLASTER WORK | TOWER C 3RD FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.72 | 15402.28 | 0 | 271924.9 | 271924.9 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 5 | 39321 |  |  |  | TOWER C 3RD FLOOR CIVIL WORK | TOWER C 3RD FLOOR EXTRA CIVIL WOK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39322 |  |  |  | TOWER C 3RD FLOOR EXTRA CIVIL WOK | TOWER C 3RD FLOOR EXTRA CIVIL WOK MASONRY WORK | 1 | SQFT | 1 | SQFT | 270785.2 |  | Started | 270785.2 | 0 | 270785.2 | 0 | 270.79 | 0 | 5524.28 | 5524.28 | 17 Mar 2020 |  | 27 Dec 2023 |  | - | - | 1381 | - | MASONRY WORK
Group | 4 | 29540 |  |  |  | TOWER C 3RD FLOOR | TOWER C 301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29532 |  |  |  | TOWER C 301 | TOWER C 301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33576 |  |  |  | TOWER C 301 WATERPROOFING WORK | TOWER C 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38637 |  |  |  | TOWER C 301 WATERPROOFING WORK | TOWER C 301 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29534 |  |  |  | TOWER C 301 | TOWER C 301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33004 |  |  |  | TOWER C 301 PLUMBING WORK | TOWER C 301 PLUMBING WORK | 1 | NOS | 0 | NOS | 696.7 |  | Tentative | 696.7 | 0 | 696.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41543 |  |  |  | TOWER C 301 PLUMBING WORK | TOWER C 301 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29533 |  |  |  | TOWER C 301 | TOWER C 301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33816 |  |  |  | TOWER C 301 ELECTRIC WORK | TOWER C 301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29535 |  |  |  | TOWER C 301 | TOWER C 301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42366 |  |  |  | TOWER C 301 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29538 |  |  |  | TOWER C 301 | TOWER C 301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33104 |  |  |  | TOWER C 301 CARPENTRY WORK | TOWER C 301 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29536 |  |  |  | TOWER C 301 | TOWER C 301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29537 |  |  |  | TOWER C 301 | TOWER C 301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29539 |  |  |  | TOWER C 301 | TOWER C 301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34341 |  |  |  | TOWER C 301 | TOWER C 301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34342 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34343 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34344 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40281 |  |  |  | TOWER C 301 COMMON WORK | TOWER C 301 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29549 |  |  |  | TOWER C 3RD FLOOR | TOWER C 302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29541 |  |  |  | TOWER C 302 | TOWER C 302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33577 |  |  |  | TOWER C 302 WATERPROOFING WORK | TOWER C 301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38638 |  |  |  | TOWER C 302 WATERPROOFING WORK | TOWER C 302 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29543 |  |  |  | TOWER C 302 | TOWER C 302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33005 |  |  |  | TOWER C 302 PLUMBING WORK | TOWER C 302 PLUMBING WORK | 1 | NOS | 0 | NOS | 696.7 |  | Tentative | 696.7 | 0 | 696.7 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Task | 6 | 41544 |  |  |  | TOWER C 302 PLUMBING WORK | TOWER C 302 CP & SANITARY FITTINGS | 1 | NOS | 1 | NOS | 8.72 |  | Tentative | 8.72 | 0 | 8.72 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | CP & SANITARY FITTINGS
Group | 5 | 29542 |  |  |  | TOWER C 302 | TOWER C 302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33817 |  |  |  | TOWER C 302 ELECTRIC WORK | TOWER C 302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29544 |  |  |  | TOWER C 302 | TOWER C 302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42367 |  |  |  | TOWER C 302 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29547 |  |  |  | TOWER C 302 | TOWER C 302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33105 |  |  |  | TOWER C 302 CARPENTRY WORK | TOWER C 302 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29545 |  |  |  | TOWER C 302 | TOWER C 302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29546 |  |  |  | TOWER C 302 | TOWER C 302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29548 |  |  |  | TOWER C 302 | TOWER C 302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34345 |  |  |  | TOWER C 302 | TOWER C 302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34346 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34347 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34348 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40282 |  |  |  | TOWER C 302 COMMON WORK | TOWER C 302 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29351 |  |  |  | TOWER C 3RD FLOOR | TOWER C 3RD FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Apr 2022 |  | - | - | 768 | -
Group | 5 | 29354 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32592 |  |  |  | TOWER C 3RD FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 3RD FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29352 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41982 |  |  |  | TOWER C 3RD FLOOR COMMON FLOORING WORK | TOWER C 3RD FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29353 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29355 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 26462 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 23 Apr 2022 |  | - | - | 768 | -
Task | 6 | 26463 |  |  |  | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 23 Apr 2022 |  | - | - | 768 | - | ELECTRIC WORK
Group | 5 | 40976 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40977 |  |  |  | TOWER C 3RD FLOOR WPC PANNELING WORK | TOWER C 3RD FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42334 |  |  |  | TOWER C 3RD FLOOR COMMON WORK | TOWER C 3RD FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42335 |  |  |  | TOWER C 3RD FLOOR COMMON FABRICATION WORK | TOWER C 3RD FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24304 |  |  |  | TOWER C | TOWER C 4TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24305 |  |  |  | TOWER C 4TH FLOOR | TOWER C 4TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24306 |  |  |  | TOWER C 4TH FLOOR CIVIL WORK | TOWER C 4TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24309 |  |  |  | TOWER C 4TH FLOOR RCC WORK | TOWER C 4TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 40410.32 |  | Started | 40410.32 | 0 | 40410.32 | 5.72 | 231294.12 | 986622.2 | 1081939.43 | 2068561.63 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 31085 |  |  |  | TOWER C 4TH FLOOR RCC WORK | TOWER C 4TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 38161.2 | 38161.2 | 17 Mar 2020 |  | 07 Sep 2022 |  | - | - | 905 | - | THREADING
Task | 6 | 38390 |  |  |  | TOWER C 4TH FLOOR RCC WORK | TOWER C 4TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 32737.92 | 32737.92 | 17 Mar 2020 |  | 16 Jul 2023 |  | - | - | 1217 | - | SAFETY NET FIXING
Group | 5 | 24307 |  |  |  | TOWER C 4TH FLOOR CIVIL WORK | TOWER C 4TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22 Dec 2022 |  | - | - | - | -
Task | 6 | 24310 |  |  |  | TOWER C 4TH FLOOR MASONRY WORK | TOWER C 4TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 332628.75 |  | Started | 332628.75 | 0 | 332628.75 | 5.72 | 1902429.55 | 0 | 291070.27 | 291070.27 |  |  | 22 Dec 2022 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24308 |  |  |  | TOWER C 4TH FLOOR CIVIL WORK | TOWER C 4TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24311 |  |  |  | TOWER C 4TH FLOOR PLASTER WORK | TOWER C 4TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.72 | 15402.28 | 0 | 262172.21 | 262172.21 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29558 |  |  |  | TOWER C 4TH FLOOR | TOWER C 401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29550 |  |  |  | TOWER C 401 | TOWER C 401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33578 |  |  |  | TOWER C 401 WATERPROOFING WORK | TOWER C 401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38639 |  |  |  | TOWER C 401 WATERPROOFING WORK | TOWER C 401 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29552 |  |  |  | TOWER C 401 | TOWER C 401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33007 |  |  |  | TOWER C 401 PLUMBING WORK | TOWER C 401 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29551 |  |  |  | TOWER C 401 | TOWER C 401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33818 |  |  |  | TOWER C 401 ELECTRIC WORK | TOWER C 401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29553 |  |  |  | TOWER C 401 | TOWER C 401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42368 |  |  |  | TOWER C 401 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29556 |  |  |  | TOWER C 401 | TOWER C 401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39382 |  |  |  | TOWER C 401 CARPENTRY WORK | TOWER C 401 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29554 |  |  |  | TOWER C 401 | TOWER C 401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29555 |  |  |  | TOWER C 401 | TOWER C 401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29557 |  |  |  | TOWER C 401 | TOWER C 401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34349 |  |  |  | TOWER C 401 | TOWER C 401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34350 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34351 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34352 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40283 |  |  |  | TOWER C 401 COMMON WORK | TOWER C 401 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29567 |  |  |  | TOWER C 4TH FLOOR | TOWER C 402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29559 |  |  |  | TOWER C 402 | TOWER C 402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33579 |  |  |  | TOWER C 402 WATERPROOFING WORK | TOWER C 402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38640 |  |  |  | TOWER C 402 WATERPROOFING WORK | TOWER C 402 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29561 |  |  |  | TOWER C 402 | TOWER C 402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33008 |  |  |  | TOWER C 402 PLUMBING WORK | TOWER C 402 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29560 |  |  |  | TOWER C 402 | TOWER C 402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33819 |  |  |  | TOWER C 402 ELECTRIC WORK | TOWER C 402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29562 |  |  |  | TOWER C 402 | TOWER C 402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42369 |  |  |  | TOWER C 402 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29565 |  |  |  | TOWER C 402 | TOWER C 402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39383 |  |  |  | TOWER C 402 CARPENTRY WORK | TOWER C 402 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29563 |  |  |  | TOWER C 402 | TOWER C 402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29564 |  |  |  | TOWER C 402 | TOWER C 402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29566 |  |  |  | TOWER C 402 | TOWER C 402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34353 |  |  |  | TOWER C 402 | TOWER C 402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34354 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34355 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34356 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40284 |  |  |  | TOWER C 402 COMMON WORK | TOWER C 402 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29357 |  |  |  | TOWER C 4TH FLOOR | TOWER C 4TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2022 |  | - | - | 898 | -
Group | 5 | 29360 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32593 |  |  |  | TOWER C 4TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 4TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29358 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41983 |  |  |  | TOWER C 4TH FLOOR COMMON FLOORING WORK | TOWER C 4TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29359 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29361 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29362 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 31 Aug 2022 |  | - | - | 898 | -
Task | 6 | 31331 |  |  |  | TOWER C 4TH FLOOR COMMON ELECTRIC WORK | TOWER C 4TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 31 Aug 2022 |  | - | - | 898 | - | ELECTRIC WORK
Group | 5 | 40978 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40979 |  |  |  | TOWER C 4TH FLOOR WPC PANNELING WORK | TOWER C 4TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42336 |  |  |  | TOWER C 4TH FLOOR COMMON WORK | TOWER C 4TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42337 |  |  |  | TOWER C 4TH FLOOR COMMON FABRICATION WORK | TOWER C 4TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24312 |  |  |  | TOWER C | TOWER C 5TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 4 | 24313 |  |  |  | TOWER C 5TH FLOOR | TOWER C 5TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Group | 5 | 24314 |  |  |  | TOWER C 5TH FLOOR CIVIL WORK | TOWER C 5TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 07 Mar 2022 |  | - | - | - | -
Task | 6 | 24317 |  |  |  | TOWER C 5TH FLOOR RCC WORK | TOWER C 5TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 133413.41 |  | Started | 133413.41 | 0 | 133413.41 | 5.72 | 763610.33 | 0 | 1079559.71 | 1079559.71 |  |  | 07 Mar 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 32568 |  |  |  | TOWER C 5TH FLOOR RCC WORK | TOWER C 5TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 27358.9 | 27358.9 | 17 Mar 2020 |  | 17 Oct 2022 |  | - | - | 945 | - | THREADING
Task | 6 | 35227 |  |  |  | TOWER C 5TH FLOOR RCC WORK | TOWER C 5TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 11 Apr 2023 |  | - | - | 1121 | - | SAFETY NET FIXING
Group | 5 | 24315 |  |  |  | TOWER C 5TH FLOOR CIVIL WORK | TOWER C 5TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 Feb 2023 |  | - | - | - | -
Task | 6 | 24318 |  |  |  | TOWER C 5TH FLOOR MASONRY WORK | TOWER C 5TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307129.5 |  | Started | 307129.5 | 0 | 307129.5 | 5.72 | 1756589.71 | 0 | 291070.27 | 291070.27 |  |  | 16 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24316 |  |  |  | TOWER C 5TH FLOOR CIVIL WORK | TOWER C 5TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 01 Aug 2023 |  | - | - | - | -
Task | 6 | 24319 |  |  |  | TOWER C 5TH FLOOR PLASTER WORK | TOWER C 5TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 5.72 | 15402.28 | 0 | 271924.9 | 271924.9 |  |  | 01 Aug 2023 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29576 |  |  |  | TOWER C 5TH FLOOR | TOWER C 501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29568 |  |  |  | TOWER C 501 | TOWER C 501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33580 |  |  |  | TOWER C 501 WATERPROOFING WORK | TOWER C 501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38641 |  |  |  | TOWER C 501 WATERPROOFING WORK | TOWER C 501 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29570 |  |  |  | TOWER C 501 | TOWER C 501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33009 |  |  |  | TOWER C 501 PLUMBING WORK | TOWER C 501 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29569 |  |  |  | TOWER C 501 | TOWER C 501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33820 |  |  |  | TOWER C 501 ELECTRIC WORK | TOWER C 501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29571 |  |  |  | TOWER C 501 | TOWER C 501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42370 |  |  |  | TOWER C 501 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29574 |  |  |  | TOWER C 501 | TOWER C 501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39384 |  |  |  | TOWER C 501 CARPENTRY WORK | TOWER C 501 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29572 |  |  |  | TOWER C 501 | TOWER C 501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29573 |  |  |  | TOWER C 501 | TOWER C 501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29575 |  |  |  | TOWER C 501 | TOWER C 501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34361 |  |  |  | TOWER C 501 | TOWER C 501 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34362 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34363 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34364 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40285 |  |  |  | TOWER C 501 COMMON WORK | TOWER C 501 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29585 |  |  |  | TOWER C 5TH FLOOR | TOWER C 502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29577 |  |  |  | TOWER C 502 | TOWER C 502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33581 |  |  |  | TOWER C 502 WATERPROOFING WORK | TOWER C 502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38642 |  |  |  | TOWER C 502 WATERPROOFING WORK | TOWER C 502 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29579 |  |  |  | TOWER C 502 | TOWER C 502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33010 |  |  |  | TOWER C 502 PLUMBING WORK | TOWER C 502 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29578 |  |  |  | TOWER C 502 | TOWER C 502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33821 |  |  |  | TOWER C 502 ELECTRIC WORK | TOWER C 502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29580 |  |  |  | TOWER C 502 | TOWER C 502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42371 |  |  |  | TOWER C 502 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29583 |  |  |  | TOWER C 502 | TOWER C 502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39385 |  |  |  | TOWER C 502 CARPENTRY WORK | TOWER C 502 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29581 |  |  |  | TOWER C 502 | TOWER C 502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29582 |  |  |  | TOWER C 502 | TOWER C 502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29584 |  |  |  | TOWER C 502 | TOWER C 502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34365 |  |  |  | TOWER C 502 | TOWER C 502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34366 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34367 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34368 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40286 |  |  |  | TOWER C 502 COMMON WORK | TOWER C 502 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29363 |  |  |  | TOWER C 5TH FLOOR | TOWER C 5TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | -
Group | 5 | 29366 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | -
Task | 6 | 32594 |  |  |  | TOWER C 5TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 5TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 25 Jan 2023 |  | - | - | 1045 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29364 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41984 |  |  |  | TOWER C 5TH FLOOR COMMON FLOORING WORK | TOWER C 5TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29365 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29367 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29879 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | -
Task | 6 | 31332 |  |  |  | TOWER C 5TH FLOOR COMMON ELECTRIC WORK | TOWER C 5TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 17 Nov 2022 |  | - | - | 976 | - | ELECTRIC WORK
Group | 5 | 40980 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40981 |  |  |  | TOWER C 5TH FLOOR WPC PANNELING WORK | TOWER C 5TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42338 |  |  |  | TOWER C 5TH FLOOR COMMON WORK | TOWER C 5TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42339 |  |  |  | TOWER C 5TH FLOOR COMMON FABRICATION WORK | TOWER C 5TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24320 |  |  |  | TOWER C | TOWER C 6TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 4 | 24321 |  |  |  | TOWER C 6TH FLOOR | TOWER C 6TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 5 | 24322 |  |  |  | TOWER C 6TH FLOOR CIVIL WORK | TOWER C 6TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Task | 6 | 24325 |  |  |  | TOWER C 6TH FLOOR RCC WORK | TOWER C 6TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135783.34 |  | Started | 135783.34 | 0 | 135783.34 | 5.72 | 777174.96 | 0 | 1079561.68 | 1079561.68 |  |  | 16 Dec 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33091 |  |  |  | TOWER C 6TH FLOOR RCC WORK | TOWER C 6TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21349.74 | 21349.74 | 17 Mar 2020 |  | 27 Nov 2022 |  | - | - | 986 | - | THREADING
Task | 6 | 33710 |  |  |  | TOWER C 6TH FLOOR RCC WORK | TOWER C 6TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 625 |  | Started | 625 | 0 | 625 | 0 | 0.63 | 0 | 70179.1 | 70179.1 | 17 Mar 2020 |  | 02 Feb 2023 |  | - | - | 1053 | - | FIRE AND SAFETY WORK
Group | 5 | 24323 |  |  |  | TOWER C 6TH FLOOR CIVIL WORK | TOWER C 6TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24326 |  |  |  | TOWER C 6TH FLOOR MASONRY WORK | TOWER C 6TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 409126.5 |  | Started | 409126.5 | 0 | 409126.5 | 5.72 | 2339949.1 | 0 | 291070.4 | 291070.4 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24324 |  |  |  | TOWER C 6TH FLOOR CIVIL WORK | TOWER C 6TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24327 |  |  |  | TOWER C 6TH FLOOR PLASTER WORK | TOWER C 6TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 0 | 2.69 | 0 | 444413.85 | 444413.85 |  |  | 04 Jan 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29594 |  |  |  | TOWER C 6TH FLOOR | TOWER C 601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29586 |  |  |  | TOWER C 601 | TOWER C 601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33582 |  |  |  | TOWER C 601 WATERPROOFING WORK | TOWER C 601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38643 |  |  |  | TOWER C 601 WATERPROOFING WORK | TOWER C 601 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29588 |  |  |  | TOWER C 601 | TOWER C 601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33011 |  |  |  | TOWER C 601 PLUMBING WORK | TOWER C 601 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29587 |  |  |  | TOWER C 601 | TOWER C 601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33822 |  |  |  | TOWER C 601 ELECTRIC WORK | TOWER C 601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29589 |  |  |  | TOWER C 601 | TOWER C 601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42372 |  |  |  | TOWER C 601 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29592 |  |  |  | TOWER C 601 | TOWER C 601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39386 |  |  |  | TOWER C 601 CARPENTRY WORK | TOWER C 601 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29590 |  |  |  | TOWER C 601 | TOWER C 601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29591 |  |  |  | TOWER C 601 | TOWER C 601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29593 |  |  |  | TOWER C 601 | TOWER C 601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34369 |  |  |  | TOWER C 601 | TOWER C 601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34370 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34371 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34372 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40287 |  |  |  | TOWER C 601 COMMON WORK | TOWER C 601 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29603 |  |  |  | TOWER C 6TH FLOOR | TOWER C 602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29595 |  |  |  | TOWER C 602 | TOWER C 602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33583 |  |  |  | TOWER C 602 WATERPROOFING WORK | TOWER C 602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38644 |  |  |  | TOWER C 602 WATERPROOFING WORK | TOWER C 602 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29597 |  |  |  | TOWER C 602 | TOWER C 602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33012 |  |  |  | TOWER C 602 PLUMBING WORK | TOWER C 602 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29596 |  |  |  | TOWER C 602 | TOWER C 602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33823 |  |  |  | TOWER C 602 ELECTRIC WORK | TOWER C 602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29598 |  |  |  | TOWER C 602 | TOWER C 602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42373 |  |  |  | TOWER C 602 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29601 |  |  |  | TOWER C 602 | TOWER C 602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39387 |  |  |  | TOWER C 602 CARPENTRY WORK | TOWER C 602 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29599 |  |  |  | TOWER C 602 | TOWER C 602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29600 |  |  |  | TOWER C 602 | TOWER C 602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29602 |  |  |  | TOWER C 602 | TOWER C 602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34373 |  |  |  | TOWER C 602 | TOWER C 602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34374 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34375 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34376 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40288 |  |  |  | TOWER C 602 COMMON WORK | TOWER C 602 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29369 |  |  |  | TOWER C 6TH FLOOR | TOWER C 6TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Dec 2022 |  | - | - | 996 | -
Group | 5 | 29372 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34025 |  |  |  | TOWER C 6TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 6TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29370 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41985 |  |  |  | TOWER C 6TH FLOOR COMMON FLOORING WORK | TOWER C 6TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29371 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29373 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29374 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 07 Dec 2022 |  | - | - | 996 | -
Task | 6 | 31333 |  |  |  | TOWER C 6TH FLOOR COMMON ELECTRIC WORK | TOWER C 6TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 07 Dec 2022 |  | - | - | 996 | - | ELECTRIC WORK
Group | 5 | 40982 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40983 |  |  |  | TOWER C 6TH FLOOR WPC PANNELING WORK | TOWER C 6TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42340 |  |  |  | TOWER C 6TH FLOOR COMMON WORK | TOWER C 6TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42341 |  |  |  | TOWER C 6TH FLOOR COMMON FABRICATION WORK | TOWER C 6TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24480 |  |  |  | TOWER C | TOWER C 7TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 4 | 24481 |  |  |  | TOWER C 7TH FLOOR | TOWER C 7TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Group | 5 | 24482 |  |  |  | TOWER C 7TH FLOOR CIVIL WORK | TOWER C 7TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 Nov 2022 |  | - | - | - | -
Task | 6 | 24485 |  |  |  | TOWER C 7TH FLOOR RCC WORK | TOWER C 7TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 140077.34 |  | Started | 140077.34 | 0 | 140077.34 | 5.72 | 801752.27 | 0 | 1079136.88 | 1079136.88 |  |  | 22 Dec 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33092 |  |  |  | TOWER C 7TH FLOOR RCC WORK | TOWER C 7TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 49200.1 | 49200.1 | 17 Mar 2020 |  | 27 Nov 2022 |  | - | - | 986 | - | THREADING
Task | 6 | 38611 |  |  |  | TOWER C 7TH FLOOR RCC WORK | TOWER C 7TH FLOOR RCC WORK SAFETY WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 38331.12 | 38331.12 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | FIRE AND SAFETY WORK
Group | 5 | 24483 |  |  |  | TOWER C 7TH FLOOR CIVIL WORK | TOWER C 7TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 08 Sep 2023 |  | - | - | - | -
Task | 6 | 24486 |  |  |  | TOWER C 7TH FLOOR MASONRY WORK | TOWER C 7TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 277040.2 | 277040.2 |  |  | 08 Sep 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24484 |  |  |  | TOWER C 7TH FLOOR CIVIL WORK | TOWER C 7TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24487 |  |  |  | TOWER C 7TH FLOOR PLASTER WORK | TOWER C 7TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Started | 2693 | 0 | 2693 | 0 | 2.69 | 0 | 262172.2 | 262172.2 |  |  | 04 Oct 2024 |  | - | - | - | - | PLASTER WORK
Group | 4 | 29612 |  |  |  | TOWER C 7TH FLOOR | TOWER C 701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29604 |  |  |  | TOWER C 701 | TOWER C 701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33584 |  |  |  | TOWER C 701 WATERPROOFING WORK | TOWER C 701 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38645 |  |  |  | TOWER C 701 WATERPROOFING WORK | TOWER C 701 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29606 |  |  |  | TOWER C 701 | TOWER C 701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33013 |  |  |  | TOWER C 701 PLUMBING WORK | TOWER C 701 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29605 |  |  |  | TOWER C 701 | TOWER C 701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33824 |  |  |  | TOWER C 701 ELECTRIC WORK | TOWER C 701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 29607 |  |  |  | TOWER C 701 | TOWER C 701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42374 |  |  |  | TOWER C 701 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29610 |  |  |  | TOWER C 701 | TOWER C 701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39388 |  |  |  | TOWER C 701 CARPENTRY WORK | TOWER C 701 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29608 |  |  |  | TOWER C 701 | TOWER C 701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29609 |  |  |  | TOWER C 701 | TOWER C 701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29611 |  |  |  | TOWER C 701 | TOWER C 701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34377 |  |  |  | TOWER C 701 | TOWER C 701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34378 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34379 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34380 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40289 |  |  |  | TOWER C 701 COMMON WORK | TOWER C 701 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29621 |  |  |  | TOWER C 7TH FLOOR | TOWER C 702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29613 |  |  |  | TOWER C 702 | TOWER C 702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33585 |  |  |  | TOWER C 702 WATERPROOFING WORK | TOWER C 702 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38646 |  |  |  | TOWER C 702 WATERPROOFING WORK | TOWER C 702 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29615 |  |  |  | TOWER C 702 | TOWER C 702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33014 |  |  |  | TOWER C 702 PLUMBING WORK | TOWER C 702 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29614 |  |  |  | TOWER C 702 | TOWER C 702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33825 |  |  |  | TOWER C 702 ELECTRIC WORK | TOWER C 702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 18408 | 18408 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 29616 |  |  |  | TOWER C 702 | TOWER C 702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42375 |  |  |  | TOWER C 702 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29619 |  |  |  | TOWER C 702 | TOWER C 702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39389 |  |  |  | TOWER C 702 CARPENTRY WORK | TOWER C 702 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29617 |  |  |  | TOWER C 702 | TOWER C 702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29618 |  |  |  | TOWER C 702 | TOWER C 702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29620 |  |  |  | TOWER C 702 | TOWER C 702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34381 |  |  |  | TOWER C 702 | TOWER C 702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34382 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34383 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34384 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40290 |  |  |  | TOWER C 702 COMMON WORK | TOWER C 702 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29375 |  |  |  | TOWER C 7TH FLOOR | TOWER C 7TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Group | 5 | 29378 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34026 |  |  |  | TOWER C 7TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 7TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29376 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41986 |  |  |  | TOWER C 7TH FLOOR COMMON FLOORING WORK | TOWER C 7TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29377 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29379 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29380 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | -
Task | 6 | 31471 |  |  |  | TOWER C 7TH FLOOR COMMON ELECTRIC WORK | TOWER C 7TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 20 Feb 2023 |  | - | - | 1071 | - | ELECTRIC WORK
Group | 5 | 40984 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40985 |  |  |  | TOWER C 7TH FLOOR WPC PANNELING WORK | TOWER C 7TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42342 |  |  |  | TOWER C 7TH FLOOR COMMON WORK | TOWER C 7TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42343 |  |  |  | TOWER C 7TH FLOOR COMMON FABRICATION WORK | TOWER C 7TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24488 |  |  |  | TOWER C | TOWER C 8TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 4 | 24489 |  |  |  | TOWER C 8TH FLOOR | TOWER C 8TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Group | 5 | 24490 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25 Aug 2022 |  | - | - | - | -
Task | 6 | 24493 |  |  |  | TOWER C 8TH FLOOR RCC WORK | TOWER C 8TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135791.42 |  | Started | 135791.42 | 0 | 135791.42 | 5.72 | 777221.2 | 0 | 1137162.16 | 1137162.16 |  |  | 25 Aug 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33093 |  |  |  | TOWER C 8TH FLOOR RCC WORK | TOWER C 8TH FLOOR RCC WORK THREADING | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 31801 | 31801 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | THREADING
Task | 6 | 38773 |  |  |  | TOWER C 8TH FLOOR RCC WORK | TOWER C 8TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 625 |  | Started | 625 | 0 | 625 | 0 | 0.63 | 0 | 2063.24 | 2063.24 | 17 Mar 2020 |  | 12 Jan 2024 |  | - | - | 1397 | - | SAFETY NET FIXING
Group | 5 | 24491 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24494 |  |  |  | TOWER C 8TH FLOOR MASONRY WORK | TOWER C 8TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 277040.2 | 277040.2 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24492 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24495 |  |  |  | TOWER C 8TH FLOOR PLASTER WORK | TOWER C 8TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 5 | 37471 |  |  |  | TOWER C 8TH FLOOR CIVIL WORK | TOWER C 8TH FLOOR CIVIL EXTRA WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 09 Feb 2023 |  | - | - | 1060 | -
Task | 6 | 37472 |  |  |  | TOWER C 8TH FLOOR CIVIL EXTRA WORK | TOWER C 8TH FLOOR CIVIL EXTRA WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 128325 | 128325 | 17 Mar 2020 |  | 09 Feb 2023 |  | - | - | 1060 | - | CIVIL EXTRA WORK
Group | 4 | 29639 |  |  |  | TOWER C 8TH FLOOR | TOWER C 801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29631 |  |  |  | TOWER C 801 | TOWER C 801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33586 |  |  |  | TOWER C 801 WATERPROOFING WORK | TOWER C 801 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38647 |  |  |  | TOWER C 801 WATERPROOFING WORK | TOWER C 801 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29633 |  |  |  | TOWER C 801 | TOWER C 801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33015 |  |  |  | TOWER C 801 PLUMBING WORK | TOWER C 801 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29632 |  |  |  | TOWER C 801 | TOWER C 801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33826 |  |  |  | TOWER C 801 ELECTRIC WORK | TOWER C 801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 21461.26 | 21461.26 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29634 |  |  |  | TOWER C 801 | TOWER C 801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42376 |  |  |  | TOWER C 801 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29637 |  |  |  | TOWER C 801 | TOWER C 801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39390 |  |  |  | TOWER C 801 CARPENTRY WORK | TOWER C 801 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29635 |  |  |  | TOWER C 801 | TOWER C 801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29636 |  |  |  | TOWER C 801 | TOWER C 801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29638 |  |  |  | TOWER C 801 | TOWER C 801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34385 |  |  |  | TOWER C 801 | TOWER C 801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34386 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34387 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34388 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40291 |  |  |  | TOWER C 801 COMMON WORK | TOWER C 801 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29630 |  |  |  | TOWER C 8TH FLOOR | TOWER C 802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29622 |  |  |  | TOWER C 802 | TOWER C 802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33587 |  |  |  | TOWER C 802 WATERPROOFING WORK | TOWER C 802 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38648 |  |  |  | TOWER C 802 WATERPROOFING WORK | TOWER C 802 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29624 |  |  |  | TOWER C 802 | TOWER C 802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33016 |  |  |  | TOWER C 802 PLUMBING WORK | TOWER C 802 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29623 |  |  |  | TOWER C 802 | TOWER C 802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33827 |  |  |  | TOWER C 802 ELECTRIC WORK | TOWER C 802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 24337.5 | 24337.5 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29625 |  |  |  | TOWER C 802 | TOWER C 802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42377 |  |  |  | TOWER C 802 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29628 |  |  |  | TOWER C 802 | TOWER C 802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39391 |  |  |  | TOWER C 802 CARPENTRY WORK | TOWER C 802 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29626 |  |  |  | TOWER C 802 | TOWER C 802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29627 |  |  |  | TOWER C 802 | TOWER C 802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29629 |  |  |  | TOWER C 802 | TOWER C 802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34389 |  |  |  | TOWER C 802 | TOWER C 802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34390 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34391 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34392 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40292 |  |  |  | TOWER C 802 COMMON WORK | TOWER C 802 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29381 |  |  |  | TOWER C 8TH FLOOR | TOWER C 8TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 22 Apr 2023 |  | - | - | 1132 | -
Group | 5 | 29384 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34027 |  |  |  | TOWER C 8TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 8TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 4.54 |  | Started | 3.54 | 1 | 4.54 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29382 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41987 |  |  |  | TOWER C 8TH FLOOR COMMON FLOORING WORK | TOWER C 8TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29383 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29385 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29386 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 22 Apr 2023 |  | - | - | 1132 | -
Task | 6 | 31472 |  |  |  | TOWER C 8TH FLOOR COMMON ELECTRIC WORK | TOWER C 8TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53952.38 | 53952.38 | 17 Mar 2020 |  | 22 Apr 2023 |  | - | - | 1132 | - | ELECTRIC WORK
Group | 5 | 40986 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40987 |  |  |  | TOWER C 8TH FLOOR WPC PANNELING WORK | TOWER C 8TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42344 |  |  |  | TOWER C 8TH FLOOR COMMON WORK | TOWER C 8TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42345 |  |  |  | TOWER C 8TH FLOOR COMMON FABRICATION WORK | TOWER C 8TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24496 |  |  |  | TOWER C | TOWER C 9TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 4 | 24497 |  |  |  | TOWER C 9TH FLOOR | TOWER C 9TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 5 | 24498 |  |  |  | TOWER C 9TH FLOOR CIVIL WORK | TOWER C 9TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Task | 6 | 24501 |  |  |  | TOWER C 9TH FLOOR RCC WORK | TOWER C 9TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 38225.24 |  | Started | 38225.24 | 0 | 38225.24 | 5.72 | 218787.51 | 0 | 1077862.96 | 1077862.96 |  |  | 17 Nov 2022 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 33456 |  |  |  | TOWER C 9TH FLOOR RCC WORK | TOWER C 9TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 30916 | 30916 | 17 Mar 2020 |  | 17 Apr 2023 |  | - | - | 1127 | - | THREADING
Task | 6 | 38920 |  |  |  | TOWER C 9TH FLOOR RCC WORK | TOWER C 9TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 83248.18 | 83248.18 | 17 Mar 2020 |  | 11 Oct 2023 |  | - | - | 1304 | - | SAFETY NET FIXING
Group | 5 | 24499 |  |  |  | TOWER C 9TH FLOOR CIVIL WORK | TOWER C 9TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24502 |  |  |  | TOWER C 9TH FLOOR MASONRY WORK | TOWER C 9TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 307126.5 |  | Started | 307126.5 | 0 | 307126.5 | 5.72 | 1756572.55 | 0 | 273641.51 | 273641.51 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24500 |  |  |  | TOWER C 9TH FLOOR CIVIL WORK | TOWER C 9TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24503 |  |  |  | TOWER C 9TH FLOOR PLASTER WORK | TOWER C 9TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29648 |  |  |  | TOWER C 9TH FLOOR | TOWER C 901 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29640 |  |  |  | TOWER C 901 | TOWER C 901 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33589 |  |  |  | TOWER C 901 WATERPROOFING WORK | TOWER C 901 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38649 |  |  |  | TOWER C 901 WATERPROOFING WORK | TOWER C 901 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29642 |  |  |  | TOWER C 901 | TOWER C 901 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33017 |  |  |  | TOWER C 901 PLUMBING WORK | TOWER C 901 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29641 |  |  |  | TOWER C 901 | TOWER C 901 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33828 |  |  |  | TOWER C 901 ELECTRIC WORK | TOWER C 901 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 24337.5 | 24337.5 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29643 |  |  |  | TOWER C 901 | TOWER C 901 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42378 |  |  |  | TOWER C 901 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29646 |  |  |  | TOWER C 901 | TOWER C 901 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39392 |  |  |  | TOWER C 901 CARPENTRY WORK | TOWER C 901 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29644 |  |  |  | TOWER C 901 | TOWER C 901 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29645 |  |  |  | TOWER C 901 | TOWER C 901 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29647 |  |  |  | TOWER C 901 | TOWER C 901 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34393 |  |  |  | TOWER C 901 | TOWER C 901 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34394 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34395 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34396 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40293 |  |  |  | TOWER C 901 COMMON WORK | TOWER C 901 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29657 |  |  |  | TOWER C 9TH FLOOR | TOWER C 902 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29649 |  |  |  | TOWER C 902 | TOWER C 902 WATERPROOFING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33608 |  |  |  | TOWER C 902 WATERPROOFING WORK | TOWER C 902 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Task | 6 | 38650 |  |  |  | TOWER C 902 WATERPROOFING WORK | TOWER C 902 DRILLING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DRILLING WORK
Group | 5 | 29651 |  |  |  | TOWER C 902 | TOWER C 902 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33018 |  |  |  | TOWER C 902 PLUMBING WORK | TOWER C 902 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29650 |  |  |  | TOWER C 902 | TOWER C 902 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33829 |  |  |  | TOWER C 902 ELECTRIC WORK | TOWER C 902 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 24337.5 | 24337.5 | 17 Mar 2020 |  | 17 Oct 2024 |  | - | - | 1676 | - | ELECTRIC WORK
Group | 5 | 29652 |  |  |  | TOWER C 902 | TOWER C 902 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42379 |  |  |  | TOWER C 902 FLOORING & DEDO WORK | TOWER C 301 FLOORING & DEDO WORK | 1 | SQFT | 1 | SQFT | 950.136 |  | Tentative | 950.14 | 0 | 950.14 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOORING & DEDO
Group | 5 | 29655 |  |  |  | TOWER C 902 | TOWER C 902 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39393 |  |  |  | TOWER C 902 CARPENTRY WORK | TOWER C 902 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29653 |  |  |  | TOWER C 902 | TOWER C 902 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29654 |  |  |  | TOWER C 902 | TOWER C 902 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29656 |  |  |  | TOWER C 902 | TOWER C 902 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34397 |  |  |  | TOWER C 902 | TOWER C 902 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34398 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34399 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34400 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40294 |  |  |  | TOWER C 902 COMMON WORK | TOWER C 902 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29387 |  |  |  | TOWER C 9TH FLOOR | TOWER C 9TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Group | 5 | 29390 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34028 |  |  |  | TOWER C 9TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 9TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 3.36 |  | Started | 2.36 | 1 | 3.36 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29388 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41988 |  |  |  | TOWER C 9TH FLOOR COMMON FLOORING WORK | TOWER C 9TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29389 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29391 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29392 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | -
Task | 6 | 31473 |  |  |  | TOWER C 9TH FLOOR COMMON ELECTRIC WORK | TOWER C 9TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 12 Sep 2023 |  | - | - | 1275 | - | ELECTRIC WORK
Group | 5 | 40988 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40989 |  |  |  | TOWER C 9TH FLOOR WPC PANNELING WORK | TOWER C 9TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42346 |  |  |  | TOWER C 9TH FLOOR COMMON WORK | TOWER C 9TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42347 |  |  |  | TOWER C 9TH FLOOR COMMON FABRICATION WORK | TOWER C 9TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24504 |  |  |  | TOWER C | TOWER C 10TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 4 | 24505 |  |  |  | TOWER C 10TH FLOOR | TOWER C 10TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Group | 5 | 24506 |  |  |  | TOWER C 10TH FLOOR CIVIL WORK | TOWER C 10TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 17 Nov 2022 |  | - | - | - | -
Task | 6 | 24509 |  |  |  | TOWER C 10TH FLOOR RCC WORK | TOWER C 10TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35747.21 |  | Started | 35747.21 | 0 | 35747.21 | 0 | 35.75 | 0 | 1714225.85 | 1714225.85 |  |  | 04 Jan 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24507 |  |  |  | TOWER C 10TH FLOOR CIVIL WORK | TOWER C 10TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | -
Task | 6 | 24510 |  |  |  | TOWER C 10TH FLOOR MASONRY WORK | TOWER C 10TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 271992 |  | Started | 271992 | 0 | 271992 | 5.72 | 1555625.06 | 0 | 0 | 0 |  |  | 20 Feb 2023 |  | - | - | - | - | MASONRY WORK
Group | 5 | 24508 |  |  |  | TOWER C 10TH FLOOR CIVIL WORK | TOWER C 10TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24511 |  |  |  | TOWER C 10TH FLOOR PLASTER WORK | TOWER C 10TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29666 |  |  |  | TOWER C 10TH FLOOR | TOWER C 1001 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29658 |  |  |  | TOWER C 1001 | TOWER C 1001 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33611 |  |  |  | TOWER C 1001 WATERPROOFING WORK | TOWER C 1001 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29660 |  |  |  | TOWER C 1001 | TOWER C 1001 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33019 |  |  |  | TOWER C 1001 PLUMBING WORK | TOWER C 1001 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29659 |  |  |  | TOWER C 1001 | TOWER C 1001 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33830 |  |  |  | TOWER C 1001 ELECTRIC WORK | TOWER C 1001 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29661 |  |  |  | TOWER C 1001 | TOWER C 1001 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29664 |  |  |  | TOWER C 1001 | TOWER C 1001 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39394 |  |  |  | TOWER C 1001 CARPENTRY WORK | TOWER C 1001 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29662 |  |  |  | TOWER C 1001 | TOWER C 1001 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29663 |  |  |  | TOWER C 1001 | TOWER C 1001 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29665 |  |  |  | TOWER C 1001 | TOWER C 1001 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34401 |  |  |  | TOWER C 1001 | TOWER C 1001 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34402 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34403 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34404 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40295 |  |  |  | TOWER C 1001 COMMON WORK | TOWER C 1001 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29675 |  |  |  | TOWER C 10TH FLOOR | TOWER C 1002 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29667 |  |  |  | TOWER C 1002 | TOWER C 1002 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33622 |  |  |  | TOWER C 1002 WATERPROOFING WORK | TOWER C 1002 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29669 |  |  |  | TOWER C 1002 | TOWER C 1002 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33020 |  |  |  | TOWER C 1002 PLUMBING WORK | TOWER C 1002 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29668 |  |  |  | TOWER C 1002 | TOWER C 1002 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33831 |  |  |  | TOWER C 1002 ELECTRIC WORK | TOWER C 1002 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29670 |  |  |  | TOWER C 1002 | TOWER C 1002 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29673 |  |  |  | TOWER C 1002 | TOWER C 1002 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 39395 |  |  |  | TOWER C 1002 CARPENTRY WORK | TOWER C 1002 CARPENTRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLUSH DOORS FOR MAIN DOOR
Group | 5 | 29671 |  |  |  | TOWER C 1002 | TOWER C 1002 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29672 |  |  |  | TOWER C 1002 | TOWER C 1002 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29674 |  |  |  | TOWER C 1002 | TOWER C 1002 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34405 |  |  |  | TOWER C 1002 | TOWER C 1002 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34406 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 14720 |  | Tentative | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34407 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34408 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40296 |  |  |  | TOWER C 1002 COMMON WORK | TOWER C 1002 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29393 |  |  |  | TOWER C 10TH FLOOR | TOWER C 10TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29396 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34029 |  |  |  | TOWER C 10TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 10TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 3.36 |  | Started | 2.36 | 1 | 3.36 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29394 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41989 |  |  |  | TOWER C 10TH FLOOR COMMON FLOORING WORK | TOWER C 10TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29395 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29397 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29398 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 31474 |  |  |  | TOWER C 10TH FLOOR COMMON ELECTRIC WORK | TOWER C 10TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40990 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40991 |  |  |  | TOWER C 10TH FLOOR WPC PANNELING WORK | TOWER C 10TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42348 |  |  |  | TOWER C 10TH FLOOR COMMON WORK | TOWER C 10TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42349 |  |  |  | TOWER C 10TH FLOOR COMMON FABRICATION WORK | TOWER C 10TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24512 |  |  |  | TOWER C | TOWER C 11TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24513 |  |  |  | TOWER C 11TH FLOOR | TOWER C 11TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24514 |  |  |  | TOWER C 11TH FLOOR CIVIL WORK | TOWER C 11TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24517 |  |  |  | TOWER C 11TH FLOOR RCC WORK | TOWER C 11TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35533.18 |  | Started | 35533.18 | 0 | 35533.18 | 0 | 35.53 | 0 | 1049424.96 | 1049424.96 |  |  | 04 Feb 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24515 |  |  |  | TOWER C 11TH FLOOR CIVIL WORK | TOWER C 11TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24518 |  |  |  | TOWER C 11TH FLOOR MASONRY WORK | TOWER C 11TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 271992 |  | Tentative | 271992 | 0 | 271992 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24516 |  |  |  | TOWER C 11TH FLOOR CIVIL WORK | TOWER C 11TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24519 |  |  |  | TOWER C 11TH FLOOR PLASTER WORK | TOWER C 11TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29684 |  |  |  | TOWER C 11TH FLOOR | TOWER C 1101 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29676 |  |  |  | TOWER C 1101 | TOWER C 1101 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33624 |  |  |  | TOWER C 1101 WATERPROOFING WORK | TOWER C 1101 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29678 |  |  |  | TOWER C 1101 | TOWER C 1101 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33021 |  |  |  | TOWER C 1101 PLUMBING WORK | TOWER C 1101 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29677 |  |  |  | TOWER C 1101 | TOWER C 1101 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33832 |  |  |  | TOWER C 1101 ELECTRIC WORK | TOWER C 1101 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29679 |  |  |  | TOWER C 1101 | TOWER C 1101 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29682 |  |  |  | TOWER C 1101 | TOWER C 1101 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29680 |  |  |  | TOWER C 1101 | TOWER C 1101 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29681 |  |  |  | TOWER C 1101 | TOWER C 1101 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29683 |  |  |  | TOWER C 1101 | TOWER C 1101 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34409 |  |  |  | TOWER C 1101 | TOWER C 1101 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34410 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34411 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34412 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40297 |  |  |  | TOWER C 1101 COMMON WORK | TOWER C 1101 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29693 |  |  |  | TOWER C 11TH FLOOR | TOWER C 1102 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29685 |  |  |  | TOWER C 1102 | TOWER C 1102 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33625 |  |  |  | TOWER C 1102 WATERPROOFING WORK | TOWER C 1102 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29687 |  |  |  | TOWER C 1102 | TOWER C 1102 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33022 |  |  |  | TOWER C 1102 PLUMBING WORK | TOWER C 1102 PLUMBING WORK | 1 | NOS | 1 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29686 |  |  |  | TOWER C 1102 | TOWER C 1102 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33833 |  |  |  | TOWER C 1102 ELECTRIC WORK | TOWER C 1102 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29688 |  |  |  | TOWER C 1102 | TOWER C 1102 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29691 |  |  |  | TOWER C 1102 | TOWER C 1102 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29689 |  |  |  | TOWER C 1102 | TOWER C 1102 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29690 |  |  |  | TOWER C 1102 | TOWER C 1102 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29692 |  |  |  | TOWER C 1102 | TOWER C 1102 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34413 |  |  |  | TOWER C 1102 | TOWER C 1102 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34414 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34415 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34416 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40298 |  |  |  | TOWER C 1102 COMMON WORK | TOWER C 1102 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29399 |  |  |  | TOWER C 11TH FLOOR | TOWER C 11TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29402 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34030 |  |  |  | TOWER C 11TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 11TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Started | 0 | 1 | 1 | 0 | 0 | 0 | 4000 | 4000 | 17 Mar 2020 |  | 05 Mar 2024 |  | - | - | 1450 | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29400 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41990 |  |  |  | TOWER C 11TH FLOOR COMMON FLOORING WORK | TOWER C 11TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29401 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29403 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29404 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 31475 |  |  |  | TOWER C 11TH FLOOR COMMON ELECTRIC WORK | TOWER C 11TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40992 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40993 |  |  |  | TOWER C 11TH FLOOR WPC PANNELING WORK | TOWER C 11TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42350 |  |  |  | TOWER C 11TH FLOOR COMMON WORK | TOWER C 11TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42351 |  |  |  | TOWER C 11TH FLOOR COMMON FABRICATION WORK | TOWER C 11TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24520 |  |  |  | TOWER C | TOWER C 12TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24521 |  |  |  | TOWER C 12TH FLOOR | TOWER C 12TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24522 |  |  |  | TOWER C 12TH FLOOR CIVIL WORK | TOWER C 12TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24525 |  |  |  | TOWER C 12TH FLOOR RCC WORK | TOWER C 12TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 35094.18 |  | Started | 35094.18 | 0 | 35094.18 | 0 | 35.09 | 0 | 1023110.96 | 1023110.96 |  |  | 04 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 39526 |  |  |  | TOWER C 12TH FLOOR RCC WORK | TOWER C 12TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 21712 | 21712 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Task | 6 | 40088 |  |  |  | TOWER C 12TH FLOOR RCC WORK | TOWER C 12TH FLOOR RCC WORK SAFETY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 6884.72 | 6884.72 | 17 Mar 2020 |  | 23 Jul 2024 |  | - | - | 1590 | - | SAFETY NET FIXING
Group | 5 | 24523 |  |  |  | TOWER C 12TH FLOOR CIVIL WORK | TOWER C 12TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24526 |  |  |  | TOWER C 12TH FLOOR MASONRY WORK | TOWER C 12TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24524 |  |  |  | TOWER C 12TH FLOOR CIVIL WORK | TOWER C 12TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24527 |  |  |  | TOWER C 12TH FLOOR PLASTER WORK | TOWER C 12TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29702 |  |  |  | TOWER C 12TH FLOOR | TOWER C 1201 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29694 |  |  |  | TOWER C 1201 | TOWER C 1201 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33627 |  |  |  | TOWER C 1201 WATERPROOFING WORK | TOWER C 1201 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29696 |  |  |  | TOWER C 1201 | TOWER C 1201 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33023 |  |  |  | TOWER C 1201 PLUMBING WORK | TOWER C 1201 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29695 |  |  |  | TOWER C 1201 | TOWER C 1201 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33834 |  |  |  | TOWER C 1201 ELECTRIC WORK | TOWER C 1201 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29697 |  |  |  | TOWER C 1201 | TOWER C 1201 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29700 |  |  |  | TOWER C 1201 | TOWER C 1201 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29698 |  |  |  | TOWER C 1201 | TOWER C 1201 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29699 |  |  |  | TOWER C 1201 | TOWER C 1201 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29701 |  |  |  | TOWER C 1201 | TOWER C 1201 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34417 |  |  |  | TOWER C 1201 | TOWER C 1201 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34418 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34419 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34420 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40299 |  |  |  | TOWER C 1201 COMMON WORK | TOWER C 1201 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29711 |  |  |  | TOWER C 12TH FLOOR | TOWER C 1202 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29703 |  |  |  | TOWER C 1202 | TOWER C 1202 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33628 |  |  |  | TOWER C 1202 WATERPROOFING WORK | TOWER C 1202 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29705 |  |  |  | TOWER C 1202 | TOWER C 1202 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33024 |  |  |  | TOWER C 1202 PLUMBING WORK | TOWER C 1202 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29704 |  |  |  | TOWER C 1202 | TOWER C 1202 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33835 |  |  |  | TOWER C 1202 ELECTRIC WORK | TOWER C 1202 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29706 |  |  |  | TOWER C 1202 | TOWER C 1202 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29709 |  |  |  | TOWER C 1202 | TOWER C 1202 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29707 |  |  |  | TOWER C 1202 | TOWER C 1202 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29708 |  |  |  | TOWER C 1202 | TOWER C 1202 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29710 |  |  |  | TOWER C 1202 | TOWER C 1202 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34421 |  |  |  | TOWER C 1202 | TOWER C 1202 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34422 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34423 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34424 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40300 |  |  |  | TOWER C 1202 COMMON WORK | TOWER C 1202 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29405 |  |  |  | TOWER C 12TH FLOOR | TOWER C 12TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29408 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34031 |  |  |  | TOWER C 12TH FLOOR COMMON DEBRISH CHUTE WORK | TOWER C 12TH FLOOR COMMON DEBRISH CHUTE WORK | 1 | RMT | 1 | RMT | 1 |  | Tentative | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | DEBRIS CHUTE INSTALLATION
Group | 5 | 29406 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41991 |  |  |  | TOWER C 12TH FLOOR COMMON FLOORING WORK | TOWER C 12TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29407 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29409 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29410 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38759 |  |  |  | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 53983.47 | 53983.47 | 17 Mar 2020 |  | 01 Mar 2024 |  | - | - | 1446 | - | ELECTRIC WORK
Group | 5 | 40994 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40995 |  |  |  | TOWER C 12TH FLOOR WPC PANNELING WORK | TOWER C 12TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42352 |  |  |  | TOWER C 12TH FLOOR COMMON WORK | TOWER C 12TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42353 |  |  |  | TOWER C 12TH FLOOR COMMON FABRICATION WORK | TOWER C 12TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24528 |  |  |  | TOWER C | TOWER C 13TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24529 |  |  |  | TOWER C 13TH FLOOR | TOWER C 13TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24530 |  |  |  | TOWER C 13TH FLOOR CIVIL WORK | TOWER C 13TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24533 |  |  |  | TOWER C 13TH FLOOR RCC WORK | TOWER C 13TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34581.3 |  | Started | 34581.3 | 0 | 34581.3 | 0 | 34.58 | 0 | 1604142.96 | 1604142.96 |  |  | 22 Mar 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 39527 |  |  |  | TOWER C 13TH FLOOR RCC WORK | TOWER C 13TH FLOOR RCC WORK THREADING WORK | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 18880 | 18880 | 17 Mar 2020 |  | 24 Feb 2024 |  | - | - | 1440 | - | THREADING
Group | 5 | 24531 |  |  |  | TOWER C 13TH FLOOR CIVIL WORK | TOWER C 13TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24534 |  |  |  | TOWER C 13TH FLOOR MASONRY WORK | TOWER C 13TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24532 |  |  |  | TOWER C 13TH FLOOR CIVIL WORK | TOWER C 13TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24535 |  |  |  | TOWER C 13TH FLOOR PLASTER WORK | TOWER C 13TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29729 |  |  |  | TOWER C 13TH FLOOR | TOWER C 1301 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29721 |  |  |  | TOWER C 1301 | TOWER C 1301 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33629 |  |  |  | TOWER C 1301 WATERPROOFING WORK | TOWER C 1301 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29723 |  |  |  | TOWER C 1301 | TOWER C 1301 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33025 |  |  |  | TOWER C 1301 PLUMBING WORK | TOWER C 1301 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29722 |  |  |  | TOWER C 1301 | TOWER C 1301 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33836 |  |  |  | TOWER C 1301 ELECTRIC WORK | TOWER C 1301 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 19 Apr 2024 |  | - | - | 1495 | - | ELECTRIC WORK
Group | 5 | 29724 |  |  |  | TOWER C 1301 | TOWER C 1301 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29727 |  |  |  | TOWER C 1301 | TOWER C 1301 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29725 |  |  |  | TOWER C 1301 | TOWER C 1301 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29726 |  |  |  | TOWER C 1301 | TOWER C 1301 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29728 |  |  |  | TOWER C 1301 | TOWER C 1301 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34425 |  |  |  | TOWER C 1301 | TOWER C 1301 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34426 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34427 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34428 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40301 |  |  |  | TOWER C 1301 COMMON WORK | TOWER C 1301 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29720 |  |  |  | TOWER C 13TH FLOOR | TOWER C 1302 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29712 |  |  |  | TOWER C 1302 | TOWER C 1302 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33630 |  |  |  | TOWER C 1302 WATERPROOFING WORK | TOWER C 1302 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29714 |  |  |  | TOWER C 1302 | TOWER C 1302 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33026 |  |  |  | TOWER C 1302 PLUMBING WORK | TOWER C 1302 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29713 |  |  |  | TOWER C 1302 | TOWER C 1302 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33837 |  |  |  | TOWER C 1302 ELECTRIC WORK | TOWER C 1302 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 29854 | 29854 | 17 Mar 2020 |  | 19 Apr 2024 |  | - | - | 1495 | - | ELECTRIC WORK
Group | 5 | 29715 |  |  |  | TOWER C 1302 | TOWER C 1302 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29718 |  |  |  | TOWER C 1302 | TOWER C 1302 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29716 |  |  |  | TOWER C 1302 | TOWER C 1302 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29717 |  |  |  | TOWER C 1302 | TOWER C 1302 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29719 |  |  |  | TOWER C 1302 | TOWER C 1302 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34429 |  |  |  | TOWER C 1302 | TOWER C 1302 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34430 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34431 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34432 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40302 |  |  |  | TOWER C 1302 COMMON WORK | TOWER C 1302 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29411 |  |  |  | TOWER C 13TH FLOOR | TOWER C 13TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29414 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29412 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41992 |  |  |  | TOWER C 13TH FLOOR COMMON FLOORING WORK | TOWER C 13TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29413 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29415 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29416 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38760 |  |  |  | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 40996 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40997 |  |  |  | TOWER C 13TH FLOOR WPC PANNELING WORK | TOWER C 13TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42354 |  |  |  | TOWER C 13TH FLOOR COMMON WORK | TOWER C 13TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42355 |  |  |  | TOWER C 13TH FLOOR COMMON FABRICATION WORK | TOWER C 13TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24536 |  |  |  | TOWER C | TOWER C 14TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24537 |  |  |  | TOWER C 14TH FLOOR | TOWER C 14TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24538 |  |  |  | TOWER C 14TH FLOOR CIVIL WORK | TOWER C 14TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24541 |  |  |  | TOWER C 14TH FLOOR RCC WORK | TOWER C 14TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 34397.44 |  | Started | 34397.44 | 0 | 34397.44 | 0 | 34.4 | 0 | 1023110.96 | 1023110.96 |  |  | 07 Oct 2024 |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41017 |  |  |  | TOWER C 14TH FLOOR RCC WORK | TOWER C 14TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 18113 | 18113 | 17 Mar 2020 |  | 15 May 2024 |  | - | - | 1521 | - | THREADING
Group | 5 | 24539 |  |  |  | TOWER C 14TH FLOOR CIVIL WORK | TOWER C 14TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24542 |  |  |  | TOWER C 14TH FLOOR MASONRY WORK | TOWER C 14TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24540 |  |  |  | TOWER C 14TH FLOOR CIVIL WORK | TOWER C 14TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24543 |  |  |  | TOWER C 14TH FLOOR PLASTER WORK | TOWER C 14TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29738 |  |  |  | TOWER C 14TH FLOOR | TOWER C 1401 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29730 |  |  |  | TOWER C 1401 | TOWER C 1401 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33631 |  |  |  | TOWER C 1401 WATERPROOFING WORK | TOWER C 1401 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29732 |  |  |  | TOWER C 1401 | TOWER C 1401 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33027 |  |  |  | TOWER C 1401 PLUMBING WORK | TOWER C 1401 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29731 |  |  |  | TOWER C 1401 | TOWER C 1401 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33838 |  |  |  | TOWER C 1401 ELECTRIC WORK | TOWER C 1401 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 29733 |  |  |  | TOWER C 1401 | TOWER C 1401 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29736 |  |  |  | TOWER C 1401 | TOWER C 1401 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29734 |  |  |  | TOWER C 1401 | TOWER C 1401 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29735 |  |  |  | TOWER C 1401 | TOWER C 1401 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29737 |  |  |  | TOWER C 1401 | TOWER C 1401 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34433 |  |  |  | TOWER C 1401 | TOWER C 1401 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34434 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34435 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34436 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40303 |  |  |  | TOWER C 1401 COMMON WORK | TOWER C 1401 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29747 |  |  |  | TOWER C 14TH FLOOR | TOWER C 1402 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29739 |  |  |  | TOWER C 1402 | TOWER C 1402 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33632 |  |  |  | TOWER C 1402 WATERPROOFING WORK | TOWER C 1402 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29741 |  |  |  | TOWER C 1402 | TOWER C 1402 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33028 |  |  |  | TOWER C 1402 PLUMBING WORK | TOWER C 1402 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29740 |  |  |  | TOWER C 1402 | TOWER C 1402 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33839 |  |  |  | TOWER C 1402 ELECTRIC WORK | TOWER C 1402 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Started | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 32450 | 32450 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 29742 |  |  |  | TOWER C 1402 | TOWER C 1402 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29745 |  |  |  | TOWER C 1402 | TOWER C 1402 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29743 |  |  |  | TOWER C 1402 | TOWER C 1402 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29744 |  |  |  | TOWER C 1402 | TOWER C 1402 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29746 |  |  |  | TOWER C 1402 | TOWER C 1402 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34437 |  |  |  | TOWER C 1402 | TOWER C 1402 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34438 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34439 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34440 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40304 |  |  |  | TOWER C 1402 COMMON WORK | TOWER C 1402 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29417 |  |  |  | TOWER C 14TH FLOOR | TOWER C 14TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29420 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29418 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41993 |  |  |  | TOWER C 14TH FLOOR COMMON FLOORING WORK | TOWER C 14TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29419 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29421 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29422 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38761 |  |  |  | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  | 10 Oct 2024 |  | - | - | 1669 | - | ELECTRIC WORK
Group | 5 | 40998 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40999 |  |  |  | TOWER C 14TH FLOOR WPC PANNELING WORK | TOWER C 14TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42356 |  |  |  | TOWER C 14TH FLOOR COMMON WORK | TOWER C 14TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42357 |  |  |  | TOWER C 14TH FLOOR COMMON FABRICATION WORK | TOWER C 14TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24544 |  |  |  | TOWER C | TOWER C 15TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24545 |  |  |  | TOWER C 15TH FLOOR | TOWER C 15TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24546 |  |  |  | TOWER C 15TH FLOOR CIVIL WORK | TOWER C 15TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24549 |  |  |  | TOWER C 15TH FLOOR RCC WORK | TOWER C 15TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 135527.9 |  | Tentative | 135527.9 | 0 | 135527.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41018 |  |  |  | TOWER C 15TH FLOOR RCC WORK | TOWER C 15TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24547 |  |  |  | TOWER C 15TH FLOOR CIVIL WORK | TOWER C 15TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24550 |  |  |  | TOWER C 15TH FLOOR MASONRY WORK | TOWER C 15TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24548 |  |  |  | TOWER C 15TH FLOOR CIVIL WORK | TOWER C 15TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24551 |  |  |  | TOWER C 15TH FLOOR PLASTER WORK | TOWER C 15TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29756 |  |  |  | TOWER C 15TH FLOOR | TOWER C 1501 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29748 |  |  |  | TOWER C 1501 | TOWER C 1501 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33633 |  |  |  | TOWER C 1501 WATERPROOFING WORK | TOWER C 1501 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29750 |  |  |  | TOWER C 1501 | TOWER C 1501 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33029 |  |  |  | TOWER C 1501 PLUMBING WORK | TOWER C 1501 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29749 |  |  |  | TOWER C 1501 | TOWER C 1501 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33841 |  |  |  | TOWER C 1501 ELECTRIC WORK | TOWER C 1501 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29751 |  |  |  | TOWER C 1501 | TOWER C 1501 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29754 |  |  |  | TOWER C 1501 | TOWER C 1501 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29752 |  |  |  | TOWER C 1501 | TOWER C 1501 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29753 |  |  |  | TOWER C 1501 | TOWER C 1501 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29755 |  |  |  | TOWER C 1501 | TOWER C 1501 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34441 |  |  |  | TOWER C 1501 | TOWER C 1501 COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34442 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34443 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34444 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40305 |  |  |  | TOWER C 1501 COMMON WORK | TOWER C 1501 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29765 |  |  |  | TOWER C 15TH FLOOR | TOWER C 1502 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29757 |  |  |  | TOWER C 1502 | TOWER C 1502 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33634 |  |  |  | TOWER C 1502 WATERPROOFING WORK | TOWER C 1502 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29759 |  |  |  | TOWER C 1502 | TOWER C 1502 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33030 |  |  |  | TOWER C 1502 PLUMBING WORK | TOWER C 1502 PLUMBING WORK | 1 | NOS | 0 | NOS | 735.62 |  | Tentative | 735.62 | 0 | 735.62 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29758 |  |  |  | TOWER C 1502 | TOWER C 1502 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33842 |  |  |  | TOWER C 1502 ELECTRIC WORK | TOWER C 1502 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29760 |  |  |  | TOWER C 1502 | TOWER C 1502 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29763 |  |  |  | TOWER C 1502 | TOWER C 1502 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29761 |  |  |  | TOWER C 1502 | TOWER C 1502 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29762 |  |  |  | TOWER C 1502 | TOWER C 1502 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29764 |  |  |  | TOWER C 1502 | TOWER C 1502 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34445 |  |  |  | TOWER C 1502 | TOWER C 1502 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34446 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34447 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34448 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40306 |  |  |  | TOWER C 1502 COMMON WORK | TOWER C 1502 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29423 |  |  |  | TOWER C 15TH FLOOR | TOWER C 15TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29426 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29424 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41994 |  |  |  | TOWER C 15TH FLOOR COMMON FLOORING WORK | TOWER C 15TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29425 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29427 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29428 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38762 |  |  |  | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 41000 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41001 |  |  |  | TOWER C 15TH FLOOR WPC PANNELING WORK | TOWER C 15TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42358 |  |  |  | TOWER C 15TH FLOOR COMMON WORK | TOWER C 15TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42359 |  |  |  | TOWER C 15TH FLOOR COMMON FABRICATION WORK | TOWER C 15TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24552 |  |  |  | TOWER C | TOWER C 16TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24553 |  |  |  | TOWER C 16TH FLOOR | TOWER C 16TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24554 |  |  |  | TOWER C 16TH FLOOR CIVIL WORK | TOWER C 16TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24557 |  |  |  | TOWER C 16TH FLOOR RCC WORK | TOWER C 16TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 18765.9 |  | Tentative | 18765.9 | 0 | 18765.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Task | 6 | 41019 |  |  |  | TOWER C 16TH FLOOR RCC WORK | TOWER C 16TH FLOOR RCC WORK THREADING | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | THREADING
Group | 5 | 24555 |  |  |  | TOWER C 16TH FLOOR CIVIL WORK | TOWER C 16TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24558 |  |  |  | TOWER C 16TH FLOOR MASONRY WORK | TOWER C 16TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24556 |  |  |  | TOWER C 16TH FLOOR CIVIL WORK | TOWER C 16TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24559 |  |  |  | TOWER C 16TH FLOOR PLASTER WORK | TOWER C 16TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29774 |  |  |  | TOWER C 16TH FLOOR | TOWER C 1601 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29766 |  |  |  | TOWER C 1601 | TOWER C 1601 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33635 |  |  |  | TOWER C 1601 WATERPROOFING WORK | TOWER C 1601 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29768 |  |  |  | TOWER C 1601 | TOWER C 1601 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33031 |  |  |  | TOWER C 1601 PLUMBING WORK | TOWER C 1601 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29767 |  |  |  | TOWER C 1601 | TOWER C 1601 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33843 |  |  |  | TOWER C 1601 ELECTRIC WORK | TOWER C 1601 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29769 |  |  |  | TOWER C 1601 | TOWER C 1601 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29772 |  |  |  | TOWER C 1601 | TOWER C 1601 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29770 |  |  |  | TOWER C 1601 | TOWER C 1601 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29771 |  |  |  | TOWER C 1601 | TOWER C 1601 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29773 |  |  |  | TOWER C 1601 | TOWER C 1601 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34449 |  |  |  | TOWER C 1601 | TOWER C 1601 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34450 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34451 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34452 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40307 |  |  |  | TOWER C 1601 COMMON WORK | TOWER C 1601 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29783 |  |  |  | TOWER C 16TH FLOOR | TOWER C 1602 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29775 |  |  |  | TOWER C 1602 | TOWER C 1602 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33636 |  |  |  | TOWER C 1602 WATERPROOFING WORK | TOWER C 1602 WATERPROOFING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WATERPROOFING WORK
Group | 5 | 29777 |  |  |  | TOWER C 1602 | TOWER C 1602 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33032 |  |  |  | TOWER C 1602 PLUMBING WORK | TOWER C 1602 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29776 |  |  |  | TOWER C 1602 | TOWER C 1602 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33844 |  |  |  | TOWER C 1602 ELECTRIC WORK | TOWER C 1602 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29778 |  |  |  | TOWER C 1602 | TOWER C 1602 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29781 |  |  |  | TOWER C 1602 | TOWER C 1602 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29779 |  |  |  | TOWER C 1602 | TOWER C 1602 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29780 |  |  |  | TOWER C 1602 | TOWER C 1602 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29782 |  |  |  | TOWER C 1602 | TOWER C 1602 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34453 |  |  |  | TOWER C 1602 | TOWER C 1602 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34454 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34455 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34456 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40308 |  |  |  | TOWER C 1602 COMMON WORK | TOWER C 1602 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5793 |  | Tentative | 0 | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29429 |  |  |  | TOWER C 16TH FLOOR | TOWER C 16TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29432 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29430 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41995 |  |  |  | TOWER C 16TH FLOOR COMMON FLOORING WORK | TOWER C 16TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29431 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29433 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29434 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 38763 |  |  |  | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | 1 | NOS | 0 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 41002 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41003 |  |  |  | TOWER C 16TH FLOOR WPC PANNELING WORK | TOWER C 16TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42360 |  |  |  | TOWER C 16TH FLOOR COMMON WORK | TOWER C 16TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42361 |  |  |  | TOWER C 16TH FLOOR COMMON FABRICATION WORK | TOWER C 16TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24560 |  |  |  | TOWER C | TOWER C 17TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24561 |  |  |  | TOWER C 17TH FLOOR | TOWER C 17TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24562 |  |  |  | TOWER C 17TH FLOOR CIVIL WORK | TOWER C 17TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24565 |  |  |  | TOWER C 17TH FLOOR RCC WORK | TOWER C 17TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 3437.9 |  | Tentative | 3437.9 | 0 | 3437.9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24563 |  |  |  | TOWER C 17TH FLOOR CIVIL WORK | TOWER C 17TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24566 |  |  |  | TOWER C 17TH FLOOR MASONRY WORK | TOWER C 17TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24564 |  |  |  | TOWER C 17TH FLOOR CIVIL WORK | TOWER C 17TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24567 |  |  |  | TOWER C 17TH FLOOR PLASTER WORK | TOWER C 17TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29792 |  |  |  | TOWER C 17TH FLOOR | TOWER C 1701 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29784 |  |  |  | TOWER C 1701 | TOWER C 1701 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29786 |  |  |  | TOWER C 1701 | TOWER C 1701 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33033 |  |  |  | TOWER C 1701 PLUMBING WORK | TOWER C 1701 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29785 |  |  |  | TOWER C 1701 | TOWER C 1701 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40396 |  |  |  | TOWER C 1701 ELECTRIC WORK | TOWER C 1701 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29787 |  |  |  | TOWER C 1701 | TOWER C 1701 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29790 |  |  |  | TOWER C 1701 | TOWER C 1701 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29788 |  |  |  | TOWER C 1701 | TOWER C 1701 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29789 |  |  |  | TOWER C 1701 | TOWER C 1701 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29791 |  |  |  | TOWER C 1701 | TOWER C 1701 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34457 |  |  |  | TOWER C 1701 | TOWER C 1701 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34458 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34459 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34460 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40309 |  |  |  | TOWER C 1701 COMMON WORK | TOWER C 1701 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5778 |  | Tentative | 0 | 5778 | 5778 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29801 |  |  |  | TOWER C 17TH FLOOR | TOWER C 1702 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29793 |  |  |  | TOWER C 1702 | TOWER C 1702 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29795 |  |  |  | TOWER C 1702 | TOWER C 1702 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33034 |  |  |  | TOWER C 1702 PLUMBING WORK | TOWER C 1702 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29794 |  |  |  | TOWER C 1702 | TOWER C 1702 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40397 |  |  |  | TOWER C 1702 ELECTRIC WORK | TOWER C 1702 ELECTRIC WORK | 1 | NOS | 1 | NOS | 1.18 |  | Tentative | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29796 |  |  |  | TOWER C 1702 | TOWER C 1702 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29799 |  |  |  | TOWER C 1702 | TOWER C 1702 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29797 |  |  |  | TOWER C 1702 | TOWER C 1702 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29798 |  |  |  | TOWER C 1702 | TOWER C 1702 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29800 |  |  |  | TOWER C 1702 | TOWER C 1702 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34461 |  |  |  | TOWER C 1702 | TOWER C 1702 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34462 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34463 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34464 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40310 |  |  |  | TOWER C 1702 COMMON WORK | TOWER C 1702 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 5778 |  | Tentative | 0 | 5778 | 5778 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29435 |  |  |  | TOWER C 17TH FLOOR | TOWER C 17TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29438 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29436 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41996 |  |  |  | TOWER C 17TH FLOOR COMMON FLOORING WORK | TOWER C 17TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29437 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29439 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29440 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41004 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41005 |  |  |  | TOWER C 17TH FLOOR WPC PANNELING WORK | TOWER C 17TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42362 |  |  |  | TOWER C 17TH FLOOR COMMON WORK | TOWER C 17TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42363 |  |  |  | TOWER C 17TH FLOOR COMMON FABRICATION WORK | TOWER C 17TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 24568 |  |  |  | TOWER C | TOWER C 18TH FLOOR | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 4 | 24569 |  |  |  | TOWER C 18TH FLOOR | TOWER C 18TH FLOOR CIVIL WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Group | 5 | 24570 |  |  |  | TOWER C 18TH FLOOR CIVIL WORK | TOWER C 18TH FLOOR RCC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24573 |  |  |  | TOWER C 18TH FLOOR RCC WORK | TOWER C 18TH FLOOR RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 227.74 |  | Tentative | 227.74 | 0 | 227.74 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 24571 |  |  |  | TOWER C 18TH FLOOR CIVIL WORK | TOWER C 18TH FLOOR MASONRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24574 |  |  |  | TOWER C 18TH FLOOR MASONRY WORK | TOWER C 18TH FLOOR MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 24572 |  |  |  | TOWER C 18TH FLOOR CIVIL WORK | TOWER C 18TH FLOOR PLASTER WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | -
Task | 6 | 24575 |  |  |  | TOWER C 18TH FLOOR PLASTER WORK | TOWER C 18TH FLOOR PLASTER WORK | 1 | SQFT | 1 | SQFT | 2693 |  | Tentative | 2693 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | - | - | - | - | PLASTER WORK
Group | 4 | 29828 |  |  |  | TOWER C 18TH FLOOR | TOWER C 1801 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29820 |  |  |  | TOWER C 1801 | TOWER C 1801 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29822 |  |  |  | TOWER C 1801 | TOWER C 1801 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33035 |  |  |  | TOWER C 1801 PLUMBING WORK | TOWER C 1801 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29821 |  |  |  | TOWER C 1801 | TOWER C 1801 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40398 |  |  |  | TOWER C 1801 ELECTRIC WORK | TOWER C 1801 ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29823 |  |  |  | TOWER C 1801 | TOWER C 1801 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29826 |  |  |  | TOWER C 1801 | TOWER C 1801 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29824 |  |  |  | TOWER C 1801 | TOWER C 1801 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29825 |  |  |  | TOWER C 1801 | TOWER C 1801 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29827 |  |  |  | TOWER C 1801 | TOWER C 1801 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34465 |  |  |  | TOWER C 1801 | TOWER C 1801 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34466 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34467 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34468 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40311 |  |  |  | TOWER C 1801 COMMON WORK | TOWER C 1801 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 3813 |  | Tentative | 0 | 3813 | 3813 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29837 |  |  |  | TOWER C 18TH FLOOR | TOWER C 1802 | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29829 |  |  |  | TOWER C 1802 | TOWER C 1802 WATERPROOFING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29831 |  |  |  | TOWER C 1802 | TOWER C 1802 PLUMBING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 33036 |  |  |  | TOWER C 1802 PLUMBING WORK | TOWER C 1802 PLUMBING WORK | 1 | NOS | 0 | NOS | 710.26 |  | Tentative | 710.26 | 0 | 710.26 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING WORK
Group | 5 | 29830 |  |  |  | TOWER C 1802 | TOWER C 1802 ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 40399 |  |  |  | TOWER C 1802 ELECTRIC WORK | TOWER C 1802 ELECTRIC WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ELECTRIC WORK
Group | 5 | 29832 |  |  |  | TOWER C 1802 | TOWER C 1802 FLOORING & DEDO WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29835 |  |  |  | TOWER C 1802 | TOWER C 1802 CARPENTRY WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29833 |  |  |  | TOWER C 1802 | TOWER C 1802 ALUMINIUM DOOR & WINDOW | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29834 |  |  |  | TOWER C 1802 | TOWER C 1802 PAINT WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29836 |  |  |  | TOWER C 1802 | TOWER C 1802 HVAC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 34469 |  |  |  | TOWER C 1802 | TOWER C 1802 COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 34470 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 COMMON RAILING WORK | 1 | RFT | 1 | RFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | BALCONY RAILING
Task | 6 | 34471 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 COMMON FALSE CEILING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PVC FALSE CEILING
Task | 6 | 34472 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 COMMON FABRICATION WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MISCELLANEOUS FABRICATION WORK
Task | 6 | 40312 |  |  |  | TOWER C 1802 COMMON WORK | TOWER C 1802 ANTI TERMITE TREATMENT | 1 | SQFT | 1 | SQFT | 3813 |  | Tentative | 0 | 3813 | 3813 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | ANTI TERMITE TREATMENT
Group | 4 | 29441 |  |  |  | TOWER C 18TH FLOOR | TOWER C 18TH FLOOR COMMON WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29444 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON DEBRISH CHUTE WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29442 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON FLOORING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41997 |  |  |  | TOWER C 18TH FLOOR COMMON FLOORING WORK | TOWER C 18TH FLOOR COMMON FLOORING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR TILE
Group | 5 | 29443 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON RAILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29445 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON FALSE CEILING WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 29446 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON ELECTRIC WORK | 0 |  | 0 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41006 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR WPC PANNELING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41007 |  |  |  | TOWER C 18TH FLOOR WPC PANNELING WORK | TOWER C 18TH FLOOR WPC PANNELING WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | WPC PANNELING WORK
Group | 5 | 42364 |  |  |  | TOWER C 18TH FLOOR COMMON WORK | TOWER C 18TH FLOOR COMMON FABRICATION WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 42365 |  |  |  | TOWER C 18TH FLOOR COMMON FABRICATION WORK | TOWER C 18TH FLOOR COMMON FABRICATION WORK | 1 | KG | 1 | KG | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | FLOOR FABRICATION WORK
Group | 3 | 41501 |  |  |  | TOWER C | TOWER C TERRACE | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41502 |  |  |  | TOWER C TERRACE | TOWER C TERRACE CIVIL WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 5 | 41503 |  |  |  | TOWER C TERRACE CIVIL WORK | TOWER C TERRACE RCC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41506 |  |  |  | TOWER C TERRACE RCC WORK | TOWER C TERRACE RCC WORK FOR SLAB | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | RCC WORK FOR SLAB
Group | 5 | 41504 |  |  |  | TOWER C TERRACE CIVIL WORK | TOWER C TERRACE MASONRY WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41507 |  |  |  | TOWER C TERRACE MASONRY WORK | TOWER C TERRACE MASONRY WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | MASONRY WORK
Group | 5 | 41505 |  |  |  | TOWER C TERRACE CIVIL WORK | TOWER C TERRACE PLASTER WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 6 | 41508 |  |  |  | TOWER C TERRACE PLASTER WORK | TOWER C TERRACE PLASTER WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLASTER WORK
Group | 3 | 41447 |  |  |  | TOWER C | TOWER C COMMON WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Group | 4 | 41448 |  |  |  | TOWER C COMMON WORK | TOWER C COMMON PLUMBING WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41449 |  |  |  | TOWER C COMMON PLUMBING WORK | TOWER C COMMON DUCT PLUMBING WORK | 1 | NOS | 1 | NOS | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | PLUMBING DUCT-PVC-SWR DRAINAGE PIPING WO
Group | 4 | 41477 |  |  |  | TOWER C COMMON WORK | TOWER C COMMON ELECTRIC WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 41478 |  |  |  | TOWER C COMMON ELECTRIC WORK | TOWER C COMMON ELECTRIC WORK | 1 | POINT | 1 | POINT | 0 | ELECTRIC WORK | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | TOWER COMMON ELECTRIC WORK
Group | 4 | 42153 | Block/Building/Tower/Wing |  | Externall Plaster | TOWER C COMMON WORK | TOWER C EXTERNAL PAINT WORK | 0 |  | 0 |  | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | -
Task | 5 | 42154 |  |  |  | TOWER C EXTERNAL PAINT WORK | TOWER C EXTERNAL PAINT WORK | 1 | SQFT | 1 | SQFT | 0 |  | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 Mar 2020 |  |  |  | - | - | - | - | EXTERNAL PAINT WORK