## WBS_Budget_Report63848189793150
WBS Budget Report
Project Name : GREENWOOD ASPIRE EXP
Page 1 of 1
Task_Name | Approved_Budget | Release_Budget | Consumed_Budget | Release_Balance_Budget | Balance_Budget
TOWER A | 415762385 | 415762385 | 0 | 415762385 | 415762385
TOWER A UP TO PLINTH LEVEL | 9251958 | 0 | 0 | 0 | 9251958
TOWER A UP TO PLINTH CIVIL WORK | 8704433 | 8704433 | 6878657.91 | 1825775.09 | 1825775.09
TOWER A UP TO PLINTH LEVEL COMMON WORK | 547525 | 547525 | 127456.94 | 420068.06 | 420068.06
TOWER A GROUND FLOOR PARKING | 9851958 | 9851958 | 0 | 9851958 | 9851958
TOWER A GROUND FLOOR PARKING CIVIL WORK | 8704433 | 8704433 | 3378471.57 | 5325961.43 | 5325961.43
TOWER A GROUND FLOOR COMMON WORK | 1147525 | 1147525 | 1098168.76 | 49356.24 | 49356.24
TOWER A 1ST FLOOR | 19157887 | 19157887 | 0 | 19157887 | 19157887
TOWER A 1ST FLOOR CIVIL WORK | 8704433 | 8704433 | 3121009.08 | 5583423.92 | 5583423.92
A 101 | 5572964 | 5572964 | 0 | 5572964 | 5572964
A 101 WATERPROOFING WORK | 195000 | 195000 | 157078.91 | 37921.09 | 37921.09
A 101 PLUMBING WORK | 543739 | 543739 | 78163.48 | 465575.52 | 465575.52
A 101 ELECTRICAL WORK | 334117 | 334117 | 79695.61 | 254421.39 | 254421.39
A 101 FLOORING & DEDO WORK | 1200000 | 1200000 | 340391.72 | 859608.28 | 859608.28
A 101 CARPENTRY WORK | 1158490 | 1158490 | 1094835.7 | 63654.3 | 63654.3
A 101 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 508437.66 | 12583.34 | 12583.34
A 101 MISC WORK | 1214336 | 1214336 | 1169240.94 | 45095.06 | 45095.06
A 102 | 4122964 | 0 | 0 | 0 | 4122964
A 102 WATERPROOFING WORK | 195000 | 195000 | 148614.47 | 46385.53 | 46385.53
A 102 PLUMBING WORK | 950000 | 950000 | 78163.48 | 871836.52 | 871836.52
A 102 ELECTRICAL WORK | 284117 | 284117 | 1120 | 282997 | 282997
A 102 FLOORING & DEDO WORK | 1200000 | 1200000 | 234604.92 | 965395.08 | 965395.08
A 102 CARPENTRY WORK | 258490 | 258490 | 11800 | 246690 | 246690
A 102 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
A 102 MISC WORK | 714336 | 714336 | 256049.26 | 458286.74 | 458286.74
TOWER A 1ST FLOOR COMMON WORK | 757526 | 757526 | 732738.96 | 24787.04 | 24787.04
TOWER A 2ND FLOOR | 23120314 | 23120314 | 0 | 23120314 | 23120314
TOWER A 2ND FLOOR CIVIL WORK | 8704433 | 8704433 | 3212325.74 | 5492107.26 | 5492107.26
A 201 | 4292964 | 4292964 | 0 | 4292964 | 4292964
A 201 WATERPROOFING WORK | 195000 | 195000 | 177721.35 | 17278.65 | 17278.65
A 201 PLUMBING WORK | 950000 | 950000 | 811074 | 138926 | 138926
A 201 ELECTRICAL WORK | 334117 | 334117 | 139698.06 | 194418.94 | 194418.94
A 201 FLOORING & DEDO WORK | 1320000 | 1320000 | 1311096.79 | 8903.21 | 8903.21
A 201 CARPENTRY WORK | 258490 | 258490 | 212499.26 | 45990.74 | 45990.74
A 201 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 510915.66 | 10105.34 | 10105.34
A 201 MISC WORK | 714336 | 714336 | 434332.01 | 280003.99 | 280003.99
A 202 | 9275391 | 9275391 | 108913.11 | 9166477.89 | 9166477.89
A 202 WATERPROOFING WORK | 195000 | 195000 | 147428.47 | 47571.53 | 47571.53
A 202 PLUMBING WORK | 950000 | 950000 | 935104.75 | 14895.25 | 14895.25
A 202 ELECTRICAL WORK | 990117 | 990117 | 376947.9 | 613169.1 | 613169.1
A 202 FLOORING & DEDO WORK | 1636042 | 1636042 | 1604691.94 | 31350.06 | 31350.06
A 202 CARPENTRY WORK | 2521490 | 2521490 | 1458507.21 | 1062982.79 | 1062982.79
A 202 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
A 202 MISC WORK | 2111721 | 2111721 | 2009227.06 | 102493.94 | 102493.94
TOWER A 2ND FLOOR COMMON WORK | 847526 | 847526 | 801099.73 | 46426.27 | 46426.27
TOWER A 3RD FLOOR | 23198586 | 23198586 | 0 | 23198586 | 23198586
TOWER A 3RD FLOOR CIVIL WORK | 8704433 | 8704433 | 3421899.48 | 5282533.52 | 5282533.52
A 301 | 8982464 | 8982464 | 0 | 8982464 | 8982464
A 301 WATERPROOFING WORK | 195000 | 195000 | 156428.92 | 38571.08 | 38571.08
A 301 PLUMBING WORK | 950000 | 950000 | 143939.33 | 806060.67 | 806060.67
A 301 ELECTRICAL WORK | 548617 | 548617 | 277735.18 | 270881.82 | 270881.82
A 301 FLOORING & DEDO WORK | 1200000 | 1200000 | 664969.32 | 535030.68 | 535030.68
A 301 CARPENTRY WORK | 4063490 | 4063490 | 3976924.39 | 86565.61 | 86565.61
A 301 ALUMINUM DOOR & WINDOW WORK | 1016021 | 1016021 | 970428.06 | 45592.94 | 45592.94
A 301 MISC WORK | 979336 | 979336 | 960734.69 | 18601.31 | 18601.31
A 302 | 4343805 | 4343805 | 0 | 4343805 | 4343805
A 302 WATERPROOFING WORK | 205841 | 205841 | 185721.06 | 20119.94 | 20119.94
A 302 PLUMBING WORK | 950000 | 950000 | 328986.37 | 621013.63 | 621013.63
A 302 ELECTRICAL WORK | 334117 | 334117 | 140960.66 | 193156.34 | 193156.34
A 302 FLOORING & DEDO WORK | 1345000 | 1345000 | 1325726.31 | 19273.69 | 19273.69
A 302 CARPENTRY WORK | 258490 | 258490 | 213451.4 | 45038.6 | 45038.6
A 302 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 505454.78 | 15566.22 | 15566.22
A 302 MISC WORK | 714336 | 714336 | 444080.36 | 270255.64 | 270255.64
TOWER A 3RD FLOOR COMMON WORK | 1167526 | 1167526 | 1116071.86 | 51454.14 | 51454.14
TOWER A 4TH FLOOR | 18132887 | 18132887 | 0 | 18132887 | 18132887
TOWER A 4TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3600086.26 | 5104346.74 | 5104346.74
A 401 | 4412964 | 0 | 0 | 0 | 4412964
A 401 WATERPROOFING WORK | 220000 | 220000 | 208437.01 | 11562.99 | 11562.99
A 401 PLUMBING WORK | 950000 | 950000 | 359048.3 | 590951.7 | 590951.7
A 401 ELECTRICAL WORK | 549117 | 549117 | 298692.85 | 250424.15 | 250424.15
A 401 FLOORING & DEDO WORK | 1200000 | 1200000 | 1131206.2 | 68793.8 | 68793.8
A 401 CARPENTRY WORK | 258490 | 258490 | 201689.16 | 56800.84 | 56800.84
A 401 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 509145.66 | 11875.34 | 11875.34
A 401 MISC WORK | 714336 | 714336 | 409081.66 | 305254.34 | 305254.34
A 402 | 4267964 | 0 | 0 | 0 | 4267964
A 402 WATERPROOFING WORK | 195000 | 195000 | 151908.2 | 43091.8 | 43091.8
A 402 PLUMBING WORK | 950000 | 950000 | 355324.53 | 594675.47 | 594675.47
A 402 ELECTRICAL WORK | 429117 | 429117 | 173997.62 | 255119.38 | 255119.38
A 402 FLOORING & DEDO WORK | 1200000 | 1200000 | 1173507.47 | 26492.53 | 26492.53
A 402 CARPENTRY WORK | 258490 | 258490 | 201702.73 | 56787.27 | 56787.27
A 402 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495010 | 26011 | 26011
A 402 MISC WORK | 714336 | 714336 | 395424.66 | 318911.34 | 318911.34
TOWER A 4TH FLOOR COMMON WORK | 747526 | 747526 | 667607.7 | 79918.3 | 79918.3
TOWER A 5TH FLOOR | 19382443 | 19382443 | 0 | 19382443 | 19382443
TOWER A 5TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3770028.43 | 4934404.57 | 4934404.57
A 501 | 4602964 | 4602964 | 0 | 4602964 | 4602964
A 501 WATERPROOFING WORK | 410000 | 410000 | 254878.38 | 155121.62 | 155121.62
A 501 PLUMBING WORK | 950000 | 950000 | 349996.51 | 600003.49 | 600003.49
A 501 ELECTRICAL WORK | 509117 | 509117 | 309483.24 | 199633.76 | 199633.76
A 501 FLOORING & DEDO WORK | 1240000 | 1240000 | 1227609.1 | 12390.9 | 12390.9
A 501 CARPENTRY WORK | 258490 | 258490 | 213489.16 | 45000.84 | 45000.84
A 501 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 518174.44 | 2846.56 | 2846.56
A 501 MISC WORK | 714336 | 714336 | 363040.78 | 351295.22 | 351295.22
A 502 | 4337964 | 0 | 0 | 0 | 4337964
A 502 WATERPROOFING WORK | 195000 | 195000 | 181573.05 | 13426.95 | 13426.95
A 502 PLUMBING WORK | 950000 | 950000 | 347513.7 | 602486.3 | 602486.3
A 502 ELECTRICAL WORK | 399117 | 399117 | 319519.31 | 79597.69 | 79597.69
A 502 FLOORING & DEDO WORK | 1250000 | 1250000 | 1244223.11 | 5776.89 | 5776.89
A 502 CARPENTRY WORK | 258490 | 258490 | 201626.08 | 56863.92 | 56863.92
A 502 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495010 | 26011 | 26011
A 502 MISC WORK | 714336 | 714336 | 424185.4 | 290150.6 | 290150.6
TOWER A 5TH FLOOR COMMON WORK | 817526 | 817526 | 777289.16 | 40236.84 | 40236.84
TOWER A 6TH FLOOR | 19257443 | 19257443 | 0 | 19257443 | 19257443
TOWER A 6TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3720654.86 | 4983778.14 | 4983778.14
A 601 | 4512964 | 4512964 | 0 | 4512964 | 4512964
A 601 WATERPROOFING WORK | 240000 | 240000 | 209945.88 | 30054.12 | 30054.12
A 601 PLUMBING WORK | 950000 | 950000 | 468434.71 | 481565.29 | 481565.29
A 601 ELECTRICAL WORK | 399117 | 399117 | 263240.86 | 135876.14 | 135876.14
A 601 FLOORING & DEDO WORK | 1430000 | 1430000 | 1416968.31 | 13031.69 | 13031.69
A 601 CARPENTRY WORK | 258490 | 258490 | 201689.16 | 56800.84 | 56800.84
A 601 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 508437.66 | 12583.34 | 12583.34
A 601 MISC WORK | 714336 | 714336 | 362719.82 | 351616.18 | 351616.18
A 602 | 4237964 | 0 | 0 | 0 | 4237964
A 602 WATERPROOFING WORK | 210000 | 210000 | 207973.5 | 2026.5 | 2026.5
A 602 PLUMBING WORK | 950000 | 950000 | 332440.24 | 617559.76 | 617559.76
A 602 ELECTRICAL WORK | 334117 | 334117 | 117764.16 | 216352.84 | 216352.84
A 602 FLOORING & DEDO WORK | 1200000 | 1200000 | 1174753.75 | 25246.25 | 25246.25
A 602 CARPENTRY WORK | 258490 | 258490 | 201675 | 56815 | 56815
A 602 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495954 | 25067 | 25067
A 602 MISC WORK | 714336 | 714336 | 372191.8 | 342144.2 | 342144.2
TOWER A 6TH FLOOR COMMON WORK | 807526 | 807526 | 760150.83 | 47375.17 | 47375.17
TOWER A 7TH FLOOR | 18017887 | 18017887 | 0 | 18017887 | 18017887
TOWER A 7TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4665561.12 | 4038871.88 | 4038871.88
A 701 | 4280464 | 4280464 | 0 | 4280464 | 4280464
A 701 WATERPROOFING WORK | 250000 | 250000 | 219297.26 | 30702.74 | 30702.74
A 701 PLUMBING WORK | 950000 | 950000 | 357643.26 | 592356.74 | 592356.74
A 701 ELECTRICAL WORK | 334117 | 334117 | 262271.41 | 71845.59 | 71845.59
A 701 FLOORING & DEDO WORK | 1240000 | 1240000 | 1237291.84 | 2708.16 | 2708.16
A 701 CARPENTRY WORK | 258490 | 258490 | 201689.16 | 56800.84 | 56800.84
A 701 ALUMINUM DOOR & WINDOW WORK | 533521 | 533521 | 529556.9 | 3964.1 | 3964.1
A 701 MISC WORK | 714336 | 714336 | 520687.6 | 193648.4 | 193648.4
A 702 | 4215464 | 4215464 | 0 | 4215464 | 4215464
A 702 WATERPROOFING WORK | 240000 | 240000 | 202087.88 | 37912.12 | 37912.12
A 702 PLUMBING WORK | 950000 | 950000 | 449624.78 | 500375.22 | 500375.22
A 702 ELECTRICAL WORK | 324117 | 324117 | 185828.54 | 138288.46 | 138288.46
A 702 FLOORING & DEDO WORK | 1200000 | 1200000 | 1170439.56 | 29560.44 | 29560.44
A 702 CARPENTRY WORK | 258490 | 258490 | 201689.16 | 56800.84 | 56800.84
A 702 ALUMINUM DOOR & WINDOW WORK | 528521 | 528521 | 511905.54 | 16615.46 | 16615.46
A 702 MISC WORK | 714336 | 714336 | 497413.6 | 216922.4 | 216922.4
TOWER A 7TH FLOOR COMMON WORK | 817526 | 817526 | 763750.08 | 53775.92 | 53775.92
TOWER A 8TH FLOOR | 17901887 | 17901887 | 0 | 17901887 | 17901887
TOWER A 8TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3879169.89 | 4825263.11 | 4825263.11
A 801 | 4231964 | 4231964 | 0 | 4231964 | 4231964
A 801 WATERPROOFING WORK | 225000 | 225000 | 210085.62 | 14914.38 | 14914.38
A 801 PLUMBING WORK | 950000 | 950000 | 462140.11 | 487859.89 | 487859.89
A 801 ELECTRICAL WORK | 410117 | 410117 | 291757.34 | 118359.66 | 118359.66
A 801 FLOORING & DEDO WORK | 1150000 | 1150000 | 1126710.32 | 23289.68 | 23289.68
A 801 CARPENTRY WORK | 258490 | 258490 | 213489.16 | 45000.84 | 45000.84
A 801 ALUMINUM DOOR & WINDOW WORK | 524021 | 524021 | 522068.44 | 1952.56 | 1952.56
A 801 MISC WORK | 714336 | 714336 | 402253.4 | 312082.6 | 312082.6
A 802 | 4267964 | 0 | 0 | 0 | 4267964
A 802 WATERPROOFING WORK | 225000 | 225000 | 200063.71 | 24936.29 | 24936.29
A 802 PLUMBING WORK | 950000 | 950000 | 467170.77 | 482829.23 | 482829.23
A 802 ELECTRICAL WORK | 449117 | 449117 | 301373.09 | 147743.91 | 147743.91
A 802 FLOORING & DEDO WORK | 1150000 | 1150000 | 1142548.24 | 7451.76 | 7451.76
A 802 CARPENTRY WORK | 258490 | 258490 | 213489.16 | 45000.84 | 45000.84
A 802 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494656 | 26365 | 26365
A 802 MISC WORK | 714336 | 714336 | 387412.86 | 326923.14 | 326923.14
TOWER A 8TH FLOOR COMMON WORK | 697526 | 697526 | 653160.41 | 44365.59 | 44365.59
TOWER A 9TH FLOOR | 18172887 | 18172887 | 0 | 18172887 | 18172887
TOWER A 9TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4111224.05 | 4593208.95 | 4593208.95
A 901 | 4502964 | 4502964 | 0 | 4502964 | 4502964
A 901 WATERPROOFING WORK | 225000 | 225000 | 210085.62 | 14914.38 | 14914.38
A 901 PLUMBING WORK | 950000 | 950000 | 482347.2 | 467652.8 | 467652.8
A 901 ELECTRICAL WORK | 414117 | 414117 | 235730.6 | 178386.4 | 178386.4
A 901 FLOORING & DEDO WORK | 1420000 | 1420000 | 1376898.38 | 4422908.32 | 43101.62
A 901 CARPENTRY WORK | 258490 | 258490 | 213489.16 | 45000.84 | 45000.84
A 901 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 509145.66 | 11875.34 | 11875.34
A 901 MISC WORK | 714336 | 714336 | 461103.74 | 253232.26 | 253232.26
A 902 | 4217964 | 0 | 0 | 0 | 4217964
A 902 WATERPROOFING WORK | 225000 | 225000 | 200063.71 | 24936.29 | 24936.29
A 902 PLUMBING WORK | 950000 | 950000 | 485908.44 | 464091.56 | 464091.56
A 902 ELECTRICAL WORK | 399117 | 399117 | 295666.73 | 103450.27 | 103450.27
A 902 FLOORING & DEDO WORK | 1150000 | 1150000 | 1081367.75 | 68632.25 | 68632.25
A 902 CARPENTRY WORK | 258490 | 258490 | 213489.16 | 45000.84 | 45000.84
A 902 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495010 | 26011 | 26011
A 902 MISC WORK | 714336 | 714336 | 446764.7 | 267571.3 | 267571.3
TOWER A 9TH FLOOR COMMON WORK | 747526 | 747526 | 690300.69 | 57225.31 | 57225.31
TOWER A 10TH FLOOR | 17883887 | 17883887 | 0 | 17883887 | 17883887
TOWER A 10TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6427645.65 | 2276787.35 | 2276787.35
A 1001 | 4173964 | 4173964 | 0 | 4173964 | 4173964
A 1001 WATERPROOFING WORK | 225000 | 225000 | 198596.56 | 26403.44 | 26403.44
A 1001 PLUMBING WORK | 555898 | 555898 | 348931.62 | 206966.38 | 206966.38
A 1001 ELECTRICAL WORK | 355117 | 355117 | 284028.01 | 71088.99 | 71088.99
A 1001 FLOORING & DEDO WORK | 1310903 | 1310903 | 1107302.83 | 203600.17 | 203600.17
A 1001 CARPENTRY WORK | 258490 | 258490 | 201717.48 | 56772.52 | 56772.52
A 1001 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 509853.66 | 11167.34 | 11167.34
A 1001 MISC WORK | 714336 | 714336 | 412226.9 | 302109.1 | 302109.1
A 1002 | 4257964 | 4257964 | 0 | 4257964 | 4257964
A 1002 WATERPROOFING WORK | 225000 | 225000 | 188663.32 | 36336.68 | 36336.68
A 1002 PLUMBING WORK | 950000 | 950000 | 350501.02 | 599498.98 | 599498.98
A 1002 ELECTRICAL WORK | 439117 | 439117 | 297478.69 | 141638.31 | 141638.31
A 1002 FLOORING & DEDO WORK | 1150000 | 1150000 | 1122434.51 | 27565.49 | 27565.49
A 1002 CARPENTRY WORK | 258490 | 258490 | 201689.16 | 56800.84 | 56800.84
A 1002 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
A 1002 MISC WORK | 714336 | 714336 | 397225.88 | 317110.12 | 317110.12
TOWER A 10TH FLOOR COMMON WORK | 747526 | 747526 | 690408.96 | 57117.04 | 57117.04
TOWER A 11TH FLOOR | 18427728 | 18427728 | 0 | 18427728 | 18427728
TOWER A 11TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6637953.64 | 2066479.36 | 2066479.36
A 1101 | 4222805 | 4222805 | 0 | 4222805 | 4222805
A1101 WATERPROOFING | 224841 | 224841 | 190212.34 | 34628.66 | 34628.66
A 1101 PLUMBING WORK | 950000 | 950000 | 471990.61 | 478009.39 | 478009.39
A 1101 ELECTRICAL WORK | 384117 | 384117 | 361979.94 | 22137.06 | 22137.06
A 1101 FLOORING & DEDO WORK | 1170000 | 1170000 | 1123473.11 | 46526.89 | 46526.89
A 1101 CARPENTRY WORK | 258490 | 258490 | 211569.16 | 46920.84 | 46920.84
A 1101 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 509145.66 | 11875.34 | 11875.34
A 1101 MISC WORK | 714336 | 714336 | 447563.24 | 266772.76 | 266772.76
A 1102 | 4267964 | 4267964 | 0 | 4267964 | 4267964
A 1102 WATERPROOFING | 225000 | 225000 | 169950.68 | 55049.32 | 55049.32
A 1102 PLUMBING WORK | 950000 | 950000 | 459539.56 | 490460.44 | 490460.44
A 1102 ELECTRICAL WORK | 449117 | 449117 | 271470.67 | 177646.33 | 177646.33
A 1102 FLOORING & DEDO WORK | 1150000 | 1150000 | 1139938.51 | 10061.49 | 10061.49
A 1102 CARPENTRY WORK | 258490 | 258490 | 211569.16 | 46920.84 | 46920.84
A 1102 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494656 | 26365 | 26365
A 1102 MISC WORK | 714336 | 714336 | 502243.2 | 212092.8 | 212092.8
TOWER A 11TH FLOOR COMMON WORK | 1232526 | 1232526 | 1229567.3 | 2958.7 | 2958.7
TOWER A 12TH FLOOR | 18047887 | 18047887 | 0 | 18047887 | 18047887
TOWER A 12TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6774894.33 | 1929538.67 | 1929538.67
A 1201 | 4297964 | 4297964 | 0 | 4297964 | 4297964
A 1201 WATERPROOFING WORK | 225000 | 225000 | 181023.8 | 43976.2 | 43976.2
A 1201 PLUMBING WORK | 950000 | 950000 | 466022.48 | 483977.52 | 483977.52
A 1201 ELECTRICAL WORK | 459117 | 459117 | 309811.79 | 149305.21 | 149305.21
A 1201 FLOORING & DEDO WORK | 1170000 | 1170000 | 1152644.57 | 17355.43 | 17355.43
A 1201 CARPENTRY WORK | 258490 | 258490 | 211569.16 | 46920.84 | 46920.84
A 1201 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 509145.66 | 11875.34 | 11875.34
A 1201 MISC WORK | 714336 | 714336 | 462610.22 | 251725.78 | 251725.78
A 1202 | 4297964 | 4297964 | 0 | 4297964 | 4297964
A 1202 WATERPROOFING WORK | 225000 | 225000 | 171036.28 | 53963.72 | 53963.72
A 1202 PLUMBING WORK | 950000 | 950000 | 351074.53 | 598925.47 | 598925.47
A 1202 ELECTRICAL WORK | 449117 | 449117 | 310066.25 | 139050.75 | 139050.75
A 1202 FLOORING & DEDO WORK | 1180000 | 1180000 | 1159288.78 | 20711.22 | 20711.22
A 1202 CARPENTRY WORK | 258490 | 258490 | 211569.16 | 46920.84 | 46920.84
A 1202 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494656 | 26365 | 26365
A 1202 MISC WORK | 714336 | 714336 | 448451.72 | 265884.28 | 265884.28
TOWER A 12TH FLOOR COMMON WORK | 747526 | 747526 | 703488 | 44038 | 44038
TOWER A 13TH FLOOR | 18063728 | 18063728 | 0 | 18063728 | 18063728
TOWER A 13TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6514308.59 | 2190124.41 | 2190124.41
A 1301 | 4283805 | 4283805 | 0 | 4283805 | 4283805
A 1301 WATERPROOFING WORK | 230841 | 230841 | 191988.36 | 38852.64 | 38852.64
A 1301 PLUMBING WORK | 950000 | 950000 | 352584.1 | 597415.9 | 597415.9
A 1301 ELECTRICAL WORK | 379117 | 379117 | 322997.63 | 56119.37 | 56119.37
A 1301 FLOORING & DEDO WORK | 1215000 | 1215000 | 1161061.5 | 53938.5 | 53938.5
A 1301 CARPENTRY WORK | 258490 | 258490 | 210617.02 | 47872.98 | 47872.98
A 1301 ALUMINUM DOOR & WINDOW WORK | 536021 | 536021 | 528848.9 | 7172.1 | 7172.1
A 1301 MISC WORK | 714336 | 714336 | 575601.12 | 138734.88 | 138734.88
A 1302 | 4347964 | 4347964 | 0 | 4347964 | 4347964
A 1302 WATERPROOFING WORK | 225000 | 225000 | 182055.12 | 42944.88 | 42944.88
A 1302 PLUMBING WORK | 950000 | 950000 | 465422.21 | 484577.79 | 484577.79
A 1302 ELECTRICAL WORK | 449117 | 449117 | 305422.44 | 143694.56 | 143694.56
A 1302 FLOORING & DEDO WORK | 1230000 | 1230000 | 1187496.79 | 42503.21 | 42503.21
A 1302 CARPENTRY WORK | 258490 | 258490 | 210617.02 | 47872.98 | 47872.98
A 1302 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 512259.54 | 8761.46 | 8761.46
A 1302 MISC WORK | 714336 | 714336 | 560421.92 | 153914.08 | 153914.08
TOWER A 13TH FLOOR COMMON WORK | 727526 | 727526 | 704321.48 | 23204.52 | 23204.52
TOWER A 14TH FLOOR | 19108887 | 19108887 | 0 | 19108887 | 19108887
TOWER A 14TH FLOOR CIVIL WORK | 8704433 | 8704433 | 7179384.22 | 1525048.78 | 1525048.78
A 1401 | 5292964 | 5292964 | 0 | 5292964 | 5292964
A 1401 WATERPROOFING WORK | 225000 | 225000 | 178961.16 | 46038.84 | 46038.84
A 1401 PLUMBING WORK | 950000 | 950000 | 458171.31 | 491828.69 | 491828.69
A 1401 ELECTRICAL WORK | 369117 | 369117 | 317950.75 | 51166.25 | 51166.25
A 1401 FLOORING & DEDO WORK | 1780000 | 1780000 | 1615511.43 | 164488.57 | 164488.57
A 1401 CARPENTRY WORK | 723490 | 723490 | 703989.18 | 19500.82 | 19500.82
A 1401 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 508437.66 | 12583.34 | 12583.34
A 1401 MISC WORK | 714336 | 714336 | 453558.08 | 260777.92 | 260777.92
A 1402 | 4413964 | 4413964 | 0 | 4413964 | 4413964
A 1402 WATERPROOFING WORK | 225000 | 225000 | 169027.92 | 55972.08 | 55972.08
A 1402 PLUMBING WORK | 950000 | 950000 | 458690.62 | 491309.38 | 491309.38
A 1402 ELECTRICAL WORK | 369117 | 369117 | 250847.25 | 118269.75 | 118269.75
A 1402 FLOORING & DEDO WORK | 1215000 | 1215000 | 1184912.06 | 30087.94 | 30087.94
A 1402 CARPENTRY WORK | 258490 | 258490 | 210617.02 | 47872.98 | 47872.98
A 1402 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495010 | 26011 | 26011
A 1402 MISC WORK | 875336 | 875336 | 870505.62 | 4830.38 | 4830.38
TOWER A 14TH FLOOR COMMON WORK | 697526 | 697526 | 651018.91 | 46507.09 | 46507.09
TOWER A 15TH FLOOR | 17847887 | 17847887 | 0 | 17847887 | 17847887
TOWER A 15TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5574666.53 | 3129766.47 | 3129766.47
A 1501 | 4232964 | 4232964 | 0 | 4232964 | 4232964
A 1501 WATERPROOFING WORK | 225000 | 225000 | 178961.16 | 46038.84 | 46038.84
A 1501 PLUMBING WORK | 950000 | 950000 | 263576.7 | 686423.3 | 686423.3
A 1501 ELECTRICAL WORK | 394117 | 394117 | 317660.14 | 76456.86 | 76456.86
A 1501 FLOORING & DEDO WORK | 1170000 | 1170000 | 1132706.52 | 37293.48 | 37293.48
A 1501 CARPENTRY WORK | 258490 | 258490 | 210617.02 | 47872.98 | 47872.98
A 1501 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 508791.66 | 12229.34 | 12229.34
A 1501 MISC WORK | 714336 | 714336 | 482146.06 | 232189.94 | 232189.94
A 1502 | 4212964 | 4212964 | 0 | 4212964 | 4212964
A 1502 WATERPROOFING WORK | 225000 | 225000 | 169027.92 | 55972.08 | 55972.08
A 1502 PLUMBING WORK | 950000 | 950000 | 354122.98 | 595877.02 | 595877.02
A 1502 ELECTRICAL WORK | 394117 | 394117 | 312940.14 | 81176.86 | 81176.86
A 1502 FLOORING & DEDO WORK | 1150000 | 1150000 | 1081326.48 | 68673.52 | 68673.52
A 1502 CARPENTRY WORK | 258490 | 258490 | 210617.02 | 47872.98 | 47872.98
A 1502 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495010 | 26011 | 26011
A 1502 MISC WORK | 714336 | 714336 | 497359.18 | 216976.82 | 216976.82
TOWER A 15TH FLOOR COMMON WORK | 697526 | 697526 | 678247.16 | 19278.84 | 19278.84
TOWER A 16TH FLOOR | 17751728 | 17751728 | 0 | 17751728 | 17751728
TOWER A 16TH FLOOR CIVIL WORK | 8704433 | 8704433 | 7100745.31 | 1603687.69 | 1603687.69
A 1601 | 4151805 | 4151805 | 0 | 4151805 | 4151805
A 1601 WATERPROOFING WORK | 228841 | 228841 | 183249.28 | 45591.72 | 45591.72
A 1601 PLUMBING WORK | 950000 | 950000 | 234842.59 | 715157.41 | 715157.41
A 1601 ELECTRICAL WORK | 329117 | 329117 | 301018.68 | 28098.32 | 28098.32
A 1601 FLOORING & DEDO WORK | 1150000 | 1150000 | 848702.34 | 301297.66 | 301297.66
A 1601 CARPENTRY WORK | 258490 | 258490 | 10044.16 | 248445.84 | 248445.84
A 1601 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 508437.66 | 12583.34 | 12583.34
A 1601 MISC WORK | 714336 | 714336 | 457115.1 | 257220.9 | 257220.9
A 1602 | 4177964 | 0 | 0 | 0 | 4177964
A 1602 WATERPROOFING WORK | 225000 | 225000 | 173316.04 | 51683.96 | 51683.96
A 1602 PLUMBING WORK | 950000 | 950000 | 357729.45 | 592270.55 | 592270.55
A 1602 ELECTRICAL WORK | 359117 | 359117 | 230777.81 | 128339.19 | 128339.19
A 1602 FLOORING & DEDO WORK | 1150000 | 1150000 | 364776.09 | 785223.91 | 785223.91
A 1602 CARPENTRY WORK | 258490 | 258490 | 198817.02 | 59672.98 | 59672.98
A 1602 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
A 1602 MISC WORK | 714336 | 714336 | 442455.1 | 271880.9 | 271880.9
TOWER A 16TH FLOOR COMMON WORK | 717526 | 717526 | 666697.4 | 50828.6 | 50828.6
TOWER A 17TH FLOOR | 17879728 | 17879728 | 0 | 17879728 | 17879728
TOWER A 17TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6032082.46 | 2672350.54 | 2672350.54
A 1701 | 4304805 | 4304805 | 0 | 4304805 | 4304805
A 1701 WATERPROOFING WORK | 231841 | 231841 | 183249.28 | 48591.72 | 48591.72
A 1701 PLUMBING WORK | 950000 | 950000 | 175412.63 | 774587.37 | 774587.37
A 1701 ELECTRICAL WORK | 329117 | 329117 | 301018.68 | 28098.32 | 28098.32
A 1701 FLOORING & DEDO WORK | 1300000 | 1300000 | 993177.35 | 306822.65 | 306822.65
A 1701 CARPENTRY WORK | 258490 | 258490 | 198817.02 | 59672.98 | 59672.98
A 1701 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 508437.66 | 12583.34 | 12583.34
A 1701 MISC WORK | 714336 | 714336 | 467561.52 | 246774.48 | 246774.48
A 1702 | 4132964 | 0 | 0 | 0 | 4132964
A 1702 WATERPROOFING WORK | 225000 | 225000 | 173316.04 | 51683.96 | 51683.96
A 1702 PLUMBING WORK | 950000 | 950000 | 148265.34 | 801734.66 | 801734.66
A 1702 ELECTRICAL WORK | 314117 | 314117 | 128133.68 | 185983.32 | 185983.32
A 1702 FLOORING & DEDO WORK | 1150000 | 1150000 | 691684.65 | 458315.35 | 458315.35
A 1702 CARPENTRY WORK | 258490 | 258490 | 198817.02 | 59672.98 | 59672.98
A 1702 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
A 1702 MISC WORK | 714336 | 714336 | 452901.52 | 261434.48 | 261434.48
TOWER A 17TH FLOOR COMMON WORK | 737526 | 737526 | 694111.85 | 43414.15 | 43414.15
TOWER A 18TH FLOOR | 19157887 | 19157887 | 0 | 19157887 | 19157887
TOWER A 18TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4930824.15 | 3773608.85 | 3773608.85
A 1801 | 5622964 | 5622964 | 0 | 5622964 | 5622964
A 1801 WATERPROOFING WORK | 205000 | 205000 | 181838 | 23162 | 23162
A 1801 PLUMBING WORK | 950000 | 950000 | 120034.25 | 829965.75 | 829965.75
A 1801 ELECTRICAL WORK | 284117 | 284117 | 182313.78 | 101803.22 | 101803.22
A 1801 FLOORING & DEDO WORK | 1150000 | 1150000 | 165300 | 984700 | 984700
A 1801 CARPENTRY WORK | 278490 | 278490 | 244129.02 | 34360.98 | 34360.98
A 1801 ALUMINUM DOOR & WINDOW WORK | 2021021 | 2021021 | 0 | 2021021 | 2021021
A 1801 MISC WORK | 714336 | 714336 | 359617.1 | 354718.9 | 354718.9
A 1802 | 4102964 | 4102964 | 0 | 4102964 | 4102964
A 1802 WATERPROOFING WORK | 205000 | 205000 | 181838 | 23162 | 23162
A 1802 PLUMBING WORK | 950000 | 950000 | 108234.25 | 841765.75 | 841765.75
A 1802 ELECTRICAL WORK | 284117 | 284117 | 190313.78 | 93803.22 | 93803.22
A 1802 FLOORING & DEDO WORK | 1150000 | 1150000 | 693466.88 | 456533.12 | 456533.12
A 1802 CARPENTRY WORK | 278490 | 278490 | 244129.02 | 34360.98 | 34360.98
A 1802 ALUMINUM DOOR & WINDOW WORK | 521021 | 0 | 0 | 0 | 521021
A 1802 MISC WORK | 714336 | 714336 | 344957.1 | 369378.9 | 369378.9
TOWER A 18TH FLOOR COMMON WORK | 717526 | 717526 | 665317.39 | 52208.61 | 52208.61
TOWER A 19TH FLOOR | 24947887 | 24947887 | 0 | 24947887 | 24947887
TOWER A 19TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4523422.98 | 4181010.02 | 4181010.02
A 1901 | 7768123 | 7768123 | 0 | 7768123 | 7768123
A 1901 WATERPROOFING WORK | 265000 | 265000 | 208093 | 56907 | 56907
A 1901 PLUMBING WORK | 950000 | 950000 | 186957.35 | 763042.65 | 763042.65
A 1901 ELECTRICAL WORK | 284117 | 284117 | 51013.15 | 233103.85 | 233103.85
A 1901 FLOORING & DEDO WORK | 1150000 | 1150000 | 217674.4 | 932325.6 | 932325.6
A 1901 CARPENTRY WORK | 318490 | 318490 | 278016.26 | 40473.74 | 40473.74
A 1901 ALUMINUM DOOR & WINDOW WORK | 4021021 | 4021021 | 1491302.32 | 2529718.68 | 2529718.68
A 1901 MISC WORK | 714336 | 714336 | 319209.7 | 395126.3 | 395126.3
A 1902 | 7757805 | 7757805 | 0 | 7757805 | 7757805
A 1902 WATERPROOFING WORK | 265000 | 265000 | 208093 | 56907 | 56907
A 1902 PLUMBING WORK | 950000 | 950000 | 186312.82 | 763687.18 | 763687.18
A 1902 ELECTRICAL WORK | 284117 | 284117 | 83746.35 | 200370.65 | 200370.65
A 1902 FLOORING & DEDO WORK | 1150000 | 1150000 | 947776.65 | 202223.35 | 202223.35
A 1902 CARPENTRY WORK | 318490 | 318490 | 278016.26 | 40473.74 | 40473.74
A 1902 ALUMINUM DOOR & WINDOW WORK | 4021021 | 4021021 | 1491302.32 | 2529718.68 | 2529718.68
A 1902 MISC WORK | 709177 | 709177 | 303523.1 | 405653.9 | 405653.9
TOWER A 19TH FLOOR COMMON WORK | 717526 | 717526 | 670799.42 | 46726.58 | 46726.58
TOWER A TERRACE | 12751958 | 12751958 | 0 | 12751958 | 12751958
TOWER A TERRACE CIVIL WORK | 8704433 | 8704433 | 932860.14 | 7771572.86 | 7771572.86
TOWER A TERRACE COMMON WORK | 4047525 | 4047525 | 2465891.56 | 1581633.44 | 1581633.44
TOWER A COMMON WORK | 16912056 | 16912056 | 0 | 16912056 | 16912056
TOWER A COMMON WATERPROOFING WORK | 407660 | 407660 | 0 | 407660 | 407660
TOWER A COMMON ELECTRIC WORK | 2865832 | 2865832 | 1839512.71 | 1026319.29 | 1026319.29
TOWER A COMMON FLOORING & DEDO WORK | 3210024 | 3210024 | 317122.66 | 2892901.35 | 2892901.34
TOWER A COMMON MISC WORK | 10428540 | 10428540 | 10404511.63 | 24028.37 | 24028.37
TOWER B | 391903932 | 391903932 | 0 | 391903932 | 391903932
TOWER B UP TO PLINTH LEVEL | 9251958 | 0 | 0 | 0 | 9251958
TOWER B UP TO PLINTH LEVEL CIVIL WORK | 8704433 | 8704433 | 5039497.01 | 3664935.99 | 3664935.99
TOWER B UP TO PLINTH LEVEL COMMON WORK | 547525 | 547525 | 127678.78 | 419846.22 | 419846.22
TOWER B GROUND FLOOR PARKING | 9551958 | 9551958 | 0 | 9551958 | 9551958
TOWER B GROUND FLOOR CIVIL WORK | 8704433 | 8704433 | 3058294.76 | 5646138.24 | 5646138.24
TOWER B GROUND FLOOR FINISHING WORK | 847525 | 847525 | 788063.97 | 59461.03 | 59461.03
TOWER B 1ST FLOOR | 18402886 | 18402886 | 0 | 18402886 | 18402886
TOWER B 1ST FLOOR CIVIL WORK | 8704433 | 8704433 | 3154812.49 | 5549620.51 | 5549620.51
B 101 | 4272964 | 4272964 | 0 | 4272964 | 4272964
B 101 WATERPROOFING WORK | 195000 | 195000 | 163900.87 | 31099.13 | 31099.13
B 101 PLUMBING WORK | 950000 | 950000 | 573380.69 | 376619.31 | 376619.31
B 101 ELECTRICAL WORK | 334117 | 334117 | 300500.44 | 33616.56 | 33616.56
B 101 FLOORING & DEDO WORK | 1300000 | 1300000 | 1230839.86 | 69160.14 | 69160.14
B 101 CARPENTRY WORK | 258490 | 258490 | 171929.06 | 86560.94 | 86560.94
B 101 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 101 MISC WORK | 714336 | 714336 | 703535.16 | 10800.84 | 10800.84
B 102 | 4357964 | 4357964 | 0 | 4357964 | 4357964
B 102 WATERPROOFING WORK | 195000 | 195000 | 151002.12 | 43997.88 | 43997.88
B 102 PLUMBING WORK | 950000 | 950000 | 509748.01 | 440251.99 | 440251.99
B 102 ELECTRICAL WORK | 334117 | 334117 | 298881.04 | 35235.96 | 35235.96
B 102 FLOORING & DEDO WORK | 1280000 | 1280000 | 1216576.9 | 63423.1 | 63423.1
B 102 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 102 ALUMINUM DOOR & WINDOW WORK | 626021 | 626021 | 624574 | 1447 | 1447
B 102 MISC WORK | 714336 | 714336 | 446829.24 | 267506.76 | 267506.76
TOWER B 1ST FLOOR COMMON WORK | 1067525 | 1067525 | 858185.51 | 209339.49 | 209339.49
TOWER B 2ND FLOOR | 17917886 | 17917886 | 0 | 17917886 | 17917886
TOWER B 2ND FLOOR CIVIL WORK | 8704433 | 8704433 | 3170032.86 | 5534400.14 | 5534400.14
B 201 | 4282964 | 4282964 | 0 | 4282964 | 4282964
B 201 WATERPROOFING WORK | 195000 | 195000 | 143309.62 | 51690.38 | 51690.38
B 201 PLUMBING WORK | 950000 | 950000 | 488885.19 | 461114.81 | 461114.81
B 201 ELECTRICAL WORK | 334117 | 334117 | 303561.21 | 30555.79 | 30555.79
B 201 FLOORING & DEDO WORK | 1310000 | 1310000 | 1251101.53 | 58898.47 | 58898.47
B 201 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 201 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 201 MISC WORK | 714336 | 714336 | 435128.86 | 279207.14 | 279207.14
B 202 | 4262964 | 4262964 | 0 | 4262964 | 4262964
B 202 WATERPROOFING WORK | 195000 | 195000 | 143309.62 | 51690.38 | 51690.38
B 202 PLUMBING WORK | 950000 | 950000 | 505260.91 | 444739.09 | 444739.09
B 202 ELECTRICAL WORK | 344117 | 344117 | 258005.65 | 86111.35 | 86111.35
B 202 FLOORING & DEDO WORK | 1280000 | 1280000 | 1219380.68 | 60619.32 | 60619.32
B 202 CARPENTRY WORK | 258490 | 258490 | 205705.08 | 52784.92 | 52784.92
B 202 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 202 MISC WORK | 714336 | 714336 | 424045.26 | 290290.74 | 290290.74
TOWER B 2ND FLOOR COMMON WORK | 667525 | 667525 | 636320.46 | 31204.54 | 31204.54
TOWER B 3RD FLOOR | 17877886 | 17877886 | 0 | 17877886 | 17877886
TOWER B 3RD FLOOR CIVIL WORK | 8704433 | 8704433 | 3490312.76 | 5214120.24 | 5214120.24
B 301 | 4222964 | 4222964 | 0 | 4222964 | 4222964
B 301 WATERPROOFING WORK | 195000 | 195000 | 143309.62 | 51690.38 | 51690.38
B 301 PLUMBING WORK | 950000 | 950000 | 485732.41 | 464267.59 | 464267.59
B 301 ELECTRICAL WORK | 384117 | 384117 | 231220.33 | 152896.67 | 152896.67
B 301 FLOORING & DEDO WORK | 1200000 | 1200000 | 1146775.43 | 53224.57 | 53224.57
B 301 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 301 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 495379.97 | 25641.03 | 25641.03
B 301 MISC WORK | 714336 | 714336 | 467670.26 | 246665.74 | 246665.74
B 302 | 4302964 | 4302964 | 0 | 4302964 | 4302964
B 302 WATERPROOFING WORK | 195000 | 195000 | 143252.12 | 51747.88 | 51747.88
B 302 PLUMBING WORK | 950000 | 950000 | 482992.97 | 467007.03 | 467007.03
B 302 ELECTRICAL WORK | 434117 | 434117 | 165449.58 | 268667.42 | 268667.42
B 302 FLOORING & DEDO WORK | 1230000 | 1230000 | 1167773.42 | 62226.58 | 62226.58
B 302 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 302 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 302 MISC WORK | 714336 | 714336 | 464870.76 | 249465.24 | 249465.24
TOWER B 3RD FLOOR COMMON WORK | 647525 | 647525 | 636902.49 | 10622.51 | 10622.51
TOWER B 4TH FLOOR | 18036886 | 18036886 | 0 | 18036886 | 18036886
TOWER B 4TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3461079.69 | 5243353.31 | 5243353.31
B 401 | 4339964 | 4339964 | 0 | 4339964 | 4339964
B 401 WATERPROFING WORK | 195000 | 195000 | 153138.93 | 41861.07 | 41861.07
B 401 PLUMBING WORK | 950000 | 950000 | 360088.83 | 589911.17 | 589911.17
B 401 ELECTRICAL WORK | 456117 | 456117 | 345259.64 | 110857.36 | 110857.36
B 401 FLOORING & DEDO WORK | 1245000 | 1245000 | 1185306.1 | 59693.9 | 59693.9
B 401 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 401 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 401 MISC WORK | 714336 | 714336 | 394172.14 | 320163.86 | 320163.86
B 402 | 4324964 | 4324964 | 0 | 4324964 | 4324964
B 402 WATERPROOFING WORK | 195000 | 195000 | 153046.93 | 41953.07 | 41953.07
B 402 PLUMBING WORK | 950000 | 950000 | 457657.48 | 492342.52 | 492342.52
B 402 ELECTRICAL WORK | 456117 | 456117 | 343863.29 | 112253.71 | 112253.71
B 402 FLOORING & DEDO WORK | 1230000 | 1230000 | 1162576.95 | 67423.05 | 67423.05
B 402 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 402 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 402 MISC WORK | 714336 | 714336 | 424045.26 | 290290.74 | 290290.74
TOWER B 4TH FLOOR COMMON WORK | 667525 | 667525 | 645075 | 22450 | 22450
TOWER B 5TH FLOOR | 18271886 | 18271886 | 0 | 18271886 | 18271886
TOWER B 5TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3488284.05 | 5216148.95 | 5216148.95
B 501 | 4407964 | 4407964 | 0 | 4407964 | 4407964
B 501 WATERPROOFING WORK | 195000 | 195000 | 171907.02 | 23092.98 | 23092.98
B 501 PLUMBING WORK | 950000 | 950000 | 462927.99 | 487072.01 | 487072.01
B 501 ELECTRICAL WORK | 539117 | 539117 | 437911.81 | 101205.19 | 101205.19
B 501 FLOORING & DEDO WORK | 1230000 | 1230000 | 1094655.18 | 135344.82 | 135344.82
B 501 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 501 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 501 MISC WORK | 714336 | 714336 | 432045.26 | 282290.74 | 282290.74
B 502 | 4471964 | 4471964 | 0 | 4471964 | 4471964
B 502 WATERPROOFING WORK | 195000 | 195000 | 171815.02 | 23184.98 | 23184.98
B 502 PLUMBING WORK | 950000 | 950000 | 459731.96 | 490268.04 | 490268.04
B 502 ELECTRICAL WORK | 603117 | 603117 | 492804.1 | 110312.9 | 110312.9
B 502 FLOORING & DEDO WORK | 1230000 | 1230000 | 1072385.8 | 157614.2 | 157614.2
B 502 CARPENTRY WORK | 258490 | 258490 | 203225.55 | 55264.45 | 55264.45
B 502 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 502 MISC WORK | 714336 | 714336 | 432045.26 | 282290.74 | 282290.74
TOWER B 5TH FLOOR COMMON WORK | 687525 | 687525 | 672489.45 | 15035.55 | 15035.55
TOWER B 6TH FLOOR | 18297886 | 18297886 | 0 | 18297886 | 18297886
TOWER B 6TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3417532.03 | 5286900.97 | 5286900.97
B 601 | 4472964 | 4472964 | 0 | 4472964 | 4472964
B 601 WATERPROOFING WORK | 195000 | 195000 | 175523.77 | 19476.23 | 19476.23
B 601 PLUMBING WORK | 950000 | 950000 | 459838.16 | 490161.84 | 490161.84
B 601 ELECTRICAL WORK | 604117 | 604117 | 493953.18 | 110163.82 | 110163.82
B 601 FLOORING & DEDO WORK | 1230000 | 1230000 | 1077289.15 | 152710.85 | 152710.85
B 601 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 601 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 601 MISC WORK | 714336 | 714336 | 432045.26 | 282290.74 | 282290.74
B 602 | 4467964 | 4467964 | 0 | 4467964 | 4467964
B 602 WATERPROOFING WORK | 195000 | 195000 | 175523.77 | 19476.23 | 19476.23
B 602 PLUMBING WORK | 950000 | 950000 | 459838.16 | 490161.84 | 490161.84
B 602 ELECTRICAL WORK | 599117 | 599117 | 490657.08 | 108459.92 | 108459.92
B 602 FLOORING & DEDO WORK | 1230000 | 1230000 | 1101848.4 | 128151.6 | 128151.6
B 602 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 602 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 602 MISC WORK | 714336 | 714336 | 432045.26 | 282290.74 | 282290.74
TOWER B 6TH FLOOR COMMON WORK | 632525 | 632525 | 617762 | 14763 | 14763
TOWER B 7TH FLOOR | 17959886 | 17959886 | 0 | 17959886 | 17959886
TOWER B 7TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3596188.39 | 5108244.61 | 5108244.61
B 701 | 4239964 | 4239964 | 0 | 4239964 | 4239964
B 701 WATERPROOFING WORK | 195000 | 195000 | 163894.14 | 31105.86 | 31105.86
B 701 PLUMBING WORK | 950000 | 950000 | 364857.91 | 585142.09 | 585142.09
B 701 ELECTRICAL WORK | 399117 | 399117 | 379297.75 | 19819.25 | 19819.25
B 701 FLOORING & DEDO WORK | 1202000 | 1202000 | 1145044.48 | 56955.52 | 56955.52
B 701 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 701 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 511905.54 | 9115.46 | 9115.46
B 701 MISC WORK | 714336 | 714336 | 476017.82 | 238318.18 | 238318.18
B 702 | 4202964 | 4202964 | 0 | 4202964 | 4202964
B 702 WATERPROOFING WORK | 195000 | 195000 | 163894.14 | 31105.86 | 31105.86
B 702 PLUMBING WORK | 950000 | 950000 | 364877.52 | 585122.48 | 585122.48
B 702 ELECTRICAL WORK | 384117 | 384117 | 293026.6 | 91090.4 | 91090.4
B 702 FLOORING & DEDO WORK | 1180000 | 1180000 | 963205.27 | 216794.73 | 216794.73
B 702 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 702 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 511905.54 | 9115.46 | 9115.46
B 702 MISC WORK | 714336 | 714336 | 487017.82 | 227318.18 | 227318.18
TOWER B 7TH FLOOR COMMON WORK | 812525 | 812525 | 626258.63 | 186266.37 | 186266.37
TOWER B 8TH FLOOR | 17936054 | 17936054 | 0 | 17936054 | 17936054
TOWER B 8TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3694283.65 | 5010149.35 | 5010149.35
B 801 | 4252964 | 4252964 | 0 | 4252964 | 4252964
B 801 WATERPROOFING WORK | 195000 | 195000 | 154668.7 | 40331.3 | 40331.3
B 801 PLUMBING WORK | 950000 | 950000 | 367894.66 | 582105.34 | 582105.34
B 801 ELECTRICAL WORK | 434117 | 434117 | 425716.26 | 8400.74 | 8400.74
B 801 FLOORING & DEDO WORK | 1180000 | 1180000 | 1067176.26 | 112823.74 | 112823.74
B 801 CARPENTRY WORK | 258490 | 258490 | 214320.02 | 44169.98 | 44169.98
B 801 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 801 MISC WORK | 714336 | 714336 | 431515.66 | 282820.34 | 282820.34
B 802 | 4306132 | 4306132 | 0 | 4306132 | 4306132
B 802 WATERPROOFING WORK | 195000 | 195000 | 154668.7 | 40331.3 | 40331.3
B 802 PLUMBING WORK | 950000 | 950000 | 367155.98 | 582844.02 | 582844.02
B 802 ELECTRICAL WORK | 434117 | 434117 | 425716.26 | 8400.74 | 8400.74
B 802 FLOORING & DEDO WORK | 1233168 | 1233168 | 1176924.53 | 56243.47 | 56243.47
B 802 CARPENTRY WORK | 258490 | 258490 | 214320.02 | 44169.98 | 44169.98
B 802 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 802 MISC WORK | 714336 | 714336 | 422195.66 | 292140.34 | 292140.34
TOWER B 8TH FLOOR COMMON WORK | 632525 | 632525 | 604107.46 | 28417.54 | 28417.54
TOWER B 9TH FLOOR | 17802886 | 17802886 | 0 | 17802886 | 17802886
TOWER B 9TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4090824.25 | 4613608.75 | 4613608.75
B 901 | 4212964 | 4212964 | 0 | 4212964 | 4212964
B 901 WATERPROOFING WORK | 195000 | 195000 | 155427.43 | 39572.57 | 39572.57
B 901 PLUMBING WORK | 950000 | 950000 | 461874.92 | 488125.08 | 488125.08
B 901 ELECTRICAL WORK | 394117 | 394117 | 377227.93 | 16889.07 | 16889.07
B 901 FLOORING & DEDO WORK | 1180000 | 1180000 | 956213.47 | 223786.53 | 223786.53
B 901 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 901 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 901 MISC WORK | 714336 | 714336 | 486388.51 | 227947.49 | 227947.49
B 902 | 4212964 | 4212964 | 0 | 4212964 | 4212964
B 902 WATERPROOFING WORK | 195000 | 195000 | 155568.06 | 39431.94 | 39431.94
B 902 PLUMBING WORK | 950000 | 950000 | 463444.32 | 486555.68 | 486555.68
B 902 ELECTRICAL WORK | 394117 | 394117 | 378142.67 | 15974.33 | 15974.33
B 902 FLOORING & DEDO WORK | 1180000 | 1180000 | 1001777.94 | 178222.06 | 178222.06
B 902 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 902 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 902 MISC WORK | 714336 | 714336 | 466304.91 | 248031.09 | 248031.09
TOWER B 9TH FLOOR COMMON WORK | 652525 | 652525 | 641210.55 | 11314.45 | 11314.45
TOWER B 10TH FLOOR | 17872886 | 17872886 | 0 | 17872886 | 17872886
TOWER B 10TH FLOOR CIVIL WORK | 8704433 | 8704433 | 7054142.16 | 1650290.84 | 1650290.84
B 1001 | 4247964 | 4247964 | 0 | 4247964 | 4247964
B 1001 WATERPROOFING WORK | 195000 | 195000 | 154626.42 | 40373.58 | 40373.58
B 1001 PLUMBING WORK | 950000 | 950000 | 466750.7 | 483249.3 | 483249.3
B 1001 ELECTRICAL WORK | 429117 | 429117 | 371440.68 | 57676.32 | 57676.32
B 1001 FLOORING & DEDO WORK | 1180000 | 1180000 | 1063725.7 | 116274.3 | 116274.3
B 1001 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 1001 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1001 MISC WORK | 714336 | 714336 | 427364.91 | 286971.09 | 286971.09
B 1002 | 4267964 | 4267964 | 0 | 4267964 | 4267964
B 1002 WATERPROOFING WORK | 195000 | 195000 | 154626.42 | 40373.58 | 40373.58
B 1002 PLUMBING WORK | 950000 | 950000 | 486985.75 | 463014.25 | 463014.25
B 1002 ELECTRICAL WORK | 449117 | 449117 | 391295.22 | 57821.78 | 57821.78
B 1002 FLOORING & DEDO WORK | 1180000 | 1180000 | 1107073.16 | 72926.84 | 72926.84
B 1002 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
B 1002 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1002 MISC WORK | 714336 | 714336 | 427364.91 | 286971.09 | 286971.09
TOWER B 10TH FLOOR COMMON WORK | 652525 | 652525 | 630234.26 | 22290.74 | 22290.74
TOWER B 11TH FLOOR | 18477886 | 18477886 | 0 | 18477886 | 18477886
TOWER B 11TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5726901.92 | 2977531.08 | 2977531.08
B 1101 | 4292964 | 4292964 | 0 | 4292964 | 4292964
B 1101 WATERPROOFING WORK | 195000 | 195000 | 182638.24 | 12361.76 | 12361.76
B 1101 PLUMBING WORK | 950000 | 950000 | 518797.62 | 431202.38 | 431202.38
B 1101 ELECTRICAL WORK | 359117 | 359117 | 327989.32 | 4211520.98 | 31127.68
B 1101 FLOORING & DEDO WORK | 1220000 | 1220000 | 1174897.81 | 45102.19 | 45102.19
B 1101 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1101 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1101 MISC WORK | 714336 | 714336 | 458711.89 | 255624.11 | 255624.11
B 1102 | 4282964 | 4282964 | 0 | 77297.99 | 4282964
B 1102 WATERPROOFING WORK | 195000 | 195000 | 154866.94 | 40133.06 | 40133.06
B 1102 PLUMBING WORK | 950000 | 950000 | 538936.73 | 411063.27 | 411063.27
B 1102 ELECTRICAL WORK | 359117 | 359117 | 327989.32 | 31127.68 | 31127.68
B 1102 FLOORING & DEDO WORK | 1210000 | 1210000 | 1190737.32 | 48765.09 | 19262.68
B 1102 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1102 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1102 MISC WORK | 714336 | 714336 | 428061.11 | 286274.89 | 286274.89
TOWER B 11TH FLOOR COMMON WORK | 1197525 | 1197525 | 1184399.86 | 13125.14 | 13125.14
TOWER B 12TH FLOOR | 17776886 | 17776886 | 0 | 17776886 | 17776886
TOWER B 12TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6993285.84 | 1711147.16 | 1711147.16
B 1201 | 4219964 | 4219964 | 0 | 4219964 | 4219964
B 1201 WATERPROOFING WORK | 195000 | 195000 | 153906.35 | 41093.65 | 41093.65
B 1201 PLUMBING WORK | 950000 | 950000 | 458580.89 | 491419.11 | 491419.11
B 1201 ELECTRICAL WORK | 356117 | 356117 | 326468.16 | 29648.84 | 29648.84
B 1201 FLOORING & DEDO WORK | 1225000 | 1225000 | 1193868.22 | 31131.78 | 31131.78
B 1201 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1201 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1201 MISC WORK | 714336 | 714336 | 442766.85 | 271569.15 | 271569.15
B 1202 | 4189964 | 4189964 | 0 | 4189964 | 4189964
B 1202 WATERPROOFING WORK | 195000 | 195000 | 136159.02 | 58840.98 | 58840.98
B 1202 PLUMBING WORK | 950000 | 950000 | 455248.57 | 494751.43 | 494751.43
B 1202 ELECTRICAL WORK | 371117 | 371117 | 368582.36 | 2534.64 | 2534.64
B 1202 FLOORING & DEDO WORK | 1180000 | 1180000 | 1149808.76 | 30191.24 | 30191.24
B 1202 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1202 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1202 MISC WORK | 714336 | 714336 | 431763.35 | 282572.65 | 282572.65
TOWER B 12TH FLOOR COMMON WORK | 662525 | 662525 | 636420.8 | 26104.2 | 26104.2
TOWER B 13TH FLOOR | 17727886 | 17727886 | 0 | 17727886 | 17727886
TOWER B 13TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6431312.21 | 2273120.79 | 2273120.79
B 1301 | 4167964 | 4167964 | 0 | 4167964 | 4167964
B 1301 WATERPROOFING WORK | 195000 | 195000 | 146269.26 | 48730.74 | 48730.74
B 1301 PLUMBING WORK | 950000 | 950000 | 448430 | 501570 | 501570
B 1301 ELECTRICAL WORK | 349117 | 349117 | 348249.7 | 867.3 | 867.3
B 1301 FLOORING & DEDO WORK | 1180000 | 1180000 | 1145189.67 | 34810.33 | 34810.33
B 1301 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1301 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 511905.54 | 9115.46 | 9115.46
B 1301 MISC WORK | 714336 | 714336 | 539827.75 | 174508.25 | 174508.25
B 1302 | 4167964 | 4167964 | 0 | 4167964 | 4167964
B 1302 WATERPROOFING WORK | 195000 | 195000 | 146269.26 | 48730.74 | 48730.74
B 1302 PLUMBING WORK | 950000 | 950000 | 449881.4 | 500118.6 | 500118.6
B 1302 ELECTRICAL WORK | 349117 | 349117 | 336975.98 | 12141.02 | 12141.02
B 1302 FLOORING & DEDO WORK | 1180000 | 1180000 | 1140154.88 | 39845.12 | 39845.12
B 1302 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1302 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1302 MISC WORK | 714336 | 714336 | 491152.75 | 223183.25 | 223183.25
TOWER B 13TH FLOOR COMMON WORK | 687525 | 687525 | 671297.49 | 16227.51 | 16227.51
TOWER B 14TH FLOOR | 17812886 | 17812886 | 0 | 17812886 | 17812886
TOWER B 14TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6158489.52 | 2545943.48 | 2545943.48
B 1401 | 4197964 | 4197964 | 0 | 4197964 | 4197964
B 1401 WATERPROOFING WORK | 195000 | 195000 | 136704.18 | 58295.82 | 58295.82
B 1401 PLUMBING WORK | 950000 | 950000 | 292470.93 | 657529.07 | 657529.07
B 1401 ELECTRICAL WORK | 379117 | 379117 | 368605.18 | 10511.82 | 10511.82
B 1401 FLOORING & DEDO WORK | 1180000 | 1180000 | 1137083.76 | 42916.24 | 42916.24
B 1401 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1401 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1401 MISC WORK | 714336 | 714336 | 467374.9 | 246961.1 | 246961.1
B 1402 | 4267964 | 4267964 | 0 | 4267964 | 4267964
B 1402 WATERPROOFING WORK | 195000 | 195000 | 136704.18 | 58295.82 | 58295.82
B 1402 PLUMBING WORK | 950000 | 950000 | 305630.63 | 644369.37 | 644369.37
B 1402 ELECTRICAL WORK | 379117 | 379117 | 368605.18 | 10511.82 | 10511.82
B 1402 FLOORING & DEDO WORK | 1180000 | 1180000 | 1145830.73 | 34169.27 | 34169.27
B 1402 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1402 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1402 MISC WORK | 714336 | 714336 | 456070.5 | 258265.5 | 258265.5
TOWER B 14TH FLOOR COMMON WORK | 642525 | 642525 | 626765.53 | 15759.47 | 15759.47
TOWER B 15TH FLOOR | 17842886 | 17842886 | 0 | 17842886 | 17842886
TOWER B 15TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6238073.1 | 2466359.9 | 2466359.9
B 1501 | 4197964 | 4197964 | 0 | 4197964 | 4197964
B 1501 WATERPROOFING WORK | 195000 | 195000 | 137893.62 | 57106.38 | 57106.38
B 1501 PLUMBING WORK | 950000 | 950000 | 356897.11 | 593102.89 | 593102.89
B 1501 ELECTRICAL WORK | 359117 | 359117 | 330089.78 | 29027.22 | 29027.22
B 1501 FLOORING & DEDO WORK | 1200000 | 1200000 | 1153363.38 | 46636.62 | 46636.62
B 1501 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1501 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1501 MISC WORK | 714336 | 714336 | 523519.3 | 190816.7 | 190816.7
B 1502 | 4162964 | 4162964 | 0 | 4162964 | 4162964
B 1502 WATERPROOFING WORK | 195000 | 195000 | 137893.62 | 57106.38 | 57106.38
B 1502 PLUMBING WORK | 950000 | 950000 | 237059.47 | 712940.53 | 712940.53
B 1502 ELECTRICAL WORK | 344117 | 344117 | 339302.1 | 4814.9 | 4814.9
B 1502 FLOORING & DEDO WORK | 1180000 | 1180000 | 587445.31 | 592554.69 | 592554.69
B 1502 CARPENTRY WORK | 258490 | 258490 | 198779.26 | 59710.74 | 59710.74
B 1502 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1502 MISC WORK | 714336 | 714336 | 512781.3 | 201554.7 | 201554.7
TOWER B 15TH FLOOR COMMON WORK | 747525 | 747525 | 729218.26 | 18306.74 | 18306.74
TOWER B 16TH FLOOR | 18052886 | 18052886 | 0 | 18052886 | 18052886
TOWER B 16TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4127631.01 | 4576801.99 | 4576801.99
B 1601 | 4312964 | 4312964 | 0 | 4312964 | 4312964
B 1601 WATERPROOFING WORK | 195000 | 195000 | 138686.58 | 56313.42 | 56313.42
B 1601 PLUMBING WORK | 950000 | 950000 | 333808.43 | 616191.57 | 616191.57
B 1601 ELECTRICAL WORK | 354117 | 354117 | 345581.89 | 8535.11 | 8535.11
B 1601 FLOORING & DEDO WORK | 1320000 | 1320000 | 1246572.75 | 73427.25 | 73427.25
B 1601 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1601 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1601 MISC WORK | 714336 | 714336 | 471497.82 | 242838.18 | 242838.18
B 1602 | 4302964 | 4302964 | 0 | 4302964 | 4302964
B 1602 WATERPROOFING WORK | 195000 | 195000 | 138686.58 | 56313.42 | 56313.42
B 1602 PLUMBING WORK | 950000 | 950000 | 336582.52 | 613417.48 | 613417.48
B 1602 ELECTRICAL WORK | 354117 | 354117 | 346808.34 | 7308.66 | 7308.66
B 1602 FLOORING & DEDO WORK | 1310000 | 1310000 | 1230337.13 | 79662.87 | 79662.87
B 1602 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1602 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1602 MISC WORK | 714336 | 714336 | 471497.82 | 242838.18 | 242838.18
TOWER B 16TH FLOOR COMMON WORK | 632525 | 632525 | 613136.3 | 19388.7 | 19388.7
TOWER B 17TH FLOOR | 17717886 | 17717886 | 0 | 17717886 | 17717886
TOWER B 17TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5297002.71 | 3407430.29 | 3407430.29
B 1701 | 4172964 | 4172964 | 0 | 4172964 | 4172964
B 1701 WATERPROOFING WORK | 195000 | 195000 | 139479.54 | 55520.46 | 55520.46
B 1701 PLUMBING WORK | 950000 | 950000 | 145648.7 | 804351.3 | 804351.3
B 1701 ELECTRICAL WORK | 354117 | 354117 | 347553.87 | 6563.13 | 6563.13
B 1701 FLOORING & DEDO WORK | 1180000 | 1180000 | 1031100.09 | 148899.91 | 148899.91
B 1701 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1701 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1701 MISC WORK | 714336 | 714336 | 478832.7 | 235503.3 | 235503.3
B 1702 | 4172964 | 4172964 | 0 | 4172964 | 4172964
B 1702 WATERPROOFING WORK | 195000 | 195000 | 139479.54 | 55520.46 | 55520.46
B 1702 PLUMBING WORK | 950000 | 950000 | 138763.74 | 811236.26 | 811236.26
B 1702 ELECTRICAL WORK | 354117 | 354117 | 348261.54 | 5855.46 | 5855.46
B 1702 FLOORING & DEDO WORK | 1180000 | 1180000 | 1019478.27 | 160521.73 | 160521.73
B 1702 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
B 1702 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 494302 | 26719 | 26719
B 1702 MISC WORK | 714336 | 714336 | 478832.7 | 235503.3 | 235503.3
TOWER B 17TH FLOOR COMMON WORK | 647525 | 647525 | 640757.25 | 6767.75 | 6767.75
TOWER B 18TH FLOOR | 17802886 | 17802886 | 0 | 17802886 | 17802886
TOWER B 18TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5300914.28 | 3403518.72 | 3403518.72
B 1801 | 4232964 | 0 | 0 | 0 | 4232964
B 1801 WATERPROOFING WORK | 355000 | 355000 | 0 | 355000 | 355000
B 1801 PLUMBING WORK | 950000 | 950000 | 121011.61 | 828988.39 | 828988.39
B 1801 ELECTRICAL WORK | 284117 | 284117 | 148590.24 | 135526.76 | 135526.76
B 1801 FLOORING & DEDO WORK | 1150000 | 1150000 | 362346.06 | 787653.94 | 787653.94
B 1801 CARPENTRY WORK | 258490 | 258490 | 244091.26 | 14398.74 | 14398.74
B 1801 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 0 | 521021 | 521021
B 1801 MISC WORK | 714336 | 714336 | 220295.12 | 494040.88 | 494040.88
B 1802 | 4232964 | 0 | 0 | 0 | 4232964
B 1802 WATERPROOFING WORK | 355000 | 355000 | 0 | 355000 | 355000
B 1802 PLUMBING WORK | 950000 | 950000 | 121115.45 | 828884.55 | 828884.55
B 1802 ELECTRICAL WORK | 284117 | 284117 | 242472.23 | 41644.77 | 41644.77
B 1802 FLOORING & DEDO WORK | 1150000 | 1150000 | 362346.06 | 787653.94 | 787653.94
B 1802 CARPENTRY WORK | 258490 | 258490 | 244091.26 | 14398.74 | 14398.74
B 1802 ALUMINUM DOOR & WINDOW WORK | 521021 | 521021 | 0 | 521021 | 521021
B 1802 MISC WORK | 714336 | 714336 | 220295.12 | 494040.88 | 494040.88
TOWER B 18TH FLOOR COMMON WORK | 632525 | 632525 | 611484.3 | 21040.7 | 21040.7
TOWER B 19TH FLOOR | 21402886 | 21402886 | 0 | 21402886 | 21402886
TOWER B 19TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4866863.64 | 3837569.36 | 3837569.36
B 1901 | 6032964 | 6032964 | 0 | 6032964 | 6032964
B 1901 WATERPROOFING WORK | 425000 | 425000 | 67968 | 357032 | 357032
B 1901 PLUMBING WORK | 950000 | 950000 | 87038.24 | 862961.76 | 862961.76
B 1901 ELECTRICAL WORK | 284117 | 284117 | 120562.23 | 163554.77 | 163554.77
B 1901 FLOORING & DEDO WORK | 1150000 | 1150000 | 268782.38 | 881217.62 | 881217.62
B 1901 CARPENTRY WORK | 288490 | 288490 | 278016.26 | 10473.74 | 10473.74
B 1901 ALUMINUM DOOR & WINDOW WORK | 2221021 | 2221021 | 0 | 2221021 | 2221021
B 1901 MISC WORK | 714336 | 714336 | 211173.72 | 503162.28 | 503162.28
B 1902 | 6032964 | 6032964 | 0 | 6032964 | 6032964
B 1902 WATERPROOFING WORK | 425000 | 425000 | 67968 | 357032 | 357032
B 1902 PLUMBING WORK | 950000 | 950000 | 89354.58 | 860645.42 | 860645.42
B 1902 ELECTRICAL WORK | 284117 | 284117 | 153295.43 | 130821.57 | 130821.57
B 1902 FLOORING & DEDO WORK | 1150000 | 1150000 | 288894.38 | 861105.62 | 861105.62
B 1902 CARPENTRY WORK | 288490 | 288490 | 278016.26 | 10473.74 | 10473.74
B 1902 ALUMINUM WORK | 2221021 | 2221021 | 0 | 2221021 | 2221021
B 1902 MISC WORK | 714336 | 714336 | 211173.72 | 503162.28 | 503162.28
TOWER B 19TH FLOOR COMMON WORK | 632525 | 632525 | 616966.33 | 15558.67 | 15558.67
TOWER B TERRACE | 11063958 | 11063958 | 0 | 11063958 | 11063958
TOWER B TERRACE CIVIL WORK | 8704433 | 8704433 | 1822246.91 | 6882186.09 | 6882186.09
TOWER B TERRACE COMMON WORK | 2359525 | 2359525 | 1929342.07 | 430182.93 | 430182.93
TOWER B COMMON WORK | 16074056 | 16074056 | 0 | 16074056 | 16074056
TOWER B COMMON WATERPROOFING WORK | 407660 | 407660 | 0 | 407660 | 407660
TOWER B COMMON ELECTRIC WORK | 1465832 | 1465832 | 65348.21 | 1400483.79 | 1400483.79
TOWER B COMMON FLOORING & DEDO WORK | 3210024 | 3210024 | 885288.83 | 2324735.17 | 2324735.17
TOWER B COMMON MISC WORK | 10990540 | 10990540 | 10960567.91 | 29972.09 | 29972.09
TOWER C | 405962373.46 | 405962373.46 | 0 | 402962373.46 | 405962373.46
TOWER C UP TO PLINTH | 11751958 | 11751958 | 0 | 11751958 | 11751958
TOWER C UP TO PLINTH CIVIL WORK | 8704433 | 8704433 | 5836046.36 | 2868386.64 | 2868386.64
TOWER C UP TO PLINTH COMMON WORK | 3047525 | 3047525 | 115119.09 | 2932405.91 | 2932405.91
TOWER C GROUND FLOOR PARKING | 9451958 | 9451958 | 0 | 9451958 | 9451958
TOWER C GROUND FLOOR CIVIL WORK | 8704433 | 8704433 | 3205488.86 | 5498944.14 | 5498944.14
TOWER C GROUND FLOOR COMMON WORK | 747525 | 747525 | 613729.57 | 133795.43 | 133795.43
TOWER C 1ST FLOOR | 17909886 | 17909886 | 0 | 17909886 | 17909886
TOWER C 1ST FLOOR CIVIL WORK | 8704433 | 8704433 | 3087490.68 | 5616942.32 | 5616942.32
C 101 | 4258964 | 4258964 | 0 | 4258964 | 4258964
C 101 WATERPROOFING WORK | 195000 | 195000 | 168076.72 | 26923.28 | 26923.28
C 101 PLUMBING WORK | 950000 | 950000 | 536538.56 | 413461.44 | 413461.44
C 101 ELECTRICAL WORK | 334117 | 334117 | 204130.72 | 129986.28 | 129986.28
C 101 FLOORING & DEDO WORK | 1200000 | 1200000 | 1142144.54 | 57855.46 | 57855.46
C 101 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 101 ALUMINUM DOOR & WINDOW WORK | 607021 | 607021 | 593425.75 | 13595.25 | 13595.25
C 101 MISC WORK | 714336 | 714336 | 345729.5 | 368606.5 | 368606.5
C 102 | 4278964 | 0 | 0 | 0 | 4278964
C 102 WATERPROOFING WORK | 195000 | 195000 | 178858.49 | 16141.51 | 16141.51
C 102 PLUMBING WORK | 950000 | 950000 | 514456.14 | 435543.86 | 435543.86
C 102 ELECTRICAL WORK | 284117 | 284117 | 197232.84 | 86884.16 | 86884.16
C 102 FLOORING & DEDO WORK | 1200000 | 1200000 | 1098128.9 | 101871.1 | 101871.1
C 102 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 102 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 102 MISC WORK | 714336 | 714336 | 422773.12 | 291562.88 | 291562.88
TOWER C 1ST FLOOR COMMON WORK | 667525 | 667525 | 660394.67 | 7130.33 | 7130.33
TOWER C 2ND FLOOR | 17794886 | 17794886 | 0 | 17794886 | 17794886
TOWER C 2ND FLOOR CIVIL WORK | 8704433 | 8704433 | 3337769.96 | 5366663.04 | 5366663.04
C 201 | 4248964 | 4248964 | 0 | 4248964 | 4248964
C 201 WATERPROOFING WORK | 195000 | 195000 | 166751.72 | 28248.28 | 28248.28
C 201 PLUMBING WORK | 950000 | 950000 | 497765.7 | 452234.3 | 452234.3
C 201 ELECTRICAL WORK | 334117 | 334117 | 204557.88 | 129559.12 | 129559.12
C 201 FLOORING & DEDO WORK | 1215000 | 1215000 | 1182798.14 | 32201.86 | 32201.86
C 201 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 201 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 201 MISC WORK | 714336 | 714336 | 427653.6 | 286682.4 | 286682.4
C 202 | 4268964 | 4268964 | 0 | 4268964 | 4268964
C 202 WATERPROOFING WORK | 195000 | 195000 | 173008.49 | 21991.51 | 21991.51
C 202 PLUMBING WORK | 950000 | 950000 | 502521.03 | 447478.97 | 447478.97
C 202 ELECTRICAL WORK | 334117 | 334117 | 204557.88 | 129559.12 | 129559.12
C 202 FLOORING & DEDO WORK | 1215000 | 1215000 | 1184668.14 | 30331.86 | 30331.86
C 202 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 202 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 202 MISC WORK | 714336 | 714336 | 450342.64 | 263993.36 | 263993.36
TOWER C 2ND FLOOR COMMON WORK | 572525 | 572525 | 565341.96 | 7183.04 | 7183.04
TOWER C 3RD FLOOR | 17754886 | 17754886 | 0 | 17754886 | 17754886
TOWER C 3RD FLOOR CIVIL WORK | 8704433 | 8704433 | 3437883.12 | 5266549.88 | 5266549.88
C 301 | 4188964 | 0 | 0 | 0 | 4188964
C 301 WATERPROOFING WORK | 200000 | 200000 | 187538.32 | 12461.68 | 12461.68
C 301 PLUMBING WORK | 950000 | 950000 | 384731.46 | 565268.54 | 565268.54
C 301 ELECTRICAL WORK | 284117 | 284117 | 65879.5 | 218237.5 | 218237.5
C 301 FLOORING & DEDO WORK | 1200000 | 1200000 | 1023847.01 | 176152.99 | 176152.99
C 301 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 301 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 301 MISC WORK | 714336 | 714336 | 419744.3 | 294591.7 | 294591.7
C 302 | 4253964 | 0 | 0 | 0 | 4253964
C 302 WATERPROOFING WORK | 195000 | 195000 | 180108.49 | 14891.51 | 14891.51
C 302 PLUMBING WORK | 950000 | 950000 | 504679.58 | 445320.42 | 445320.42
C 302 ELECTRICAL WORK | 334117 | 334117 | 195176.88 | 138940.12 | 138940.12
C 302 FLOORING & DEDO WORK | 1200000 | 1200000 | 1164266.14 | 35733.86 | 35733.86
C 302 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 302 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 302 MISC WORK | 714336 | 714336 | 467832.6 | 246503.4 | 246503.4
TOWER C 3RD FLOOR COMMON WORK | 607525 | 607525 | 604807.99 | 2717.01 | 2717.01
TOWER C 4TH FLOOR | 18015886 | 18015886 | 0 | 18015886 | 18015886
TOWER C 4TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3536159.84 | 5168273.16 | 5168273.16
C 401 | 4348964 | 4348964 | 0 | 4348964 | 4348964
C 401 WATERPROOFING WORK | 195000 | 195000 | 169759.96 | 25240.04 | 25240.04
C 401 PLUMBING WORK | 950000 | 950000 | 409466.66 | 540533.34 | 540533.34
C 401 ELECTRICAL WORK | 434117 | 434117 | 243323.82 | 190793.18 | 190793.18
C 401 FLOORING & DEDO WORK | 1215000 | 1215000 | 1212591.67 | 2408.33 | 2408.33
C 401 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 401 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 401 MISC WORK | 714336 | 714336 | 432136.42 | 282199.58 | 282199.58
C 402 | 4284964 | 4284964 | 0 | 4284964 | 4284964
C 402 WATERPROOFING WORK | 195000 | 195000 | 179125.38 | 15874.62 | 15874.62
C 402 PLUMBING WORK | 950000 | 950000 | 303413.55 | 646586.45 | 646586.45
C 402 ELECTRICAL WORK | 339117 | 339117 | 179970.52 | 159146.48 | 159146.48
C 402 FLOORING & DEDO WORK | 1226000 | 1226000 | 1224321.79 | 1678.21 | 1678.21
C 402 CARPENTRY WORK | 258490 | 258490 | 202492.86 | 55997.14 | 55997.14
C 402 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 402 MISC WORK | 714336 | 714336 | 459541.92 | 254794.08 | 254794.08
TOWER C 4TH FLOOR COMMON WORK | 677525 | 677525 | 625484.45 | 52040.55 | 52040.55
TOWER C 5TH FLOOR | 18299886 | 18284886 | 0 | 18284886 | 18299886
TOWER C 5TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3508050.66 | 5196382.34 | 5196382.34
C 501 | 4428964 | 4428964 | 0 | 4428964 | 4428964
C 501 WATERPROOFING WORK | 210000 | 210000 | 190457.56 | 19542.44 | 19542.44
C 501 PLUMBING WORK | 950000 | 950000 | 420100.56 | 529899.44 | 529899.44
C 501 ELECTRICAL WORK | 464117 | 464117 | 318092.4 | 146024.6 | 146024.6
C 501 FLOORING & DEDO WORK | 1250000 | 1250000 | 1241025.77 | 8974.23 | 8974.23
C 501 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
C 501 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 501 MISC WORK | 714336 | 714336 | 421912.9 | 292423.1 | 292423.1
C 502 | 4498964 | 4498964 | 0 | 4498964 | 4498964
C 502 WATERPROOFING WORK | 210000 | 210000 | 199822.98 | 10177.02 | 10177.02
C 502 PLUMBING WORK | 950000 | 950000 | 419888.16 | 530111.84 | 530111.84
C 502 ELECTRICAL WORK | 444117 | 444117 | 303211.69 | 140905.31 | 140905.31
C 502 FLOORING & DEDO WORK | 1235000 | 1235000 | 1217447.84 | 17552.16 | 17552.16
C 502 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
C 502 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 502 MISC WORK | 714336 | 714336 | 441028.9 | 273307.1 | 273307.1
TOWER C 5TH FLOOR COMMON WORK | 667525 | 667525 | 624549.95 | 42975.05 | 42975.05
TOWER C 6TH FLOOR | 17899886 | 17899886 | 0 | 17899886 | 17899886
TOWER C 6TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3650082.75 | 5054350.25 | 5054350.25
C 601 | 4293964 | 4293964 | 0 | 4293964 | 4293964
C 601 WATERPROOFING WORK | 195000 | 195000 | 178779.43 | 16220.57 | 16220.57
C 601 PLUMBING WORK | 950000 | 950000 | 319789.21 | 630210.79 | 630210.79
C 601 ELECTRICAL WORK | 349117 | 349117 | 202240.72 | 146876.28 | 146876.28
C 601 FLOORING & DEDO WORK | 1245000 | 1245000 | 1231981.75 | 13018.25 | 13018.25
C 601 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
C 601 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 601 MISC WORK | 714336 | 714336 | 391718.82 | 322617.18 | 322617.18
C 602 | 4253964 | 0 | 0 | 0 | 4253964
C 602 WATERPROOFING WORK | 195000 | 195000 | 170451.93 | 24548.07 | 24548.07
C 602 PLUMBING WORK | 950000 | 950000 | 315266.74 | 634733.26 | 634733.26
C 602 ELECTRICAL WORK | 334117 | 334117 | 206121.51 | 127995.49 | 127995.49
C 602 FLOORING & DEDO WORK | 1200000 | 1200000 | 1183867 | 16133 | 16133
C 602 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
C 602 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 602 MISC WORK | 714336 | 714336 | 410995.3 | 303340.7 | 303340.7
TOWER C 6TH FLOOR COMMON WORK | 647525 | 647525 | 615509.45 | 32015.55 | 32015.55
TOWER C 7TH FLOOR | 18340886 | 18340886 | 0 | 18340886 | 18340886
TOWER C 7TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3955074.1 | 4749358.9 | 4749358.9
C 701 | 4465964 | 4465964 | 0 | 4465964 | 4465964
C 701 WATERPROOFING WORK | 195000 | 195000 | 186588.33 | 8411.67 | 8411.67
C 701 PLUMBING WORK | 950000 | 950000 | 451883.34 | 498116.66 | 498116.66
C 701 ELECTRICAL WORK | 449117 | 449117 | 306189.61 | 142927.39 | 142927.39
C 701 FLOORING & DEDO WORK | 1277000 | 1277000 | 1251667.14 | 25332.86 | 25332.86
C 701 CARPENTRY WORK | 258490 | 258490 | 203228.02 | 55261.98 | 55261.98
C 701 ALUMINUM DOOR & WINDOW WORK | 603021 | 603021 | 601978.76 | 1042.24 | 1042.24
C 701 MISC WORK | 714336 | 714336 | 533350.92 | 180985.08 | 180985.08
C 702 | 4481964 | 4481964 | 0 | 4481964 | 4481964
C 702 WATERPROOFING WORK | 195000 | 195000 | 178212.62 | 16787.38 | 16787.38
C 702 PLUMBING WORK | 950000 | 950000 | 446429.81 | 503570.19 | 503570.19
C 702 ELECTRICAL WORK | 449117 | 449117 | 308143.06 | 140973.94 | 140973.94
C 702 FLOORING & DEDO WORK | 1292000 | 1292000 | 1263978.88 | 28021.12 | 28021.12
C 702 CARPENTRY WORK | 258490 | 258490 | 202941.61 | 55548.39 | 55548.39
C 702 ALUMINUM DOOR & WINDOW WORK | 623021 | 623021 | 621070.87 | 1950.13 | 1950.13
C 702 MISC WORK | 714336 | 714336 | 551965.42 | 162370.58 | 162370.58
TOWER C 7TH FLOOR COMMON WORK | 667525 | 667525 | 661779.99 | 5745.01 | 5745.01
TOWER C 8TH FLOOR | 18141244 | 18141244 | 0 | 18141244 | 18141244
TOWER C 8TH FLOOR CIVIL WORK | 8704433 | 8704433 | 3814944.18 | 4889488.82 | 4889488.82
C 801 | 4449322 | 4449322 | 0 | 4449322 | 4449322
C 801 WATERPROOFING WORK | 195000 | 195000 | 179673.92 | 15326.08 | 15326.08
C 801 PLUMBING WORK | 950000 | 950000 | 241315.74 | 708684.26 | 708684.26
C 801 ELECTRICAL WORK | 529475 | 529475 | 299475.18 | 229999.82 | 229999.82
C 801 FLOORING & DEDO WORK | 1220000 | 1220000 | 1190982.71 | 29017.29 | 29017.29
C 801 CARPENTRY WORK | 258490 | 258490 | 202723.31 | 55766.69 | 55766.69
C 801 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 801 MISC WORK | 714336 | 714336 | 416389.32 | 297946.68 | 297946.68
C 802 | 4349964 | 4349964 | 0 | 4349964 | 4349964
C 802 WATERPROOFING WORK | 195000 | 195000 | 171273.21 | 23726.79 | 23726.79
C 802 PLUMBING WORK | 950000 | 950000 | 349486.01 | 600513.99 | 600513.99
C 802 ELECTRICAL WORK | 399117 | 399117 | 299475.18 | 99641.82 | 99641.82
C 802 FLOORING & DEDO WORK | 1226000 | 1226000 | 1197714.35 | 28285.65 | 28285.65
C 802 CARPENTRY WORK | 258490 | 258490 | 202723.31 | 55766.69 | 55766.69
C 802 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 802 MISC WORK | 714336 | 714336 | 434823.28 | 279512.72 | 279512.72
TOWER C 8TH FLOOR COMMON WORK | 637525 | 637525 | 589350.96 | 48174.04 | 48174.04
TOWER C 9TH FLOOR | 17854886 | 17854886 | 0 | 17854886 | 17854886
TOWER C 9TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4116393.15 | 4588039.85 | 4588039.85
C 901 | 4293964 | 0 | 0 | 0 | 4293964
C 901 WATERPROOFING WORK | 195000 | 195000 | 179673.92 | 15326.08 | 15326.08
C 901 PLUMBING WORK | 950000 | 950000 | 239789.06 | 710210.94 | 710210.94
C 901 ELECTRICAL WORK | 444117 | 444117 | 333850.91 | 110266.09 | 110266.09
C 901 FLOORING & DEDO WORK | 1150000 | 1150000 | 1088803.1 | 61196.9 | 61196.9
C 901 CARPENTRY WORK | 258490 | 258490 | 202723.31 | 55766.69 | 55766.69
C 901 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 901 MISC WORK | 714336 | 714336 | 410386.42 | 303949.58 | 303949.58
C 902 | 4228964 | 0 | 0 | 0 | 4228964
C 902 WATERPROOFING WORK | 195000 | 195000 | 171273.21 | 23726.79 | 23726.79
C 902 PLUMBING WORK | 950000 | 950000 | 219576.96 | 730423.04 | 730423.04
C 902 ELECTRICAL WORK | 359117 | 359117 | 127204.09 | 231912.91 | 231912.91
C 902 FLOORING & DEDO WORK | 1150000 | 1150000 | 800797.21 | 349202.79 | 349202.79
C 902 CARPENTRY WORK | 258490 | 258490 | 202723.31 | 55766.69 | 55766.69
C 902 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 902 MISC WORK | 714336 | 714336 | 429192.08 | 285143.92 | 285143.92
TOWER C 9TH FLOOR COMMON WORK | 627525 | 627525 | 625217.24 | 2307.76 | 2307.76
TOWER C 10TH FLOOR | 18190218 | 18190218 | 0 | 18190218 | 18190218
TOWER C 10TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6226652.16 | 2477780.84 | 2477780.84
C 1001 | 4500525 | 4500525 | 0 | 4500525 | 4500525
C 1001 WATERPROOFING WORK | 195000 | 195000 | 178779.43 | 16220.57 | 16220.57
C 1001 PLUMBING WORK | 950000 | 950000 | 252676.09 | 697323.91 | 697323.91
C 1001 ELECTRICAL WORK | 450678 | 450678 | 402688.54 | 47989.46 | 47989.46
C 1001 FLOORING & DEDO WORK | 1350000 | 1350000 | 1174928.1 | 175071.9 | 175071.9
C 1001 CARPENTRY WORK | 258490 | 258490 | 202723.31 | 55766.69 | 55766.69
C 1001 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1001 MISC WORK | 714336 | 714336 | 421274.52 | 293061.48 | 293061.48
C 1002 | 4356991.73 | 4356991.73 | 0 | 4356991.73 | 4356991.73
C 1002 WATERPROOFING WORK | 195000 | 195000 | 170451.93 | 24548.07 | 24548.07
C 1002 PLUMBING WORK | 950000 | 950000 | 252676.09 | 697323.91 | 697323.91
C 1002 ELECTRICAL WORK | 402888 | 402888 | 397012.74 | 5875.26 | 5875.26
C 1002 FLOORING & DEDO WORK | 1150000 | 1150000 | 1145125.9 | 4874.1 | 4874.1
C 1002 CARPENTRY WORK | 258490 | 258490 | 202723.31 | 55766.69 | 55766.69
C 1002 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 1002 MISC WORK | 714336 | 714336 | 439548 | 274788 | 274788
TOWER C 10TH FLOOR COMMON WORK | 627525 | 627525 | 619651.88 | 7873.12 | 7873.12
TOWER C 11TH FLOOR | 18640780 | 18640780 | 0 | 18640780 | 18640780
TOWER C 11TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4946444.2 | 3757988.8 | 3757988.8
C 1101 | 4376911 | 4376911 | 0 | 4376911 | 4376911
C 1101 WATERPROOFING WORK | 195000 | 195000 | 158901.28 | 36098.72 | 36098.72
C 1101 PLUMBING WORK | 950000 | 950000 | 184133.65 | 765866.35 | 765866.35
C 1101 ELECTRICAL WORK | 407064 | 407064 | 346269.66 | 60794.34 | 60794.34
C 1101 FLOORING & DEDO WORK | 1245000 | 1245000 | 1214833.22 | 30166.78 | 30166.78
C 1101 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1101 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1101 MISC WORK | 714336 | 714336 | 389801.32 | 324534.68 | 324534.68
C 1102 | 4371911 | 4371911 | 0 | 4371911 | 4371911
C 1102 WATERPROOFING WORK | 195000 | 195000 | 150525.59 | 44474.41 | 44474.41
C 1102 PLUMBING WORK | 950000 | 950000 | 215892.33 | 734107.67 | 734107.67
C 1102 ELECTRICAL WORK | 407064 | 407064 | 360305.64 | 46758.36 | 46758.36
C 1102 FLOORING & DEDO WORK | 1245000 | 1245000 | 1241497.09 | 3502.91 | 3502.91
C 1102 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1102 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 1102 MISC WORK | 714336 | 714336 | 443388.9 | 270947.1 | 270947.1
TOWER C 11TH FLOOR COMMON WORK | 1187525 | 1187525 | 1184132.59 | 3392.41 | 3392.41
TOWER C 12TH FLOOR | 17854886 | 17854886 | 0 | 17854886 | 17854886
TOWER C 12TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6769623.34 | 1934809.66 | 1934809.66
C 1201 | 4198964 | 4198964 | 0 | 4198964 | 4198964
C 1201 WATERPROOFING WORK | 195000 | 195000 | 159672.54 | 35327.46 | 35327.46
C 1201 PLUMBING WORK | 950000 | 950000 | 175139.91 | 774860.09 | 774860.09
C 1201 ELECTRICAL WORK | 319117 | 319117 | 146940.32 | 172176.68 | 172176.68
C 1201 FLOORING & DEDO WORK | 1180000 | 1180000 | 1155041.07 | 24958.93 | 24958.93
C 1201 CARPENTRY WORK | 258490 | 258490 | 198779.26 | 59710.74 | 59710.74
C 1201 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1201 MISC WORK | 714336 | 714336 | 402688.1 | 311647.9 | 311647.9
C 1202 | 4228964 | 4228964 | 0 | 4228964 | 4228964
C 1202 WATERPROOFING WORK | 187500 | 187500 | 151345.04 | 36154.96 | 36154.96
C 1202 PLUMBING WORK | 950000 | 950000 | 168670.01 | 781329.99 | 781329.99
C 1202 ELECTRICAL WORK | 319117 | 319117 | 146940.32 | 172176.68 | 172176.68
C 1202 FLOORING & DEDO WORK | 1190000 | 1190000 | 1161325.7 | 28674.3 | 28674.3
C 1202 CARPENTRY WORK | 258490 | 258490 | 198779.26 | 59710.74 | 59710.74
C 1202 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 1202 MISC WORK | 714336 | 714336 | 421674.3 | 292661.7 | 292661.7
TOWER C 12TH FLOOR COMMON WORK | 697525 | 697525 | 682206.65 | 15318.35 | 15318.35
TOWER C 13TH FLOOR | 18054886 | 18054886 | 0 | 18054886 | 18054886
TOWER C 13TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6741812.2 | 1962620.8 | 1962620.8
C 1301 | 4174964 | 4174964 | 0 | 4174964 | 4174964
C 1301 WATERPROOFING WORK | 202500 | 202500 | 167867.04 | 34632.96 | 34632.96
C 1301 PLUMBING WORK | 942500 | 942500 | 190317.51 | 752182.49 | 752182.49
C 1301 ELECTRICAL WORK | 304117 | 304117 | 161131.25 | 142985.75 | 142985.75
C 1301 FLOORING & DEDO WORK | 1150000 | 1150000 | 1129275.79 | 20724.21 | 20724.21
C 1301 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1301 ALUMINUM DOOR & WINDOW WORK | 603021 | 603021 | 601978.76 | 1042.24 | 1042.24
C 1301 MISC WORK | 714336 | 714336 | 514381 | 199955 | 199955
C 1302 | 4371879 | 4371879 | 0 | 4371879 | 4371879
C 1302 WATERPROOFING WORK | 195000 | 195000 | 159491.35 | 35508.65 | 35508.65
C 1302 PLUMBING WORK | 950000 | 950000 | 167326.55 | 782673.45 | 782673.45
C 1302 ELECTRICAL WORK | 416032 | 416032 | 362364.18 | 53667.82 | 53667.82
C 1302 FLOORING & DEDO WORK | 1215000 | 1215000 | 1194773.73 | 20226.27 | 20226.27
C 1302 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1302 ALUMINUM DOOR & WINDOW WORK | 623021 | 623021 | 621070.87 | 1950.13 | 1950.13
C 1302 MISC WORK | 714336 | 714336 | 563517.62 | 150818.38 | 150818.38
TOWER C 13TH FLOOR COMMON WORK | 717525 | 717525 | 671069.05 | 46455.95 | 46455.95
TOWER C 14TH FLOOR | 18246301.46 | 18246301.46 | 0 | 18246301.46 | 18246301.46
TOWER C 14TH FLOOR CIVIL WORK | 8713433 | 8713433 | 6928400.86 | 1785032.14 | 1785032.14
C 1401 | 4530155.46 | 4530155.46 | 0 | 4530155.46 | 4530155.46
C 1401 WATERPROOFING WORK | 195000 | 195000 | 158253.29 | 36746.71 | 36746.71
C 1401 PLUMBING WORK | 950000 | 950000 | 212959.67 | 737040.33 | 737040.33
C 1401 ELECTRICAL WORK | 395341 | 395341 | 363725.19 | 31615.81 | 31615.81
C 1401 FLOORING & DEDO WORK | 1434967.46 | 1434967.46 | 1412661.36 | 22306.1 | 22306.1
C 1401 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1401 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1401 MISC WORK | 714336 | 714336 | 446085.2 | 268250.8 | 268250.8
C 1402 | 4325188 | 4325188 | 0 | 4325188 | 4325188
C 1402 WATERPROOFING WORK | 195000 | 195000 | 149900.77 | 45099.23 | 45099.23
C 1402 PLUMBING WORK | 950000 | 950000 | 190172.54 | 759827.46 | 759827.46
C 1402 ELECTRICAL WORK | 395341 | 395341 | 363725.19 | 31615.81 | 31615.81
C 1402 FLOORING & DEDO WORK | 1210000 | 1210000 | 1185920.92 | 24079.08 | 24079.08
C 1402 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1402 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 1402 MISC WORK | 714336 | 714336 | 465040.72 | 249295.28 | 249295.28
TOWER C 14TH FLOOR COMMON WORK | 657525 | 657525 | 611845.63 | 45679.37 | 45679.37
TOWER C 15TH FLOOR | 18168314 | 18168314 | 0 | 18168314 | 18168314
TOWER C 15TH FLOOR CIVIL WORK | 8704433 | 8704433 | 6512260.08 | 2192172.92 | 2192172.92
C 1501 | 4471051 | 4471051 | 0 | 4471051 | 4471051
C 1501 WATERPROOFING WORK | 195000 | 195000 | 158253.29 | 36746.71 | 36746.71
C 1501 PLUMBING WORK | 950000 | 950000 | 191799.33 | 758200.67 | 758200.67
C 1501 ELECTRICAL WORK | 401204 | 401204 | 370264.14 | 30939.86 | 30939.86
C 1501 FLOORING & DEDO WORK | 1370000 | 1370000 | 1079863.2 | 290136.8 | 290136.8
C 1501 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1501 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1501 MISC WORK | 714336 | 714336 | 448873.3 | 265462.7 | 265462.7
C 1502 | 4265305 | 4265305 | 0 | 4265305 | 4265305
C 1502 WATERPROOFING WORK | 195000 | 195000 | 149900.77 | 45099.23 | 45099.23
C 1502 PLUMBING WORK | 950000 | 950000 | 203633.35 | 746366.65 | 746366.65
C 1502 ELECTRICAL WORK | 395458 | 395458 | 364798.61 | 30659.39 | 30659.39
C 1502 FLOORING & DEDO WORK | 1150000 | 1150000 | 1071400.87 | 78599.13 | 78599.13
C 1502 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1502 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 1502 MISC WORK | 714336 | 714336 | 510213.45 | 204122.55 | 204122.55
TOWER C 15TH FLOOR COMMON WORK | 717525 | 717525 | 669267.66 | 48257.34 | 48257.34
TOWER C 16TH FLOOR | 18165839 | 18165839 | 0 | 18165839 | 18165839
TOWER C 16TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5973585.14 | 2730847.86 | 2730847.86
C 1601 | 4511941 | 4511941 | 0 | 4511941 | 4511941
C 1601 WATERPROOFING WORK | 195000 | 195000 | 161407.84 | 33592.16 | 33592.16
C 1601 PLUMBING WORK | 950000 | 950000 | 194283.87 | 755716.13 | 755716.13
C 1601 ELECTRICAL WORK | 412094 | 412094 | 410535.74 | 1558.26 | 1558.26
C 1601 FLOORING & DEDO WORK | 1400000 | 1400000 | 996893.92 | 403106.08 | 403106.08
C 1601 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1601 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1601 MISC WORK | 714336 | 714336 | 461506.62 | 252829.38 | 252829.38
C 1602 | 4331940 | 4331940 | 0 | 4331940 | 4331940
C 1602 WATERPROOFING WORK | 195000 | 195000 | 153032.15 | 41967.85 | 41967.85
C 1602 PLUMBING WORK | 950000 | 950000 | 197850.92 | 752149.08 | 752149.08
C 1602 ELECTRICAL WORK | 412093 | 412093 | 410535.74 | 1557.26 | 1557.26
C 1602 FLOORING & DEDO WORK | 1200000 | 1200000 | 961360.31 | 238639.69 | 238639.69
C 1602 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1602 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 597900.68 | 4120.32 | 4120.32
C 1602 MISC WORK | 714336 | 714336 | 479472.12 | 234863.88 | 234863.88
TOWER C 16TH FLOOR COMMON WORK | 617525 | 617525 | 606393.36 | 11131.64 | 11131.64
TOWER C 17TH FLOOR | 17893160 | 17893160 | 0 | 17893160 | 17893160
TOWER C 17TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5591372.34 | 3113060.66 | 3113060.66
C 1701 | 4262804 | 4262804 | 0 | 4262804 | 4262804
C 1701 WATERPROOFING WORK | 195000 | 195000 | 161407.84 | 33592.16 | 33592.16
C 1701 PLUMBING WORK | 950000 | 950000 | 148496.85 | 801503.15 | 801503.15
C 1701 ELECTRICAL WORK | 412957 | 412957 | 411398.55 | 1558.45 | 1558.45
C 1701 FLOORING & DEDO WORK | 1150000 | 1150000 | 961441.12 | 188558.88 | 188558.88
C 1701 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1701 ALUMINUM DOOR & WINDOW WORK | 582021 | 582021 | 581277.73 | 743.27 | 743.27
C 1701 MISC WORK | 714336 | 714336 | 468774.24 | 245561.76 | 245561.76
C 1702 | 4282398 | 4282398 | 0 | 4282398 | 4282398
C 1702 WATERPROOFING WORK | 195000 | 195000 | 153032.15 | 41967.85 | 41967.85
C 1702 PLUMBING WORK | 950000 | 950000 | 144353.96 | 805646.04 | 805646.04
C 1702 ELECTRICAL WORK | 413551 | 413551 | 411993.27 | 1557.73 | 1557.73
C 1702 FLOORING & DEDO WORK | 1150000 | 1150000 | 910889.47 | 239110.53 | 239110.53
C 1702 CARPENTRY WORK | 258490 | 258490 | 210579.26 | 47910.74 | 47910.74
C 1702 ALUMINUM DOOR & WINDOW WORK | 602021 | 602021 | 581277.73 | 20743.27 | 20743.27
C 1702 MISC WORK | 713336 | 713336 | 487388.74 | 225947.26 | 225947.26
TOWER C 17TH FLOOR COMMON WORK | 642525 | 642525 | 628100.39 | 14424.61 | 14424.61
TOWER C 18TH FLOOR | 20697886 | 20697886 | 0 | 20697886 | 20697886
TOWER C 18TH FLOOR CIVIL WORK | 8704433 | 8704433 | 5231822.97 | 3472610.03 | 3472610.03
C 1801 | 5682964 | 5682964 | 0 | 5682964 | 5682964
C 1801 WATERPROOFING WORK | 205000 | 205000 | 178747 | 26253 | 26253
C 1801 PLUMBING WORK | 950000 | 950000 | 154283.05 | 795716.95 | 795716.95
C 1801 ELECTRICAL WORK | 384117 | 384117 | 137449.97 | 246667.03 | 246667.03
C 1801 FLOORING & DEDO WORK | 1150000 | 1150000 | 152950 | 997050 | 997050
C 1801 CARPENTRY WORK | 258490 | 258490 | 244091.26 | 14398.74 | 14398.74
C 1801 ALUMINUM DOOR & WINDOW WORK | 521021 | 0 | 0 | 0 | 521021
C 1801 MISC WORK | 714336 | 714336 | 405291.42 | 309044.58 | 309044.58
C 1802 | 5692964 | 5692964 | 0 | 5692964 | 5692964
C 1802 WATERPROOFING WORK | 205000 | 205000 | 178747 | 26253 | 26253
C 1802 PLUMBING WORK | 950000 | 950000 | 155222.89 | 794777.11 | 794777.11
C 1802 ELECTRICAL WORK | 384117 | 384117 | 173939.22 | 210177.78 | 210177.78
C 1802 FLOORING & DEDO WORK | 1150000 | 1150000 | 743078.28 | 406921.72 | 406921.72
C 1802 CARPENTRY WORK | 258490 | 258490 | 244091.26 | 14398.74 | 14398.74
C 1802 ALUMINUM DOOR & WINDOW WORK | 2021021 | 2021021 | 16622.95 | 2004398.05 | 2004398.05
C 1802 MISC WORK | 714336 | 714336 | 422725.92 | 291610.08 | 291610.08
TOWER C 18TH FLOOR COMMON WORK | 617525 | 617525 | 605013.35 | 12511.65 | 12511.65
TOWER C 19TH FLOOR | 23087886 | 23087886 | 0 | 23087886 | 23087886
TOWER C 19TH FLOOR CIVIL WORK | 8704433 | 8704433 | 4553033.95 | 4151399.05 | 4151399.05
C 1901 | 5972964 | 5972964 | 0 | 5972964 | 5972964
C 1901 WATERPROOFING WORK | 355000 | 355000 | 249780.93 | 105219.07 | 105219.07
C 1901 PLUMBING WORK | 950000 | 950000 | 153457.56 | 796542.44 | 796542.44
C 1901 ELECTRICAL WORK | 284117 | 284117 | 70767.37 | 213349.63 | 213349.63
C 1901 FLOORING & DEDO WORK | 1150000 | 1150000 | 172654.4 | 977345.6 | 977345.6
C 1901 CARPENTRY WORK | 298490 | 298490 | 294978.76 | 3511.24 | 3511.24
C 1901 ALUMINUM DOOR & WINDOW WORK | 2221021 | 2221021 | 0 | 2221021 | 2221021
C 1901 MISC WORK | 714336 | 714336 | 340348.7 | 373987.3 | 373987.3
C 1902 | 7792964 | 7792964 | 0 | 7792964 | 7792964
C 1902 WATERPROOFING WORK | 355000 | 355000 | 249780.93 | 105219.07 | 105219.07
C 1902 PLUMBING WORK | 950000 | 950000 | 385823.56 | 564176.44 | 564176.44
C 1902 ELECTRICAL WORK | 284117 | 284117 | 112669.12 | 171447.88 | 171447.88
C 1902 FLOORING & DEDO WORK | 1150000 | 1150000 | 631905.37 | 518094.63 | 518094.63
C 1902 CARPENTRY WORK | 318490 | 318490 | 306778.76 | 11711.24 | 11711.24
C 1902 ALUMINUM DOOR & WINDOW WORK | 4021021 | 4021021 | 1671617.49 | 2349403.51 | 2349403.51
C 1902 MISC WORK | 714336 | 714336 | 388682.92 | 325653.08 | 325653.08
TOWER C 19TH FLOOR COMMON WORK | 617525 | 617525 | 607498.18 | 10026.82 | 10026.82
TOWER C TERRACE | 13091881 | 13091881 | 0 | 13091881 | 13091881
TOWER C TERRACE CIVIL WORK | 8704433 | 8704433 | 1234220.71 | 7470212.29 | 7470212.29
TOWER C TERRACE COMMON WORK | 4387448 | 4387448 | 2385874.66 | 2001573.34 | 2001573.34
TOWER C COMMON WORK | 20632065 | 20632065 | 0 | 20632065 | 20632065
TOWER C COMMON WATERPROOFING WORK | 407660 | 407660 | 0 | 407660 | 407660
TOWER C COMMON ELECTRIC WORK | 1585832 | 1585832 | 1571903.71 | 13928.29 | 13928.29
TOWER C COMMON FLOORING & DEDO WORK | 3210024 | 3210024 | 867164.03 | 2342859.97 | 2342859.97
TOWER C COMMON MISC WORK | 15428549 | 15428549 | 15264855.38 | 163693.62 | 163693.62
ASPIRE OFFICE | 1000000 | 1000000 | 70746.57 | 929253.43 | 929253.43
CLUB HOUSE | 30819001 | 30819001 | 0 | 30819001 | 30819001
CLUB HOUSE CIVIL WORK | 4875429 | 4875429 | 4155139.18 | 720289.82 | 720289.82
CLUB HOUSE FLOORING & DEDO WORK | 3093908 | 3093908 | 3035488.37 | 58419.63 | 58419.63
CLUB HOUSE PLUMBING WORK | 1772500 | 1772500 | 518165.78 | 1254334.22 | 1254334.22
CLUB HOUSE ELECTRIC WORK | 3672500 | 3672500 | 3525494.07 | 147005.93 | 147005.93
CLUB HOUSE AIR CONDITIONING / HVAC | 1624986 | 1624986 | 1212607.62 | 412378.38 | 412378.38
CLUB HOUSE MISC WORK | 15779678 | 15779678 | 15560259.31 | 219418.69 | 219418.69
COMMON WORK | 126752956 | 126752956 | 0 | 19703212.5 | 126752956
COMMON CIVIL WORK | 9430493 | 9430493 | 8799883.37 | 630609.63 | 630609.63
COMMON PLUMBING WORK | 11692684 | 11692684 | 8720386.83 | 2972297.17 | 2972297.17
COMMON ELECTRIC WORK | 37131430 | 37131430 | 22749404.1 | 14382025.9 | 14382025.9
COMMON FIRE & SAFETY WORK | 19470691 | 19470691 | 12337272.88 | 7133418.12 | 7133418.12
COMMON DG SET | 3450000 | 3450000 | 0 | 3450000 | 3450000
CONSULTANCY CHARGES | 19470691 | 19470691 | 206532.46 | 19264158.54 | 19264158.54
COMMON MISCELLANEOUS WORK | 26106967 | 26106967 | 25280638.57 | 826328.43 | 826328.43