## Material Receipt Details6384879
Material Receipt Details
NEPTUNE TRION EXP
Page 1 of 1
Total Records: 38 Records 1 to 38
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Rate | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Balance Issue Qty | Issue Qty | Stock Qty | Stock Value | TechUnit_Name | Inv_Amount | Paid_Amount | Bal_PO_Qty1 | Bal_ReqQty1 | Est_Vs_Paid_Value
110mm X 20' X 4 KG_PVC PIPE - NOS | TOWER A 2ND FLOOR RCC WORK FOR SLAB | PLUMBING MATERIAL | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 1172.45 | 2344.9 | 2 | 0 | 2 | 0 | 95 | 113891.055 | NOS | 1987.2 | 0 | 0 | 0 | 2
20 x 32 MS COUPLER - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 4 | 1 | 4 | 4 | 1 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 158.12 | 632.48 | 4 | 0 | 4 | 0 | 119 | 22344.48 | NOS | 536 | 536 | 0 | 0 | -532
20mm MS COUPLER - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 270 | 1 | 270 | 189 | 1 | 189 | 189 | 81 | 0 | 189 | 0 | 189 | 0 | 63.72 | 12043.08 | 189 | 0 | 189 | 0 | 8509 | 653927.5363 | NOS | 10206 | 10206 | 0 | 81 | -9936
20X25 MS COUPLER - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 86 | 1 | 86 | 86 | 1 | 86 | 86 | 0 | 0 | 86 | 0 | 86 | 0 | 96.76 | 8321.36 | 86 | 0 | 86 | 0 | 2325 | 246510.26 | NOS | 7052 | 7052 | 0 | 0 | -6966
25mm MS COUPLER - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 410 | 1 | 410 | 410 | 1 | 410 | 410 | 0 | 0 | 410 | 0 | 410 | 0 | 88.5 | 36285 | 410 | 0 | 410 | 0 | 11562 | 1088015.9256 | NOS | 30750 | 30750 | 0 | 0 | -30340
25X32 MS COUPLER - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 74 | 1 | 74 | 74 | 1 | 74 | 74 | 0 | 0 | 74 | 0 | 74 | 0 | 158.12 | 11700.88 | 74 | 0 | 74 | 0 | 2242 | 375084.6306 | NOS | 9916 | 9916 | 0 | 0 | -9842
32mm MS COUPLER - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 216 | 1 | 216 | 216 | 1 | 216 | 216 | 0 | 0 | 216 | 0 | 216 | 0 | 139.24 | 30075.84 | 216 | 0 | 216 | 0 | 6753 | 963022.1072 | NOS | 25488 | 25488 | 0 | 0 | -25272
32MM x 10 KG PVC PIPE - RMT | TOWER A 2ND FLOOR RCC WORK FOR SLAB | ELECTRICAL MATERIAL | 75 | 1 | 75 | 70 | 1 | 70 | 70 | 5 | 0 | 70 | 0 | 70 | 0 | 36.58 | 2560.6 | 70 | 0 | 70 | 0 | 2876 | 161633.807 | RMT | 2170 | 0 | 0 | 5 | 75
75mm X 20' X 4 KG_PVC PIPE - NOS | TOWER A 2ND FLOOR RCC WORK FOR SLAB | PLUMBING MATERIAL | 22 | 1 | 22 | 22 | 1 | 22 | 22 | 0 | 0 | 22 | 0 | 22 | 0 | 594.72 | 13083.84 | 22 | 0 | 22 | 0 | 112 | 69937.9813 | NOS | 11088 | 0 | 0 | 0 | 22
AAC BLOCK_600X200X225 - CMT | TOWER A 2ND FLOOR 9" AAC BLOCK MASONRY WORK | CIVIL MATERIAL | 28 | 3399.9 | 95197.2 | 28 | 3399.9 | 95197.2 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 2625 | 73500 | 27.997 | 0.003 | 27.997 | 0 | 1029.78 | 3292807.4564 | CMT | 69992.5 | 69992.5 | 0 | 0 | 25204.7
BINDING WIRE - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 1800 | 1 | 1800 | 1800 | 1 | 1800 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 0 | 54.28 | 97704 | 1800 | 0 | 1800 | 0 | 0 | 0 | KG | 0 | 0 | 0 | 0 | 1800
BLOCK MORTAR - BAGS | TOWER A 2ND FLOOR 4.5" AAC BLOCK MASONRY WORK | CHEMICAL | 100 | 468.46 | 46846 | 100 | 468.46 | 46846 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 336.3 | 33630 | 100 | 0 | 100 | 0 | 2949 | 1125311.45 | BAGS | 28500 | 0 | 0 | 0 | 46846
BRICKS_REGULAR - NOS | TOWER A 2ND FLOOR 4.5" AAC BLOCK MASONRY WORK | CIVIL MATERIAL | 5000 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 6.825 | 34125 | 5000 | 0 | 5000 | 0 | 288153 | 1971088.36 | NOS | 32500 | 0 | 0 | 0 | 5000
CEMENT PPC - BAGS - BAGS | TOWER A 2ND FLOOR INTERNAL MALA FINISH PLASTER WORK | CIVIL MATERIAL | 150 | 1 | 150 | 150 | 1 | 150 | 150 | 0 | 0 | 150 | 0 | 150 | 0 | 340.0064 | 51000.96 | 150 | 0 | 98 | 52 | 15601 | 5292488.63 | BAGS | 39844.5 | 0 | 0 | 0 | 150
CEMENT PPC - BAGS - BAGS | TOWER A 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | CIVIL MATERIAL | 550 | 1 | 550 | 450 | 1 | 450 | 450 | 100 | 0 | 450 | 0 | 450 | 0 | 346.6667 | 156000 | 450 | 0 | 450 | 0 | 15601 | 5292488.63 | BAGS | 121875 | 0 | 0 | 100 | 550
COARSE SAND - TONN | TOWER A 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | CIVIL MATERIAL | 23 | 1 | 23 | 23 | 1 | 23 | 23 | 0 | 0 | 23 | 0 | 23 | 0 | 1060.5 | 24391.5 | 3.61 | 19.39 | 3.61 | 0 | 3760.03 | 3734932.67 | TONN | 3646.1 | 0 | 0 | 0 | 23
COARSE SAND - TONN | TOWER A 2ND FLOOR INTERNAL MALA FINISH PLASTER WORK | CIVIL MATERIAL | 30 | 1 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3760.03 | 3734932.67 | TONN | 0 | 0 | 0 | 30 | 30
COVER BLOCK - NOS | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 5000 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 1.003 | 5015 | 5000 | 0 | 5000 | 0 | 195600 | 216627.1 | NOS | 4250 | 0 | 0 | 0 | 5000
COVER BLOCK - NOS | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 5000 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 1.003 | 5015 | 5000 | 0 | 5000 | 0 | 195600 | 216627.1 | NOS | 4250 | 0 | 0 | 0 | 5000
D WALL - SQMT | TOWER A 2ND FLOOR DRY WALL WORK | CIVIL MATERIAL | 756.6 | 1.18 | 892.788 | 756.6 | 1.18 | 892.788 | 756.6 | 0 | 0 | 756.6 | 0 | 756.6 | 0 | 1237.6 | 936368.16 | 0 | 756.6 | 0 | 0 | 7246.991 | 8968876.055 | SQMT | 0 | 0 | 0 | 0 | 892.788
EXPANSION JOINT SHEET - SHEET | TOWER A 2ND FLOOR RCC WORK FOR SLAB | MISC MATERIAL | 112 | 1 | 112 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 94080.0004 | SHEET | 0 | 0 | 0 | 112 | 112
FAIRMATE_FAIR FIBRE - NOS | TOWER A 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | CHEMICAL | 1440 | 1 | 1440 | 72 | 1 | 72 | 72 | 1368 | 0 | 72 | 0 | 72 | 0 | 41.89 | 3016.08 | 72 | 0 | 72 | 0 | 1786 | 76373.14 | NOS | 2556 | 0 | 0 | 1368 | 1440
FIBRE CHICKEN MESH JALI - NOS | TOWER A 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | CIVIL MATERIAL | 216 | 1 | 216 | 3 | 1 | 3 | 3 | 213 | 0 | 3 | 0 | 3 | 0 | 1631.94 | 4895.82 | 3 | 0 | 3 | 0 | 144 | 239068 | NOS | 4149 | 0 | 0 | 213 | 216
GREEN BREADED PIPE(CURING)_1"_30 MTR - RMT | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | MISC MATERIAL | 30 | 1 | 30 | 30 | 1 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 57.0293 | 1710.879 | 30 | 0 | 30 | 0 | 185 | 18644 | RMT | 1449.9 | 0 | 0 | 0 | 30
PT CABLE WITH ACCESSORIES - RMT | TOWER A 2ND FLOOR RCC WORK FOR PT CABLE LAYING | CIVIL MATERIAL | 3732.48 | 1 | 3732.48 | 3732.48 | 1 | 3732.48 | 3732.48 | 0 | 0 | 3732.48 | 0 | 3732.48 | 0 | 133.576 | 498569.7485 | 3732.48 | 0 | 3732.48 | 0 | 73161.25 | 8814486.684 | RMT | 422516.736 | 207400.512 | 0 | 0 | -203668.032
RMC M-45 - CMT | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 35 | 1 | 35 | 35 | 1 | 35 | 35 | 0 | 0 | 35 | 0 | 35 | 0 | 5304.9966 | 185674.881 | 0 | 35 | 0 | 0 | 59.5 | 333357.715 | CMT | 0 | 0 | 0 | 0 | 35
STEEL_08MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 10450 | 1 | 10450 | 10450 | 4886.47 | 0 | 10450 | 0 | 10450 | 0 | 45.3002 | 473387.097 | 10450 | 0 | -4886.47 | 15336.47 | 174214.4 | 11541699.158 | KG | 401175.5 | 802351 | 0 | 4886.47 | -787014.53
STEEL_10MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 9300 | 1 | 9300 | 9300 | 6036.47 | 0 | 9300 | 0 | 9300 | 0 | 43.896 | 408232.8 | 9120 | 180 | 9120 | 0 | 147839.18 | 9569624.7102 | KG | 339264 | 678528 | 0 | 6036.47 | -663191.53
STEEL_10MM - KG | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 12718 | 1 | 12718 | 12718 | 1 | 12718 | 12718 | 0 | 0 | 12718 | 0 | 12718 | 0 | 46.3976 | 590084.6768 | 12680 | 38 | 12680 | 0 | 147839.18 | 9569624.7102 | KG | 498577.6 | 0 | 0 | 0 | 12718
STEEL_12MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 4000 | 1 | 4000 | 4000 | 11336.47 | 0 | 4000 | 0 | 4000 | 0 | 42.9048 | 171619.2 | 3970 | 30 | 3970 | 0 | 39793.71 | 2632893.956 | KG | 144349.2 | 288698.4 | 0 | 11336.47 | -273361.93
STEEL_16MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 6580 | 1 | 6580 | 6580 | 8756.47 | 0 | 6580 | 0 | 180 | 6400 | 42.9048 | 7722.864 | 180 | 0 | 180 | 0 | 82661.36 | 5440279.563 | KG | 6544.8 | 13089.6 | 6400 | 8756.47 | 2246.87
STEEL_16MM - KG | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 1100 | 1 | 1100 | 1100 | 1 | 1100 | 1100 | 0 | 0 | 1100 | 0 | 1100 | 0 | 45.3946 | 49934.06 | 1065 | 35 | 1065 | 0 | 82661.36 | 5440279.563 | KG | 40970.55 | 0 | 0 | 0 | 1100
STEEL_20MM - KG | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 3880 | 1 | 3880 | 3880 | 1 | 3880 | 3880 | 0 | 0 | 3880 | 0 | 3880 | 0 | 45.0052 | 174620.176 | 3880 | 0 | 3880 | 0 | 86208.93 | 5530831.562 | KG | 147983.2 | 0 | 0 | 0 | 3880
STEEL_20MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 2600 | 1 | 2600 | 2600 | 12736.47 | 0 | 2600 | 0 | 2600 | 0 | 42.5036 | 110509.36 | 2540 | 60 | -12796.47 | 15336.47 | 86208.93 | 5530831.562 | KG | 91490.8 | 182981.6 | 0 | 12736.47 | -167645.13
STEEL_25MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 3150 | 1 | 3150 | 3150 | 12186.47 | 0 | 3150 | 0 | 3150 | 0 | 42.9048 | 135150.12 | 3150 | 0 | -12186.47 | 15336.47 | 66376.15 | 4227244.8565 | KG | 114534 | 229068 | 0 | 12186.47 | -213731.53
STEEL_25MM - KG | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 9735 | 1 | 9735 | 9735 | 1 | 9735 | 9735 | 0 | 0 | 9735 | 0 | 9735 | 0 | 45.3946 | 441916.431 | 9710 | 25 | 9710 | 0 | 66376.15 | 4227244.8565 | KG | 373543.7 | 0 | 0 | 0 | 9735
STEEL_32MM - KG | TOWER A 2ND FLOOR RCC WORK FOR COLUMN | CIVIL MATERIAL | 7000 | 1 | 7000 | 7000 | 1 | 7000 | 7000 | 0 | 0 | 7000 | 0 | 7000 | 0 | 46.3976 | 324783.2 | 7000 | 0 | 7000 | 0 | 28656.55 | 1742770.5325 | KG | 275240 | 0 | 0 | 0 | 7000
STEEL_32MM - KG | TOWER A 2ND FLOOR RCC WORK FOR SLAB | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 460 | 1 | 460 | 460 | 14876.47 | 0 | 460 | 0 | 460 | 0 | 43.896 | 20192.16 | 460 | 0 | -14876.47 | 15336.47 | 28656.55 | 1742770.5325 | KG | 17112 | 34224 | 0 | 14876.47 | -18887.53