## Material Receipt Summary6384879
Material Receipt Summary
Bill Date From : 15/04/2024 To : 22/04/2024
Page 1 of 1
Total Records: 30 Records 1 to 30
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Issue Qty | Balance Issue Qty | Stock Qty | Stock Value
110mm X 20' X 4 KG_PVC PIPE - NOS |  | PLUMBING MATERIAL | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 1172.45 | 2344.9 | 2 | 0 | 0 | 2 | 95 | 113891.055
20 x 32 MS COUPLER - NOS |  | CIVIL MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 158.12 | 632.48 | 4 | 0 | 0 | 4 | 119 | 22344.48
20mm MS COUPLER - NOS |  | CIVIL MATERIAL | 270 | 1 | 270 | 189 | 189 | 189 | 81 | 0 | 189 | 0 | 189 | 0 | 63.72 | 12043.08 | 189 | 0 | 0 | 189 | 8509 | 653927.5363
20X25 MS COUPLER - NOS |  | CIVIL MATERIAL | 86 | 1 | 86 | 86 | 86 | 86 | 0 | 0 | 86 | 0 | 86 | 0 | 96.76 | 8321.36 | 86 | 0 | 0 | 86 | 2325 | 246510.26
25mm MS COUPLER - NOS |  | CIVIL MATERIAL | 410 | 1 | 410 | 410 | 410 | 410 | 0 | 0 | 410 | 0 | 410 | 0 | 88.5 | 36285 | 410 | 0 | 0 | 410 | 11562 | 1088015.9256
25X32 MS COUPLER - NOS |  | CIVIL MATERIAL | 74 | 1 | 74 | 74 | 74 | 74 | 0 | 0 | 74 | 0 | 74 | 0 | 158.12 | 11700.88 | 74 | 0 | 0 | 74 | 2242 | 375084.6306
32mm MS COUPLER - NOS |  | CIVIL MATERIAL | 216 | 1 | 216 | 216 | 216 | 216 | 0 | 0 | 216 | 0 | 216 | 0 | 139.24 | 30075.84 | 216 | 0 | 0 | 216 | 6753 | 963022.1072
32MM x 10 KG PVC PIPE - RMT |  | ELECTRICAL MATERIAL | 75 | 1 | 75 | 70 | 70 | 70 | 5 | 0 | 70 | 0 | 70 | 0 | 36.58 | 2560.6 | 70 | 0 | 0 | 70 | 2876 | 161633.807
75mm X 20' X 4 KG_PVC PIPE - NOS |  | PLUMBING MATERIAL | 22 | 1 | 22 | 22 | 22 | 22 | 0 | 0 | 22 | 0 | 22 | 0 | 594.72 | 13083.84 | 22 | 0 | 0 | 22 | 112 | 69937.9813
AAC BLOCK_600X200X225 - CMT |  | CIVIL MATERIAL | 28 | 3399.9 | 95197.2 | 28 | 95197.2 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 2625 | 73500 | 27.997 | 0.003 | 0 | 27.997 | 1029.78 | 3292807.4564
BINDING WIRE - KG |  | CIVIL MATERIAL | 1800 | 1 | 1800 | 1800 | 1800 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 0 | 54.28 | 97704 | 1800 | 0 | 0 | 1800 | 0 | 0
BLOCK MORTAR - BAGS |  | CHEMICAL | 100 | 468.46 | 46846 | 100 | 46846 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 336.3 | 33630 | 100 | 0 | 0 | 100 | 2949 | 1125311.45
BRICKS_REGULAR - NOS |  | CIVIL MATERIAL | 5000 | 1 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 5000 | 0 | 5000 | 0 | 6.825 | 34125 | 5000 | 0 | 0 | 5000 | 288153 | 1971088.36
CEMENT PPC - BAGS - BAGS |  | CIVIL MATERIAL | 700 | 1 | 700 | 600 | 600 | 600 | 100 | 0 | 600 | 0 | 600 | 0 | 345.0016 | 207000.96 | 600 | 0 | 2734 | -2134 | 15601 | 5292488.63
COARSE SAND - TONN |  | CIVIL MATERIAL | 53 | 1 | 53 | 23 | 23 | 23 | 30 | 0 | 23 | 0 | 23 | 0 | 1060.5 | 24391.5 | 3.61 | 19.39 | 0 | 3.61 | 3760.03 | 3734932.67
COVER BLOCK - NOS |  | CIVIL MATERIAL | 10000 | 1 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 10000 | 0 | 10000 | 0 | 1.003 | 10030 | 10000 | 0 | 0 | 10000 | 195600 | 216627.1
D WALL - SQMT |  | CIVIL MATERIAL | 756.6 | 1.18 | 892.79 | 756.6 | 892.788 | 756.6 | 0 | 0 | 756.6 | 0 | 756.6 | 0 | 1237.6 | 936368.16 | 0 | 756.6 | 0 | 0 | 7246.991 | 8968876.055
EXPANSION JOINT SHEET - SHEET |  | MISC MATERIAL | 112 | 1 | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 94080.0004
FAIRMATE_FAIR FIBRE - NOS |  | CHEMICAL | 1440 | 1 | 1440 | 72 | 72 | 72 | 1368 | 0 | 72 | 0 | 72 | 0 | 41.89 | 3016.08 | 72 | 0 | 0 | 72 | 1786 | 76373.14
FIBRE CHICKEN MESH JALI - NOS |  | CIVIL MATERIAL | 216 | 1 | 216 | 3 | 3 | 3 | 213 | 0 | 3 | 0 | 3 | 0 | 1631.94 | 4895.82 | 3 | 0 | 0 | 3 | 144 | 239068
GREEN BREADED PIPE(CURING)_1"_30 MTR - RMT |  | MISC MATERIAL | 30 | 1 | 30 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 57.0293 | 1710.879 | 30 | 0 | 1 | 29 | 185 | 18644
PT CABLE WITH ACCESSORIES - RMT |  | CIVIL MATERIAL | 3732.48 | 1 | 3732.48 | 3732.48 | 3732.48 | 3732.48 | 0 | 0 | 3732.48 | 0 | 3732.48 | 0 | 133.576 | 498569.7485 | 3732.48 | 0 | 0 | 3732.48 | 73161.25 | 8814486.684
RMC M-45 - CMT |  | CIVIL MATERIAL | 35 | 1 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 0 | 35 | 0 | 5304.9966 | 185674.881 | 0 | 35 | 0 | 0 | 59.5 | 333357.715
STEEL_08MM - KG |  | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 10450 | 10450 | 10450 | 4886.47 | 0 | 10450 | 0 | 10450 | 0 | 45.3002 | 473387.097 | 10450 | 0 | 275117.6 | -264667.6 | 174214.4 | 11541699.158
STEEL_10MM - KG |  | CIVIL MATERIAL | 28054.47 | 1 | 28054.47 | 22018 | 22018 | 22018 | 6036.47 | 0 | 22018 | 0 | 22018 | 0 | 45.341 | 998317.4768 | 21800 | 218 | 234172.82 | -212372.82 | 147839.18 | 9569624.7102
STEEL_12MM - KG |  | CIVIL MATERIAL | 15336.47 | 1 | 15336.47 | 4000 | 4000 | 4000 | 11336.47 | 0 | 4000 | 0 | 4000 | 0 | 42.9048 | 171619.2 | 3970 | 30 | 69835.29 | -65865.29 | 39793.71 | 2632893.956
STEEL_16MM - KG |  | CIVIL MATERIAL | 16436.47 | 1 | 16436.47 | 7680 | 7680 | 7680 | 8756.47 | 0 | 7680 | 0 | 1280 | 6400 | 45.0445 | 57656.924 | 1245 | 35 | 165418.64 | -164173.64 | 82661.36 | 5440279.563
STEEL_20MM - KG |  | CIVIL MATERIAL | 19216.47 | 1 | 19216.47 | 6480 | 6480 | 6480 | 12736.47 | 0 | 6480 | 0 | 6480 | 0 | 44.0015 | 285129.536 | 6420 | 60 | 121490.07 | -115070.07 | 86208.93 | 5530831.562
STEEL_25MM - KG |  | CIVIL MATERIAL | 25071.47 | 1 | 25071.47 | 12885 | 12885 | 12885 | 12186.47 | 0 | 12885 | 0 | 12885 | 0 | 44.7859 | 577066.551 | 12860 | 25 | 215696.85 | -202836.85 | 66376.15 | 4227244.8565
STEEL_32MM - KG |  | CIVIL MATERIAL | 22336.47 | 1 | 22336.47 | 7460 | 7460 | 7460 | 14876.47 | 0 | 7460 | 0 | 7460 | 0 | 46.2433 | 344975.36 | 7460 | 0 | 160948.45 | -153488.45 | 28656.55 | 1742770.5325