## Material Receipt Summary6385119
Material Receipt Summary
Bill Date From : 13/05/2024 To : 20/05/2024
Page 1 of 1
Total Records: 203 Records 1 to 203
Material | Task | Material Category | Estimated Qty | Estimated Rate | Estimated Amount | Requisition Qty | Requisition Amount | Requisition Approved Qty | Balance Requisition Qty | Balance Requisition Approved Qty | Procurement Qty | Balance Procurement Qty | PO Qty | Balance PO Qty | PO Rate | PO Amount | GRN Qty | Balance GRN Qty | Issue Qty | Balance Issue Qty | Stock Qty | Stock Value
(2200IN-0) VESSEL CONICAL BELL LAVATORY Conical Bell - NOS |  | SANITARYWARE & CP FITTINGS | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 2267.19 | 4534.38 | 2 | 0 | 0 | 2 | 2 | 4534.38
(26351IN-M-NA) INSTAFLUSHTM NXT GEN-MECH IN WALL TANK - NOS |  | SANITARYWARE & CP FITTINGS | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 3379.99 | 6759.98 | 2 | 0 | 0 | 2 | 2 | 6759.98
1 1/2"_CPVC COUPLER - NOS |  | PLUMBING MATERIAL | 16 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 79.65 | 1274.4 | 16 | 0 | 0 | 16 | 16 | 1274.4
1 1/2"_CPVC END CAP - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 56.0725 | 448.58 | 8 | 0 | 0 | 8 | 8 | 448.58
1 1/2"x3/4" _CPVC BUSHING - NOS |  | PLUMBING MATERIAL | 8 | 1.18 | 9.44 | 8 | 9.44 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 50.975 | 407.8 | 8 | 0 | 0 | 8 | 8 | 407.8
1 1/4" CPVC ELBOW 90 DEGREE - NOS |  | PLUMBING MATERIAL | 4 | 1.18 | 4.72 | 4 | 4.72 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 67.545 | 270.18 | 4 | 0 | 0 | 4 | 4 | 270.18
1 1/4" X 3/4"_CPVC BUSHING - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 31.2225 | 249.78 | 8 | 0 | 0 | 8 | 8 | 249.78
1 1/4" X 3/4"_CPVC REDUCER ELBOW - NOS |  | PLUMBING MATERIAL | 4 | 1.18 | 4.72 | 4 | 4.72 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 67.545 | 270.18 | 4 | 0 | 0 | 4 | 4 | 270.18
1 1/4" X 3/4"_CPVC REDUCER TEE. - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 133.8125 | 1070.5 | 8 | 0 | 0 | 8 | 8 | 1070.5
1 1/4" X 5MTR X SDR 11_CPVC PIPE - NOS |  | PLUMBING MATERIAL | 14 | 1 | 14 | 14 | 14 | 14 | 0 | 0 | 14 | 0 | 14 | 0 | 1137.4014 | 15923.6196 | 14 | 0 | 0 | 14 | 14 | 15923.62
1 1/4"_CPVC END CAP - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 38.2325 | 305.86 | 8 | 0 | 0 | 8 | 8 | 305.86
1 1/4"_CPVC TEE - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 86.02 | 344.08 | 4 | 0 | 0 | 4 | 4 | 344.08
1 SQMM 2 CORE COPPER FLEXIBLE WIRE - RMT |  | ELECTRICAL MATERIAL | 200 | 1 | 200 | 200 | 200 | 200 | 0 | 0 | 200 | 0 | 200 | 0 | 29.0752 | 5815.04 | 200 | 0 | 0 | 200 | 200 | 5815.04
1 SQMM WIRE - RMT |  | ELECTRICAL MATERIAL | 600 | 1.18 | 708 | 600 | 708 | 600 | 0 | 0 | 600 | 0 | 600 | 0 | 10.6987 | 6419.2 | 600 | 0 | 0 | 600 | 1470 | 15896.6
1 x 3 x 2.5 Sqmm PVC FLAT CABLE - RMT |  | ELECTRICAL MATERIAL | 50 | 1 | 50 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 50 | 0 | 75.52 | 3776 | 50 | 0 | 0 | 50 | 50 | 4411.88
1"_UPVC COUPLER - NOS |  | PLUMBING MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 11.68 | 35.04 | 3 | 0 | 0 | 3 | 33 | 385.5
1-1/2" x 3/4" CPVC TEE - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 189.2475 | 1513.98 | 8 | 0 | 0 | 8 | 8 | 1513.98
1-1/2" x 5Mtr SDR-11 CPVC Pipe - NOS |  | PLUMBING MATERIAL | 13 | 1.18 | 15.34 | 13 | 15.34 | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 1561.14 | 20294.82 | 13 | 0 | 0 | 13 | 13 | 20294.82
1-1/4" CPVC COUPLER - NOS |  | PLUMBING MATERIAL | 16 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 43.33 | 693.28 | 16 | 0 | 0 | 16 | 16 | 693.28
1.5 SQMM FLEXIBLE CABLE - RMT |  | ELECTRICAL MATERIAL | 100 | 1 | 100 | 100 | 100 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1/2" CPVC THEARDED END PLUG - NOS |  | PLUMBING MATERIAL | 40 | 1 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 40 | 0 | 8.921 | 356.84 | 40 | 0 | 0 | 40 | 40 | 356.84
1/2"_UPVC BALL VALVE - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 84.37 | 337.48 | 4 | 0 | 0 | 4 | 34 | 2983.57
1/2"_UPVC END CAP - NOS |  | PLUMBING MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 4.2217 | 12.6651 | 3 | 0 | 0 | 3 | 3 | 12.665
100 AMP 4 POLE MCB - NOS |  | ELECTRICAL MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 MM TEE MOLD (A061000001) (R9) - NOS |  | ELECTRICAL MATERIAL | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 123.9 | 247.8 | 0 | 2 | 0 | 0 | 0 | 0
100 W LED FLOOD LIGHT - NOS |  | ELECTRICAL MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2019.36
100 X 65 X 100MM PVC TEE MOLD (A061000003) (R9) - NOS |  | PLUMBING MATERIAL | 13 | 1.18 | 15.34 | 13 | 15.34 | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 181.9554 | 2365.4202 | 0 | 13 | 0 | 0 | 0 | 0
100MM GEOREX GREY ENDCAP (A061001500) (R9) - NOS |  | PLUMBING MATERIAL | 4 | 1.18 | 4.72 | 4 | 4.72 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 50.27 | 201.08 | 0 | 4 | 0 | 0 | 0 | 0
100MM POWERDRAIN COUPLER GEOREX(200 MM) (F07100PDC2) (R9) - NOS |  | PLUMBING MATERIAL | 7 | 1.18 | 8.26 | 7 | 8.26 | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 191.16 | 1338.12 | 0 | 7 | 0 | 0 | 0 | 0
10MM GRIT - TONN |  | CIVIL MATERIAL | 6 | 1 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10MM NUT - NOS |  | PLUMBING MATERIAL | 60 | 1.18 | 70.8 | 60 | 70.8 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10MM NUTS - KG |  | PLUMBING MATERIAL | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10mm_BULLET FASTNER - NOS |  | PLUMBING MATERIAL | 30 | 1 | 30 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 24.78 | 743.4 | 30 | 0 | 0 | 30 | 30 | 743.4
110 MM PVC SILENCIO PLAIN Y - NOS |  | PLUMBING MATERIAL | 12 | 1 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 560.0983 | 6721.1796 | 12 | 0 | 0 | 12 | 12 | 6721.18
110MM 45DEGREE SILENCIO BAND - NOS |  | PLUMBING MATERIAL | 49 | 1.18 | 57.82 | 49 | 57.82 | 49 | 0 | 0 | 49 | 0 | 49 | 0 | 332.1902 | 16277.3216 | 49 | 0 | 0 | 49 | 49 | 16277.32
110MM PVC END CAP 6 KGF/cm2 - NOS |  | PLUMBING MATERIAL | 16 | 5.9 | 94.4 | 16 | 94.4 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 59.7075 | 955.32 | 16 | 0 | 0 | 16 | 16 | 955.32
110MM SILENCIO ELBOW 87.5 DEGREE - NOS |  | PLUMBING MATERIAL | 36 | 1.18 | 42.48 | 36 | 42.48 | 36 | 0 | 0 | 36 | 0 | 36 | 0 | 358.7433 | 12914.7588 | 36 | 0 | 0 | 36 | 36 | 12914.76
110MM SILENCIO PIPE 3 M S/S - NOS |  | PLUMBING MATERIAL | 62 | 1.0348 | 64.16 | 62 | 64.16 | 62 | 0 | 0 | 62 | 0 | 62 | 0 | 1904.579 | 118083.8996 | 62 | 0 | 0 | 62 | 62 | 118083.9
110mm X 20' X 4 KG_PVC PIPE - NOS |  | PLUMBING MATERIAL | 12 | 1 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 1681.075 | 20172.9 | 12 | 0 | 0 | 12 | 12 | 20172.9
110mm X 75/50_SILENCIO MULTI FLOOR TRAP - NOS |  | PLUMBING MATERIAL | 1 | 1.18 | 1.18 | 1 | 1.18 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1072.14 | 1072.14 | 1 | 0 | 0 | 1 | 1 | 1072.14
110mm X 75/50_SWR PVC MUTIFLOOR TRAP - NOS |  | PLUMBING MATERIAL | 16 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110X75X50MM_ SILENCIO MULTI FLOOR TRAP HIGH RISER - NOS |  | PLUMBING MATERIAL | 16 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 310.3163 | 4965.0608 | 16 | 0 | 0 | 16 | 16 | 4965.06
11543IN-4-CP JULY TALL PILLAR LAVATORY FAUCET - NOS |  | SANITARYWARE & CP FITTINGS | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 3064.71 | 6129.42 | 2 | 0 | 0 | 2 | 2 | 6129.42
11568IN-7B- CP COMPLEMENTARY ANGLE VALVE - NOS |  | SANITARYWARE & CP FITTINGS | 4 | 1.18 | 4.72 | 4 | 4.72 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 350 | 1400 | 4 | 0 | 0 | 4 | 4 | 1400
12 MODULE SURFACE BOX - NOS |  | ELECTRICAL MATERIAL | 8 | 1 | 8 | 5 | 5 | 5 | 3 | 0 | 5 | 0 | 5 | 0 | 135.7 | 678.5 | 5 | 0 | 0 | 5 | 8 | 1071.44
12 X 4 SWITCH BOARD - NOS |  | ELECTRICAL MATERIAL | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 118 | 236 | 2 | 0 | 0 | 2 | 2 | 236
12927IN-CP HEALTH FAUCET W/SDSPRAY, METAL HOSE - NOS |  | SANITARYWARE & CP FITTINGS | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 1034.99 | 2069.98 | 2 | 0 | 0 | 2 | 2 | 2069.98
15 AMP SOCKET - NOS |  | ELECTRICAL MATERIAL | 24 | 1 | 24 | 20 | 20 | 20 | 4 | 0 | 20 | 0 | 20 | 0 | 104.533 | 2090.66 | 20 | 0 | 0 | 20 | 28 | 2914.58
15 AMP SWITCH - NOS |  | ELECTRICAL MATERIAL | 24 | 1 | 24 | 20 | 20 | 20 | 4 | 0 | 20 | 0 | 20 | 0 | 72.4642 | 1449.284 | 20 | 0 | 0 | 20 | 28 | 2229.224
150mm dia concealed sleeve pvc pipe 4kg/cm2 - RMT |  | PLUMBING MATERIAL | 16 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160x110 SILENCIO SWEPT PLAIN TEE - NOS |  | PLUMBING MATERIAL | 8 | 1.18 | 9.44 | 8 | 9.44 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 1359.1475 | 10873.18 | 8 | 0 | 0 | 8 | 8 | 10873.18
18131IN-S-0 PATIO WALL- HUNG TOILET W/ SC SEAT - NOS |  | PLUMBING MATERIAL | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 5774.99 | 11549.98 | 2 | 0 | 0 | 2 | 2 | 11550
2" x 1 1/2"_UPVC BUSHING - NOS |  | PLUMBING MATERIAL | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 54.16 | 54.16 | 1 | 0 | 0 | 1 | 1 | 54.16
2"_UPVC FAPT - NOS |  | PLUMBING MATERIAL | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 41.42 | 41.42 | 1 | 0 | 0 | 1 | 1 | 41.42
2"_UPVC MAPT - NOS |  | PLUMBING MATERIAL | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 36.32 | 36.32 | 1 | 0 | 0 | 1 | 1 | 36.32
2.5 SQ.MM 2 CORE CABLE - RMT |  | ELECTRICAL MATERIAL | 30 | 1 | 30 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 61.36 | 1840.8 | 30 | 0 | 0 | 30 | 30 | 1840.8
20 AMP 2 POLE MCB - NOS |  | ELECTRICAL MATERIAL | 6 | 1 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 AMP SINGLE POLE MCB - NOS |  | ELECTRICAL MATERIAL | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 MM CONDUIT PIPE - NOS |  | ELECTRICAL MATERIAL | 10 | 1.18 | 11.8 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20mm MS COUPLER - NOS |  | CIVIL MATERIAL | 5544 | 1 | 5544 | 4834 | 4834 | 4834 | 710 | 0 | 4834 | 0 | 4834 | 0 | 58.8955 | 284700.96 | 4779 | 55 | 0 | 4779 | 5668 | 333512.25
20X25 MS COUPLER - NOS |  | CIVIL MATERIAL | 1238 | 1 | 1238 | 1123 | 1123 | 1123 | 115 | 0 | 1123 | 0 | 1123 | 0 | 115.4309 | 129628.9 | 1115 | 8 | 0 | 1115 | 1115 | 128826.5
237ML_CPVC SOLUTION (TIN) - TIN |  | PLUMBING MATERIAL | 7 | 1 | 7 | 7 | 7 | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 301.4057 | 2109.84 | 7 | 0 | 0 | 7 | 7 | 2109.84
2400 MM X 800 MM - MOTTO_CRYSTAL WHITE - SQFT |  | FLOORING MATERIAL | 992 | 1.18 | 1170.56 | 992 | 1170.56 | 992 | 0 | 0 | 992 | 0 | 992 | 0 | 108.56 | 107691.52 | 0 | 992 | 0 | 0 | 0 | 0
2400 X 200 Dark Grey - Motto - SQFT |  | FLOORING MATERIAL | 25 | 1 | 25 | 21.1 | 21.1 | 21.1 | 3.9 | 0 | 21.1 | 0 | 21.1 | 0 | 194.0034 | 4093.4717 | 0 | 21.1 | 0 | 0 | 0 | 0
2400X300 Dark Grey - Motto - SQFT |  | FLOORING MATERIAL | 35 | 1 | 35 | 32 | 32 | 32 | 3 | 0 | 32 | 0 | 32 | 0 | 243.6113 | 7795.5616 | 0 | 32 | 0 | 0 | 0 | 0
25mm MS COUPLER - NOS |  | CIVIL MATERIAL | 4218 | 1 | 4218 | 4018 | 4018 | 4018 | 200 | 0 | 4018 | 0 | 4018 | 0 | 102.435 | 411584 | 2678 | 1340 | 0 | 2678 | 3609 | 374318.0428
25X32 MS COUPLER - NOS |  | CIVIL MATERIAL | 447 | 1 | 447 | 377 | 377 | 377 | 70 | 0 | 377 | 0 | 377 | 0 | 190.7875 | 71926.9 | 377 | 0 | 0 | 377 | 377 | 71926.9
28476IN-M- CP RIVIERA IWT FACEPLATE MECHANICAL-CP - NOS |  | SANITARYWARE & CP FITTINGS | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 935 | 1870 | 2 | 0 | 0 | 2 | 2 | 1870
3" HINGES - NOS |  | HARDWARE MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3" X 4" Silencio Reducer Socket - NOS |  | PLUMBING MATERIAL | 17 | 1.18 | 20.06 | 17 | 20.06 | 17 | 0 | 0 | 17 | 0 | 17 | 0 | 282.5876 | 4803.99 | 17 | 0 | 0 | 17 | 17 | 4803.99
3/4" CPVC METAL CLAMP - NOS |  | PLUMBING MATERIAL | 48 | 1 | 48 | 48 | 48 | 48 | 0 | 0 | 48 | 0 | 48 | 0 | 3.54 | 169.92 | 48 | 0 | 0 | 48 | 48 | 169.92
3/4" X 1/2" _CPVC BRASS ELBOW (BRASS FPT X SOC ELBOW 90 DEG) - NOS |  | PLUMBING MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 57.9867 | 173.9601 | 3 | 0 | 0 | 3 | 3 | 173.96
3/4" X 1/2" _CPVC FABT ( REDUCER COUPLER BRASS THD X SOC) - NOS |  | PLUMBING MATERIAL | 16 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 70.7288 | 1131.6608 | 16 | 0 | 0 | 16 | 16 | 1131.66
3/4" X 5MTR X SDR 11_CPVC PIPE - NOS |  | PLUMBING MATERIAL | 55 | 1 | 55 | 55 | 55 | 55 | 0 | 0 | 55 | 0 | 55 | 0 | 430.1102 | 23656.0599 | 55 | 0 | 0 | 55 | 55 | 23656.06
3/4"_CPVC END CAP - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 11.47 | 91.76 | 8 | 0 | 0 | 8 | 8 | 91.76
3/4"_CPVC BRASS ELBOW - NOS |  | PLUMBING MATERIAL | 32 | 1 | 32 | 32 | 32 | 32 | 0 | 0 | 32 | 0 | 32 | 0 | 84.7475 | 2711.92 | 32 | 0 | 0 | 32 | 32 | 2711.92
3/4"_CPVC COUPLER - NOS |  | PLUMBING MATERIAL | 72 | 1 | 72 | 72 | 72 | 72 | 0 | 0 | 72 | 0 | 72 | 0 | 12.7439 | 917.5608 | 72 | 0 | 0 | 72 | 72 | 917.56
3/4"_CPVC ELBOW 90 DEG - NOS |  | PLUMBING MATERIAL | 144 | 1 | 144 | 144 | 144 | 144 | 0 | 0 | 144 | 0 | 144 | 0 | 15.2928 | 2202.156 | 144 | 0 | 0 | 144 | 144 | 2202.16
3/4"_CPVC ELBOW-45 - NOS |  | PLUMBING MATERIAL | 52 | 1 | 52 | 52 | 52 | 52 | 0 | 0 | 52 | 0 | 52 | 0 | 22.3019 | 1159.6988 | 52 | 0 | 0 | 52 | 52 | 1159.7
3/4"_CPVC TEE - NOS |  | PLUMBING MATERIAL | 18 | 1 | 18 | 18 | 18 | 18 | 0 | 0 | 18 | 0 | 18 | 0 | 24.9934 | 449.8808 | 18 | 0 | 0 | 18 | 18 | 449.88
3/4"_EPDM CLAMP - NOS |  | PLUMBING MATERIAL | 24 | 1 | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 24 | 0 | 18.88 | 453.12 | 24 | 0 | 0 | 24 | 24 | 453.12
3/4"_ZOLOTO BALL VALVE - NOS |  | PLUMBING MATERIAL | 34 | 1 | 34 | 34 | 34 | 34 | 0 | 0 | 34 | 0 | 34 | 0 | 459.7359 | 15631.02 | 2 | 32 | 0 | 2 | 2 | 1023.18
3/4"X1/2" CPVC BRASS FTA 90 DEG - NOS |  | PLUMBING MATERIAL | 1 | 1.18 | 1.18 | 1 | 1.18 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 149.74 | 149.74 | 1 | 0 | 0 | 1 | 1 | 149.74
32AMP x 4 Pole MCB - NOS |  | ELECTRICAL MATERIAL | 14 | 1 | 14 | 12 | 12 | 12 | 2 | 0 | 12 | 0 | 12 | 0 | 1109.5025 | 13314.0299 | 12 | 0 | 0 | 12 | 16 | 18074.05
32mm dia concealed sleeve pvc pipe 10kg/cm2 - RMT |  | PLUMBING MATERIAL | 721 | 1 | 721 | 661 | 661 | 661 | 60 | 0 | 661 | 0 | 661 | 0 | 45.9295 | 30359.4036 | 624 | 37 | 0 | 624 | 624 | 28684.42
32mm MS COUPLER - NOS |  | CIVIL MATERIAL | 1201 | 1 | 1201 | 1037 | 1037 | 1037 | 164 | 0 | 1037 | 0 | 1037 | 0 | 153.1838 | 158851.6 | 342 | 695 | 0 | 342 | 865 | 133074.4711
32MM x 10 KG PVC PIPE - RMT |  | ELECTRICAL MATERIAL | 500 | 1 | 500 | 500 | 500 | 500 | 0 | 0 | 500 | 0 | 210 | 290 | 62.1354 | 13048.44 | 210 | 0 | 0 | 210 | 390 | 19632.84
4 SQMM X 4 CORE_ CABLE - RMT |  | ELECTRICAL MATERIAL | 100 | 1 | 100 | 100 | 100 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 182.7112 | 18271.12 | 100 | 0 | 0 | 100 | 300 | 47647.22
4"_ SILENCIO PLAIN Y - NOS |  | PLUMBING MATERIAL | 17 | 1 | 17 | 17 | 17 | 17 | 0 | 0 | 17 | 0 | 17 | 0 | 570.4712 | 9698.0104 | 17 | 0 | 0 | 17 | 17 | 9698.01
4"_ U CLAMP - NOS |  | PLUMBING MATERIAL | 150 | 1 | 150 | 150 | 150 | 150 | 0 | 0 | 150 | 0 | 150 | 0 | 57.348 | 8602.2 | 150 | 0 | 0 | 150 | 150 | 8602.2
4"_SILENCIO PLAIN BEND 87.5 DEGREE - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 365.385 | 1461.54 | 4 | 0 | 0 | 4 | 4 | 1461.54
4"_SILENCIO PLAIN TEE SWEPT - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 468.34 | 1873.36 | 4 | 0 | 0 | 4 | 4 | 1873.36
4"X 2" L CLAMP - NOS |  | PLUMBING MATERIAL | 300 | 1.18 | 354 | 300 | 354 | 300 | 0 | 0 | 300 | 0 | 300 | 0 | 24.78 | 7434 | 300 | 0 | 0 | 300 | 300 | 7434
4"X6'_ SILENCIO PIPE D/S - NOS |  | PLUMBING MATERIAL | 9 | 1 | 9 | 9 | 9 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 1320.7144 | 11886.4296 | 9 | 0 | 0 | 9 | 9 | 11886.43
4'' SWR SWEPT TEE - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40MM MS PIPE 18KG - 20FT - NOS |  | CIVIL MATERIAL | 65 | 1 | 65 | 65 | 65 | 65 | 0 | 0 | 65 | 0 | 65 | 0 | 836.8015 | 54392.1 | 65 | 0 | 0 | 65 | 65 | 100341.3011
40MM X 6KG X 20'_PVC PIPE - NOS |  | PLUMBING MATERIAL | 15 | 1 | 15 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 15 | 0 | 217.2147 | 3258.2205 | 0 | 15 | 0 | 0 | 0 | 0
5 AMP SOCKET - NOS |  | ELECTRICAL MATERIAL | 24 | 1 | 24 | 20 | 20 | 20 | 4 | 0 | 20 | 0 | 20 | 0 | 55.518 | 1110.36 | 20 | 0 | 0 | 20 | 30 | 1564.44
5 AMP SWITCH - NOS |  | ELECTRICAL MATERIAL | 24 | 1 | 24 | 20 | 20 | 20 | 4 | 0 | 20 | 0 | 20 | 0 | 24.281 | 485.62 | 20 | 0 | 0 | 20 | 42 | 1131.54
50 MM CHECK VALVE HORIZONTAL NRV - NOS |  | PLUMBING MATERIAL | 1 | 1.18 | 1.18 | 1 | 1.18 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1050.2 | 1050.2 | 1 | 0 | 0 | 1 | 1 | 1227.05
50 MM SS NIPPLE & NUT BOLT - NOS |  | PLUMBING MATERIAL | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 619.5 | 1239 | 2 | 0 | 0 | 2 | 2 | 1447.65
50MM _SILENCIO PLAIN BEND - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 182.37 | 729.48 | 4 | 0 | 0 | 4 | 4 | 729.48
50mm 6kg PVC Pipe - 3 Mtr - NOS |  | ELECTRICAL MATERIAL | 14 | 1 | 14 | 6 | 6 | 6 | 8 | 0 | 6 | 0 | 6 | 0 | 273.9267 | 1643.5602 | 6 | 0 | 0 | 6 | 6 | 1643.56
50mm HDPE Pipe - RMT |  | PLUMBING MATERIAL | 6 | 1.18 | 7.08 | 6 | 7.08 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 210.04 | 1260.24 | 6 | 0 | 0 | 6 | 6 | 1472.46
50MM PVC BEND 45 DEGREE - NOS |  | PLUMBING MATERIAL | 20 | 1.18 | 23.6 | 20 | 23.6 | 20 | 0 | 0 | 20 | 0 | 20 | 0 | 20.768 | 415.36 | 20 | 0 | 0 | 20 | 20 | 415.36
50MM SILENCIO PIPE 10' D/S - NOS |  | PLUMBING MATERIAL | 1 | 1.18 | 1.18 | 1 | 1.18 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1004.66 | 1004.66 | 1 | 0 | 0 | 1 | 1 | 1004.66
50MM X 6KG X 6MTR_PVC PIPE - NOS |  | ELECTRICAL MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 390.6975 | 3125.58 | 8 | 0 | 0 | 8 | 8 | 3125.58
50MM_ SILENCIO 45 BEND - NOS |  | PLUMBING MATERIAL | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 184.32 | 184.32 | 1 | 0 | 0 | 1 | 1 | 184.32
50MM_COUPLER SILENCIO - NOS |  | PLUMBING MATERIAL | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 232.34 | 232.34 | 1 | 0 | 0 | 1 | 1 | 232.34
50MM_PVC ELBOW - NOS |  | PLUMBING MATERIAL | 28 | 1 | 28 | 28 | 28 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 25.3107 | 708.6996 | 28 | 0 | 0 | 28 | 28 | 708.7
50MM_PVC END CAP - NOS |  | PLUMBING MATERIAL | 4 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 11.68 | 46.72 | 4 | 0 | 0 | 4 | 4 | 46.72
6" EPDM CLAMP - NOS |  | PLUMBING MATERIAL | 48 | 1.18 | 56.64 | 48 | 56.64 | 48 | 0 | 0 | 48 | 0 | 48 | 0 | 76.7 | 3681.6 | 48 | 0 | 0 | 48 | 48 | 3681.6
6" MS Heavy Clamp - NOS |  | PLUMBING MATERIAL | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 649 | 1298 | 2 | 0 | 0 | 2 | 2 | 1516.58
600 X 600 MORDENA GREY- ALLENCERA - SQFT |  | FLOORING MATERIAL | 878 | 1 | 878 | 876.5 | 876.5 | 876.5 | 1.5 | 0 | 876.5 | 0 | 876.5 | 0 | 27.1596 | 23805.3672 | 876 | 0.5 | 0 | 876 | 876 | 23787.66
600X1200 Geneva Grey - GT Series-Lavish - SQFT |  | FLOORING MATERIAL | 150 | 1 | 150 | 150 | 150 | 150 | 0 | 0 | 150 | 0 | 150 | 0 | 59 | 8850 | 150 | 0 | 0 | 150 | 150 | 8850
600X600 SKC1900 - PARKOS - SQFT |  | FLOORING MATERIAL | 3744 | 1 | 3744 | 3742.5 | 3742.5 | 3742.5 | 1.5 | 0 | 3742.5 | 0 | 3742.5 | 0 | 26.1123 | 97725.0984 | 46.5 | 3696 | 0 | 46.5 | 46.5 | 1646.1
65MM GEOREX GREY ENDCAP (A060651500) (R9) - NOS |  | PLUMBING MATERIAL | 12 | 1.18 | 14.16 | 12 | 14.16 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 43.8967 | 526.7604 | 0 | 12 | 0 | 0 | 0 | 0
65MM HOSE CLAMP - NOS |  | PLUMBING MATERIAL | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 141.6 | 283.2 | 2 | 0 | 0 | 2 | 2 | 330.89
65MM POWERDRAIN COUPLER GEOREX(200 MM) (F07065PDC2) (R9) - NOS |  | PLUMBING MATERIAL | 52 | 1.18 | 61.36 | 52 | 61.36 | 52 | 0 | 0 | 52 | 0 | 52 | 0 | 111.8638 | 5816.9176 | 0 | 52 | 0 | 0 | 0 | 0
75 mm 6kg PVC Pipe - 3 Mtr - NOS |  | ELECTRICAL MATERIAL | 72 | 1 | 72 | 72 | 72 | 72 | 0 | 0 | 72 | 0 | 72 | 0 | 606.0125 | 43632.9 | 44 | 28 | 0 | 44 | 44 | 26664.56
75mm dia concealed sleeve pvc pipe 4kg/cm2 - RMT |  | PLUMBING MATERIAL | 88 | 1 | 88 | 88 | 88 | 88 | 0 | 0 | 88 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
800 X 2400 Nano - Moto - SQFT |  | FLOORING MATERIAL | 42 | 1 | 42 | 41.31 | 41.31 | 41.31 | 0.69 | 0 | 41.31 | 0 | 0 | 41.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
800X1600 K2-Emil Grey-Lavish - SQFT |  | FLOORING MATERIAL | 200 | 1 | 200 | 192.9 | 192.9 | 192.9 | 7.1 | 0 | 192.9 | 0 | 192.9 | 0 | 59 | 11381.1 | 192.9 | 0 | 0 | 192.9 | 192.9 | 11381.1
800X1600 PEBBLE GREY GLOSSY - SQFT |  | FLOORING MATERIAL | 14238.4 | 1.18 | 16801.32 | 14238.4 | 16801.312 | 14238.4 | 0 | 0 | 14238.4 | 0 | 14238.4 | 0 | 42.48 | 604847.232 | 0 | 14238.4 | 0 | 0 | 0 | 0
800X1600 Pebble Grey-B tile - SQFT |  | FLOORING MATERIAL | 1102 | 1 | 1102 | 1102 | 1102 | 1102 | 0 | 0 | 1102 | 0 | 1102 | 0 | 59 | 65018 | 1102 | 0 | 0 | 1102 | 1102 | 65018
AAC BLOCK_600X200X100 - CMT |  | CIVIL MATERIAL | 25 | 3399.9 | 84997.5 | 25 | 84997.5 | 25 | 0 | 0 | 25 | 0 | 25 | 0 | 4073.58 | 101839.5 | 25 | 0 | 0 | 25 | 25 | 101839.5
AAC BLOCK_600X200X150 - CMT |  | CIVIL MATERIAL | 94 | 3399.9 | 319590.6 | 94 | 319590.6 | 94 | 0 | 0 | 94 | 0 | 94 | 0 | 3901.5297 | 366743.7906 | 93.056 | 0.944 | 0 | 93.056 | 93.056 | 363109.403
AAC BLOCK_600X200X225 - CMT |  | CIVIL MATERIAL | 1084.28 | 3399.9 | 3686443.57 | 831.474 | 2826928.4526 | 831.474 | 252.806 | 0 | 831.474 | 0 | 831.474 | 0 | 3947.211 | 3282003.355 | 751.447 | 80.027 | 0 | 751.447 | 751.447 | 2977648.74
BARRICATION TAPE - NOS |  | MISC MATERIAL | 48 | 1 | 48 | 37 | 37 | 37 | 11 | 0 | 37 | 0 | 37 | 0 | 295 | 10915 | 37 | 0 | 0 | 37 | 48 | 14602.5
BLOCK MORTAR - BAGS |  | CHEMICAL | 1015 | 468.46 | 475486.9 | 815 | 381794.9 | 815 | 200 | 0 | 815 | 0 | 815 | 0 | 366.6036 | 298781.9 | 792 | 23 | 0 | 792 | 792 | 289241.6
Brass MTA CPVC 20 mm - NOS |  | PLUMBING MATERIAL | 4 | 1.18 | 4.72 | 4 | 4.72 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 166.945 | 667.78 | 4 | 0 | 0 | 4 | 4 | 667.78
BRICKS_REGULAR - NOS |  | CIVIL MATERIAL | 837339.55 | 1 | 837339.55 | 13000 | 13000 | 13000 | 824339.55 | 0 | 13000 | 0 | 13000 | 0 | 5.5446 | 72080 | 13000 | 0 | 0 | 13000 | 13000 | 88076.68
CEMENT OPC 53 GRADE BAG - BAGS |  | CIVIL MATERIAL | 883013.85 | 1 | 883013.85 | 0 | 0 | 0 | 883013.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CEMENT PPC - BAGS - BAGS |  | CIVIL MATERIAL | 3872 | 1 | 3872 | 3850 | 3850 | 3650 | 22 | 200 | 3650 | 200 | 3500 | 150 | 334.1153 | 1169403.52 | 3500 | 0 | 0 | 3500 | 4500 | 1506400.64
COARSE SAND - TONN |  | CIVIL MATERIAL | 1098.72 | 1 | 1098.72 | 982.74 | 982.74 | 982.74 | 115.98 | 0 | 982.74 | 0 | 945.36 | 37.38 | 1026.9464 | 970834.0068 | 917.22 | 28.14 | 0 | 917.22 | 917.22 | 941798.88
COVER BLOCK_20MM - NOS |  | CIVIL MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COVER BLOCK_25MM - NOS |  | CIVIL MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D WALL - SQMT |  | CIVIL MATERIAL | 7680 | 1.18 | 9062.4 | 7680 | 9062.4 | 7680 | 0 | 0 | 7680 | 0 | 7210 | 470 | 1445.85 | 10424578.5 | 2831.16 | 4378.84 | 0 | 2831.16 | 2831.16 | 4093433.1
DR.FIXIT LW+ - PAIL |  | CHEMICAL | 5 | 1.18 | 5.9 | 5 | 5.9 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 1949.952 | 9749.76 | 5 | 0 | 0 | 5 | 5 | 9749.76
DR.FIXIT_PEDECRETE URP 301- 20 KG - PAIL |  | CHEMICAL | 9 | 3733.4444 | 33601 | 9 | 33601 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 4631.28 | 41681.52 | 9 | 0 | 0 | 9 | 11 | 51180.52
EMPTY DRUM - NOS |  | MISC MATERIAL | 30 | 1.18 | 35.4 | 30 | 35.4 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 908.6 | 27258 | 30 | 0 | 0 | 30 | 30 | 27258
FAIRMATE_FAIR FIBRE - NOS |  | CHEMICAL | 1000 | 45 | 45000 | 1000 | 45000 | 1000 | 0 | 0 | 1000 | 0 | 1000 | 0 | 45.0052 | 45005.2 | 1000 | 0 | 0 | 1000 | 1000 | 45005.2
FIBRE CHICKEN MESH JALI - NOS |  | CIVIL MATERIAL | 11 | 1 | 11 | 11 | 11 | 11 | 0 | 0 | 11 | 0 | 11 | 0 | 1416 | 15576 | 10 | 1 | 0 | 10 | 10 | 14160
FINE SAND - TONN |  | CIVIL MATERIAL | 883013.85 | 1 | 883013.85 | 44 | 44 | 0 | 882969.85 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FOSROC CONBEXTRA GP2_25KG - PAIL |  | CHEMICAL | 42 | 1 | 42 | 42 | 42 | 42 | 0 | 0 | 42 | 0 | 42 | 0 | 442 | 18564 | 41 | 1 | 0 | 41 | 41 | 18127.4
FRP ISOLATED CHANNEL PATTI_2 MTR. - NOS |  | PLUMBING MATERIAL | 8 | 1 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 0 | 6 | 2 | 348.1 | 2088.6 | 6 | 0 | 0 | 6 | 6 | 2088.6
GRANITE-STEEL GREY WITH GROOVE DETAILS - SQFT |  | FLOORING MATERIAL | 105 | 1 | 105 | 101.6 | 101.6 | 101.6 | 3.4 | 0 | 101.6 | 0 | 101.6 | 0 | 86.2865 | 8766.7071 | 0 | 101.6 | 0 | 0 | 0 | 0
HALOGEN - NOS |  | ELECTRICAL MATERIAL | 2 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HASION CLOTH - RMT |  | MISC MATERIAL | 1475 | 1 | 1475 | 1475 | 1475 | 1475 | 0 | 0 | 1475 | 0 | 1475 | 0 | 30.6093 | 45148.6875 | 1400 | 75 | 0 | 1400 | 1400 | 42898.8
HOLDTITE_100 GMS - TIN |  | PLUMBING MATERIAL | 1 | 1.18 | 1.18 | 1 | 1.18 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 114.46 | 114.46 | 1 | 0 | 0 | 1 | 1 | 114.46
Insert plate 150x250 mm- 12 mm Thick - NOS |  | CIVIL MATERIAL | 110 | 1.18 | 129.8 | 74 | 87.32 | 74 | 36 | 0 | 74 | 0 | 74 | 0 | 390.3568 | 28886.4 | 74 | 0 | 0 | 74 | 74 | 28886.4
Insert plate 250x250 mm- 12 mm Thick - NOS |  | CIVIL MATERIAL | 12 | 1.18 | 14.16 | 12 | 14.16 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 926.3 | 11115.6 | 12 | 0 | 0 | 12 | 12 | 11115.6
Insert plate 250x300 mm- 12 mm Thick - NOS |  | CIVIL MATERIAL | 20 | 1.18 | 23.6 | 20 | 23.6 | 20 | 0 | 0 | 20 | 0 | 20 | 0 | 1073.8 | 21476 | 20 | 0 | 0 | 20 | 20 | 21476
Insert plate 250x350 mm -12mm Thick - NOS |  | CIVIL MATERIAL | 204 | 1.18 | 240.72 | 132 | 155.76 | 132 | 72 | 0 | 132 | 0 | 132 | 0 | 1004.7879 | 132632 | 132 | 0 | 0 | 132 | 132 | 132632
INSULATION TAPE - NOS |  | ELECTRICAL MATERIAL | 20 | 1 | 20 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 20 | 0 | 10.62 | 212.4 | 20 | 0 | 0 | 20 | 25 | 253.7
JASTI KHILLA 2" - KG |  | PLUMBING MATERIAL | 5 | 1.18 | 5.9 | 5 | 5.9 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 103.84 | 519.2 | 5 | 0 | 0 | 5 | 10 | 1109.2
JASTI KHILLA 3" - PKT |  | PLUMBING MATERIAL | 2 | 1.18 | 2.36 | 2 | 2.36 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 259.6 | 519.2 | 2 | 0 | 0 | 2 | 2 | 519.2
LED T5 - NOS |  | ELECTRICAL MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 218.4 | 655.2 | 3 | 0 | 0 | 3 | 26 | 5726.15
Leopard LEDB-789 (Carving) 600X1200 - SQFT |  | FLOORING MATERIAL | 1100 | 1.18 | 1298 | 1100 | 1298 | 1100 | 0 | 0 | 1100 | 0 | 1100 | 0 | 34.22 | 37642 | 0 | 1100 | 0 | 0 | 0 | 0
Letoza Grey william Dark 800 X 1600 - SQFT |  | FLOORING MATERIAL | 2168 | 1.18 | 2558.24 | 2168 | 2558.24 | 2168 | 0 | 0 | 2168 | 0 | 2168 | 0 | 36.58 | 79305.44 | 0 | 2168 | 0 | 0 | 0 | 0
METAL 63-90 - TONN |  | CIVIL MATERIAL | 27.49 | 1 | 27.49 | 27.49 | 27.49 | 27.49 | 0 | 0 | 27.49 | 0 | 27.49 | 0 | 689.8505 | 18963.9902 | 27.49 | 0 | 0 | 27.49 | 27.49 | 18963.99
MS HOLLOW ROUND PIPE 40MM DIA (2.5 TO 3.0MM GAUGE) - KG |  | CIVIL MATERIAL | 1026 | 1 | 1026 | 1026 | 1026 | 1026 | 0 | 0 | 1026 | 0 | 1026 | 0 | 78.0684 | 80098.164 | 1011 | 15 | 0 | 1011 | 1011 | 78956.52
MS SLEEVE PIPE - 100MM OD X 1' 6" - NOS |  | ELECTRICAL MATERIAL | 82 | 1.18 | 96.76 | 58 | 68.44 | 58 | 24 | 0 | 58 | 0 | 58 | 0 | 378.2103 | 21936.2 | 58 | 0 | 0 | 58 | 58 | 21936.2
MS SLEEVE PIPE - 100MM OD X 2' - NOS |  | ELECTRICAL MATERIAL | 30 | 1.18 | 35.4 | 26 | 30.68 | 26 | 4 | 0 | 26 | 0 | 26 | 0 | 369.8846 | 9617 | 26 | 0 | 0 | 26 | 26 | 9617
MS SLEEVE PIPE - 125MM OD X 1' 6" - NOS |  | ELECTRICAL MATERIAL | 30 | 1.18 | 35.4 | 30 | 35.4 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 531 | 15930 | 0 | 30 | 0 | 0 | 0 | 0
MS SLEEVE PIPE - 125MM OD X 2' - NOS |  | ELECTRICAL MATERIAL | 30 | 1.18 | 35.4 | 30 | 35.4 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 708 | 21240 | 0 | 30 | 0 | 0 | 0 | 0
MS SLEEVE PIPE - 141MM OD X 1' 6" - NOS |  | ELECTRICAL MATERIAL | 30 | 1.18 | 35.4 | 30 | 35.4 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 708 | 21240 | 30 | 0 | 0 | 30 | 30 | 21240
MS SLEEVE PIPE - 141MM OD X 2' - NOS |  | ELECTRICAL MATERIAL | 60 | 1.18 | 70.8 | 60 | 70.8 | 60 | 0 | 0 | 60 | 0 | 60 | 0 | 955.8 | 57348 | 60 | 0 | 0 | 60 | 60 | 57348
MS SLEEVE PIPE - 75MM OD X 1' 6" - NOS |  | ELECTRICAL MATERIAL | 650 | 1.18 | 767 | 641 | 756.38 | 641 | 9 | 0 | 641 | 0 | 641 | 0 | 255.3292 | 163666 | 641 | 0 | 0 | 641 | 641 | 163666
MS SLEEVE PIPE - 75MM OD X 2' - NOS |  | ELECTRICAL MATERIAL | 506 | 1.18 | 597.08 | 458 | 540.44 | 458 | 48 | 0 | 458 | 0 | 458 | 0 | 318.1878 | 145730 | 458 | 0 | 0 | 458 | 458 | 145730
NUT BOLT WITH WASHER 6MM - KG |  | PLUMBING MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 129.8 | 389.4 | 3 | 0 | 0 | 3 | 3 | 389.4
POP BAGS- 20 KG - NOS |  | CIVIL MATERIAL | 10 | 1.18 | 11.8 | 10 | 11.8 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 157.5 | 1575 | 0 | 10 | 0 | 0 | 0 | 0
PT CABLE WITH ACCESSORIES - RMT |  | CIVIL MATERIAL | 33000 | 1 | 33000 | 0 | 0 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PVC COMBINE BOX - 15A 2 SWITCH 2 PLUGS & 5A 2 SWITCH 2 PLUGS - NOS |  | ELECTRICAL MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 99.1267 | 297.38 | 3 | 0 | 0 | 3 | 7 | 981.78
PVC RUBBER LUBRICANT_500GM (PIPE JOINT LUBRICANT) - NOS |  | PLUMBING MATERIAL | 13 | 1 | 13 | 13 | 13 | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 71.7446 | 932.68 | 13 | 0 | 0 | 13 | 13 | 932.68
RMC M-30 - CMT |  | CIVIL MATERIAL | 0 | 0 | 0 | 48 | 220800 | 0 | -48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RMC M-35 - CMT |  | CIVIL MATERIAL | 2318.5 | 1.1662 | 2703.79 | 2318.5 | 2703.79 | 2318.5 | 0 | 0 | 2318.5 | 0 | 2318.5 | 0 | 5744.4966 | 13318615.4038 | 2282.5 | 36 | 0 | 2282.5 | 2282.5 | 13327337.78
RMC M-40 - AGILE - CMT |  | RMC MATERIAL | 3.5 | 1.18 | 4.13 | 3.5 | 4.13 | 3.5 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 6770.0043 | 23695.0151 | 3 | 0.5 | 0 | 3 | 3 | 20310.01
RMC M-40 - CMT |  | CIVIL MATERIAL | 600 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | 600 | 0 | 600 | 0 | 4950.0056 | 2970003.36 | 0 | 600 | 0 | 0 | 0 | 0
RMC M-45 - CMT |  | CIVIL MATERIAL | 30 | 1 | 30 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 6350.0047 | 190500.141 | 30 | 0 | 0 | 30 | 30 | 190500.1
SAFETY BELT WITH HARNESS - NOS |  | MISC MATERIAL | 3 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 2 | 1 | 1232 | 2464 | 2 | 0 | 0 | 2 | 4 | 4459
SILENCIO 110 MM COUPLER - NOS |  | PLUMBING MATERIAL | 10 | 1.18 | 11.8 | 10 | 11.8 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 293.112 | 2931.12 | 10 | 0 | 0 | 10 | 10 | 2931.12
SILENCIO 110 MM x 3 FT D/S PIPE - NOS |  | PLUMBING MATERIAL | 16 | 1.18 | 18.88 | 16 | 18.88 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 691.3625 | 11061.8 | 16 | 0 | 0 | 16 | 16 | 11061.8
SILENCIO 160 MM COUPLER - NOS |  | PLUMBING MATERIAL | 10 | 1 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 574.754 | 5747.54 | 10 | 0 | 0 | 10 | 10 | 5747.54
SILENCIO 160 MM x 10 FT S/S PIPE - NOS |  | PLUMBING MATERIAL | 19 | 1.18 | 22.42 | 19 | 22.42 | 19 | 0 | 0 | 19 | 0 | 19 | 0 | 2977.6358 | 56575.0802 | 19 | 0 | 0 | 19 | 19 | 56575.08
SILENCIO 160 MM x 110 MM REDUCER SINGLE Y - NOS |  | PLUMBING MATERIAL | 8 | 1.18 | 9.44 | 8 | 9.44 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 710.4775 | 5683.82 | 8 | 0 | 0 | 8 | 8 | 5683.82
STEEL GREY GRANITE - SQFT |  | FLOORING MATERIAL | 15 | 1 | 15 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STEEL_08MM - KG |  | CIVIL MATERIAL | 347813 | 1 | 347813 | 213835 | 213835 | 213835 | 133978 | 0 | 213835 | 0 | 209125 | 4710 | 63.2793 | 13233286.964 | 191445 | 17680 | 0 | 191445 | 192195 | 12509260.403
STEEL_10MM - KG |  | CIVIL MATERIAL | 344523 | 1 | 344523 | 219560 | 219560 | 219560 | 124963 | 0 | 219560 | 0 | 212630 | 6930 | 61.8679 | 13154979.328 | 185850 | 26780 | 0 | 185850 | 186160 | 12073837.299
STEEL_12MM - KG |  | CIVIL MATERIAL | 210406 | 1 | 210406 | 96673.56 | 96673.56 | 96673.56 | 113732.44 | 0 | 96673.56 | 0 | 89313.56 | 7360 | 58.7245 | 5244893.8994 | 71213 | 18100.56 | 0 | 71213 | 71573 | 4548964.703
STEEL_16MM - KG |  | CIVIL MATERIAL | 277390 | 8.2117 | 2277849 | 167390 | 2099763 | 167390 | 110000 | 0 | 167390 | 0 | 167340 | 50 | 60.2356 | 10079827.049 | 149565 | 17775 | 0 | 149565 | 156085 | 9766979.728
STEEL_20MM - KG |  | CIVIL MATERIAL | 220726 | 1 | 220726 | 94751 | 94751 | 94751 | 125975 | 0 | 94751 | 0 | 92071 | 2680 | 62.9229 | 5793369.7669 | 88595 | 3476 | 0 | 88595 | 90095 | 5693736.456
STEEL_25MM - KG |  | CIVIL MATERIAL | 232905 | 1 | 232905 | 110565 | 110565 | 110565 | 122340 | 0 | 110565 | 0 | 98295 | 12270 | 58.4323 | 5743604.2595 | 76775 | 21520 | 0 | 76775 | 78275 | 4947956.117
STEEL_32MM - KG |  | CIVIL MATERIAL | 148345 | 1 | 148345 | 108795 | 108795 | 37295 | 39550 | 71500 | 37295 | 71500 | 27795 | 9500 | 63.8322 | 1774216.754 | 27735 | 60 | 0 | 27735 | 27735 | 1770297.724
SUBMERSIBLE PUMP - NOS |  | PLUMBING MATERIAL | 1 | 26529 | 26529 | 1 | 26529 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 15466.76 | 15466.76 | 1 | 0 | 0 | 1 | 1 | 15466.76
T5 TUBE STICK - NOS |  | ELECTRICAL MATERIAL | 45 | 1 | 45 | 45 | 45 | 45 | 0 | 0 | 45 | 0 | 45 | 0 | 186.8333 | 8407.5 | 45 | 0 | 0 | 45 | 70 | 13275
TAFLON TAP - NOS |  | SANITARYWARE & CP FITTINGS | 30 | 1 | 30 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 20.06 | 601.8 | 30 | 0 | 0 | 30 | 30 | 601.8
TARPAULIN SHEET - NOS |  | MISC MATERIAL | 6 | 1 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
THREADED BAR_10MM - NOS |  | PLUMBING MATERIAL | 30 | 1 | 30 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 126.26 | 3787.8 | 30 | 0 | 0 | 30 | 30 | 3787.8
WASHER 10MM - KG |  | MISC MATERIAL | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WASHER M10 - NOS |  | MISC MATERIAL | 60 | 1 | 60 | 60 | 60 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WATER STOPPER - RMT |  | CIVIL MATERIAL | 100 | 100 | 10000 | 100 | 10000 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 100.3 | 10030 | 0 | 100 | 0 | 0 | 25 | 2743.5
WIRE BRUSH - NOS |  | HOUSEKEEPING MATERIAL | 5 | 1 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 53.1 | 265.5 | 5 | 0 | 0 | 5 | 5 | 265.5