## PO Supply Report638519020593298
PO Supply Report
From 21-02-2024 To 21-05-2024
Page 1 of 1
Total Records: 155 Records 1 To 155
Project Name | Req.SrNo | Req.No | Req. Date | Material | Unit | Req.Qty | Req.Approved Qty | PO No. | PO Date | Supplier Name | PO Qty | PO_Rate | GST Scheme | GST Amount | Other Charges Amount | POValue | GRN No. | Challan_No | GRN Date | GRN Qty | Delay days from date of PO | Store | Bill Value | Bal Qty | Bal Value | GRN_Remark | Task_Name
ANTICA GREENWOOD | 49754 | 52382 | 2024-03-11 | ALOPECIA PLANT | NOS | 10 | 10 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49753 | 52383 | 2024-03-11 | ARECA PALM | NOS | 60 | 60 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49752 | 52384 | 2024-03-11 | CARPET LAWN | NOS | 300 | 300 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49751 | 52385 | 2024-03-11 | UREA FERTILIZER | BAGS | 7 | 7 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49750 | 52386 | 2024-03-11 | Lily ( White ) | NOS | 240 | 240 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49749 | 52387 | 2024-03-11 | TOHFA PLANT | NOS | 80 | 80 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49748 | 52388 | 2024-03-11 | SPARA GRASS PLANT | NOS | 40 | 40 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49747 | 52389 | 2024-03-11 | CHAMPA PLANT | NOS | 3 | 3 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49746 | 52390 | 2024-03-11 | TRAVELLERS PALM | NOS | 4 | 4 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49745 | 52391 | 2024-03-11 | FICUS | NOS | 5 | 5 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 GARDENING WORK
ANTICA GREENWOOD | 49743 | 52410 | 2024-03-11 | ROPE LIGHT FOR CEILING ( Warm White ) | RFT | 1.5748 | 1.5748 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50474 | 53008 | 2024-04-03 | 1 SQMM 3 CORE FLEXIBLE CABLE | RMT | 55 | 55 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50473 | 53009 | 2024-04-03 | 1.5 SQMM 3 CORE FLEXIBLE CABLE | RMT | 30 | 30 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 51782 | 54409 | 2024-04-17 | GASKET | NOS | 6 | 6 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51781 | 54410 | 2024-04-17 | KOHLER_10879- IN-4-FP-CP-SINGLE BATH & SHOWER TRIM | NOS | 4 | 4 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51780 | 54411 | 2024-04-17 | WASTE COUPLLING | NOS | 6 | 6 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51779 | 54412 | 2024-04-17 | PILLAR COCK | NOS | 6 | 6 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52089 | 54442 | 2024-04-19 | BLOCK MORTAR | BAGS | 30 | 30 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 71 9" AAC BLOCK WORK
ANTICA GREENWOOD | 52087 | 54444 | 2024-04-19 | HANGING LIGHT | NOS | 6 | 6 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52418 | 55115 | 2024-05-01 | (10386IN-CP) BATH SPOUT, W/DIVERTER, FLAT FACE,160MM | NOS | 4 | 4 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52393 | 55445 | 2024-04-30 | LIFT ELEVATORS | NOS | 1 | 1 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 LIFT INSTALLATION WORK
ANTICA GREENWOOD | 52782 | 55534 | 2024-05-10 | DOOR BELL | NOS | 1 | 1 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52780 | 55536 | 2024-05-10 | BOLLARD LIGHT | NOS | 10 | 10 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49791 | 55615 | 2024-03-15 | 20MM AGGREGATE | TONN | 1.85 | 1.85 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | INFRA CIVIL EXTRA WORK
ANTICA GREENWOOD | 52401 | 54763 | 2024-05-01 | CHIMNEY | NOS | 1 | 1 | 7107 | 01 May 2024 | AARYAN KITCHEN GALLERY | 1 | 13600 | C + SGST 18% I/P URD | 0 | 0 | 13600 | 0 |  |  | 0 | -45411 |  | 0 | 1 | 13600 |  | VILLA 17 KITCHEN APPLIANCES
ANTICA GREENWOOD | 52400 | 54764 | 2024-05-01 | HOB | NOS | 1 | 1 | 7107 | 01 May 2024 | AARYAN KITCHEN GALLERY | 1 | 19900 | C + SGST 18% I/P URD | 0 | 0 | 19900 | 0 |  |  | 0 | -45411 |  | 0 | 1 | 19900 |  | VILLA 17 KITCHEN APPLIANCES
ANTICA GREENWOOD | 47660 | 50146 | 2024-02-28 | 1"_CPVC TANK NIPPLE | NOS | 4 | 4 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 4 | 127 | C + SGST 18% I/P RD | 197.52 | 0 | 508 | 30069 | 3381 | 13 Mar 2024 | 4 | 13 | Antica Site Store | 508 | 0 | 0 | 11.03.2024 | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 47659 | 50147 | 2024-02-28 | 1"_CPVC TANK NIPPLE | NOS | 4 | 4 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 4 | 127 | C + SGST 18% I/P RD | 197.52 | 0 | 508 | 30069 | 3381 | 13 Mar 2024 | 4 | 13 | Antica Site Store | 508 | 0 | 0 | 11.03.2024 | VILLA 89 PLUMBING WORK
ANTICA GREENWOOD | 47658 | 50148 | 2024-02-28 | 1"_CPVC TANK NIPPLE | NOS | 4 | 4 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 4 | 127 | C + SGST 18% I/P RD | 197.52 | 0 | 508 | 30069 | 3381 | 13 Mar 2024 | 4 | 13 | Antica Site Store | 508 | 0 | 0 | 11.03.2024 | VILLA 71 PLUMBING WORK
ANTICA GREENWOOD | 47657 | 50149 | 2024-02-28 | 1"_CPVC TANK NIPPLE | NOS | 4 | 4 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 4 | 127 | C + SGST 18% I/P RD | 197.52 | 0 | 508 | 30069 | 3381 | 13 Mar 2024 | 4 | 13 | Antica Site Store | 508 | 0 | 0 | 11.03.2024 | VILLA 02 PLUMBING WORK
ANTICA GREENWOOD | 47656 | 50150 | 2024-02-28 | 1 1/2"_CPVC TANK NIPPLE | NOS | 1 | 1 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 1 | 293 | C + SGST 18% I/P RD | 113.92 | 0 | 293 | 30068 | 3381 | 13 Mar 2024 | 1 | 13 | Antica Site Store | 293 | 0 | 0 | 11.03.2024 | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 47655 | 50151 | 2024-02-28 | 1 1/2"_CPVC TANK NIPPLE | NOS | 1 | 1 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 1 | 293 | C + SGST 18% I/P RD | 113.92 | 0 | 293 | 30068 | 3381 | 13 Mar 2024 | 1 | 13 | Antica Site Store | 293 | 0 | 0 | 11.03.2024 | VILLA 89 PLUMBING WORK
ANTICA GREENWOOD | 47654 | 50152 | 2024-02-28 | 1 1/2"_CPVC TANK NIPPLE | NOS | 1 | 1 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 1 | 293 | C + SGST 18% I/P RD | 113.92 | 0 | 293 | 30068 | 3381 | 13 Mar 2024 | 1 | 13 | Antica Site Store | 293 | 0 | 0 | 11.03.2024 | VILLA 71 PLUMBING WORK
ANTICA GREENWOOD | 47653 | 50153 | 2024-02-28 | 1 1/2"_CPVC TANK NIPPLE | NOS | 1 | 1 | 6827 | 29 Feb 2024 | Arihant Trade Centre | 1 | 293 | C + SGST 18% I/P RD | 113.92 | 0 | 293 | 30068 | 3381 | 13 Mar 2024 | 1 | 13 | Antica Site Store | 293 | 0 | 0 | 11.03.2024 | VILLA 02 PLUMBING WORK
ANTICA GREENWOOD | 49776 | 52402 | 2024-03-13 | 110 MM ECO DRAIN PIPE | RFT | 40 | 40 | 6915 | 14 Mar 2024 | Arihant Trade Centre | 40 | 111.89 | C + SGST 18% I/P RD | 443.08 | 0 | 4475.6 | 30445 | 3554 | 02 Apr 2024 | 40 | 19 | Antica Site Store | 4475.6 | 0 | 0 | 22.03.2024 | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51777 | 54414 | 2024-04-17 | 12" x 12" DRAIN JALI | NOS | 2 | 0 | 7069 | 20 Apr 2024 | Arihant Trade Centre | 0 | 2138 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45400 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51776 | 54415 | 2024-04-17 | 6" X 6"-3 PIC. JALI | NOS | 9 | 0 | 7069 | 20 Apr 2024 | Arihant Trade Centre | 0 | 340 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45400 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52197 | 54448 | 2024-04-20 | WC CONNECTOR | NOS | 6 | 0 | 7069 | 20 Apr 2024 | Arihant Trade Centre | 0 | 107 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45400 |  | 0 | 0 | 0 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51777 | 54455 | 2024-04-17 | 12" x 12" DRAIN JALI | NOS | 2 | 2 | 7073 | 20 Apr 2024 | Arihant Trade Centre | 2 | 2138 | C + SGST 18% I/P RD | 500.3 | 0 | 4276 | 0 |  |  | 0 | -45400 |  | 0 | 2 | 4276 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 51776 | 54456 | 2024-04-17 | 6" X 6"-3 PIC. JALI | NOS | 9 | 9 | 7073 | 20 Apr 2024 | Arihant Trade Centre | 9 | 340 | C + SGST 18% I/P RD | 358.02 | 0 | 3060 | 0 |  |  | 0 | -45400 |  | 0 | 9 | 3060 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 53071 | 55812 | 2024-05-21 | U shaped Rail 600 x 100 mm | NOS | 1 | 1 | 7194 | 21 May 2024 | Arihant Trade Centre | 1 | 6067.8 | C + SGST 18% I/P RD | 1092.2 | 0 | 6067.8 | 0 |  |  | 0 | -45431 |  | 0 | 1 | 6067.8 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52781 | 55535 | 2024-05-10 | SPIKE LIGHT | NOS | 15 | 15 | 7150 | 10 May 2024 | Ark Communication | 15 | 490 | C + SGST 18% I/P RD | 1323 | 0 | 7350 | 0 |  |  | 0 | -45420 |  | 0 | 15 | 7350 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49794 | 52432 | 2024-03-15 | RMC M-20 | CMT | 7 | 7 | 6940 | 16 Mar 2024 | Concept RMC | 7 | 3957.62 | C + SGST 18% I/P RD | 8370.36 | 0 | 27703.34 | 30530 | 1037 | 03 Apr 2024 | 7 | 18 | Antica Site Store | 27703.34 | 0 | 0 | 13.03.2024 | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB
ANTICA GREENWOOD | 49793 | 52433 | 2024-03-15 | RMC M-20 | CMT | 4.75 | 4.75 | 6940 | 16 Mar 2024 | Concept RMC | 4.75 | 3957.62 | C + SGST 18% I/P RD | 8370.36 | 0 | 18798.695 | 30531 | 1051 | 03 Apr 2024 | 4.5 | 18 | Antica Site Store | 17809.29 | 0.25 | 989.405 | 16.03.2024 | VILLA 89 CIVIL WORK UP TO GROUND FLOOR RCC
ANTICA GREENWOOD | 49740 | 52396 | 2024-03-11 | 200 Ltr. HEAT ABSORPTION WATER HEATER | NOS | 1 | 1 | 6916 | 14 Mar 2024 | Devyami Automatic Pumps & Controls P.Ltd | 1 | 120000 | C + SGST 18% I/P RD | 18360 | 0 | 120000 | 30447 | 1372 | 02 Apr 2024 | 1 | 19 | Antica Site Store | 120000 | 0 | 0 | 16.03.2024 | VILLA 17 SOFTNER INSTALLATION
ANTICA GREENWOOD | 49739 | 52397 | 2024-03-11 | MANUAL SOFTENER(100 Ltr) | NOS | 1 | 1 | 6916 | 14 Mar 2024 | Devyami Automatic Pumps & Controls P.Ltd | 1 | 46000 | C + SGST 18% I/P RD | 7038 | 0 | 46000 | 30449 | 1372 | 02 Apr 2024 | 1 | 19 | Antica Site Store | 46000 | 0 | 0 | 16.03.2024 | VILLA 17 SOFTNER INSTALLATION
ANTICA GREENWOOD | 49738 | 52398 | 2024-03-11 | SOFTNER FEED WATER PUMP | NOS | 1 | 1 | 6916 | 14 Mar 2024 | Devyami Automatic Pumps & Controls P.Ltd | 1 | 18100 | C + SGST 18% I/P RD | 2769.3 | 0 | 18100 | 30450 | 1372 | 02 Apr 2024 | 1 | 19 | Antica Site Store | 18100 | 0 | 0 | 16.03.2024 | VILLA 17 SOFTNER INSTALLATION
ANTICA GREENWOOD | 49780 | 52404 | 2024-03-13 | 15 LTR RO UNDER SINK PRESSURISED SYSTEM | NOS | 1 | 1 | 6916 | 14 Mar 2024 | Devyami Automatic Pumps & Controls P.Ltd | 1 | 25800 | C + SGST 18% I/P RD | 3947.4 | 0 | 25800 | 30446 | 1372 | 02 Apr 2024 | 1 | 19 | Antica Site Store | 25800 | 0 | 0 | 16.03.2024 | VILLA 17 SOFTNER INSTALLATION
ANTICA GREENWOOD | 49779 | 52405 | 2024-03-13 | HYDRO PNEUMATIC SUBMERSIBLE PRESSURE SYSTEM | NOS | 1 | 1 | 6916 | 14 Mar 2024 | Devyami Automatic Pumps & Controls P.Ltd | 1 | 45800 | C + SGST 18% I/P RD | 7007.4 | 0 | 45800 | 30448 | 1372 | 02 Apr 2024 | 1 | 19 | Antica Site Store | 45800 | 0 | 0 | 16.03.2024 | VILLA 17 SOFTNER INSTALLATION
ANTICA GREENWOOD | 49801 | 52434 | 2024-03-15 | JUNCTION BOX - WEATHER PROOF | NOS | 5 | 5 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 5 | 35 | C + SGST 18% I/P RD | 31.5 | 0 | 175 | 0 |  |  | 0 | -45364 |  | 0 | 5 | 175 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49800 | 52435 | 2024-03-15 | 4U NETWORK RACK 550MMX450MM | NOS | 1 | 1 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 1 | 2600 | C + SGST 18% I/P RD | 468 | 0 | 2600 | 0 |  |  | 0 | -45364 |  | 0 | 1 | 2600 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49799 | 52436 | 2024-03-15 | 4TB HARD DISK | NOS | 1 | 1 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 1 | 5000 | C + SGST 18% I/P RD | 900 | 0 | 5000 | 0 |  |  | 0 | -45364 |  | 0 | 1 | 5000 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49798 | 52437 | 2024-03-15 | 8 PORT POE SWITCH | NOS | 1 | 1 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 1 | 4200 | C + SGST 18% I/P RD | 756 | 0 | 4200 | 0 |  |  | 0 | -45364 |  | 0 | 1 | 4200 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49797 | 52438 | 2024-03-15 | IP CAMERA - 2MP | NOS | 5 | 5 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 5 | 3250 | C + SGST 18% I/P RD | 2925 | 0 | 16250 | 0 |  |  | 0 | -45364 |  | 0 | 5 | 16250 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49796 | 52439 | 2024-03-15 | RJ-45 CONNECTOR | NOS | 10 | 10 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 10 | 15 | C + SGST 18% I/P RD | 27 | 0 | 150 | 0 |  |  | 0 | -45364 |  | 0 | 10 | 150 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49795 | 52440 | 2024-03-15 | HIKVISION 8 CHANNEL NVR | NOS | 1 | 1 | 6930 | 15 Mar 2024 | HD Infosys & Automation | 1 | 6200 | C + SGST 18% I/P RD | 1116 | 0 | 6200 | 0 |  |  | 0 | -45364 |  | 0 | 1 | 6200 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 47649 | 50138 | 2024-02-27 | BINDING WIRE | KG | 25 | 25 | 6829 | 29 Feb 2024 | HINDUSTAN HARDWARE | 25 | 65 | C + SGST 18% I/P RD | 292.5 | 0 | 1625 | 29975 | 2657 | 11 Mar 2024 | 25 | 11 | Antica Site Store | 1625 | 0 | 0 | 09.03.2024 | INFRA CIVIL EXTRA WORK
ANTICA GREENWOOD | 52785 | 55531 | 2024-05-10 | WASTE COUPLING | NOS | 1 | 1 | 7151 | 10 May 2024 | HINDUSTAN HARDWARE | 1 | 250 | C + SGST 18% I/P RD | 90 | 0 | 250 | 0 |  |  | 0 | -45420 |  | 0 | 1 | 250 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52776 | 55540 | 2024-05-10 | GREEN BREADED PIPE(CURING)_3/4"_30 MTR | RMT | 90 | 90 | 7151 | 10 May 2024 | HINDUSTAN HARDWARE | 90 | 28.333 | C + SGST 18% I/P RD | 459 | 0 | 2549.97 | 0 |  |  | 0 | -45420 |  | 0 | 90 | 2549.97 |  | INFRA GARDEN WORK
ANTICA GREENWOOD | 49381 | 51963 | 2024-03-05 | EXHAUST FAN | NOS | 6 | 6 | 6858 | 06 Mar 2024 | Indian Light House | 6 | 1200 | C + SGST 18% I/P RD | 1296 | 0 | 7200 | 30984 | 070 | 01 May 2024 | 4 | 56 | Antica Site Store | 4800 | 0 | 0 | 29/04/2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49381 | 51963 | 2024-03-05 | EXHAUST FAN | NOS | 6 | 6 | 6858 | 06 Mar 2024 | Indian Light House | 6 | 1200 | C + SGST 18% I/P RD | 1296 | 0 | 7200 | 30328 | 5859 | 28 Mar 2024 | 2 | 22 | Antica Site Store | 2400 | 4 | 4800 | 02.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49380 | 51964 | 2024-03-05 | ATOMBREG 1200MM RENESA PRIME CEILING FAN IN WHITE BODY | NOS | 12 | 12 | 6858 | 06 Mar 2024 | Indian Light House | 12 | 2840 | C + SGST 18% I/P RD | 6134.4 | 0 | 34080 | 30327 | 5859 | 28 Mar 2024 | 12 | 22 | Antica Site Store | 34080 | 0 | 0 | 02.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49379 | 51965 | 2024-03-05 | PHILIPS 6/8W PICTURE LIGHT IN BLACK BODY | NOS | 8 | 8 | 6858 | 06 Mar 2024 | Indian Light House | 8 | 1200 | C + SGST 18% I/P RD | 1728 | 0 | 9600 | 30330 | 5859 | 28 Mar 2024 | 8 | 22 | Antica Site Store | 9600 | 0 | 0 | 02.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49378 | 51966 | 2024-03-05 | PHILIPS 7W SURFACE RIMLESS 6Watt 4k | NOS | 20 | 20 | 6858 | 06 Mar 2024 | Indian Light House | 20 | 500 | C + SGST 18% I/P RD | 1800 | 0 | 10000 | 30332 | 5859 | 28 Mar 2024 | 20 | 22 | Antica Site Store | 10000 | 0 | 0 | 02.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49377 | 51967 | 2024-03-05 | PHILIPS 7W COB ASTRA SPOT 4K WHITE IN BODY COLOUR | NOS | 61 | 61 | 6858 | 06 Mar 2024 | Indian Light House | 61 | 700 | C + SGST 18% I/P RD | 7686 | 0 | 42700 | 30331 | 5859 | 28 Mar 2024 | 61 | 22 | Antica Site Store | 42700 | 0 | 0 | 02.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49376 | 51968 | 2024-03-05 | PHILIPS 12W COB ASTRA SPOT 4K WHITE IN BODY COLOUR | NOS | 85 | 85 | 6858 | 06 Mar 2024 | Indian Light House | 85 | 950 | C + SGST 18% I/P RD | 14535 | 0 | 80750 | 30329 | 5859 | 28 Mar 2024 | 85 | 22 | Antica Site Store | 80750 | 0 | 0 | 02.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49744 | 52392 | 2024-03-11 | ROPE LIGHT CONNECTOR | NOS | 4 | 4 | 6918 | 14 Mar 2024 | Indian Light House | 4 | 175 | C + SGST 12% I/P RD | 84 | 0 | 700 | 30333 | 5860 | 28 Mar 2024 | 4 | 14 | Antica Site Store | 700 | 0 | 0 | 19.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49743 | 52393 | 2024-03-11 | ROPE LIGHT FOR CEILING ( Warm White ) | RFT | 100 | 98.4252 | 6918 | 14 Mar 2024 | Indian Light House | 98.4252 | 35.06 | C + SGST 18% I/P RD | 621.14 | 0 | 3450.7875 | 30334 | 5860 | 28 Mar 2024 | 98.4252 | 14 | Antica Site Store | 3450.7875 | 0 | 0 | 19.03.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50475 | 53007 | 2024-04-03 | 2M FOOT LIGHT | NOS | 4 | 4 | 7146 | 09 May 2024 | Indian Light House | 4 | 650 | C + SGST 18% I/P RD | 468 | 0 | 2600 | 0 |  |  | 0 | -45419 |  | 0 | 4 | 2600 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52086 | 54445 | 2024-04-19 | LED STRIP LIGHT | RMT | 20 | 20 | 7083 | 23 Apr 2024 | Indian Light House | 20 | 320 | C + SGST 18% I/P RD | 1152 | 0 | 6400 | 31276 | 071 | 16 May 2024 | 20 | 23 | Antica Site Store | 6400 | 0 | 0 | 29.04.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52085 | 54446 | 2024-04-19 | 12 A DRIVER | NOS | 1 | 1 | 7083 | 23 Apr 2024 | Indian Light House | 1 | 550 | C + SGST 18% I/P RD | 99 | 0 | 550 | 31275 | 071 | 16 May 2024 | 1 | 23 | Antica Site Store | 550 | 0 | 0 | 29.04.2024 | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 47651 | 50145 | 2024-02-28 | CEMENT PPC - BAGS | BAGS | 60 | 60 | 6818 | 28 Feb 2024 | J K Cement Works | 60 | 250 | C + SGST 28% I/P RD | 18200 | 0 | 15000 | 29755 | 5841 | 04 Mar 2024 | 60 | 5 | Antica Site Store | 15000 | 0 | 0 | 26.02.2024 | INFRA WORK ROAD SIDE RAIN WATER CHANNEL
ANTICA GREENWOOD | 52201 | 54625 | 2024-04-22 | CEMENT PPC - BAGS | BAGS | 120 | 120 | 7080 | 22 Apr 2024 | J K Cement Works | 120 | 242.19 | C + SGST 28% I/P RD | 8137.58 | 0 | 29062.8 | 31020 | 6419 | 03 May 2024 | 120 | 11 | Antica Site Store | 29062.8 | 0 | 0 | 22.04.2024 | VILLA 89 PLASTER WORK
ANTICA GREENWOOD | 52088 | 54443 | 2024-04-19 | 8 SWG COPPER EARTH WIRE (RMT) | RMT | 60 | 60 | 7072 | 20 Apr 2024 | JATIN ELECTRICALS | 60 | 105 | C + SGST 18% I/P RD | 1134 | 0 | 6300 | 0 |  |  | 0 | -45400 |  | 0 | 60 | 6300 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 53072 | 55811 | 2024-05-21 | 2400 MM X 800 MM - MOTTO_CRYSTAL WHITE | SQFT | 830 | 830 | 7193 | 21 May 2024 | JAY SHREE CHAMUNDA CERAMICS | 830 | 92 | C + SGST 18% I/P RD | 13744.8 | 0 | 76360 | 0 |  |  | 0 | -45431 |  | 0 | 830 | 76360 |  | VILLA 89 FLOORING WORK
ANTICA GREENWOOD | 52197 | 54454 | 2024-04-20 | WC CONNECTOR | NOS | 6 | 6 | 7074 | 20 Apr 2024 | KALPVRUKSH TRADERS | 6 | 107 | C + SGST 18% I/P RD | 63.56 | 0 | 642 | 0 |  |  | 0 | -45400 |  | 0 | 6 | 642 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52974 | 55643 | 2024-05-15 | AAC BLOCK_600X200X225 | CMT | 17 | 17 | 7175 | 16 May 2024 | Kunthunath Enterprise | 17 | 3392.86 | C + SGST 12% I/P RD | 6921.44 | 0 | 57678.62 | 0 |  |  | 0 | -45426 |  | 0 | 17 | 57678.62 |  | VILLA A4 UP TO GROUND FLOOR 9" ACC BLOCK MASONRY
ANTICA GREENWOOD | 51714 | 54316 | 2024-04-15 | BLOCK MORTAR | BAGS | 30 | 30 | 7043 | 16 Apr 2024 | Laxmi Trading & Company | 30 | 285 | C + SGST 18% I/P RD | 1539 | 0 | 8550 | 30855 | 212 | 28 Apr 2024 | 30 | 12 | Antica Site Store | 8550 | 0 | 0 | 23/04/2024 | VILLA 71 UP TO FIRST FLOOR MASONRY WORK
ANTICA GREENWOOD | 47662 | 50156 | 2024-02-28 | SPLIT AC 2 TONN | NOS | 9 | 9 | 6828 | 29 Feb 2024 | Lynx Communication Systems Pvt.Ltd. | 9 | 33936 | C + SGST 28% I/P RD | 85518.72 | 0 | 305424 | 30444 | 115 | 02 Apr 2024 | 2 | 33 | Antica Site Store | 67872 | 0 | 0 | 30.03.2024 | VILLA 17 AC INSTALLATION WORK
ANTICA GREENWOOD | 47662 | 50156 | 2024-02-28 | SPLIT AC 2 TONN | NOS | 9 | 9 | 6828 | 29 Feb 2024 | Lynx Communication Systems Pvt.Ltd. | 9 | 33936 | C + SGST 28% I/P RD | 85518.72 | 0 | 305424 | 30211 | 049 | 20 Mar 2024 | 7 | 20 | Antica Site Store | 237552 | 2 | 67872 | 14.03.2024 | VILLA 17 AC INSTALLATION WORK
ANTICA GREENWOOD | 52419 | 55114 | 2024-05-03 | NATURAL WHITE MARBLE | SQFT | 35 | 35 | 7119 | 04 May 2024 | Mitesh Marble | 35 | 300 | C + SGST 18% I/P RD | 1890 | 0 | 10500 | 0 |  |  | 0 | -45414 |  | 0 | 35 | 10500 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49777 | 52401 | 2024-03-13 | 24" x 24" SIMPLE POLISH KOTA STONE | SQFT | 900 | 900 | 6921 | 14 Mar 2024 | SAWARIYA GRANITE INDUSTRIES | 900 | 32 | C + SGST 5% I/P RD | 1440 | 0 | 28800 | 30206 | 164 | 20 Mar 2024 | 900 | 6 | Antica Site Store | 28800 | 0 | 0 | 16.03.2024_225 NOS | VILLA 17 FLOORING WORK
ANTICA GREENWOOD | 49126 | 51969 | 2024-03-01 | COFFEE BROWN GRANITE | SQFT | 300 | 300 | 6879 | 09 Mar 2024 | SHAKTI GRANITE | 300 | 120 | C + SGST 18% I/P RD | 6480 | 0 | 36000 | 30463 | 172 | 02 Apr 2024 | 289 | 24 | Antica Site Store | 34680 | 0 | 0 | 20.03.2024 | VILLA 17 FLOORING WORK
ANTICA GREENWOOD | 49126 | 51969 | 2024-03-01 | COFFEE BROWN GRANITE | SQFT | 300 | 300 | 6879 | 09 Mar 2024 | SHAKTI GRANITE | 300 | 120 | C + SGST 18% I/P RD | 6480 | 0 | 36000 | 30258 | 172 | 21 Mar 2024 | 11 | 12 | Antica Site Store | 1320 | 289 | 34680 | 20/03/2024 | VILLA 17 FLOORING WORK
ANTICA GREENWOOD | 49125 | 51970 | 2024-03-01 | 24" X 24" LEATHER FINISH KOTA STONE | SQFT | 200 | 200 | 6879 | 09 Mar 2024 | SHAKTI GRANITE | 200 | 45 | C + SGST 5% I/P RD | 450 | 0 | 9000 | 30212 | 171 | 20 Mar 2024 | 200 | 11 | Antica Site Store | 9000 | 0 | 0 | 16.03.2024 | VILLA 17 PARKING FLOORING WORK
ANTICA GREENWOOD | 51715 | 54315 | 2024-04-15 | COFFEE BROWN GRANITE | SQFT | 240 | 240 | 7041 | 16 Apr 2024 | SHAKTI GRANITE | 240 | 120 | C + SGST 18% I/P RD | 5184 | 0 | 28800 | 30998 | 8 | 03 May 2024 | 240 | 17 | Antica Site Store | 28800 | 0 | 0 | 19.04.2024 REC-250SQFT | VILLA 17 FLOORING WORK
ANTICA GREENWOOD | 47650 | 50137 | 2024-02-27 | 2 1/2" NAILS | KG | 25 | 25 | 6824 | 29 Feb 2024 | SHRAVAN ENTERPRISE | 25 | 88 | C + SGST 18% I/P RD | 396 | 0 | 2200 | 0 |  |  | 0 | -45349 |  | 0 | 25 | 2200 |  | INFRA CIVIL EXTRA WORK
ANTICA GREENWOOD | 49792 | 55612 | 2024-03-15 | COARSE SAND | TONN | 30 | 30 | 7166 | 14 May 2024 | Shree Mahalaxmi Transport | 30 | 875 | C + SGST 5% I/P RD | 1934.18 | 0 | 26250 | 0 |  |  | 0 | -45424 |  | 0 | 30 | 26250 |  | INFRA CIVIL EXTRA WORK
ANTICA GREENWOOD | 49791 | 55613 | 2024-03-15 | 20MM AGGREGATE | TONN | 30 | 28.15 | 7166 | 14 May 2024 | Shree Mahalaxmi Transport | 28.15 | 950 | C + SGST 5% I/P RD | 1337.12 | 0 | 26742.5 | 0 |  |  | 0 | -45424 |  | 0 | 28.15 | 26742.5 |  | INFRA CIVIL EXTRA WORK
ANTICA GREENWOOD | 52220 | 54627 | 2024-04-23 | ROFF- T29 MASTER-FIX ADHESIVE -MFA | TIN | 2 | 2 | 7082 | 23 Apr 2024 | Shree Ram Agency | 2 | 1567.79 | C + SGST 18% I/P RD | 564.4 | 0 | 3135.58 | 0 |  |  | 0 | -45403 |  | 0 | 2 | 3135.58 |  | VILLA 71 DOOR & WINDOW FRAME WORK
ANTICA GREENWOOD | 51778 | 54413 | 2024-04-17 | (16346IN-CP) KOHLER MAKE -SHOWER ARM | NOS | 4 | 4 | 7071 | 20 Apr 2024 | Shreeji Spacio Solutions Pvt. Ltd | 4 | 4160 | C + SGST 18% I/P RD | 1779.14 | 0 | 16640 | 31202 | 175 | 13 May 2024 | 1 | 23 | Antica Site Store | 4160 | 3 | 12480 | 05.05.2024 | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52198 | 54453 | 2024-04-20 | (22541IN-4FP-CP) HONE RECESSED BATH & SHOWER TRIM | NOS | 4 | 4 | 7071 | 20 Apr 2024 | Shreeji Spacio Solutions Pvt. Ltd | 4 | 5250 | C + SGST 18% I/P RD | 2404.08 | 0 | 21000 | 0 |  |  | 0 | -45400 |  | 0 | 4 | 21000 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52417 | 55116 | 2024-05-01 | 75376IN-1 TRACE VESSEL WITH 1TH | NOS | 2 | 2 | 7145 | 09 May 2024 | Shreeji Spacio Solutions Pvt. Ltd | 2 | 12000 | C + SGST 18% I/P RD | 2566.08 | 0 | 24000 | 0 |  |  | 0 | -45419 |  | 0 | 2 | 24000 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52755 | 55511 | 2024-05-09 | 20138IN-CP -COMPLEMENTARY SQUARE SHOWERARM WALL MOUNT | NOS | 2 | 2 | 7145 | 09 May 2024 | Shreeji Spacio Solutions Pvt. Ltd | 2 | 966.83 | C + SGST 18% I/P RD | 348.06 | 0 | 1933.66 | 0 |  |  | 0 | -45419 |  | 0 | 2 | 1933.66 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 52777 | 55539 | 2024-05-10 | K-22534IN-4ND-CP SINGLE CONTROL BASIN FAUCET W/O DRAIN IN PO | NOS | 2 | 2 | 7149 | 10 May 2024 | Shreeji Spacio Solutions Pvt. Ltd | 2 | 9250 | C + SGST 18% I/P RD | 2117.88 | 0 | 18500 | 0 |  |  | 0 | -45420 |  | 0 | 2 | 18500 |  | VILLA 17 PLUMBING WORK
ANTICA GREENWOOD | 50042 | 52519 | 2024-03-26 | 15 AMP SWITCH | NOS | 7 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 436 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50041 | 52520 | 2024-03-26 | 15 AMP SOCKET | NOS | 4 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 562 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50040 | 52521 | 2024-03-26 | 15 AMP INDICATOR SWITCH | NOS | 7 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 436 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50039 | 52522 | 2024-03-26 | ROUND FAN PLATE 7" DIA | NOS | 20 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 40 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50038 | 52523 | 2024-03-26 | 5 AMP SWITCH | NOS | 15 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 210 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50037 | 52524 | 2024-03-26 | 5 AMP SOCKET | NOS | 15 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 278 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50036 | 52525 | 2024-03-26 | 6 MODULE PLATE | NOS | 8 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 562 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50035 | 52526 | 2024-03-26 | 2 MODULE PLATE | NOS | 6 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 262 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50034 | 52527 | 2024-03-26 | 4 MODULE PLATE | NOS | 4 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 306 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50033 | 52528 | 2024-03-26 | 8 MODULE PLATE | NOS | 12 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 624 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50032 | 52529 | 2024-03-26 | 3 MODULE PLATE | NOS | 3 | 0 | 6958 | 26 Mar 2024 | Smit Enterprise | 0 | 292 | C + SGST 18% I/P RD | 0 | 0 | 0 | 0 |  |  | 0 | -45375 |  | 0 | 0 | 0 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50040 | 54008 | 2024-03-26 | 15 AMP INDICATOR SWITCH | NOS | 7 | 7 | 7008 | 09 Apr 2024 | Smit Enterprise | 7 | 436 | C + SGST 18% I/P RD | 203.26 | 0 | 3052 | 0 |  |  | 0 | -45389 |  | 0 | 7 | 3052 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50041 | 54009 | 2024-03-26 | 15 AMP SOCKET | NOS | 4 | 4 | 7008 | 09 Apr 2024 | Smit Enterprise | 4 | 562 | C + SGST 18% I/P RD | 149.72 | 0 | 2248 | 0 |  |  | 0 | -45389 |  | 0 | 4 | 2248 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50042 | 54010 | 2024-03-26 | 15 AMP SWITCH | NOS | 7 | 7 | 7008 | 09 Apr 2024 | Smit Enterprise | 7 | 436 | C + SGST 18% I/P RD | 203.26 | 0 | 3052 | 0 |  |  | 0 | -45389 |  | 0 | 7 | 3052 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50035 | 54011 | 2024-03-26 | 2 MODULE PLATE | NOS | 6 | 6 | 7008 | 09 Apr 2024 | Smit Enterprise | 6 | 262 | C + SGST 18% I/P RD | 104.7 | 0 | 1572 | 0 |  |  | 0 | -45389 |  | 0 | 6 | 1572 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50032 | 54012 | 2024-03-26 | 3 MODULE PLATE | NOS | 3 | 3 | 7008 | 09 Apr 2024 | Smit Enterprise | 3 | 292 | C + SGST 18% I/P RD | 58.34 | 0 | 876 | 0 |  |  | 0 | -45389 |  | 0 | 3 | 876 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50034 | 54013 | 2024-03-26 | 4 MODULE PLATE | NOS | 4 | 4 | 7008 | 09 Apr 2024 | Smit Enterprise | 4 | 306 | C + SGST 18% I/P RD | 81.52 | 0 | 1224 | 0 |  |  | 0 | -45389 |  | 0 | 4 | 1224 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50037 | 54014 | 2024-03-26 | 5 AMP SOCKET | NOS | 15 | 15 | 7008 | 09 Apr 2024 | Smit Enterprise | 15 | 278 | C + SGST 18% I/P RD | 277.72 | 0 | 4170 | 0 |  |  | 0 | -45389 |  | 0 | 15 | 4170 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50038 | 54015 | 2024-03-26 | 5 AMP SWITCH | NOS | 15 | 15 | 7008 | 09 Apr 2024 | Smit Enterprise | 15 | 210 | C + SGST 18% I/P RD | 209.8 | 0 | 3150 | 0 |  |  | 0 | -45389 |  | 0 | 15 | 3150 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50036 | 54016 | 2024-03-26 | 6 MODULE PLATE | NOS | 8 | 8 | 7008 | 09 Apr 2024 | Smit Enterprise | 8 | 562 | C + SGST 18% I/P RD | 299.44 | 0 | 4496 | 0 |  |  | 0 | -45389 |  | 0 | 8 | 4496 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50033 | 54017 | 2024-03-26 | 8 MODULE PLATE | NOS | 12 | 12 | 7008 | 09 Apr 2024 | Smit Enterprise | 12 | 624 | C + SGST 18% I/P RD | 498.7 | 0 | 7488 | 0 |  |  | 0 | -45389 |  | 0 | 12 | 7488 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 50039 | 54018 | 2024-03-26 | ROUND FAN PLATE 7" DIA | NOS | 20 | 20 | 7008 | 09 Apr 2024 | Smit Enterprise | 20 | 40 | C + SGST 18% I/P RD | 144 | 0 | 800 | 0 |  |  | 0 | -45389 |  | 0 | 20 | 800 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52422 | 55361 | 2024-05-03 | 6 SQMM X 2 CORE COPPER FLEXIBLE CABLE | RMT | 15 | 15 | 7156 | 13 May 2024 | Synergy Lightings | 15 | 133.98 | C + SGST 18% I/P RD | 361.74 | 0 | 2009.7 | 0 |  |  | 0 | -45423 |  | 0 | 15 | 2009.7 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52421 | 55362 | 2024-05-03 | 2.5 SQMM 4 CORE COPPER FLEXIBLE WIRE | RMT | 18 | 18 | 7156 | 13 May 2024 | Synergy Lightings | 18 | 116.16 | C + SGST 18% I/P RD | 376.36 | 0 | 2090.88 | 0 |  |  | 0 | -45423 |  | 0 | 18 | 2090.88 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52420 | 55363 | 2024-05-03 | 10 SQMM 4 CORE COPPER FLEXIBLE WIRE | RMT | 18 | 18 | 7156 | 13 May 2024 | Synergy Lightings | 18 | 434 | C + SGST 18% I/P RD | 1406.16 | 0 | 7812 | 0 |  |  | 0 | -45423 |  | 0 | 18 | 7812 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52784 | 55532 | 2024-05-10 | TRANSPERENT WIRE | RMT | 15 | 15 | 7156 | 13 May 2024 | Synergy Lightings | 15 | 60 | C + SGST 18% I/P RD | 162 | 0 | 900 | 0 |  |  | 0 | -45423 |  | 0 | 15 | 900 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52783 | 55533 | 2024-05-10 | WALL LIGHT | NOS | 4 | 4 | 7156 | 13 May 2024 | Synergy Lightings | 4 | 340 | C + SGST 18% I/P RD | 244.8 | 0 | 1360 | 0 |  |  | 0 | -45423 |  | 0 | 4 | 1360 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52779 | 55537 | 2024-05-10 | 15MM ALUMINIUM PROFILE | RFT | 60 | 60 | 7156 | 13 May 2024 | Synergy Lightings | 60 | 16.66 | C + SGST 18% I/P RD | 179.92 | 0 | 999.6 | 0 |  |  | 0 | -45423 |  | 0 | 60 | 999.6 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52778 | 55538 | 2024-05-10 | EXHAUST FAN | NOS | 6 | 6 | 7156 | 13 May 2024 | Synergy Lightings | 6 | 845 | C + SGST 18% I/P RD | 912.6 | 0 | 5070 | 0 |  |  | 0 | -45423 |  | 0 | 6 | 5070 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52816 | 55553 | 2024-05-11 | ANGLE HOLDER | NOS | 8 | 8 | 7156 | 13 May 2024 | Synergy Lightings | 8 | 22 | C + SGST 18% I/P RD | 31.68 | 0 | 176 | 0 |  |  | 0 | -45423 |  | 0 | 8 | 176 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52815 | 55554 | 2024-05-11 | J-HOOK | NOS | 2 | 2 | 7156 | 13 May 2024 | Synergy Lightings | 2 | 32 | C + SGST 18% I/P RD | 11.52 | 0 | 64 | 0 |  |  | 0 | -45423 |  | 0 | 2 | 64 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52814 | 55555 | 2024-05-11 | ROUND FAN PLATE 7" DIA | NOS | 2 | 2 | 7156 | 13 May 2024 | Synergy Lightings | 2 | 24 | C + SGST 18% I/P RD | 8.64 | 0 | 48 | 0 |  |  | 0 | -45423 |  | 0 | 2 | 48 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52813 | 55556 | 2024-05-11 | 10 SQMM RING TYPE COPPER LUG | NOS | 20 | 20 | 7156 | 13 May 2024 | Synergy Lightings | 20 | 6 | C + SGST 18% I/P RD | 21.6 | 0 | 120 | 0 |  |  | 0 | -45423 |  | 0 | 20 | 120 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 52812 | 55557 | 2024-05-11 | 2.5 SQMM RING TYPE COPPER LUG | NOS | 4 | 4 | 7156 | 13 May 2024 | Synergy Lightings | 4 | 2.05 | C + SGST 18% I/P RD | 1.48 | 0 | 8.2 | 0 |  |  | 0 | -45423 |  | 0 | 4 | 8.2 |  | VILLA 17 ELECTRICAL WORK
ANTICA GREENWOOD | 49742 | 52394 | 2024-03-11 | CONSOLE TABLE WITH MARBLE | NOS | 1 | 1 | 6911 | 13 Mar 2024 | Technocrat Engineers | 1 | 34152 | C + SGST 18% I/P RD | 6147.36 | 1770 | 34152 | 0 |  |  | 0 | -45362 |  | 0 | 1 | 34152 |  | VILLA 17 CARPENTRY WORK
ANTICA GREENWOOD | 49741 | 52395 | 2024-03-11 | INDIAN MADE DESIGNER EXPOSE WOODEN FRAME SOFA (7") | NOS | 1 | 1 | 6911 | 13 Mar 2024 | Technocrat Engineers | 1 | 80952 | C + SGST 18% I/P RD | 14571.36 | 1770 | 80952 | 0 |  |  | 0 | -45362 |  | 0 | 1 | 80952 |  | VILLA 17 CARPENTRY WORK
ANTICA GREENWOOD | 49778 | 52400 | 2024-03-13 | DINING CHAIR | NOS | 1 | 1 | 6911 | 13 Mar 2024 | Technocrat Engineers | 1 | 8852 | C + SGST 18% I/P RD | 12746.88 | 1770 | 8852 | 0 |  |  | 0 | -45362 |  | 0 | 1 | 8852 |  | VILLA 17 CARPENTRY WORK
ANTICA GREENWOOD | 49781 | 52403 | 2024-03-13 | DINING CHAIR | NOS | 7 | 7 | 6911 | 13 Mar 2024 | Technocrat Engineers | 7 | 8852 | C + SGST 18% I/P RD | 12746.88 | 1770 | 61964 | 0 |  |  | 0 | -45362 |  | 0 | 7 | 61964 |  | VILLA 17 CARPENTRY WORK
ANTICA GREENWOOD | 52090 | 54441 | 2024-04-19 | TILE FIXO X'TRAPLUS -20 KG (WHITE) | BAGS | 30 | 30 | 7065 | 20 Apr 2024 | Ultratech Cement Limited | 30 | 627 | C + SGST 18% I/P RD | 3385.8 | 0 | 18810 | 0 |  |  | 0 | -45400 |  | 0 | 30 | 18810 |  | VILLA 17 FLOORING WORK
ANTICA GREENWOOD | 52406 | 54761 | 2024-05-01 | DISHWASHER | NOS | 1 | 1 | 7108 | 01 May 2024 | Umiya Incorporation | 1 | 40234.38 | C + SGST 28% I/P RD | 11265.62 | 0 | 40234.38 | 0 |  |  | 0 | -45411 |  | 0 | 1 | 40234.38 |  | VILLA 17 KITCHEN APPLIANCES
ANTICA GREENWOOD | 52402 | 54762 | 2024-05-01 | WASHING MACHINE | NOS | 1 | 1 | 7108 | 01 May 2024 | Umiya Incorporation | 1 | 26171.88 | C + SGST 28% I/P RD | 7328.12 | 0 | 26171.88 | 0 |  |  | 0 | -45411 |  | 0 | 1 | 26171.88 |  | VILLA 17 KITCHEN APPLIANCES
ANTICA GREENWOOD | 49834 | 52442 | 2024-03-16 | TEAK WOOD SIZE 2"X1/2" X 2 FT | NOS | 36 | 36 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 36 | 34 | C + SGST 18% I/P RD | 220.32 | 0 | 1224 | 0 |  |  | 0 | -45365 |  | 0 | 36 | 1224 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49833 | 52443 | 2024-03-16 | TEAK WOOD SIZE 2"X1/2" X 7 FT | NOS | 68 | 68 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 68 | 122 | C + SGST 18% I/P RD | 1493.28 | 0 | 8296 | 0 |  |  | 0 | -45365 |  | 0 | 68 | 8296 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49832 | 52444 | 2024-03-16 | TEAK WOOD SIZE 4"X1/2" X 8 FT | NOS | 4 | 4 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 4 | 280 | C + SGST 18% I/P RD | 201.6 | 0 | 1120 | 0 |  |  | 0 | -45365 |  | 0 | 4 | 1120 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49816 | 52445 | 2024-03-15 | TEAK WOOD SIZE 4"X2" X 7 FT | NOS | 74 | 74 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 74 | 1050 | C + SGST 18% I/P RD | 13986 | 0 | 77700 | 0 |  |  | 0 | -45365 |  | 0 | 74 | 77700 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49815 | 52446 | 2024-03-15 | TEAK WOOD SIZE 4"X2" X 4 FT | NOS | 40 | 40 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 40 | 600 | C + SGST 18% I/P RD | 4320 | 0 | 24000 | 0 |  |  | 0 | -45365 |  | 0 | 40 | 24000 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49814 | 52447 | 2024-03-15 | TEAK WOOD SIZE 4"X2" X 3 FT | NOS | 36 | 36 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 36 | 440 | C + SGST 18% I/P RD | 2851.2 | 0 | 15840 | 0 |  |  | 0 | -45365 |  | 0 | 36 | 15840 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49813 | 52448 | 2024-03-15 | TEAK WOOD SIZE 4"X2" X 2 FT | NOS | 30 | 30 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 30 | 290 | C + SGST 18% I/P RD | 1566 | 0 | 8700 | 0 |  |  | 0 | -45365 |  | 0 | 30 | 8700 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49812 | 52449 | 2024-03-15 | TEAK WOOD SIZE 4"X1/2" X 7 FT | NOS | 58 | 58 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 58 | 245 | C + SGST 18% I/P RD | 2557.8 | 0 | 14210 | 0 |  |  | 0 | -45365 |  | 0 | 58 | 14210 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49811 | 52450 | 2024-03-15 | TEAK WOOD SIZE 4"X1/2" X 4 FT | NOS | 34 | 34 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 34 | 140 | C + SGST 18% I/P RD | 856.8 | 0 | 4760 | 0 |  |  | 0 | -45365 |  | 0 | 34 | 4760 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49810 | 52451 | 2024-03-15 | TEAK WOOD SIZE 4"X1/2" X 2 FT | NOS | 28 | 28 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 28 | 70 | C + SGST 18% I/P RD | 352.8 | 0 | 1960 | 0 |  |  | 0 | -45365 |  | 0 | 28 | 1960 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49809 | 52452 | 2024-03-15 | TEAK WOOD SIZE 3"X2" X 8 FT | NOS | 36 | 36 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 36 | 875 | C + SGST 18% I/P RD | 5670 | 0 | 31500 | 0 |  |  | 0 | -45365 |  | 0 | 36 | 31500 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49808 | 52453 | 2024-03-15 | TEAK WOOD SIZE 3"X2" X 7 FT | NOS | 68 | 68 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 68 | 735 | C + SGST 18% I/P RD | 8996.4 | 0 | 49980 | 0 |  |  | 0 | -45365 |  | 0 | 68 | 49980 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49807 | 52454 | 2024-03-15 | TEAK WOOD SIZE 3"X2" X 4 FT | NOS | 50 | 50 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 50 | 436 | C + SGST 18% I/P RD | 3924 | 0 | 21800 | 0 |  |  | 0 | -45365 |  | 0 | 50 | 21800 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49806 | 52455 | 2024-03-15 | TEAK WOOD SIZE 3"X2" X 2 FT | NOS | 36 | 36 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 36 | 218 | C + SGST 18% I/P RD | 1412.64 | 0 | 7848 | 0 |  |  | 0 | -45365 |  | 0 | 36 | 7848 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49805 | 52456 | 2024-03-15 | TEAK WOOD SIZE 3"X2" X 10 FT | NOS | 2 | 2 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 2 | 1142 | C + SGST 18% I/P RD | 411.12 | 0 | 2284 | 0 |  |  | 0 | -45365 |  | 0 | 2 | 2284 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49804 | 52457 | 2024-03-15 | TEAK WOOD SIZE 3"X2" X 1 FT | NOS | 604 | 604 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 604 | 109 | C + SGST 18% I/P RD | 11850.48 | 0 | 65836 | 0 |  |  | 0 | -45365 |  | 0 | 604 | 65836 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49803 | 52458 | 2024-03-15 | TEAK WOOD SIZE 2"X1/2" X 8 FT | NOS | 4 | 4 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 4 | 139 | C + SGST 18% I/P RD | 100.08 | 0 | 556 | 0 |  |  | 0 | -45365 |  | 0 | 4 | 556 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 49802 | 52459 | 2024-03-15 | TEAK WOOD SIZE 2"X1/2" X 4 FT | NOS | 44 | 44 | 6939 | 16 Mar 2024 | Vishwakarma Interior Gallery | 44 | 69 | C + SGST 18% I/P RD | 546.48 | 0 | 3036 | 0 |  |  | 0 | -45365 |  | 0 | 44 | 3036 |  | VILLA 81 CARPENTRY WORK
ANTICA GREENWOOD | 52092 | 54440 | 2024-04-19 | BRICKS_REGULAR | NOS | 4000 | 4000 | 7064 | 20 Apr 2024 | WESTERN BRICKS | 4000 | 6.5 | C + SGST 12% I/P RD | 3120 | 0 | 26000 | 30999 | 244 | 03 May 2024 | 4000 | 13 | Antica Site Store | 26000 | 0 | 0 | 23.04.2024 | INFRA COMPOUND WALL 9" BRICK MASONRY WORK