## Requisition_Detail_Browse638522
Requisition Detail Browse
From Date : 01/12/2023 To date: 25/05/2024
Status : All
Page 1 of 1
Total Records: 212 Records 1 to 212
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | CEMENT PPC - BAGS | 44304 | 46575 | 08 Dec 2023 | 2023-12-11 12:00 | BAGS |  | 200 | 200 | Pur.nrpl3 | 6500 | 341.99 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 110mm X 6' X D/S_SWR PVC PIPE | 46013 | 48491 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6654 | 364.74 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 110mm X 3' X D/S_SWR PVC PIPE | 46014 | 48490 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6654 | 198.59 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 110mm_SWR PVC ELBOW_45 | 46015 | 48489 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6654 | 72.04 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 110mm_SWR PVC P TRAP | 46016 | 48488 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6654 | 221.96 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 40MM X 6KG X 20'_PVC PIPE | 46017 | 48487 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 6654 | 259.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 40MM _PVC ELBOW | 46018 | 48486 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 18 | 18 | Pur.nrpl3 | 6654 | 36.02 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1 1/2"_CPVC ELBOW 90 DEGREE | 46019 | 48485 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6654 | 129.99 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1 1/2" x 1" CPVC TEE | 46020 | 48484 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 6654 | 179.05 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1" X 5MTR X SDR 11_CPVC PIPE | 46021 | 48483 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6654 | 665.87 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1"_CPVC TEE | 46022 | 48482 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6654 | 37.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1"_CPVC ELBOW 90 deg | 46023 | 48481 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 50 | 50 | Pur.nrpl3 | 6654 | 29.95 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 25x20MM CPVC TEE | 46024 | 48480 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6654 | 69.46 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1" X 3/4"_CPVC BUSHING | 46025 | 48479 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6654 | 18.48 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 3/4"_CPVC ELBOW 90 DEG | 46026 | 48478 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 48 | 48 | Pur.nrpl3 | 6654 | 15.29 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 3/4" X 1/2" _CPVC BRASS ELBOW (BRASS FPT X SOC ELBOW 90 DEG) | 46027 | 48477 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 28 | 28 | Pur.nrpl3 | 6654 | 57.99 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 3/4"X1/2" CPVC BRASS FTA 90 DEG | 46028 | 48476 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6654 | 149.74 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 3/4"_CPVC TEE | 46029 | 48475 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6654 | 24.85 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 3/4"_CPVC STEP OVER BEND | 46030 | 48474 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6654 | 70.73 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 237ML_CPVC SOLUTION (TIN) | 46031 | 48473 | 12 Jan 2024 | 2024-01-12 12:00 | TIN |  | 8 | 8 | Pur.nrpl3 | 6654 | 302.08 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | JASTI KHILLA 2 1/2" | 46032 | 48472 | 12 Jan 2024 | 2024-01-12 12:00 | PKT |  | 1 | 1 | Pur.nrpl3 | 6719 | 259.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | TAFLON TAP | 46033 | 48471 | 12 Jan 2024 | 2024-01-12 12:00 | NOS |  | 24 | 24 | Pur.nrpl3 | 6654 | 23.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | 20MM AGGREGATE | 46086 | 48693 | 17 Jan 2024 | 2024-01-20 12:00 | TONN |  | 30 | 30 | Pur.nrpl3 | 6649 | 918.75 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (26351IN-M-NA) INSTAFLUSHTM NXT GEN-MECH IN WALL TANK | 46320 | 48738 | 18 Jan 2024 | 2024-01-20 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6651 | 3143.46 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (4177IN-M-CP) DROPLET FACEPLATE POLISHED CHROME | 46321 | 48737 | 18 Jan 2024 | 2024-01-20 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6651 | 672.68 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (2200IN-0) VESSEL CONICAL BELL LAVATORY Conical Bell | 46322 | 48736 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "(2200IN-0) VESSEL CONICAL BELL LAVATORY Conical Bell" | 6 | 6 | Pur.nrpl3 | 6651 | 1893.29 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (P16316IN-4FP-CP) JULY RECESSED B&S TRIM 40MM | 46323 | 48735 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "(P16316IN-4FP-CP) JULY RECESSED B&S TRIM 40MM" | 5 | 5 | Pur.nrpl3 | 6651 | 814.17 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | KOH-882IN-CP_AQUA TURBO 235 MANUAL | 46324 | 48734 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "(882IN-CP) AQUA TURBO 235 MANUAL VALVE Valve" | 5 | 5 | Pur.nrpl3 | 6651 | 2316.45 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (73198IN-CP) RAINDUET ROUND 203MM RAINHEAD | 46325 | 48733 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "(73198IN-CP) ROUND 203 MM RAIN SHOWERHEAD (16346IN-CP) MASTERSHOWER ELBOW SHOWER ARM" | 6 | 6 | Pur.nrpl3 | 6651 | 3435.44 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (72421IN-CP) AWAKENB110 MULTI MODE HANDSHOWER | 46326 | 48732 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "72421IN-CP AWAKEN B110 MULTI MODE HANDSHOWER" | 6 | 6 | Pur.nrpl3 | 6651 | 1731.23 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 9040IN-CP HANDSHOWER BRACKET | 46327 | 48731 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "9040IN-CP HANDSHOWER BRACKET" | 6 | 6 | Pur.nrpl3 | 6651 | 236.66 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (80154IN-4-CP) JULY ANGLE VALVE Fittings-Angle Valve | 46328 | 48730 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "80154IN-4AV-CP JULY ANGLE VALVE FFittings-Angle Valve" | 18 | 18 | Pur.nrpl3 | 6651 | 587.79 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (10386IN-CP) BATH SPOUT, W/DIVERTER, FLAT FACE,160MM | 46329 | 48729 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "(10386IN-CP) BATH SPOUT, W/DIVERTER, FLAT FACE,160MM Complementary" | 5 | 5 | Pur.nrpl3 | 6651 | 2019.32 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (29929IN-4ND-CP) JULY COMFORT HEIGHT TALL LAV W/O DRAIN | 46330 | 48728 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "(29929IN-4ND-CP) JULY COMFORT HEIGHT TALL LAV W/O DRAIN" | 6 | 6 | Pur.nrpl3 | 6651 | 3708.11 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (75823IN-CP) BOTTLE TRAP 350MM | 46331 | 48727 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "75823IN-CP BOTTLE TRAP 350MM" | 6 | 6 | Pur.nrpl3 | 6651 | 1205.17 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | KOH-45432IN-CP_GRID DRAIN W/OVERFLOW | 46332 | 48726 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "45432IN-CP GRID DRAIN W/OVERFLOW HOLE" | 6 | 6 | Pur.nrpl3 | 6651 | 253.38 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (97258IN-CP) ELATE HEALTH FAUCET WITH HOSE & BRACKET | 46333 | 48725 | 18 Jan 2024 | 2024-01-20 12:00 | NOS | "97258IN-CP ELATE HEALTH FAUCET WITH HOSE & BRACKET" | 6 | 6 | Pur.nrpl3 | 6651 | 1197.45 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | KOHLER_8827IN-2-0-WC SEAT COVER | 46334 | 48724 | 18 Jan 2024 | 2024-01-20 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6651 | 1176.87 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (5573IN-0) REACH"! WH BOWL ONLY | 46335 | 48723 | 18 Jan 2024 | 2024-01-18 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6651 | 4675.34 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | 3.9 X 13_ SCREW | 46340 | 48808 | 19 Jan 2024 | 2024-01-23 12:00 | NOS |  | 1700 | 1700 | Pur.nrpl3 | 6663 | 0.83 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | 12X50_PVC WALL PLUG | 46341 | 48807 | 19 Jan 2024 | 2024-01-23 12:00 | BOX |  | 15 | 15 | Pur.nrpl3 | 6663 | 41.30 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | 6MM CEMENT SHEET | 46342 | 48920 | 19 Jan 2024 | 2024-01-23 12:00 | SQFT |  | 1200 | 1200 | Pur.nrpl3 | 6722 | 51.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | 7 X 25 SELF DRIVEN SCREW | 46343 | 48805 | 19 Jan 2024 | 2024-01-23 12:00 | BOX |  | 7 | 7 | Pur.nrpl3 | 6663 | 885.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | 75X10_SS WOODEN SCREW | 46344 | 48804 | 19 Jan 2024 | 2024-01-23 12:00 | PKT |  | 10 | 10 | Pur.nrpl3 | 6663 | 155.76 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | KHUNIYA_1/2" | 46345 | 48803 | 19 Jan 2024 | 2024-01-23 12:00 | NOS |  | 600 | 600 | Pur.nrpl3 | 6663 | 4.13 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CERA SHEET WORK | ALU.PIPE 1 1/2" X 1"_12' | 46346 | 48802 | 19 Jan 2024 | 2024-01-23 12:00 | NOS |  | 220 | 220 | Pur.nrpl3 | 6774 | 442.50 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 110mm_SWR BEND | 46347 | 48801 | 19 Jan 2024 | 2024-01-23 12:00 | NOS |  | 22 | 22 | Pur.nrpl3 | 6654 | 88.26 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | ULTRATECH XTRAPLUS GREY-20 KG | 46348 | 48800 | 19 Jan 2024 | 2024-01-23 12:00 | BAGS |  | 100 | 100 | Pur.nrpl3 | 6655 | 700.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | ARALDITE_1.80KG | 46349 | 48799 | 19 Jan 2024 | 2024-01-23 12:00 | PAIL |  | 5 | 5 | Pur.nrpl3 | 6679 | 1380.01 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | SINGLE SIDE POLISH KOTA STONE _ 5' x 2' (60" x 24") | 46405 | 49137 | 19 Jan 2024 | 2024-01-23 12:00 | SQFT |  | 4 | 4 | Pur.nrpl3 | 6708 | 63.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | SINGLE SIDE POLISH KOTA STONE _ 2' X3' (24" X 36") | 46406 | 49136 | 19 Jan 2024 | 2024-01-23 12:00 | SQFT |  | 2 | 2 | Pur.nrpl3 | 6708 | 52.50 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | SINGLE SIDE POLISH KOTA STONE _ 6' x 2' (72" x 24") | 46407 | 49135 | 19 Jan 2024 | 2024-01-23 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 6708 | 819.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | WATER TANK - 1000 LTR | 46430 | 48839 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 6683 | 8500.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1" VERTICAL NRV | 46441 | 48828 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6719 | 383.50 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1"_CPVC MABT | 46442 | 48827 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 6654 | 263.16 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1"_CPVC BALL VALVE Short Handle | 46443 | 48826 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 6654 | 244.05 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1" CPVC BALL COCK | 46444 | 48825 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1"_CPVC FABT | 46445 | 48824 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6654 | 272.08 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1/2 X 1 CP NIPPLE | 46446 | 48823 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6719 | 47.20 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | SINK COCK | 46447 | 48822 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6945 | 1650.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | RACK BOLT - WC | 46448 | 48821 | 20 Jan 2024 | 2024-01-20 12:00 | PAIR |  | 6 | 6 | Pur.nrpl3 | 6719 | 259.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 65MM_CPVC FAPT | 46449 | 48820 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6654 | 327.52 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 65MM_CPVC TANK ADAPTOR LONG | 46450 | 48819 | 20 Jan 2024 | 2024-01-20 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6654 | 1097.89 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | 600X1200_LEOPARD_6422 | 46540 | 49452 | 24 Jan 2024 | 2024-01-24 12:00 | SQFT |  | 400 | 400 | Pur.nrpl3 | 6749 | 35.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | 600X1200_LEOPARD_6423 | 46541 | 49451 | 24 Jan 2024 | 2024-01-24 12:00 | SQFT |  | 968 | 968 | Pur.nrpl3 | 6749 | 35.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | 600X1200_LEOPARD_6377 | 46542 | 49450 | 24 Jan 2024 | 2024-01-24 12:00 | SQFT |  | 176 | 176 | Pur.nrpl3 | 6749 | 35.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | 600X1200_LEOPARD_6376 | 46543 | 49449 | 24 Jan 2024 | 2024-01-24 12:00 | SQFT |  | 602 | 602 | Pur.nrpl3 | 6749 | 35.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | 600X1200_LEOPARD_6402 | 46544 | 49448 | 24 Jan 2024 | 2024-01-24 12:00 | SQFT |  | 111 | 111 | Pur.nrpl3 | 6749 | 35.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | 600X1200_LEOPARD_6403 | 46545 | 49447 | 24 Jan 2024 | 2024-01-24 12:00 | SQFT |  | 500 | 500 | Pur.nrpl3 | 6749 | 35.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | SINGLE SIDE POLISH KOTA STONE _ 2' X3' (24" X 36") | 46799 | 49134 | 30 Jan 2024 | 2024-01-30 12:00 | SQFT |  | 10 | 10 | Pur.nrpl3 | 6708 | 52.50 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN & BATHROOM FLOORING & DEDO WORK | SINGLE SIDE POLISH KOTA STONE _ 5' x 2' (60" x 24") | 46800 | 49133 | 30 Jan 2024 | 2024-01-30 12:00 | SQFT |  | 36 | 36 | Pur.nrpl3 | 6708 | 63.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1" BALL COCK | 46899 | 49359 | 02 Feb 2024 | 2024-02-02 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6718 | 740.47 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 10 SQ.MM WIRE | 46906 | 49358 | 02 Feb 2024 | 2024-02-02 12:00 | RMT | Red Colour Cable - 50 Mtr Yellow Colour Cable - 50 Mtr Black Colour Cable - 50 Mtr Blue Colour Cable - 50 Mtr | 200 | 200 | Pur.nrpl3 | 6723 | 100.72 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PARKING FLOORING WORK | STEEL GREY GRANITE | 46979 | 49434 | 05 Feb 2024 | 2024-02-07 12:00 | SQFT |  | 150 | 150 | Pur.nrpl3 | 6748 | 86.14 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PARKING FLOORING WORK | 24" X 24" LEATHER FINISH KOTA STONE | 46980 | 49433 | 05 Feb 2024 | 2024-02-05 12:00 | SQFT |  | 750 | 750 | Pur.nrpl3 | 6748 | 47.25 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | COFFEE BROWN GRANITE | 46981 | 49432 | 05 Feb 2024 | 2024-02-07 12:00 | SQFT |  | 500 | 500 | Pur.nrpl3 | 6748 | 126.26 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 1 SQMM FLEXIBLE CABLE | 47026 | 49514 | 06 Feb 2024 | 2024-02-09 12:00 | RMT | RED-300 YELLOW-1500 BLUE-1000 BLACK-2000 GREEN-1800 | 6600 | 6600 | Pur.nrpl3 | 6776 | 11.08 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 1.5 SQMM FLEXIBLE CABLE | 47027 | 49513 | 06 Feb 2024 | 2024-02-09 12:00 | RMT | RED-200 YELLOW-200 BLUE-200 BLACK-600 | 1200 | 1200 | Pur.nrpl3 | 6776 | 16.05 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 2.5 SQMM WIRE | 47028 | 49512 | 06 Feb 2024 | 2024-02-09 12:00 | RMT | RED-200 YELLOW-200 BLUE-200 BLACK-600 | 1200 | 1200 | Pur.nrpl3 | 6776 | 26.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 4 SQMM FLEXIBLE CABLE | 47029 | 49511 | 06 Feb 2024 | 2024-02-09 12:00 | RMT | RED-100 YELLOW-100 BLUE-100 BLACK-300 GREEN-50 | 650 | 650 | Pur.nrpl3 | 6776 | 39.47 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | CAT 6 CABLE | 47030 | 49510 | 06 Feb 2024 | 2024-02-09 12:00 | RMT | NET Cable | 305 | 305 | Pur.nrpl3 | 6776 | 25.25 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | RJ-6 TV WIRE - COPPER | 47031 | 49509 | 06 Feb 2024 | 2024-02-09 12:00 | RMT |  | 300 | 300 | Pur.nrpl3 | 6776 | 17.46 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | INSULATION TAPE | 47032 | 49508 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 50 | 50 | Pur.nrpl3 | 6767 | 10.62 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 3 MODULE PLATE | 47033 | 49507 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6759 | 127.49 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 8 MODULE PLATE | 47034 | 49506 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 42 | 42 | Pur.nrpl3 | 6759 | 272.44 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 6 MODULE PLATE | 47035 | 49505 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 15 | 15 | Pur.nrpl3 | 6759 | 245.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 1 MODULE PLATE | 47036 | 49504 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6759 | 108.28 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 2 MODULE PLATE | 47037 | 49503 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 9 | 9 | Pur.nrpl3 | 6759 | 114.39 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 4 MODULE PLATE | 47038 | 49502 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6759 | 133.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 10AMP x 1 POLE MCB | 47039 | 49501 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 25 | 25 | Pur.nrpl3 | 6767 | 108.56 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 16 AMP SINGLE POLE MCB | 47040 | 49500 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6767 | 108.56 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 20 AMP SINGLE POLE MCB | 47041 | 49499 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6767 | 108.56 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 6 AMP MCB SINGLE POLE | 47042 | 49498 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 8 | 8 | Pur.nrpl3 | 6767 | 108.56 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 6 WAY TPN DB | 47043 | 49497 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6767 | 3071.54 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | BELL PUSH | 47044 | 49496 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6759 | 197.34 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | BLANK SWITCH | 47045 | 49495 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 40 | 40 | Pur.nrpl3 | 6759 | 25.32 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 15 AMP SOCKET | 47046 | 49494 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 25 | 25 | Pur.nrpl3 | 6759 | 245.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 15 AMP SWITCH | 47047 | 49493 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 25 | 25 | Pur.nrpl3 | 6759 | 190.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 5 AMP 2 WAY SWITCH | 47048 | 49492 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 20 | 20 | Pur.nrpl3 | 6759 | 139.71 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | FAN REGULATOR | 47049 | 49491 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6759 | 635.69 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 5 AMP SOCKET | 47050 | 49490 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 85 | 85 | Pur.nrpl3 | 6759 | 121.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 5 AMP SWITCH | 47051 | 49489 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 210 | 210 | Pur.nrpl3 | 6759 | 91.69 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 25 AMP ELCB 2 POLE | 47052 | 49488 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 6767 | 1760.56 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 40AMAP TPN | 47053 | 49487 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6767 | 942.82 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 63 AMP ELCB | 47054 | 49486 | 06 Feb 2024 | 2024-02-09 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 6767 | 2108.66 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | COARSE SAND | 47200 | 49485 | 06 Feb 2024 | 2024-02-06 12:00 | TONN | SHREE MAHALAXMI TRANSPORT PLS MAKE PO | 11.44 | 11.44 | Pur.nrpl3 | 6744 | 918.75 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 EXTERNAL DOUBLE COAT PLASTER | COARSE SAND | 47201 | 49484 | 06 Feb 2024 | 2024-02-06 12:00 | TONN | SHREE MAHALAXMI TRANSPORT PLS MAKE PO | 100 | 100 | Pur.nrpl3 | 6744 | 918.75 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | 20MM AGGREGATE | 47202 | 49483 | 06 Feb 2024 | 2024-02-06 12:00 | TONN | SHREE MAHALAXMI TRANSPORT PLS MAKE PO | 27.58 | 27.58 | Pur.nrpl3 | 6744 | 918.75 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | KITCHEN SINK | 47298 | 49834 | 12 Feb 2024 | 2024-02-12 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6945 | 6550.01 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | BOTTLE TRAP | 47299 | 49833 | 12 Feb 2024 | 2024-02-12 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | WASTE COUPLING | 47322 | 49832 | 14 Feb 2024 | 2024-02-14 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7151 | 295.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | TECOMA | 47419 | 49957 | 19 Feb 2024 | 2024-02-19 12:00 | NOS |  | 150 | 150 | Pur.nrpl3 | 6791 | 25.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1 1/2"_CPVC TANK NIPPLE | 47656 | 50150 | 28 Feb 2024 | 2024-02-28 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6827 | 186.70 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 1"_CPVC TANK NIPPLE | 47660 | 50146 | 28 Feb 2024 | 2024-02-28 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 6827 | 80.93 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 AC INSTALLATION WORK | SPLIT AC 2 TONN | 47662 | 50156 | 28 Feb 2024 | 2024-02-28 12:00 | NOS |  | 9 | 9 | Pur.nrpl3 | 6828 | 43438.08 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PARKING FLOORING WORK | 24" X 24" LEATHER FINISH KOTA STONE | 49125 | 51970 | 01 Mar 2024 | 2024-03-01 12:00 | SQFT |  | 200 | 200 | Pur.nrpl3 | 6879 | 47.25 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | COFFEE BROWN GRANITE | 49126 | 51969 | 01 Mar 2024 | 2024-03-01 12:00 | SQFT |  | 300 | 300 | Pur.nrpl3 | 6879 | 141.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | PHILIPS 12W COB ASTRA SPOT 4K WHITE IN BODY COLOUR | 49376 | 51968 | 05 Mar 2024 | 2024-03-05 12:00 | NOS |  | 85 | 85 | Pur.nrpl3 | 6858 | 1121.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | PHILIPS 7W COB ASTRA SPOT 4K WHITE IN BODY COLOUR | 49377 | 51967 | 05 Mar 2024 | 2024-03-05 12:00 | NOS |  | 61 | 61 | Pur.nrpl3 | 6858 | 826.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | PHILIPS 7W SURFACE RIMLESS 6Watt 4k | 49378 | 51966 | 05 Mar 2024 | 2024-03-05 12:00 | NOS |  | 20 | 20 | Pur.nrpl3 | 6858 | 590.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | PHILIPS 6/8W PICTURE LIGHT IN BLACK BODY | 49379 | 51965 | 05 Mar 2024 | 2024-03-05 12:00 | NOS |  | 8 | 8 | Pur.nrpl3 | 6858 | 1416.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ATOMBREG 1200MM RENESA PRIME CEILING FAN IN WHITE BODY | 49380 | 51964 | 05 Mar 2024 | 2024-03-05 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 6858 | 3351.20 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | EXHAUST FAN | 49381 | 51963 | 05 Mar 2024 | 2024-03-05 12:00 | NOS | USHA EXHAUST FAN 250MM | 6 | 6 | Pur.nrpl3 | 6858 | 1416.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 SOFTNER INSTALLATION | SOFTNER FEED WATER PUMP | 49738 | 52398 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6916 | 18154.30 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 SOFTNER INSTALLATION | MANUAL SOFTENER(100 Ltr) | 49739 | 52397 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6916 | 46138.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 SOFTNER INSTALLATION | 200 Ltr. HEAT ABSORPTION WATER HEATER | 49740 | 52396 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6916 | 120360.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CARPENTRY WORK | INDIAN MADE DESIGNER EXPOSE WOODEN FRAME SOFA (7") | 49741 | 52395 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6911 | 95523.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CARPENTRY WORK | CONSOLE TABLE WITH MARBLE | 49742 | 52394 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6911 | 40299.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ROPE LIGHT FOR CEILING ( Warm White ) | 49743 | 52393 | 11 Mar 2024 | 2024-03-11 12:00 | RFT | 30 MTR | 100 | 98.4252 | Pur.nrpl3 | 6918 | 41.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ROPE LIGHT FOR CEILING ( Warm White ) | 49743 | 52410 | 11 Mar 2024 | 2024-03-11 12:00 | RFT | 30 MTR | 1.5748 | 1.5748 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ROPE LIGHT CONNECTOR | 49744 | 52392 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 6918 | 196.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | FICUS | 49745 | 52391 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 5 | 5 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | TRAVELLERS PALM | 49746 | 52390 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | CHAMPA PLANT | 49747 | 52389 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | SPARA GRASS PLANT | 49748 | 52388 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 40 | 40 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | TOHFA PLANT | 49749 | 52387 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 80 | 80 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | Lily ( White ) | 49750 | 52386 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 240 | 240 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | UREA FERTILIZER | 49751 | 52385 | 11 Mar 2024 | 2024-03-11 12:00 | BAGS |  | 7 | 7 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | CARPET LAWN | 49752 | 52384 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 300 | 300 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | ARECA PALM | 49753 | 52383 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 60 | 60 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 GARDENING WORK | ALOPECIA PLANT | 49754 | 52382 | 11 Mar 2024 | 2024-03-11 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 110 MM ECO DRAIN PIPE | 49776 | 52402 | 13 Mar 2024 | 2024-03-13 12:00 | RFT |  | 40 | 40 | Pur.nrpl3 | 6915 | 72.62 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | 24" x 24" SIMPLE POLISH KOTA STONE | 49777 | 52401 | 13 Mar 2024 | 2024-03-13 12:00 | SQFT |  | 900 | 900 | Pur.nrpl3 | 6921 | 33.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CARPENTRY WORK | DINING CHAIR | 49778 | 52400 | 13 Mar 2024 | 2024-03-13 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6911 | 10445.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 SOFTNER INSTALLATION | HYDRO PNEUMATIC SUBMERSIBLE PRESSURE SYSTEM | 49779 | 52405 | 13 Mar 2024 | 2024-03-13 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6916 | 45937.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 SOFTNER INSTALLATION | 15 LTR RO UNDER SINK PRESSURISED SYSTEM | 49780 | 52404 | 13 Mar 2024 | 2024-03-13 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6916 | 25877.40 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 CARPENTRY WORK | DINING CHAIR | 49781 | 52403 | 13 Mar 2024 | 2024-03-13 12:00 | NOS |  | 7 | 7 | Pur.nrpl3 | 6911 | 10445.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | RMC M-20 | 49794 | 52432 | 15 Mar 2024 | 2024-03-15 12:00 | CMT | SQ Slab casting | 7 | 7 | Pur.nrpl3 | 6940 | 4669.99 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | HIKVISION 8 CHANNEL NVR | 49795 | 52440 | 15 Mar 2024 | 2024-03-15 12:00 | NOS | CCTV | 1 | 1 | Pur.nrpl3 | 6930 | 7316.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | RJ-45 CONNECTOR | 49796 | 52439 | 15 Mar 2024 | 2024-03-15 12:00 | NOS |  | 10 | 10 | Pur.nrpl3 | 6930 | 17.70 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | IP CAMERA - 2MP | 49797 | 52438 | 15 Mar 2024 | 2024-03-15 12:00 | NOS |  | 5 | 5 | Pur.nrpl3 | 6930 | 3835.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 8 PORT POE SWITCH | 49798 | 52437 | 15 Mar 2024 | 2024-03-15 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6930 | 4956.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 4TB HARD DISK | 49799 | 52436 | 15 Mar 2024 | 2024-03-15 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6930 | 5900.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 4U NETWORK RACK 550MMX450MM | 49800 | 52435 | 15 Mar 2024 | 2024-03-15 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 6930 | 3068.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | JUNCTION BOX - WEATHER PROOF | 49801 | 52434 | 15 Mar 2024 | 2024-03-15 12:00 | NOS |  | 5 | 5 | Pur.nrpl3 | 6930 | 41.30 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 3 MODULE PLATE | 50032 | 54012 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 7008 | 127.49 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 8 MODULE PLATE | 50033 | 54017 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 12 | 12 | Pur.nrpl3 | 7008 | 272.44 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 4 MODULE PLATE | 50034 | 54013 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 7008 | 133.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 2 MODULE PLATE | 50035 | 54011 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 7008 | 114.39 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 6 MODULE PLATE | 50036 | 54016 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 8 | 8 | Pur.nrpl3 | 7008 | 245.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 5 AMP SOCKET | 50037 | 54014 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 15 | 15 | Pur.nrpl3 | 7008 | 121.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 5 AMP SWITCH | 50038 | 54015 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 15 | 15 | Pur.nrpl3 | 7008 | 91.69 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ROUND FAN PLATE 7" DIA | 50039 | 54018 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 20 | 20 | Pur.nrpl3 | 7008 | 47.20 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 15 AMP INDICATOR SWITCH | 50040 | 54008 | 26 Mar 2024 | 2024-03-26 12:00 | NOS |  | 7 | 7 | Pur.nrpl3 | 7008 | 190.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 15 AMP SOCKET | 50041 | 54009 | 26 Mar 2024 | 2024-03-26 12:00 | NOS | 16 AMP SOCKET | 4 | 4 | Pur.nrpl3 | 7008 | 245.37 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 15 AMP SWITCH | 50042 | 54010 | 26 Mar 2024 | 2024-03-26 12:00 | NOS | 16 AMP SWITCH | 7 | 7 | Pur.nrpl3 | 7008 | 190.36 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 1.5 SQMM 3 CORE FLEXIBLE CABLE | 50473 | 53009 | 03 Apr 2024 | 2024-04-03 12:00 | RMT |  | 30 | 30 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 1 SQMM 3 CORE FLEXIBLE CABLE | 50474 | 53008 | 03 Apr 2024 | 2024-04-03 12:00 | RMT |  | 55 | 55 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 2M FOOT LIGHT | 50475 | 53007 | 03 Apr 2024 | 2024-04-03 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 7146 | 767.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | COFFEE BROWN GRANITE | 51715 | 54315 | 15 Apr 2024 | 2024-04-15 12:00 | SQFT |  | 240 | 240 | Pur.nrpl3 | 7041 | 141.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 6" X 6"-3 PIC. JALI | 51776 | 54456 | 17 Apr 2024 | 2024-04-17 12:00 | NOS |  | 9 | 9 | Pur.nrpl3 | 7073 | 260.78 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 12" x 12" DRAIN JALI | 51777 | 54455 | 17 Apr 2024 | 2024-04-17 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 7073 | 1639.85 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (16346IN-CP) KOHLER MAKE -SHOWER ARM | 51778 | 54413 | 17 Apr 2024 | 2024-04-17 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 7071 | 2915.83 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | PILLAR COCK | 51779 | 54412 | 17 Apr 2024 | 2024-04-17 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | WASTE COUPLLING | 51780 | 54411 | 17 Apr 2024 | 2024-04-17 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | KOHLER_10879- IN-4-FP-CP-SINGLE BATH & SHOWER TRIM | 51781 | 54410 | 17 Apr 2024 | 2024-04-17 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | GASKET | 51782 | 54409 | 17 Apr 2024 | 2024-04-17 12:00 | NOS | 4" WC RUBBER GASKET - WHITE | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 12 A DRIVER | 52085 | 54446 | 19 Apr 2024 | 2024-04-19 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7083 | 649.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | LED STRIP LIGHT | 52086 | 54445 | 19 Apr 2024 | 2024-04-19 12:00 | RMT |  | 20 | 20 | Pur.nrpl3 | 7083 | 377.60 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | HANGING LIGHT | 52087 | 54444 | 19 Apr 2024 | 2024-04-19 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 8 SWG COPPER EARTH WIRE (RMT) | 52088 | 54443 | 19 Apr 2024 | 2024-04-19 12:00 | RMT |  | 60 | 60 | Pur.nrpl3 | 7072 | 123.90 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | TILE FIXO X'TRAPLUS -20 KG (WHITE) | 52090 | 54441 | 19 Apr 2024 | 2024-04-19 12:00 | BAGS |  | 30 | 30 | Pur.nrpl3 | 7065 | 739.86 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | WC CONNECTOR | 52197 | 54454 | 20 Apr 2024 | 2024-04-20 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 7074 | 69.44 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (22541IN-4FP-CP) HONE RECESSED BATH & SHOWER TRIM | 52198 | 54453 | 20 Apr 2024 | 2024-04-20 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 7071 | 3940.02 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 LIFT INSTALLATION WORK | LIFT ELEVATORS | 52393 | 55445 | 30 Apr 2024 | 2024-04-30 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN APPLIANCES | HOB | 52400 | 54764 | 01 May 2024 | 2024-05-01 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7107 | 19900.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN APPLIANCES | CHIMNEY | 52401 | 54763 | 01 May 2024 | 2024-05-01 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7107 | 13600.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN APPLIANCES | WASHING MACHINE | 52402 | 54762 | 01 May 2024 | 2024-05-01 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7108 | 33500.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 KITCHEN APPLIANCES | DISHWASHER | 52406 | 54761 | 01 May 2024 | 2024-05-01 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7108 | 51500.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 75376IN-1 TRACE VESSEL WITH 1TH | 52417 | 55116 | 01 May 2024 | 2024-05-01 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 7145 | 8411.04 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | (10386IN-CP) BATH SPOUT, W/DIVERTER, FLAT FACE,160MM | 52418 | 55115 | 01 May 2024 | 2024-05-01 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | NATURAL WHITE MARBLE | 52419 | 55114 | 03 May 2024 | 2024-05-03 12:00 | SQFT |  | 35 | 35 | Pur.nrpl3 | 7119 | 354.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 10 SQMM 4 CORE COPPER FLEXIBLE WIRE | 52420 | 55363 | 03 May 2024 | 2024-05-03 12:00 | RMT |  | 18 | 18 | Pur.nrpl3 | 7156 | 512.12 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 2.5 SQMM 4 CORE COPPER FLEXIBLE WIRE | 52421 | 55362 | 03 May 2024 | 2024-05-03 12:00 | RMT |  | 18 | 18 | Pur.nrpl3 | 7156 | 137.07 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 6 SQMM X 2 CORE COPPER FLEXIBLE CABLE | 52422 | 55361 | 03 May 2024 | 2024-05-03 12:00 | RMT |  | 15 | 15 | Pur.nrpl3 | 7156 | 158.10 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | 20138IN-CP -COMPLEMENTARY SQUARE SHOWERARM WALL MOUNT | 52755 | 55511 | 09 May 2024 | 2024-05-09 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 7145 | 1140.86 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | K-22534IN-4ND-CP SINGLE CONTROL BASIN FAUCET W/O DRAIN IN PO | 52777 | 55539 | 10 May 2024 | 2024-05-10 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 7149 | 6941.94 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | EXHAUST FAN | 52778 | 55538 | 10 May 2024 | 2024-05-10 12:00 | NOS | EXHAUST FAN - 150MM | 6 | 6 | Pur.nrpl3 | 7156 | 997.10 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 15MM ALUMINIUM PROFILE | 52779 | 55537 | 10 May 2024 | 2024-05-10 12:00 | RFT | For strip light | 60 | 60 | Pur.nrpl3 | 7156 | 19.66 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | BOLLARD LIGHT | 52780 | 55536 | 10 May 2024 | 2024-05-10 12:00 | NOS | garden light | 10 | 10 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | SPIKE LIGHT | 52781 | 55535 | 10 May 2024 | 2024-05-10 12:00 | NOS | garden light | 15 | 15 | Pur.nrpl3 | 7150 | 578.20 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | DOOR BELL | 52782 | 55534 | 10 May 2024 | 2024-05-10 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | WALL LIGHT | 52783 | 55533 | 10 May 2024 | 2024-05-10 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 7156 | 401.20 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | TRANSPERENT WIRE | 52784 | 55532 | 10 May 2024 | 2024-05-10 12:00 | RMT |  | 15 | 15 | Pur.nrpl3 | 7156 | 70.80 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | WASTE COUPLING | 52785 | 55531 | 10 May 2024 | 2024-05-10 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7151 | 295.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 2.5 SQMM RING TYPE COPPER LUG | 52812 | 55557 | 11 May 2024 | 2024-05-11 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 7156 | 2.42 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | 10 SQMM RING TYPE COPPER LUG | 52813 | 55556 | 11 May 2024 | 2024-05-11 12:00 | NOS |  | 20 | 20 | Pur.nrpl3 | 7156 | 7.08 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ROUND FAN PLATE 7" DIA | 52814 | 55555 | 11 May 2024 | 2024-05-11 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 7156 | 28.32 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | J-HOOK | 52815 | 55554 | 11 May 2024 | 2024-05-11 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 7156 | 37.76 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 ELECTRICAL WORK | ANGLE HOLDER | 52816 | 55553 | 11 May 2024 | 2024-05-11 12:00 | NOS |  | 8 | 8 | Pur.nrpl3 | 7156 | 25.96 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 PLUMBING WORK | U shaped Rail 600 x 100 mm | 53071 | 55812 | 21 May 2024 | 2024-05-21 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 7194 | 7160.00 | Raised | Normal | Approved |  | Regular Purchase
ANTICA GREENWOOD | VILLA 17 FLOORING WORK | 600 X 600 VITRIFIED TILES | 53286 | 55816 | 22 May 2024 | 2024-05-22 12:00 | SQFT | VILLA 17 FLOORING WORK | 450 | 450 | Pur.nrpl3 | 7197 | 28.00 | Raised | Normal | Approved |  | Regular Purchase