## Requisition_Detail_Browse638598
Requisition Detail Browse
From Date : 01/04/2018 To date: 21/08/2024
Status : Pending For PO
Page 1 of 1
Total Records: 95 Records 1 to 95
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GREENWOODS SERENITY | VILLA A3 PLASTER WORK | FIBRE CHICKEN MESH JALI | 12247 | 13231 | 16 Dec 2021 | 2021-12-16 12:00 | NOS |  | 20 | 20 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B36 CIVIL WORK PLASTER WORK | FIBRE CHICKEN MESH JALI | 12248 | 13261 | 16 Dec 2021 | 2021-12-16 12:00 | NOS |  | 10 | 10 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B46 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | RMC M-25 | 12603 | 13727 | 31 Dec 2021 | 2021-12-31 12:00 | CMT |  | 25 | 25 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B46 CIVIL WORK PLASTER WORK | CEMENT PPC - BAGS | 14529 | 57926 | 29 Mar 2022 | 2022-03-29 12:00 | BAGS |  | 91 | 91 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE PLUMBING WORK | URINAL | 14544 | 15819 | 29 Mar 2022 | 2022-03-29 12:00 | NOS |  | 4 | 4 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B42 CIVIL WORK UP TO PLINTH RCC WORK FOR SLAB | RMC M-15 | 19886 | 21493 | 16 Jun 2022 | 2022-06-16 12:00 | CMT |  | 28 | 28 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA UG TANK & STP CIVIL WORK | CEMENT PPC - BAGS | 20158 | 21536 | 18 Jun 2022 | 2022-06-18 12:00 | BAGS |  | 61 | 61 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA UG TANK & STP CIVIL WORK | CEMENT PPC - BAGS | 20338 | 35966 | 27 Jun 2022 | 2022-06-27 12:00 | BAGS |  | 200 | 200 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 FLOORING WORK FLOORING & DEDO | STEEL GREY GRANITE - LAPATRO FINISH | 23017 | 24769 | 21 Aug 2022 | 2022-08-21 12:00 | SQFT |  | 100 | 100 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE HVAC INSTALLATION | SPLIT AC 2.2 TONN | 23397 | 29055 | 09 Sep 2022 | 2022-09-09 12:00 | NOS |  | 3 | 3 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B8 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | STEEL_10MM | 31046 | 32609 | 18 Feb 2023 | 2023-02-18 12:00 | KG |  | 300 | 300 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A34 SECOND FLOOR RCC WORK FOR SLAB | STEEL_10MM | 31047 | 32608 | 18 Feb 2023 | 2023-02-18 12:00 | KG |  | 300 | 300 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A37 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | STEEL_10MM | 31048 | 32607 | 18 Feb 2023 | 2023-02-18 12:00 | KG |  | 300 | 300 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 FLOORING WORK FLOORING & DEDO | WOODEN FLOORING | 31303 | 35389 | 06 Mar 2023 | 2023-03-06 12:00 | SQFT |  | 780 | 780 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 FLOORING WORK FLOORING & DEDO | WOODEN SKIRTING | 31304 | 35391 | 06 Mar 2023 | 2023-03-06 12:00 | RFT |  | 168 | 168 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE FLOORING AND DEDO WORK | WOODEN FLOORING | 31305 | 35390 | 06 Mar 2023 | 2023-03-06 12:00 | SQFT |  | 150 | 150 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE FLOORING AND DEDO WORK | WOODEN SKIRTING | 31306 | 35392 | 06 Mar 2023 | 2023-03-06 12:00 | RFT |  | 280 | 280 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | CHANDELIER | 31816 | 33455 | 16 Mar 2023 | 2023-03-16 12:00 | NOS | FOYER,DINING,STAIRCASE | 3 | 3 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 CARPENTERY WORK FURNITURE WORK | 10'' SUPPORT LEG BRASS FINISH | 32590 | 38747 | 03 Apr 2023 | 2023-04-03 12:00 | NOS | FF MASTERBED ROOM AS PER SAMPLE PHOTO.PLEASE CONFIRM FINISH BEFORE PROCUREMENT | 12 | 12 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 CARPENTERY WORK FURNITURE WORK | HANDLE PROFILE | 32591 | 36580 | 03 Apr 2023 | 2023-04-03 12:00 | NOS | 3 FEET PROFILE HANDLE BRASS FINIFH/FF MASTERBED ROOM AS PER SAMPLE PHOTO.PLEASE CONFIRM FINISH BEFORE PROCUREMENT | 2 | 2 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 CARPENTERY WORK FURNITURE WORK | 12MM_W/P PLY | 32597 | 34258 | 03 Apr 2023 | 2023-04-03 12:00 | SHEET | DRAWERS AND STARIR PANELING 8X4 SIZE IS 710 BWP | 15 | 15 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | 20MM PVC ELECTRIC PIPE | 32796 | 34666 | 12 Apr 2023 | 2023-04-12 12:00 | RMT |  | 11 | 11 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | 0.75 SQ.MM 2 CORE CABLE | 32818 | 34459 | 12 Apr 2023 | 2023-04-12 12:00 | NOS |  | 25 | 25 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE SWIMMING POOL CIVIL WORK | 10MM GRIT | 32937 | 36180 | 14 Apr 2023 | 2023-04-14 12:00 | TONN | CLUBHOUSE SWIMMING POOL | 22 | 22 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE SWIMMING POOL CIVIL WORK | 20MM AGGREGATE | 32938 | 59640 | 14 Apr 2023 | 2023-04-14 12:00 | TONN | INFRA COMPUND WALL | 123 | 123 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 CARPENTERY WORK FURNITURE WORK | 12 MM MS BRIGHT BAR | 34222 | 35860 | 12 May 2023 | 2023-05-12 12:00 | KG |  | 28 | 28 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3475 | 3698 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A3 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3476 | 3697 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A21 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3477 | 3696 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A23 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3478 | 3695 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE RCC WORK UP TO GROUND FLOOR SLAB | CEMENT OPC 53 GRADE BAG | 3479 | 3694 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 CARPENTERY WORK FURNITURE WORK | DRAWER LOCK | 34909 | 36579 | 31 May 2023 | 2023-05-31 12:00 | NOS | EUROPA F-370 CUPBOARD LOCK | 2 | 2 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA ELECTRIC WORK | METER BOX 1 1/2 X 2 | 35848 | 37595 | 19 Jun 2023 | 2023-06-19 12:00 | NOS | PVC meter peti -6 | 6 | 6 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA ELECTRIC WORK | JUNCTION BOX - WEATHER PROOF | 37240 | 39001 | 13 Jul 2023 | 2023-07-13 12:00 | NOS | Infra--> Electrical PVC Weather Proof switch board protection box 6 Nos | 6 | 6 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE FLOORING AND DEDO WORK | JAISALMER MARBLE | 42265 | 44388 | 30 Sep 2023 | 2023-10-01 12:00 | SQFT | Flooring & Dedo work | 0.56 | 0.56 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | WALL LIGHT | 43489 | 45779 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | T5 TUBE STICK NOS | 43490 | 45778 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | CEILING FAN | 43491 | 49859 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 6 SQMM FLEXIBLE WIRE | 43513 | 46723 | 03 Nov 2023 | 2023-11-03 12:00 | RMT |  | 130 | 130 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 2.5 SQMM WIRE | 43517 | 46722 | 03 Nov 2023 | 2023-11-03 12:00 | RMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 7W ROUND CYLINDER LIGHT | 43522 | 50337 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 80 | 80 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | HANGING LIGHT | 43523 | 51978 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 7 | 7 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | HANGING LIGHT | 43523 | 53113 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | WALL LIGHT | 43524 | 45744 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 13 | 13 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 13W SPOT LIGHT WHITE | 43525 | 45743 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 1.5 SQMM 3 CORE FLEXIBLE CABLE | 43528 | 55367 | 03 Nov 2023 | 2023-11-03 12:00 | RMT |  | 100 | 100 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | STREET LIGHT | 43530 | 45738 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 GARDENING WORK | SILVER OAK | 44213 | 46391 | 06 Dec 2023 | 2023-12-09 12:00 | NOS | Villa 01-->COMMON WORK-->GARDENING WORK | 50 | 50 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B42 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X150 | 45313 | 47712 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A28 CIVIL WORK FIRST FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X150 | 45314 | 47711 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A38 CIVIL WORK 1ST FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X150 | 45315 | 47710 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 PLUMBING WORK | PILLAR COCK | 45876 | 48463 | 09 Jan 2024 | 2024-01-09 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 PLUMBING WORK | WASTE PIPE | 45877 | 48462 | 09 Jan 2024 | 2024-01-09 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A33 CIVIL WORK UP TO GF MASONRY WORK | AAC BLOCK 600X200X100 | 46534 | 48927 | 24 Jan 2024 | 2024-01-27 12:00 | CMT |  | 35 | 35 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B7 CIVIL WORK FIRST FLOOR MASONRY WORK | AAC BLOCK 600X200X100 | 46535 | 57313 | 24 Jan 2024 | 2024-01-27 12:00 | CMT |  | 4.91 | 4.91 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA GARDEN WORK | BOTTLE PALM | 47359 | 49870 | 17 Feb 2024 | 2024-02-17 12:00 | NOS | Plants to be atlease 8-9 ft Tall | 40 | 40 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA GARDEN WORK | Champa White | 47360 | 49869 | 17 Feb 2024 | 2024-02-17 12:00 | NOS |  | 40 | 40 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE HOUSEKEEPING WORK | SS Railing polishing agent (d7) | 47595 | 50291 | 26 Feb 2024 | 2024-02-26 12:00 | LTR |  | 2 | 2 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE HOUSEKEEPING WORK | NIRMA POWDER | 47604 | 50193 | 26 Feb 2024 | 2024-02-26 12:00 | PKT |  | 10 | 10 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA ELECTRIC WORK | LED FLOOD LIGHT 150W | 47607 | 50192 | 26 Feb 2024 | 2024-02-26 12:00 | NOS | for night work | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Urgent | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | DOME LIGHT | 49030 | 50289 | 01 Mar 2024 | 2024-03-01 12:00 | NOS |  | 56 | 56 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 1 SQMM WIRE | 49032 | 50287 | 01 Mar 2024 | 2024-03-01 12:00 | RMT | YELLOW=300 BLACK=600 GREEN=300 BLUE=300 | 1500 | 1500 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 2.5 SQMM WIRE | 49033 | 50286 | 01 Mar 2024 | 2024-03-01 12:00 | RMT | YELLOW=100 BLACK=200 RED=100 BLUE=100 | 1000 | 1000 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | HANGING LIGHT | 49036 | 53112 | 01 Mar 2024 | 2024-03-01 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | PHILIPS 7W COB ASTRA SPOT 4K BLACK IN BODY COLOUR | 49037 | 50282 | 01 Mar 2024 | 2024-03-01 12:00 | NOS |  | 25 | 25 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | CHANDELIER | 49040 | 53111 | 01 Mar 2024 | 2024-03-01 12:00 | NOS |  | 1 | 1 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 35X8 WOODEN SCREW | 49041 | 50278 | 01 Mar 2024 | 2024-03-01 12:00 | PKT |  | 50 | 50 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | CAT 6 CABLE | 49044 | 50275 | 01 Mar 2024 | 2024-03-01 12:00 | RMT |  | 305 | 305 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | PIKA PIPE | 49046 | 50273 | 01 Mar 2024 | 2024-03-01 12:00 | RMT |  | 100 | 100 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A28 CIVIL WORK FIRST FLOOR MASONRY WORK | BLOCK MORTAR | 49442 | 52968 | 07 Mar 2024 | 2024-03-07 12:00 | BAGS |  | 30 | 30 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA INTERNAL COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 49457 | 54438 | 07 Mar 2024 | 2024-03-07 12:00 | TONN |  | 16.5 | 16.5 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A29 CIVIL WORK FIRST FLOOR MASONRY WORK | AAC BLOCK 600X200X100 | 49463 | 52067 | 07 Mar 2024 | 2024-03-07 12:00 | CMT |  | 25 | 25 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B4 FLOORING & DEDO WORK | PROTECTION FILM | 49847 | 54032 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B43 FLOORING & DEDO WORK | PROTECTION FILM | 49848 | 54031 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B41 FLOORING & DEDO WORK | PROTECTION FILM | 49849 | 54030 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A40 FLOORING & DEDO WORK | PROTECTION FILM | 49850 | 54029 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B8 FLOORING & DEDO WORK | PROTECTION FILM | 49851 | 54028 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A 21-22 FLOORING & DEDO WORK | PROTECTION FILM | 49852 | 54027 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A35 FLOORING WORK | PROTECTION FILM | 49853 | 54026 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B45 FLOORING WORK | PROTECTION FILM | 49854 | 54033 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | BLOCK MORTAR | 50334 | 54639 | 31 Mar 2024 | 2024-03-31 12:00 | BAGS | only po kunthunath | 20 | 20 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE SWIMMING POOL PLUMBING WORK | WATER TANK - 1000 LTR | 51750 | 55161 | 16 Apr 2024 | 2024-04-16 12:00 | NOS |  | 1 | 1 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 20 MM GI JUNCTION BOX -3 WAY | 52213 | 54636 | 22 Apr 2024 | 2024-04-22 12:00 | NOS | BLACK | 200 | 200 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 CARPENTERY WORK FURNITURE WORK | CRYSTAL MATT WHITE 2400 MM X 800 MM | 52216 | 54630 | 22 Apr 2024 | 2024-04-22 12:00 | SQFT |  | 1 | 1 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | LeGRAND_6A SWITCH 1W1M AR_573400 | 53063 | 56205 | 21 May 2024 | 2024-05-21 12:00 | NOS | BLACK COLOUR | 100 | 100 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | LeGRAND_6A SWITCH 1W1M AR_573400 | 53063 | 56211 | 21 May 2024 | 2024-05-21 12:00 | NOS | BLACK COLOUR | 18 | 18 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | LeGRAND_6A SOCKET 2M AR_573470 | 53064 | 56210 | 21 May 2024 | 2024-05-21 12:00 | NOS | BLACK COLOUR | 5 | 5 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | LeGRAND_6A SOCKET 2M AR_573470 | 53064 | 56204 | 21 May 2024 | 2024-05-21 12:00 | NOS | BLACK COLOUR | 50 | 50 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | BLANK SWITCH | 53065 | 56209 | 21 May 2024 | 2024-05-21 12:00 | NOS | BLACK COLOUR | 4 | 4 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 ELECTRIC WORK | 8mm Profile Light (white Colour) | 53066 | 56776 | 21 May 2024 | 2024-05-21 12:00 | RFT |  | 3.6 | 3.6 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA CIVIL WORK | TARPAULIN SHEET | 54500 | 57252 | 25 Jun 2024 | 2024-06-25 12:00 | NOS |  | 5 | 5 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA ROAD WORK | BINDING WIRE | 55010 | 58250 | 15 Jul 2024 | 2024-07-15 12:00 | KG |  | 100 | 100 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | SERENITY OFFICE | WATER BOTTLE - 300 ML | 7403 | 21504 | 07 Jul 2021 | 2021-07-07 12:00 | BOX |  | 200 | 200 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE IT MISC MATERIAL | WATER JUG - 20 LTR | 9100 | 17002 | 28 Sep 2021 | 2021-09-28 12:00 | NOS |  | 50 | 50 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE IT MISC MATERIAL | WATER JUG - 20 LTR | 9100 | 17003 | 28 Sep 2021 | 2021-09-28 12:00 | NOS |  | 35 | 35 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase