## Requisition_Detail_Browse638628
Requisition Detail Browse
From Date : 01/08/2014 To date: 25/09/2024
Status : Pending For PO
Page 1 of 1
Total Records: 78 Records 1 to 78
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GREENWOODS SERENITY | VILLA A3 PLASTER WORK | FIBRE CHICKEN MESH JALI | 12247 | 13231 | 16 Dec 2021 | 2021-12-16 12:00 | NOS |  | 20 | 20 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B36 CIVIL WORK PLASTER WORK | FIBRE CHICKEN MESH JALI | 12248 | 13261 | 16 Dec 2021 | 2021-12-16 12:00 | NOS |  | 10 | 10 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE PLUMBING WORK | URINAL | 14544 | 15819 | 29 Mar 2022 | 2022-03-29 12:00 | NOS |  | 4 | 4 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE HVAC INSTALLATION | SPLIT AC 2.2 TONN | 23397 | 29055 | 09 Sep 2022 | 2022-09-09 12:00 | NOS |  | 3 | 3 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 FLOORING WORK FLOORING & DEDO | WOODEN FLOORING | 31303 | 35389 | 06 Mar 2023 | 2023-03-06 12:00 | SQFT |  | 780 | 780 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 FLOORING WORK FLOORING & DEDO | WOODEN SKIRTING | 31304 | 35391 | 06 Mar 2023 | 2023-03-06 12:00 | RFT |  | 168 | 168 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE FLOORING AND DEDO WORK | WOODEN FLOORING | 31305 | 35390 | 06 Mar 2023 | 2023-03-06 12:00 | SQFT |  | 150 | 150 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE FLOORING AND DEDO WORK | WOODEN SKIRTING | 31306 | 35392 | 06 Mar 2023 | 2023-03-06 12:00 | RFT |  | 280 | 280 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE SWIMMING POOL CIVIL WORK | 10MM GRIT | 32937 | 36180 | 14 Apr 2023 | 2023-04-14 12:00 | TONN | CLUBHOUSE SWIMMING POOL | 22 | 22 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUBHOUSE SWIMMING POOL CIVIL WORK | 20MM AGGREGATE | 32938 | 60965 | 14 Apr 2023 | 2023-04-14 12:00 | TONN | INFRA COMPUND WALL | 79.5 | 79.5 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B7 UP TO PLINTH COMMON WORK | COARSE SAND | 34484 | 61126 | 22 May 2023 | 2023-05-22 12:00 | TONN |  | 10 | 10 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A30 CIVIL WORK PLASTER WORK | COARSE SAND | 34485 | 61127 | 22 May 2023 | 2023-05-22 12:00 | TONN |  | 18.16 | 18.16 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3475 | 3698 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A3 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3476 | 3697 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A21 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3477 | 3696 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A23 UP TO PLINTH MASONRY WORK | CEMENT OPC 53 GRADE BAG | 3478 | 3695 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE RCC WORK UP TO GROUND FLOOR SLAB | CEMENT OPC 53 GRADE BAG | 3479 | 3694 | 21 Dec 2020 | 2020-12-21 12:00 | BAGS |  | 60 | 60 | pur.nrpl1 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B45 CIVIL WORK UP TO FIRST FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X225 | 36341 | 61128 | 27 Jun 2023 | 2023-06-27 12:00 | CMT |  | 20 | 20 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 37885 | 61125 | 03 Aug 2023 | 2023-08-03 12:00 | TONN |  | 8.5 | 8.5 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B7 CIVIL WORK GROUND FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X225 | 38175 | 61123 | 05 Aug 2023 | 2023-08-05 12:00 | CMT |  | 8 | 8 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 38180 | 61124 | 05 Aug 2023 | 2023-08-05 12:00 | TONN |  | 4.82 | 4.82 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA UG TANK & STP CIVIL WORK | COARSE SAND | 40331 | 61121 | 22 Aug 2023 | 2023-08-22 12:00 | TONN | ONLY PO VALAM TRADING_900 RS + GST | 165.34 | 165.34 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL PLASTER WORK | COARSE SAND | 40733 | 61120 | 27 Aug 2023 | 2023-08-27 12:00 | TONN |  | 5.87 | 5.87 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | BRICKS_REGULAR | 40735 | 61122 | 27 Aug 2023 | 2023-08-27 12:00 | NOS |  | 12100 | 12100 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B7 CIVIL WORK GROUND FLOOR MASONRY WORK (SQFT) | AAC BLOCK 600X200X225 | 41772 | 61119 | 13 Sep 2023 | 2023-09-16 12:00 | CMT |  | 0.83 | 0.83 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA INTERNAL COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 41773 | 61118 | 13 Sep 2023 | 2023-09-16 12:00 | TONN |  | 36.97 | 36.97 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 42257 | 61115 | 29 Sep 2023 | 2023-10-02 12:00 | TONN |  | 14.1 | 14.1 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 42257 | 61113 | 29 Sep 2023 | 2023-10-02 12:00 | TONN |  | 19.38 | 19.38 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B42 UP TO FIRST FLOOR MASONRY WORK | AAC BLOCK 600X200X225 | 42310 | 61117 | 04 Oct 2023 | 2023-10-07 12:00 | CMT |  | 5.2 | 5.2 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B42 CIVIL WORK UP TO GROUND FLOOR MASONRY WORK | AAC BLOCK 600X200X150 | 42586 | 61116 | 11 Oct 2023 | 2023-10-14 12:00 | CMT |  | 2.6 | 2.6 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA UG TANK & STP CIVIL WORK | COARSE SAND | 43025 | 61112 | 26 Oct 2023 | 2023-10-26 12:00 | TONN | R K ENTERPRISE | 3.69 | 3.69 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B8 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | 20MM AGGREGATE | 43026 | 61114 | 26 Oct 2023 | 2023-10-26 12:00 | TONN | R K ENTERPRISE ONLY PO | 0.71 | 0.71 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | WALL LIGHT | 43489 | 45779 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 3 | 3 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | T5 TUBE STICK NOS | 43490 | 45778 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 4 | 4 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | CEILING FAN | 43491 | 49859 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 2 | 2 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 6 SQMM FLEXIBLE WIRE | 43513 | 46723 | 03 Nov 2023 | 2023-11-03 12:00 | RMT |  | 130 | 130 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 2.5 SQMM WIRE | 43517 | 46722 | 03 Nov 2023 | 2023-11-03 12:00 | RMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 7W ROUND CYLINDER LIGHT | 43522 | 50337 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 80 | 80 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 13W SPOT LIGHT WHITE | 43525 | 45743 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | STREET LIGHT | 43530 | 45738 | 03 Nov 2023 | 2023-11-03 12:00 | NOS |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A34 PLASTER WORK | COARSE SAND | 43727 | 61111 | 23 Nov 2023 | 2023-11-23 12:00 | TONN |  | 3.16 | 3.16 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA INTERNAL COMPOUND WALL CIVIL WORK | BRICKS_REGULAR | 43740 | 61110 | 24 Nov 2023 | 2023-11-24 12:00 | NOS |  | 10000 | 10000 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA INTERNAL COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 43750 | 61109 | 24 Nov 2023 | 2023-11-24 12:00 | TONN |  | 12.59 | 12.59 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A1 GARDENING WORK | SILVER OAK | 44213 | 46391 | 06 Dec 2023 | 2023-12-09 12:00 | NOS | Villa 01-->COMMON WORK-->GARDENING WORK | 50 | 50 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA INTERNAL COMPOUND WALL CIVIL WORK | FINE SAND | 44751 | 61108 | 20 Dec 2023 | 2023-12-20 12:00 | TONN |  | 10.48 | 10.48 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A34 GROUND FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X225 | 45309 | 61107 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 4.814 | 4.814 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B42 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X150 | 45313 | 47712 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A28 CIVIL WORK FIRST FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X150 | 45314 | 47711 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A38 CIVIL WORK 1ST FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X150 | 45315 | 47710 | 26 Dec 2023 | 2023-12-26 12:00 | CMT |  | 20 | 20 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A 21-22 PLASTER WORK | COARSE SAND | 45395 | 61106 | 28 Dec 2023 | 2023-12-28 12:00 | TONN | ONLY PO RK ENTERPRISE BILL NO-488/494 | 0.92 | 0.92 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL PLASTER WORK | 20MM AGGREGATE | 46217 | 61105 | 17 Jan 2024 | 2024-01-17 12:00 | TONN |  | 65.75 | 65.75 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B7 CIVIL WORK FIRST FLOOR MASONRY WORK | AAC BLOCK 600X200X100 | 46535 | 57313 | 24 Jan 2024 | 2024-01-27 12:00 | CMT |  | 4.91 | 4.91 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA COMPOUND WALL CIVIL WORK | BRICKS_REGULAR | 46977 | 61104 | 05 Feb 2024 | 2024-02-07 12:00 | NOS |  | 29000 | 29000 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A38 CIVIL WORK 2ND FLOOR MASONRY WORK | AAC BLOCK 600X200X225 | 47337 | 61102 | 15 Feb 2024 | 2024-02-20 12:00 | CMT |  | 50 | 50 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A33 CIVIL WORK UP TO FF MASONRY WORK | AAC BLOCK 600X200X225 | 47338 | 61103 | 15 Feb 2024 | 2024-02-20 12:00 | CMT |  | 5.989 | 5.989 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA ELECTRIC WORK | LED FLOOD LIGHT 150W | 47607 | 50192 | 26 Feb 2024 | 2024-02-26 12:00 | NOS | for night work | 6 | 6 | Pur.nrpl3 | 0 | 0 |  | Urgent | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 1 SQMM WIRE | 49032 | 50287 | 01 Mar 2024 | 2024-03-01 12:00 | RMT | YELLOW=300 BLACK=600 GREEN=300 BLUE=300 | 1500 | 1500 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | 2.5 SQMM WIRE | 49033 | 50286 | 01 Mar 2024 | 2024-03-01 12:00 | RMT | YELLOW=100 BLACK=200 RED=100 BLUE=100 | 1000 | 1000 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | PHILIPS 7W COB ASTRA SPOT 4K BLACK IN BODY COLOUR | 49037 | 50282 | 01 Mar 2024 | 2024-03-01 12:00 | NOS |  | 25 | 25 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | CAT 6 CABLE | 49044 | 50275 | 01 Mar 2024 | 2024-03-01 12:00 | RMT |  | 305 | 305 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | CLUB HOUSE ELECTRIC WORK | PIKA PIPE | 49046 | 50273 | 01 Mar 2024 | 2024-03-01 12:00 | RMT |  | 100 | 100 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B42 CIVIL WORK UP TO SECOND FLOOR RCC WORK FOR SLAB | AAC BLOCK 600X200X225 | 49445 | 61098 | 07 Mar 2024 | 2024-03-07 12:00 | CMT |  | 1.04 | 1.04 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B45 CIVIL WORK PLASTER WORK | COARSE SAND | 49454 | 61101 | 07 Mar 2024 | 2024-03-07 12:00 | TONN |  | 28.52 | 28.52 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | INFRA INTERNAL COMPOUND WALL CIVIL WORK | 20MM AGGREGATE | 49457 | 61100 | 07 Mar 2024 | 2024-03-07 12:00 | TONN |  | 50 | 50 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A29 CIVIL WORK FIRST FLOOR MASONRY WORK | AAC BLOCK 600X200X100 | 49463 | 52067 | 07 Mar 2024 | 2024-03-07 12:00 | CMT |  | 25 | 25 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B4 FLOORING & DEDO WORK | PROTECTION FILM | 49847 | 54032 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B43 FLOORING & DEDO WORK | PROTECTION FILM | 49848 | 54031 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B41 FLOORING & DEDO WORK | PROTECTION FILM | 49849 | 54030 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A40 FLOORING & DEDO WORK | PROTECTION FILM | 49850 | 54029 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B8 FLOORING & DEDO WORK | PROTECTION FILM | 49851 | 54028 | 19 Mar 2024 | 2024-03-19 12:00 | ROLL |  | 8 | 8 | Pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B43 CIVIL WORK PLASTER WORK | CEMENT PPC - BAGS | 52826 | 60130 | 13 May 2024 | 2024-05-13 12:00 | BAGS |  | 80 | 80 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A38 CIVIL WORK PLASTER WORK | CEMENT PPC - BAGS | 52827 | 60129 | 13 May 2024 | 2024-05-13 12:00 | BAGS |  | 200 | 200 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A33 PLASTER WORK | CEMENT PPC - BAGS | 52828 | 60128 | 13 May 2024 | 2024-05-13 12:00 | BAGS |  | 100 | 100 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA A35 GROUND FLOOR MASONRY WORK | BRICKS_REGULAR | 53004 | 61099 | 18 May 2024 | 2024-05-18 12:00 | NOS |  | 2000 | 2000 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | VILLA B45 CIVIL WORK PLASTER WORK | CEMENT PPC - BAGS | 54343 | 60131 | 22 Jun 2024 | 2024-06-22 12:00 | BAGS |  | 87 | 87 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE HOUSEKEEPING WORK | WATER BOTTLE - 200 ML | 55687 | 61097 | 26 Jul 2024 | 2024-07-26 12:00 | BOX |  | 10 | 10 | pur.nrpl4 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE IT MISC MATERIAL | WATER JUG - 20 LTR | 9100 | 17002 | 28 Sep 2021 | 2021-09-28 12:00 | NOS |  | 50 | 50 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase
GREENWOODS SERENITY | OFFICE IT MISC MATERIAL | WATER JUG - 20 LTR | 9100 | 17003 | 28 Sep 2021 | 2021-09-28 12:00 | NOS |  | 35 | 35 | pur.nrpl3 | 0 | 0 |  | Normal | Approved |  | Regular Purchase