## Requisition_Detail_Browse638682
Requisition Detail Browse
Library : Neptune Library
From Date : 01/10/2024 To date: 26/11/2024
Material : REFNETS
Status : All
Page 1 of 1
Total Records: 99 Records 1 to 99
Project | Task_Name | Material_Name | ReqSr_no | Requisition_Id | Requisition_Date | Requirement_Date | Unit | Specifications | Qty | Approved_Qty | Approved_By | PO_No | Net_Rate | PO_Status | Priority | Req_Status | Brand_Name | Procurement_Mode
GREENWOODS AARANYA | TOWER A 201 HVAC WORK | REFNETS | 61610 | 65432 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 401 HVAC WORK | REFNETS | 61611 | 65431 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 404 HVAC WORK | REFNETS | 61612 | 65430 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 501 HVAC WORK | REFNETS | 61613 | 65429 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 502 HVAC WORK | REFNETS | 61614 | 65428 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 601 HVAC WORK | REFNETS | 61615 | 65427 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 602 HVAC WORK | REFNETS | 61616 | 65426 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 603 HVAC WORK | REFNETS | 61617 | 65425 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 604 HVAC WORK | REFNETS | 61618 | 65424 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 701 HVAC WORK | REFNETS | 61619 | 65423 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 703 HVAC WORK | REFNETS | 61620 | 65422 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 704 HVAC WORK | REFNETS | 61621 | 65421 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 803 HVAC WORK | REFNETS | 61622 | 65420 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 804 HVAC WORK | REFNETS | 61623 | 65419 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 903 HVAC WORK | REFNETS | 61624 | 65418 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1004 HVAC WORK | REFNETS | 61625 | 65417 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1101 HVAC WORK | REFNETS | 61626 | 65416 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1201 HVAC WORK | REFNETS | 61627 | 65415 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1202 HVAC WORK | REFNETS | 61628 | 65414 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1203 HVAC WORK | REFNETS | 61629 | 65413 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1204 HVAC WORK | REFNETS | 61630 | 65412 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1302 HVAC WORK | REFNETS | 61631 | 65411 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1401 HVAC WORK | REFNETS | 61632 | 65410 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1402 HVAC WORK | REFNETS | 61633 | 65409 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1403 HVAC WORK | REFNETS | 61634 | 65408 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1404 HVAC WORK | REFNETS | 61635 | 65407 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 304 HVAC WORK | REFNETS | 61636 | 65406 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1501 HVAC WORK | REFNETS | 61637 | 65405 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 702 HVAC WORK | REFNETS | 61638 | 65404 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1504 HVAC WORK | REFNETS | 61639 | 65403 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1602 HVAC WORK | REFNETS | 61640 | 65402 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 802 HVAC WORK | REFNETS | 61641 | 65401 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 901 HVAC WORK | REFNETS | 61642 | 65400 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 902 HVAC WORK | REFNETS | 61643 | 65399 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER A 1001 HVAC WORK | REFNETS | 61644 | 65398 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 103 HVAC WORK | REFNETS | 61645 | 65397 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 3 | 3 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1102 HVAC WORK | REFNETS | 61646 | 65396 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1104 HVAC WORK | REFNETS | 61647 | 65395 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1201 HVAC WORK | REFNETS | 61648 | 65394 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1202 HVAC WORK | REFNETS | 61649 | 65393 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1203 HVAC WORK | REFNETS | 61650 | 65392 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1204 HVAC WORK | REFNETS | 61651 | 65391 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1302 HVAC WORK | REFNETS | 61652 | 65390 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1401 HVAC WORK | REFNETS | 61653 | 65389 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1404 HVAC WORK | REFNETS | 61654 | 65388 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1502 HVAC WORK | REFNETS | 61655 | 65387 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1503 HVAC WORK | REFNETS | 61656 | 65386 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1601 HVAC WORK | REFNETS | 61657 | 65385 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 301 HVAC WORK | REFNETS | 61658 | 65384 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 304 HVAC WORK | REFNETS | 61659 | 65383 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 401 HVAC WORK | REFNETS | 61660 | 65382 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 404 HVAC WORK | REFNETS | 61661 | 65381 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 501 HVAC WORK | REFNETS | 61662 | 65380 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 504 HVAC WORK | REFNETS | 61663 | 65379 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 902 HVAC WORK | REFNETS | 61664 | 65378 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 903 HVAC WORK | REFNETS | 61665 | 65377 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 601 HVAC WORK | REFNETS | 61666 | 65376 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 603 HVAC WORK | REFNETS | 61667 | 65375 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 604 HVAC WORK | REFNETS | 61668 | 65374 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1103 HVAC WORK | REFNETS | 61669 | 65373 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 703 HVAC WORK | REFNETS | 61670 | 65372 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 704 HVAC WORK | REFNETS | 61671 | 65371 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 801 HVAC WORK | REFNETS | 61672 | 65370 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 804 HVAC WORK | REFNETS | 61673 | 65369 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 904 HVAC WORK | REFNETS | 61674 | 65368 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1001 HVAC WORK | REFNETS | 61675 | 65367 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1002 HVAC WORK | REFNETS | 61676 | 65366 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1003 HVAC WORK | REFNETS | 61677 | 65365 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER B 1004 HVAC WORK | REFNETS | 61678 | 65364 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 4 | 4 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 102 HVAC WORK | REFNETS | 61679 | 65363 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 201 HVAC WORK | REFNETS | 61680 | 65362 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 202 HVAC WORK | REFNETS | 61681 | 65361 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 501 HVAC WORK | REFNETS | 61682 | 65360 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 701 HVAC WORK | REFNETS | 61683 | 65359 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 702 HVAC WORK | REFNETS | 61684 | 65358 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 801 HVAC WORK | REFNETS | 61685 | 65357 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 802 HVAC WORK | REFNETS | 61686 | 65356 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1001 HVAC WORK | REFNETS | 61687 | 65355 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1002 HVAC WORK | REFNETS | 61688 | 65354 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1201 HVAC WORK | REFNETS | 61689 | 65353 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1302 HVAC WORK | REFNETS | 61690 | 65352 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1402 HVAC WORK | REFNETS | 61691 | 65351 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1501 HVAC WORK | REFNETS | 61692 | 65350 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 1502 HVAC WORK | REFNETS | 61693 | 65349 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 402 HVAC WORK | REFNETS | 61694 | 65348 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 601 HVAC WORK | REFNETS | 61695 | 65347 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER D 902 HVAC WORK | REFNETS | 61696 | 65346 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 401 HVAC WORK | REFNETS | 61697 | 65345 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 802 HVAC WORK | REFNETS | 61698 | 65344 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 1201 HVAC WORK | REFNETS | 61699 | 65343 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 1401 HVAC WORK | REFNETS | 61700 | 65342 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 1501 HVAC WORK | REFNETS | 61701 | 65341 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 1601 HVAC WORK | REFNETS | 61702 | 65340 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 301 HVAC WORK | REFNETS | 61703 | 65339 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 501 HVAC WORK | REFNETS | 61704 | 65338 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 601 HVAC WORK | REFNETS | 61705 | 65337 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 801 HVAC WORK | REFNETS | 61706 | 65336 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 901 HVAC WORK | REFNETS | 61707 | 65335 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase
GREENWOODS AARANYA | TOWER C 1001 HVAC WORK | REFNETS | 61708 | 65334 | 19 Nov 2024 | 2024-11-19 12:00 | PAIR | for VRF System | 5 | 5 | Pur.nrpl3 | 8032 | 2914.56 | Raised | Normal | Approved |  | Regular Purchase