## 638626872431617772_00001.xlsx
Contractor Payment Report - Detail
Bill Date From : 04/09/1986 To : 24/09/2024
Contractor : Krishna Associates
Page 1 of 1
Total Records: 67 Records 1 to 67
Project | Contractor | Bill_No | Bill_Date | Voucher_No | WO_SrNo | WO_Type | WOTotalAmt | Debit_Amount | Advance_Recovery | TDS_Amt | Retention_Amt | Bill Submitted | GrossBillAmt | Approved in Contract | Approved in Accounts | Total Payment Made | Balance Payment As On Today
GREENWOOD ASPIRE EXP | Krishna Associates | 38 | 2020-12-23 | EV - 331 | 63 | Construction | 211518744.53 | 0 | 0 | 28227 | 94090 | 2098213.61 | 2220530.61 | 2098213.61 | 0 | 77322 | 77322
GREENWOOD ASPIRE EXP | Krishna Associates | 39 | 2020-12-23 | EV - 332 | 63 | Construction | 211518744.53 | 0 | 0 | 24756 | 82518 | 1840159.54 | 1947433.54 | 1840159.54 | 0 | 922678 | 922678
GREENWOOD ASPIRE EXP | Krishna Associates | 55 | 2021-01-21 | EV - 412 | 63 | Construction | 211518744.53 | 0 | 0 | 21296 | 95155 | 1558830.7 | 1675281.7 | 1558830.7 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 56 | 2021-01-21 | EV - 413 | 63 | Construction | 211518744.53 | 0 | 0 | 26742 | 89139 | 1987798.7 | 2103679.7 | 1987798.7 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 70 | 2021-03-06 | EV - 535 | 63 | Construction | 211518744.53 | 0 | 0 | 25003 | 83343 | 1858544.56 | 1966890.56 | 1858544.56 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 71 | 2021-03-06 | EV - 536 | 63 | Construction | 211518744.53 | 0 | 0 | 28748 | 95826 | 2136938.96 | 2261512.96 | 2136938.96 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 117 | 2021-05-17 | EV - 927 | 63 | Construction | 211518744.53 | 0 | 0 | 25003 | 83343 | 1858544.56 | 1966890.56 | 1858544.56 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 133 | 2021-06-22 | EV - 1003 | 63 | Construction | 211518744.53 | 0 | 0 | 27732 | 92439 | 2061387.64 | 2181558.64 | 2061387.64 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 137 | 2021-06-26 | EV - 1021 | 63 | Construction | 211518744.53 | 0 | 0 | 24996 | 83319 | 1858022.6 | 1966337.6 | 1858022.6 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 145 | 2021-07-16 | EV - 1074 | 63 | Construction | 211518744.53 | 0 | 0 | 31409 | 104697 | 2334770.52 | 2470876.52 | 2334770.52 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 151 | 2021-07-27 | EV - 1096 | 63 | Construction | 211518744.53 | 0 | 0 | 24749 | 82498 | 1839703.68 | 1946950.68 | 1839703.68 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 152 | 2021-07-27 | EV - 1097 | 63 | Construction | 211518744.53 | 0 | 0 | 15570 | 51900 | 1157402.84 | 1224872.84 | 1157402.84 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 177 | 2021-08-28 | EV - 1210 | 63 | Construction | 211518744.53 | 0 | 0 | 8485 | 28282 | 630688.79 | 667455.79 | 630688.79 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 182 | 2021-08-31 | EV - 1220 | 63 | Construction | 211518744.53 | 0 | 0 | 5796 | 19320 | 430845 | 455961 | 430845 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 187 | 2021-09-25 | EV - 1292 | 63 | Construction | 211518744.53 | 0 | 0 | 31770 | 105899 | 2361545.73 | 2499214.73 | 2361545.73 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 190 | 2021-09-30 | EV - 1315 | 63 | Construction | 211518744.53 | 0 | 0 | 24759 | 82528.93 | 1840394.81 | 1947682.74 | 1840394.81 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 194 | 2021-10-05 | EV - 1336 | 63 | Construction | 211518744.53 | 0 | 0 | 35205 | 117350.97 | 2616927.05 | 2769483.02 | 2616927.05 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 195 | 2021-10-05 | EV - 1337 | 63 | Construction | 211518744.53 | 0 | 0 | 5796 | 19320.38 | 430844.62 | 455961 | 430844.62 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 201 | 2021-10-23 | EV - 1397 | 63 | Construction | 211518744.53 | 0 | 0 | 74268 | 247561.49 | 5520621.67 | 5842451.16 | 5520621.67 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 203 | 2021-10-23 | EV - 1402 | 63 | Construction | 211518744.53 | 0 | 0 | 5796 | 19320.38 | 430844.62 | 455961 | 430844.62 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 215 | 2021-11-02 | EV - 1457 | 63 | Construction | 211518744.53 | 0 | 0 | 23181 | 77269.28 | 1723104.72 | 1823555 | 1723104.72 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 224 | 2021-11-23 | EV - 1484 | 63 | Construction | 211518744.53 | 0 | 0 | 23545 | 78481.7 | 1750141.42 | 1852168.12 | 1750141.42 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 225 | 2021-11-24 | EV - 1486 | 63 | Construction | 211518744.53 | 0 | 0 | 5739 | 19129.26 | 426582.25 | 451450.51 | 426582.25 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 236 | 2021-12-18 | EV - 1570 | 63 | Construction | 211518744.53 | 0 | 0 | 23992 | 79973.96 | 1783419.5 | 1887385.46 | 1783419.5 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 237 | 2021-12-18 | EV - 1571 | 63 | Construction | 211518744.53 | 0 | 0 | 16544 | 55145.11 | 1229735.28 | 1301424.39 | 1229735.28 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 238 | 2021-12-28 | EV - 1613 | 63 | Construction | 211518744.53 | 0 | 0 | 23824 | 79414.28 | 1770938.72 | 1874177 | 1770938.72 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 239 | 2021-12-28 | EV - 1614 | 63 | Construction | 211518744.53 | 0 | 0 | 5323 | 17743.84 | 395687.87 | 418754.71 | 395687.87 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 249 | 2022-01-23 | EV - 1698 | 63 | Construction | 211518744.53 | 0 | 0 | 23181 | 77269.28 | 1723104.72 | 1823555 | 1723104.72 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 250 | 2022-01-23 | EV - 1699 | 63 | Construction | 211518744.53 | 0 | 0 | 23188 | 77292.71 | 1723627.25 | 1824107.96 | 1723627.25 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 251 | 2022-01-24 | EV - 1700 | 63 | Construction | 211518744.53 | 0 | 0 | 17789 | 59296.62 | 1322314.56 | 1399400.18 | 1322314.56 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 252 | 2022-01-24 | EV - 1701 | 63 | Construction | 211518744.53 | 0 | 0 | 14448 | 48160.64 | 1073982.2 | 1136590.84 | 1073982.2 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 275 | 2022-02-14 | EV - 1774 | 63 | Construction | 211518744.53 | 0 | 0 | 23188 | 77292.71 | 1723627.25 | 1824107.96 | 1723627.25 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 309 | 2022-02-28 | EV - 1852 | 63 | Construction | 211518744.53 | 0 | 0 | 16011 | 53369.17 | 1190132.19 | 1259512.36 | 1190132.19 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 323 | 2022-03-10 | EV - 1907 | 63 | Construction | 211518744.53 | 0 | 0 | 16181 | 53935.33 | 1202757.48 | 1272873.81 | 1202757.48 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 324 | 2022-03-10 | EV - 1908 | 63 | Construction | 211518744.53 | 0 | 0 | 25003 | 83342.82 | 1858544.74 | 1966890.56 | 1858544.74 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 325 | 2022-03-10 | EV - 1909 | 63 | Construction | 211518744.53 | 0 | 0 | 49776 | 165918.61 | 3699984.59 | 3915679.2 | 3699984.59 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 331 | 2022-03-30 | EV - 1996 | 63 | Construction | 211518744.53 | 0 | 0 | 14894 | 49646.04 | 1107106.78 | 1171646.82 | 1107106.78 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 344 | 2022-04-14 | EV - 2032 | 63 | Construction | 211518744.53 | 0 | 0 | 48625 | 162084.56 | 3614486.06 | 3825195.62 | 3614486.06 | 3614486.06 | 0 | 3614486.06
GREENWOOD ASPIRE EXP | Krishna Associates | 345 | 2022-04-14 | EV - 2033 | 63 | Construction | 211518744.53 | 0 | 0 | 2295 | 7650 | 170595 | 180540 | 170595 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 376 | 2022-05-17 | EV - 2146 | 63 | Construction | 211518744.53 | 0 | 0 | 1650 | 5500 | 122650 | 129800 | 122650 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 377 | 2022-05-17 | EV - 2147 | 63 | Construction | 211518744.53 | 0 | 0 | 12151 | 40504 | 903239.32 | 955894.32 | 903239.32 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 378 | 2022-05-17 | EV - 2148 | 63 | Construction | 211518744.53 | 49560 | 0 | 30347 | 101156.52 | 2206230.28 | 2387293.8 | 2206230.28 | 0 | 49560 | 49560
GREENWOOD ASPIRE EXP | Krishna Associates | 379 | 2022-05-17 | EV - 2149 | 63 | Construction | 211518744.53 | 0 | 0 | 11880 | 39600 | 883080 | 934560 | 883080 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 380 | 2022-05-17 | EV - 2150 | 63 | Construction | 211518744.53 | 0 | 0 | 7670 | 25565.32 | 570106.42 | 603341.74 | 570106.42 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 436 | 2022-06-28 | EV - 2333 | 63 | Construction | 211518744.53 | 0 | 0 | 25972 | 86573.96 | 1930599.5 | 2043145.46 | 1930599.5 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 437 | 2022-06-28 | EV - 2334 | 63 | Construction | 211518744.53 | 8260 | 0 | 25089 | 83629.04 | 1856667.3 | 1973645.34 | 1856667.3 | 0 | 8260 | 8260
GREENWOOD ASPIRE EXP | Krishna Associates | 471 | 2022-07-13 | EV - 2387 | 63 | Construction | 211518744.53 | 0 | 0 | 50851 | 169501.86 | 3779891.04 | 4000243.9 | 3779891.04 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 984 | 2023-02-16 | EV - 3253 | 63 | Construction | 211518744.53 | 0 | 0 | 30004 | 100012.66 | 2230282.07 | 2360298.73 | 2230282.07 | 0 | 2220281 | 2220281
GREENWOOD ASPIRE EXP | Krishna Associates | 1299 | 2023-04-28 | EV - 155 | 63 | Construction | 211518744.53 | 0 | 0 | 75002.4 | 250008 | 5575178.4 | 5900188.8 | 5575178.4 | 0 | 5000000 | 5000000
GREENWOOD ASPIRE EXP | Krishna Associates | 1357 | 2023-05-19 | EV - 278 | 63 | Construction | 211518744.53 | 0 | 0 | 99340 | 331131.9 | 7384240.92 | 7814712.82 | 7384240.92 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 1358 | 2023-05-19 | EV - 279 | 63 | Construction | 211518744.53 | 0 | 0 | 13161 | 43868.99 | 978278.39 | 1035308.38 | 978278.39 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 1456 | 2023-06-26 | EV - 461 | 63 | Construction | 211518744.53 | 0 | 0 | 5270 | 17565.02 | 391699.46 | 414534.48 | 391699.46 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 1519 | 2023-07-24 | EV - 619 | 63 | Construction | 211518744.53 | 0 | 0 | 112499 | 374996.38 | 8362419.2 | 8849914.58 | 8362419.2 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 1621 | 2023-08-18 | EV - 803 | 63 | Construction | 211518744.53 | 0 | 0 | 30476 | 101586.55 | 2265379.85 | 2397442.4 | 2265379.85 | 2265379.85 | 0 | 2265379.85
GREENWOOD ASPIRE EXP | Krishna Associates | 1622 | 2023-08-18 | EV - 804 | 63 | Construction | 211518744.53 | 0 | 0 | 53767 | 179223.55 | 3996685.07 | 4229675.62 | 3996685.07 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 1623 | 2023-08-18 | EV - 805 | 63 | Construction | 211518744.53 | 0 | 0 | 28257 | 94189.98 | 2100436.02 | 2222883 | 2100436.02 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2118 | 2024-01-18 | EV - 1801 | 63 | Construction | 211518744.53 | 0 | 0 | 22863 | 76209.5 | 1699471.73 | 1798544.23 | 1699471.73 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2119 | 2024-01-18 | EV - 1802 | 63 | Construction | 211518744.53 | 0 | 0 | 24869 | 82896 | 1848580.6 | 1956345.6 | 1848580.6 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2120 | 2024-01-18 | EV - 1803 | 63 | Construction | 211518744.53 | 0 | 0 | 17490 | 58300 | 1300090 | 1375880 | 1300090 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2121 | 2024-01-18 | EV - 1804 | 63 | Construction | 211518744.53 | 0 | 0 | 19179 | 63930.46 | 1425649.4 | 1508758.86 | 1425649.4 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2160 | 2024-01-24 | EV - 1860 | 63 | Construction | 211518744.53 | 0 | 0 | 39729 | 132428.41 | 2953153.06 | 3125310.47 | 2953153.06 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2161 | 2024-01-24 | EV - 1861 | 63 | Construction | 211518744.53 | 0 | 0 | 35309 | 117695.78 | 2624615.77 | 2777620.55 | 2624615.77 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2162 | 2024-01-25 | EV - 1864 | 63 | Construction | 211518744.53 | 0 | 0 | 22502 | 75005.7 | 1672626.82 | 1770134.52 | 1672626.82 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2264 | 2024-02-23 | EV - 2048 | 63 | Construction | 211518744.53 | 0 | 0 | 47100 | 157000.94 | 3501121.32 | 3705222.26 | 3501121.32 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2369 | 2024-04-04 | EV - 21 | 63 | Construction | 211518744.53 | 0 | 0 | 60006 | 200021.43 | 4460478.23 | 4720505.66 | 4460478.23 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2383 | 2024-04-18 | EV - 63 | 63 | Construction | 211518744.53 | 0 | 0 | 38115 | 127049.99 | 2833214.99 | 2998379.98 | 2833214.99 | 0 | 0 | 0
GREENWOOD ASPIRE EXP | Krishna Associates | 2781 | 2024-09-13 | EV - 868 | 63 | Construction | 211518744.53 | 0 | 0 | 30569 | 101897.21 | 2272308.19 | 2404774.4 | 2272308.19 | 0 | 0 | 0