## Contractor_Work_Order6386425517
Contractor Work Order
From 15 Sep 2005 To 12 Oct 2024
Page 1 of 1
Total Records: 383 Records 1 To 383
Contrator | WO No | Revision | Wo_Date | Project | Task Name | Labour Name | Qty | Rate | Amount | Ret. % | Specifications | WO_Type | WO_Type2
Aadwik Infrabuild Pvt Ltd | 320 | 0 | 23 Mar 2024 | NEPTUNE TRION EXP | COMMON PLUMBING WORK | PROVIDING & LAYING K-7 PIPE 150 MM DIA SUSPENDED | 60 | 3725 | 223500 | 5 |  | Job Work
B S Window Solution | 463 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | TOWER A ALUMINUM WORK | LABOR FOR OPENABLE ALUMINIUM DOOR (SQFT) | 19 | 585 | 11115 | 5 | STAIR CABIN DOOR PROVISION | Job Work
B S Window Solution | 463 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | TOWER B ALUMINUM WORK | LABOR FOR OPENABLE ALUMINIUM DOOR (SQFT) | 39.75 | 585 | 23253.75 | 5 |  | Job Work
B S Window Solution | 463 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | TOWER C ALUMINUM WORK | LABOR FOR OPENABLE ALUMINIUM DOOR (SQFT) | 19.5 | 585 | 11407.5 | 5 |  | Job Work
BAIDYANATH PASWAN | 180 | 0 | 11 Jul 2022 | GREENWOOD ASPIRE EXP | C 1401 FLOORING & DEDO WORK | LABOR FOR ITALIAN MIRROR POLISH (RFT) | 230 | 48 | 11040 | 5 |  | Job Work
BAIDYANATH PASWAN | 180 | 0 | 11 Jul 2022 | GREENWOOD ASPIRE EXP | C 1401 FLOORING & DEDO WORK | LABOR FOR ITALIAN MIRROR POLISH (SQFT) | 700 | 48 | 33600 | 5 |  | Job Work
CHIRAG ELECTRICALS | 330 | 0 | 02 May 2024 | NEPTUNE TRION EXP | COMMON ELECTRIC WORK | CHARGES FOR M10/8 THREADED ROD (RMT) | 10 | 33 | 330 | 3 |  | Job Work
CHIRAG ELECTRICALS | 330 | 0 | 02 May 2024 | NEPTUNE TRION EXP | COMMON ELECTRIC WORK | CHARGES FOR M8 BULLET FASTENER (NOS) | 10 | 15 | 150 | 3 |  | Job Work
CHIRAG ELECTRICALS | 330 | 0 | 02 May 2024 | NEPTUNE TRION EXP | COMMON ELECTRIC WORK | CHARGES FOR SLOTTED C CHANNEL 35 x 15 x 1.6 MM | 10 | 27 | 270 | 3 |  | Job Work
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 5TH FLOOR FLOORING & DEDO WORK | LABOR FOR DOUBLE PATTI DHAAR POLISH (RFT) | 100 | 25 | 2500 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 5TH FLOOR FLOORING & DEDO WORK | LABOR FOR MOLDING (RFT) | 200 | 20 | 4000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 5TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE TRADE & RISER | 100 | 45 | 4500 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 5TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 100 | 40 | 4000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 5TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTI (RFT) | 100 | 40 | 4000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 6TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTI (RFT) | 280 | 40 | 11200 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 6TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 200 | 40 | 8000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 6TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE TRADE & RISER | 400 | 45 | 18000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 6TH FLOOR FLOORING & DEDO WORK | LABOR FOR MOLDING (RFT) | 450 | 20 | 9000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 6TH FLOOR FLOORING & DEDO WORK | LABOR FOR DOUBLE PATTI DHAAR POLISH (RFT) | 200 | 25 | 5000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 7TH FLOOR FLOORING & DEDO WORK | LABOR FOR DOUBLE PATTI DHAAR POLISH (RFT) | 200 | 25 | 5000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 7TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE TRADE & RISER | 400 | 45 | 18000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 7TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 200 | 40 | 8000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 7TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTI (RFT) | 280 | 40 | 11200 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 8TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTI (RFT) | 280 | 40 | 11200 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 8TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 200 | 40 | 8000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 8TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE TRADE & RISER | 400 | 45 | 18000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 8TH FLOOR FLOORING & DEDO WORK | LABOR FOR DOUBLE PATTI DHAAR POLISH (RFT) | 200 | 25 | 5000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 8TH FLOOR FLOORING & DEDO WORK | LABOR FOR MOLDING (RFT) | 450 | 20 | 9000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 9TH FLOOR FLOORING & DEDO WORK | LABOR FOR MOLDING (RFT) | 450 | 20 | 9000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 9TH FLOOR FLOORING & DEDO WORK | LABOR FOR DOUBLE PATTI DHAAR POLISH (RFT) | 200 | 25 | 5000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 9TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE TRADE & RISER | 400 | 45 | 18000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 9TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 200 | 40 | 8000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 9TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTI (RFT) | 280 | 40 | 11200 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 10TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTI (RFT) | 280 | 40 | 11200 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 10TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 200 | 40 | 8000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 10TH FLOOR FLOORING & DEDO WORK | LABOUR FOR GRANITE TRADE & RISER | 400 | 45 | 18000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 10TH FLOOR FLOORING & DEDO WORK | LABOR FOR DOUBLE PATTI DHAAR POLISH (RFT) | 200 | 25 | 5000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 10TH FLOOR FLOORING & DEDO WORK | LABOR FOR MOLDING (RFT) | 450 | 20 | 9000 | 5 |  | Construction
Deepak H Prajapati | 144 | 0 | 04 Dec 2021 | NEPTUNE TRION EXP | TOWER A 1ST FLOOR COMMON TOILET FLOORING & DEDO WORK | LABOUR FOR GRANITE (SQFT) | 560 | 40 | 22400 | 5 |  | Construction
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER A COMMON PAINT WORK | LABOR FOR 2ND COAT PUTTY (SQFT) | 6000 | 2.5 | 15000 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER A COMMON PAINT WORK | LABOR FOR PRIMER (SQFT) | 6500 | 2.5 | 16250 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER A COMMON PAINT WORK | LABOR FOR 1ST COAT PUTTY (SQFT) | 6500 | 2.5 | 16250 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER B COMMON PAINT WORK | LABOR FOR 1ST COAT PUTTY (SQFT) | 11000 | 2.5 | 27500 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER B COMMON PAINT WORK | LABOR FOR 2ND COAT PUTTY (SQFT) | 11000 | 2.5 | 27500 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER B COMMON PAINT WORK | LABOR FOR PRIMER (SQFT) | 11000 | 2.5 | 27500 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER C COMMON PAINT WORK | LABOR FOR PRIMER (SQFT) | 6500 | 2.5 | 16250 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER C COMMON PAINT WORK | LABOR FOR 2ND COAT PUTTY (SQFT) | 6500 | 2.5 | 16250 | 5 |  | Job Work
Devarshi enterprise | 445 | 0 | 03 Aug 2024 | GREENWOOD ASPIRE EXP | TOWER C COMMON PAINT WORK | LABOR FOR 1ST COAT PUTTY (SQFT) | 6500 | 2.5 | 16250 | 5 |  | Job Work
G.A.PARMAR | 461 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | TOWER A PASSANGER LIFT WORK | LABOR FOR PASSENGER LIFT (NOS) | 1 | 5000 | 5000 | 5 | Tower and Floor : Tower A & C --- Passenger Lift Work | Job Work
G.A.PARMAR | 461 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | TOWER C PASSANGER LIFT WORK | LABOR FOR PASSENGER LIFT (NOS) | 1 | 5000 | 5000 | 5 | Tower and Floor : Tower A & C --- Passenger Lift Work | Job Work
Geo Designs & Research Pvt. Ltd | 14 | 0 | 10 Jun 2021 | GREENWOODS AARANYA | TESTING OF MATERIALS | CHARGES FOR BEND TEST OF STEEL | 100 | 110 | 11000 | 0 |  | Job Work
Geo Designs & Research Pvt. Ltd | 14 | 0 | 10 Jun 2021 | GREENWOODS AARANYA | TESTING OF MATERIALS | CHARGES FOR REBEND TEST OF STEEL | 100 | 160 | 16000 | 0 |  | Job Work
Geo Designs & Research Pvt. Ltd | 14 | 0 | 10 Jun 2021 | GREENWOODS AARANYA | TESTING OF MATERIALS | CHARGES FOR TENSILE TEST - COUPLER | 100 | 500 | 50000 | 0 |  | Job Work
Geo Designs & Research Pvt. Ltd | 14 | 0 | 10 Jun 2021 | GREENWOODS AARANYA | TESTING OF MATERIALS | CHARGES FOR TENSILE TEST OF STEEL (22 TO 30MM) | 100 | 300 | 30000 | 0 |  | Job Work
Geo Designs & Research Pvt. Ltd | 14 | 0 | 10 Jun 2021 | GREENWOODS AARANYA | TESTING OF MATERIALS | CHARGES FOR TENSILE TEST OF STEEL (UP TO 20MM) | 200 | 250 | 50000 | 0 |  | Job Work
Isha Construction & New-Tech Demolition | 38 | 0 | 18 Apr 2022 | GREENWOODS AARANYA | TOWER C 2ND FLOOR RCC WORK REBARING WORK | LABOR FOR 16 MM REBARING | 50 | 290 | 14500 | 5 |  | Construction
K K CONSTRUCTION | 21 | 0 | 03 Mar 2021 | NEPTUNE OBELISK EXP | 2ND FLOOR RCC WORK FOR SLAB | DEPART SHUTTERING CARPENTER | 370 | 500 | 185000 | 5 |  | Construction
K K CONSTRUCTION | 21 | 0 | 03 Mar 2021 | NEPTUNE OBELISK EXP | COMMON CIVIL EXTRA WORK | DEPART LABOR | 820 | 300 | 246000 | 5 |  | Construction
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C 2ND FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 167 | 580 | 96860 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER A GROUND FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 117 | 580 | 67860 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C GROUND FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 117 | 580 | 67860 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER B GROUND FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 116 | 580 | 67280 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER A 1ST FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 184 | 580 | 106720 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER B 1ST FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 182 | 580 | 105560 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C 1ST FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 184 | 580 | 106720 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER A 2ND FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 167 | 580 | 96860 | 5 |  | Job Work
MAA ASHAPURA IMPERIAL | 368 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER B 2ND FLOOR CARPENTRY WORK | LABOR FOR TRAP DOOR (SQFT) | 166 | 580 | 96280 | 5 |  | Job Work
Manishaben Solanki | 98 | 0 | 28 Sep 2023 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR LONG ROUTE TRIP (NOS) | 100 | 1000 | 100000 | 0 |  | Job Work
Manishaben Solanki | 98 | 0 | 28 Sep 2023 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR SHORT ROUTE TRIP | 100 | 200 | 20000 | 0 |  | Job Work
Manishaben Solanki | 98 | 0 | 28 Sep 2023 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR LONG ROUTE TRIP (NOS) | 100 | 1200 | 120000 | 0 |  | Job Work
Manishaben Solanki | 98 | 0 | 28 Sep 2023 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR SHORT ROUTE TRIP | 50 | 300 | 15000 | 0 |  | Job Work
Manishaben Solanki | 98 | 0 | 28 Sep 2023 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR SHORT ROUTE TRIP | 50 | 700 | 35000 | 0 |  | Job Work
Miran Decorators | 195 | 0 | 07 Oct 2024 | GREENWOODS AARANYA | TOWER D GROUND FLOOR PUNNING WORK | LABOR FOR CEILING PUNNING WORK | 140 | 25 | 3500 | 5 |  | Job Work
Miran Decorators | 195 | 0 | 07 Oct 2024 | GREENWOODS AARANYA | TOWER D 1ST FLOOR PUNNING WORK | LABOR FOR CEILING PUNNING WORK | 140 | 25 | 3500 | 5 |  | Job Work
Miran Decorators | 195 | 0 | 07 Oct 2024 | GREENWOODS AARANYA | TOWER D 2ND FLOOR PUNNING WORK | LABOR FOR CEILING PUNNING WORK | 140 | 25 | 3500 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B GROUND FLOOR FALSE CEILING WORK | LABOR FOR LIGHT CUT OUT | 25 | 30 | 750 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B GROUND FLOOR FALSE CEILING WORK | LABOR FOR GYPSUM CEILING (SQFT) | 650 | 55 | 35750 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 1ST FLOOR FALSE CEILING WORK | LABOR FOR GYPSUM CEILING (SQFT) | 850 | 55 | 46750 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 1ST FLOOR FALSE CEILING WORK | LABOR FOR LIGHT CUT OUT | 32 | 30 | 960 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 1ST FLOOR FALSE CEILING WORK | LABOR FOR WALL GROOVE | 100 | 18 | 1800 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 1ST FLOOR FALSE CEILING WORK | LABOR FOR WALL PUNNING (SQFT) | 100 | 25 | 2500 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 2ND FLOOR FALSE CEILING WORK | LABOR FOR WALL PUNNING (SQFT) | 100 | 25 | 2500 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 2ND FLOOR FALSE CEILING WORK | LABOR FOR WALL GROOVE | 100 | 18 | 1800 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 2ND FLOOR FALSE CEILING WORK | LABOR FOR LIGHT CUT OUT | 32 | 30 | 960 | 5 |  | Job Work
Miran Decorators | 196 | 0 | 09 Oct 2024 | GREENWOODS AARANYA | TOWER B 2ND FLOOR FALSE CEILING WORK | LABOR FOR GYPSUM CEILING (SQFT) | 850 | 55 | 46750 | 5 |  | Job Work
OSTRICH ELEVATORS PVT LTD. | 8 | 0 | 08 Apr 2021 | GLOBAL | LIFT WORK | REPAIR & REPLACEMENT CHARGES OF ARD SYSTEM | 2 | 38000 | 76000 | 5 |  | Job Work
OSTRICH ELEVATORS PVT LTD. | 8 | 0 | 08 Apr 2021 | GLOBAL | LIFT WORK | REPAIR & REPLACEMENT CHARGES OF BLOWER | 2 | 2950 | 5900 | 5 |  | Job Work
OSTRICH ELEVATORS PVT LTD. | 8 | 0 | 08 Apr 2021 | GLOBAL | LIFT WORK | REPAIR & REPLACEMENT CHARGES OF LED LIGHT (NOS) | 6 | 350 | 2100 | 5 |  | Job Work
OSTRICH ELEVATORS PVT LTD. | 8 | 0 | 08 Apr 2021 | GLOBAL | LIFT WORK | REPAIR & REPLACEMENT CHARGES OF SEMI TOUCH AVOX BUTTON COP | 1 | 34000 | 34000 | 5 | B1 + B2 + G + 5 AUDODOOR SEMI TOUCH AVOX BUTTON COP | Job Work
OSTRICH ELEVATORS PVT LTD. | 8 | 0 | 08 Apr 2021 | GLOBAL | LIFT WORK | REPAIR & REPLACEMENT CHARGES OF SEMI TOUCH AVOX BUTTON LOP | 8 | 2850 | 22800 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER A 1ST FLOOR 4.5" AAC BLOCK MASONRY WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | 800 | 23 | 18400 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER A 1ST FLOOR RCC WORK FOR SILL & LINTEL | LABOR FOR RCC LINTEL | 200 | 120 | 24000 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER A 1ST FLOOR INTERNAL MALA FINISH PLASTER WORK | LABOUR FOR PLASTER (SQFT) | 900 | 28 | 25200 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C GROUND FLOOR 9" AAC BLOCK MASONRY WORK | LABOR FOR 9" MASONRY WORK (SQFT) | 250 | 26 | 6500 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C GROUND FLOOR 9" AAC BLOCK MASONRY WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | 200 | 23 | 4600 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C GROUND FLOOR RCC WORK FOR SILL & LINTEL | LABOR FOR RCC COPING (RFT) | 100 | 50 | 5000 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | TOWER C GROUND FLOOR INTERNAL MALA FINISH PLASTER WORK | LABOUR FOR PLASTER (SQFT) | 200 | 28 | 5600 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | COMMON CIVIL WORK | DEPART LABOR | 30 | 350 | 10500 | 5 |  | Job Work
pravinsinh Barkala | 370 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | COMMON CIVIL WORK | DEPART MASON | 30 | 650 | 19500 | 5 |  | Job Work
RAJESH KAUSHIK BHARAT | 369 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | COMMON CIVIL WORK | DEPART LABOR | 90 | 350 | 31500 | 5 |  | Job Work
RAJESH KAUSHIK BHARAT | 369 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | COMMON CIVIL WORK | DEPART MASON | 90 | 650 | 58500 | 5 |  | Job Work
Rathod Enterprise | 194 | 0 | 07 Oct 2024 | GREENWOODS AARANYA | COMMON PASSENGER LIFT WORK | CHARGES FOR 25MM EARTHING WORK (SET) | 2 | 3500 | 7000 | 5 |  | Job Work
Rathod Enterprise | 194 | 0 | 07 Oct 2024 | GREENWOODS AARANYA | COMMON PASSENGER LIFT WORK | INSTALLATION CHARGES FOR EARTHING (SET) | 2 | 1000 | 2000 | 5 |  | Job Work
Rathod Enterprise | 194 | 0 | 07 Oct 2024 | GREENWOODS AARANYA | COMMON PASSENGER LIFT WORK | LABOR FOR CHEMICAL BAG - FOR EARTHING (SET) | 4 | 700 | 2800 | 5 |  | Job Work
Sanjay Goswami | 61 | 0 | 16 Dec 2023 | NEPTUNE OBELISK EXP | GROUND FLOOR PAINT WORK | LABOR FOR SCAFFOLDING (SQFT) | 3500 | 5.5 | 19250 | 5 |  | Job Work
Sanjay Goswami | 61 | 0 | 16 Dec 2023 | NEPTUNE OBELISK EXP | GROUND FLOOR PAINT WORK | LABOR FOR 2 COAT PUTTY & 1 COAT PRIMER | 3500 | 7.5 | 26250 | 5 |  | Job Work
Sanjay Goswami | 61 | 0 | 16 Dec 2023 | NEPTUNE OBELISK EXP | 1ST FLOOR PAINT WORK | LABOR FOR 2 COAT PUTTY & 1 COAT PRIMER | 2400 | 7.5 | 18000 | 5 |  | Job Work
Schindler India Private Limited | 75 | 0 | 01 Jul 2024 | NEPTUNE OBELISK EXP | COMMON LIFT WORK | LABOR FOR LIFT ACCESSORIES | 1 | 210169.65 | 210169.65 | 0 | stainless steel -AISI 304 -LINEN | Job Work
Schindler India Private Limited | 367 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | FRONT PASSENGER LIFT (TOWER A-1) | AMC OF LIFT | 1 | 73739 | 73739 | 0 | Equipment - 11706012, Start date: 01-10-2024 upto 1 year Equipment - 11706014, Start date: 12-11-2024 upto 1 year Equipment - 11706011, Start date: 29-12-2024 upto 1 year Equipment - 11706013, Start date: 20-06-2025 upto 1 year | Consultancy
Schindler India Private Limited | 367 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | FRONT PASSENGER LIFT (TOWER A-2) | AMC OF LIFT | 1 | 73739 | 73739 | 0 | Equipment - 11706012, Start date: 01-10-2024 upto 1 year Equipment - 11706014, Start date: 12-11-2024 upto 1 year Equipment - 11706011, Start date: 29-12-2024 upto 1 year Equipment - 11706013, Start date: 20-06-2025 upto 1 year | Consultancy
Schindler India Private Limited | 367 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | FRONT PASSENGER LIFT (TOWER C-1) | AMC OF LIFT | 1 | 73739 | 73739 | 0 | Equipment - 11706012, Start date: 01-10-2024 upto 1 year Equipment - 11706014, Start date: 12-11-2024 upto 1 year Equipment - 11706011, Start date: 29-12-2024 upto 1 year Equipment - 11706013, Start date: 20-06-2025 upto 1 year | Consultancy
Schindler India Private Limited | 367 | 0 | 09 Oct 2024 | NEPTUNE TRION EXP | FRONT PASSENGER LIFT (TOWER C-2) | AMC OF LIFT | 1 | 73739 | 73739 | 0 | Equipment - 11706012, Start date: 01-10-2024 upto 1 year Equipment - 11706014, Start date: 12-11-2024 upto 1 year Equipment - 11706011, Start date: 29-12-2024 upto 1 year Equipment - 11706013, Start date: 20-06-2025 upto 1 year | Consultancy
SHREE RAM CARTING | 81 | 0 | 04 Oct 2024 | NEPTUNE OBELISK EXP | COMMON CARTING EXPENSES | LABOR FOR LONG ROUTE TRIP (NOS) | 6 | 900 | 5400 | 5 |  | Job Work
SHREE RAM CARTING | 81 | 0 | 04 Oct 2024 | NEPTUNE OBELISK EXP | COMMON CARTING EXPENSES | LABOR FOR SHORT ROUTE TRIP | 425 | 150 | 63750 | 5 |  | Job Work
SHREE RAM CARTING | 81 | 0 | 04 Oct 2024 | NEPTUNE OBELISK EXP | COMMON CARTING EXPENSES | TRACTOR WITH TRAILOR CHARGES (DAY) | 3 | 1950 | 5850 | 5 |  | Job Work
SHREE RAM CARTING | 81 | 0 | 04 Oct 2024 | NEPTUNE OBELISK EXP | COMMON CARTING EXPENSES | LABOR FOR SHORT ROUTE TRIP | 248 | 350 | 86800 | 5 |  | Job Work
SHREE RAM CARTING | 193 | 0 | 30 Sep 2024 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR LONG ROUTE TRIP (NOS) | 20 | 900 | 18000 | 0 |  | Job Work
SHREE RAM CARTING | 193 | 0 | 30 Sep 2024 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR SHORT ROUTE TRIP | 400 | 350 | 140000 | 0 |  | Job Work
SHREE RAM CARTING | 193 | 0 | 30 Sep 2024 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | TRACTOR CHARGES WITH JCB (NOS) | 25 | 150 | 3750 | 0 |  | Job Work
SHREE RAM CARTING | 193 | 0 | 30 Sep 2024 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | LABOR FOR LONG ROUTE TRIP (NOS) | 10 | 600 | 6000 | 0 |  | Job Work
SHREE RAM CARTING | 193 | 0 | 30 Sep 2024 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | CHARGES FOR SITE TO OUTSIDE TRIP (NOS) | 10 | 2000 | 20000 | 0 |  | Job Work
SHREE RAM CARTING | 193 | 0 | 30 Sep 2024 | GREENWOODS AARANYA | COMMON CARTING EXPANSES | RENT FOR TRACTOR | 20 | 1950 | 39000 | 0 |  | Job Work
Shree Ram Fabrication | 329 | 0 | 28 Jul 2023 | GREENWOOD ASPIRE EXP | COMMON MISCELLANEOUS FABRICATION WORK | SUPPLY & INSTALLATION OF BOTTOM ROLLER | 4 | 9500 | 38000 | 5 |  | Job Work
Shree Ram Fabrication | 329 | 0 | 28 Jul 2023 | GREENWOOD ASPIRE EXP | COMMON MISCELLANEOUS FABRICATION WORK | SUPPLY & INSTALLATION OF FABRICATED GATE (KG) | 4500 | 135 | 607500 | 5 |  | Job Work
Shree Ram Fabrication | 329 | 0 | 28 Jul 2023 | GREENWOOD ASPIRE EXP | COMMON MISCELLANEOUS FABRICATION WORK | LABOR FOR ANCHOR FASTNERS (NOS) | 400 | 175 | 70000 | 5 |  | Job Work
Shree Ram Fabrication | 366 | 0 | 05 Oct 2024 | NEPTUNE TRION EXP | TOWER A UPPER BASEMENT FABRICATION WORK | CHARGES FOR BOX PIPE (SQFT) | 1824 | 95 | 173280 | 5 |  | Job Work
Shree Ram Fabrication | 366 | 0 | 05 Oct 2024 | NEPTUNE TRION EXP | TOWER A UPPER BASEMENT FABRICATION WORK | LABOR FOR GI SHEET FIXING (SQFT) | 420 | 95 | 39900 | 5 | Purpose of Work : BASEMENT STORE WORK | Job Work
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 11TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 12TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 13TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 14TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 15TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 16TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 17TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER C 18TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 11TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 12TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 13TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 14TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 15TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 16TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 17TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREENATH ENGINEERING | 42 | 0 | 10 Jun 2022 | GREENWOODS AARANYA | TOWER D 18TH FLOOR MASONRY WORK | LABOR FOR 08 MM REBARING | 230 | 60 | 13800 | 5 |  | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B UP TO PLINTH CIVIL WORK | LABBOR FOR CONCRETE M30 (CMT) | 40 | 4967.4 | 198696 | 5 | LABBOR FOR CONCRETE M30 (CMT) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B UP TO PLINTH CIVIL WORK | LABOR FOR CENTERING & FORM WORK (SQMT) | 250 | 511.35 | 127837.5 | 5 | LABOR FOR CENTERING & FORM WORK (SQMT) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B UP TO PLINTH CIVIL WORK | LABOUR FOR PCC (CMT) | 5 | 3798.6 | 18993 | 5 | LABOUR FOR PCC (CMT) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B UP TO PLINTH CIVIL WORK | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | 3 | 74511 | 223533 | 5 | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | 60 | 74511 | 4470660 | 5 | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR MS ELECTRICAL BOX - 4"X4"X2.5" | 45 | 160 | 7200 | 5 | CHARGES FOR MS ELECTRICAL BOX - 4"X4"X2.5" | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 25MM | 318 | 135 | 42930 | 5 | CHARGES FOR COUPLER WITH THREADING - 25MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 32MM | 78 | 200 | 15600 | 5 | CHARGES FOR COUPLER WITH THREADING - 32MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 25 X 20MM | 20 | 92 | 1840 | 5 | CHARGES FOR COUPLER WITH THREADING - 25 X 20MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 32 X 25MM | 18 | 140 | 2520 | 5 | CHARGES FOR COUPLER WITH THREADING - 32 X 25MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 16MM | 20 | 65 | 1300 | 5 | CHARGES FOR COUPLER WITH THREADING - 16MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 20MM | 168 | 95 | 15960 | 5 |  | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | LABOR FOR 32MM PVC PIPE (MTR) | 15 | 155 | 2325 | 5 | LABOR FOR 32MM PVC PIPE (MTR) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | LABOR FOR CONDUIT PIPE 25MM (MTR) | 250 | 120 | 30000 | 5 | LABOR FOR CONDUIT PIPE 25MM (MTR) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | LABOR FOR INSTALLING 75MM PVC PIPE (RMT) | 5 | 155 | 775 | 5 | LABOR FOR INSTALLING 75MM PVC PIPE (RMT) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | LABBOR FOR CONCRETE M30 (CMT) | 400 | 4967.4 | 1986960 | 5 | LABBOR FOR CONCRETE M30 (CMT) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR 25MM BEND | 60 | 30 | 1800 | 5 | CHARGES FOR 25MM BEND | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B GROUND FLOOR CIVIL WORK | CHARGES FOR 25MM PVC COUPLER | 120 | 23 | 2760 | 5 | CHARGES FOR 25MM PVC COUPLER | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 20 X 16MM | 36 | 60 | 2160 | 5 | CHARGES FOR COUPLER WITH THREADING - 20 X 16MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 25 X 16MM | 24 | 92 | 2208 | 5 | CHARGES FOR COUPLER WITH THREADING - 25 X 16MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 20MM | 132 | 95 | 12540 | 5 |  | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 16MM | 20 | 65 | 1300 | 5 | CHARGES FOR COUPLER WITH THREADING - 16MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 32 X 25MM | 18 | 140 | 2520 | 5 | CHARGES FOR COUPLER WITH THREADING - 32 X 25MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 25 X 20MM | 92 | 92 | 8464 | 5 | CHARGES FOR COUPLER WITH THREADING - 25 X 20MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 32 X 16MM | 8 | 140 | 1120 | 5 | CHARGES FOR COUPLER WITH THREADING - 32 X 16MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 32MM | 82 | 200 | 16400 | 5 | CHARGES FOR COUPLER WITH THREADING - 32MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER B 1ST FLOOR CIVIL WORK | CHARGES FOR COUPLER WITH THREADING - 25MM | 248 | 135 | 33480 | 5 | CHARGES FOR COUPLER WITH THREADING - 25MM | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER A UP TO PLINTH CIVIL WORK | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | 18 | 74511 | 1341198 | 5 | CHARGES FOR TMT FE-500 GRADE STEEL (TON) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 24 | 0 | 11 Jun 2022 | GREENWOODS ABODE | TOWER A UP TO PLINTH CIVIL WORK | LABBOR FOR CONCRETE M30 (CMT) | 540 | 4967.4 | 2682396 | 5 | LABBOR FOR CONCRETE M30 (CMT) | Construction
SHREYPATH INFRASTRUCTURE PVT LTD | 74 | 0 | 27 Apr 2023 | GREENWOODS AARANYA | TOWER B BASEMENT CIVIL EXTRA WORK CIVIL EXTRA WORK | LABOR FOR UG TANK (LTR) | 781954 | 4.5 | 3518793 | 5 |  | Construction
SOOKIRTI BUILDERS | 281 | 0 | 18 Oct 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR COMMON CIVIL WORK | LABOR FOR RCC PARDI (SQFT) | 235 | 180 | 42300 | 5 |  | Construction
SOOKIRTI BUILDERS | 281 | 0 | 18 Oct 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR COMMON CIVIL WORK | LABOR FOR SINGLE COAT PLASTER WORK (SQFT) | 100 | 21 | 2100 | 5 |  | Construction
SOOKIRTI BUILDERS | 281 | 0 | 18 Oct 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR COMMON CIVIL WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | 25 | 20 | 500 | 5 |  | Construction
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 10TH FLOOR FABRICATION WORK | CHARGES FOR MONKEY LADDER | 165 | 134 | 22110 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 5TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 6TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 7TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 8TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 9TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 10TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 11TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 12TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 13TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 14TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 15TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 16TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
Star Engineering | 309 | 0 | 20 Jan 2024 | NEPTUNE TRION EXP | TOWER C 17TH FLOOR DUCT FABRICATION WORK | CHARGES FOR MONKEY LADDER | 15 | 134 | 2010 | 5 |  | Job Work
SURYA ASSOCIATES | 462 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | CLUB HOUSE WATERPROOFING WORK | LABOR FOR INJECTION GROUTING (NOS) | 70 | 400 | 28000 | 5 | LABOR FOR INJECTION GROUTING WITH CEMENT Clubhouse Squash room PU and Injection Grouting Work. | Job Work
SURYA ASSOCIATES | 462 | 0 | 11 Oct 2024 | GREENWOOD ASPIRE EXP | CLUB HOUSE WATERPROOFING WORK | LABOR FOR PU INJECTION GROUTING (NOS) | 70 | 1800 | 126000 | 5 |  | Job Work
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOR FOR JOINT TREATMENT(RFT) | 80 | 21.2 | 1696 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | 450 | 40.85 | 18382.5 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOR FOR IPS (SQFT) | 333 | 20 | 6660 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOR FOR GLASS FIBER MESH (SQFT) | 333 | 12 | 3996 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOR FOR NANOFLEX WATERPROOFING (SQFT) | 333 | 62 | 20646 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOR FOR BBCC (SQFT) | 450 | 40 | 18000 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 01 WATERPROOFING WORK | LABOR FOR CORNER TREATMENT TAPE (RFT) | 77 | 23.2 | 1786.4 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOR FOR CORNER TREATMENT TAPE (RFT) | 76 | 23.2 | 1763.2 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOR FOR BBCC (SQFT) | 450 | 40 | 18000 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOR FOR NANOFLEX WATERPROOFING (SQFT) | 334 | 62 | 20708 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOR FOR GLASS FIBER MESH (SQFT) | 334 | 12 | 4008 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOR FOR IPS (SQFT) | 334 | 20 | 6680 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | 450 | 40.85 | 18382.5 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 02 WATERPROOFING WORK | LABOR FOR JOINT TREATMENT(RFT) | 80 | 21.2 | 1696 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOR FOR JOINT TREATMENT(RFT) | 80 | 21.2 | 1696 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | 450 | 40.85 | 18382.5 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOR FOR IPS (SQFT) | 333 | 20 | 6660 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOR FOR GLASS FIBER MESH (SQFT) | 333 | 12 | 3996 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOR FOR NANOFLEX WATERPROOFING (SQFT) | 333 | 62 | 20646 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOR FOR BBCC (SQFT) | 450 | 40 | 18000 | 5 |  | Construction
TARSONS ENTERPRISE | 248 | 0 | 04 Jul 2023 | NEPTUNE TRION EXP | TOWER C 4TH FLOOR OFFICE NO 03 WATERPROOFING WORK | LABOR FOR CORNER TREATMENT TAPE (RFT) | 77 | 23.2 | 1786.4 | 5 |  | Construction
TARSONS ENTERPRISE | 421 | 0 | 15 Apr 2024 | GREENWOOD ASPIRE EXP | COMMON WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | 5000 | 40 | 200000 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 | For Framing works of Office & toilet area | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 4TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 5TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | GROUND FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 937.75 | 17 | 15941.75 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | GROUND FLOOR SHOP NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 50 | 17 | 850 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | GROUND FLOOR SHOP NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 50 | 17 | 850 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | GROUND FLOOR SHOP NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 50 | 17 | 850 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | GROUND FLOOR SHOP NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 50 | 17 | 850 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 1ST FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 937.75 | 17 | 15941.75 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 1ST FLOOR SHOP NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 1ST FLOOR SHOP NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 1ST FLOOR SHOP NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 1ST FLOOR SHOP NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 2ND FLOOR SHOP NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 2ND FLOOR SHOP NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 2ND FLOOR SHOP NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 2ND FLOOR SHOP NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 30 | 17 | 510 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 3RD FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 15TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 9TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 9TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 9TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 9TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 9TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 7TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 8TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 9TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 10TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 11TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 12TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 13TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 14TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 16TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 17TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 18TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 62 | 0 | 05 Jan 2024 | NEPTUNE OBELISK EXP | 6TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | 20 | 17 | 340 | 5 |  | Job Work
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | TOWER A GROUND FLOOR COMMON FLOORING & DEDO WORK | LABOR FOR SKIRTING (RFT) | 500 | 40 | 20000 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (800X1600) | 50 | 16 | 800 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES SKIRTING (800X1600) | 250 | 27 | 6750 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (600X600) | 30 | 16 | 480 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES DEDO (1200X600) | 1590 | 28 | 44520 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (600X600) | 160 | 17 | 2720 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (800X1600) | 1350 | 28 | 37800 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1701 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES SKIRTING (600X600) | 100 | 16 | 1600 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES SKIRTING (600X600) | 45 | 16 | 720 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (800X1600) | 2230 | 28 | 62440 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (600X600) | 90 | 17 | 1530 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (1200X600) | 555 | 22 | 12210 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (600X600) | 9 | 16 | 144 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES SKIRTING (800X1600) | 505 | 27 | 13635 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (1200X600) | 18 | 16 | 288 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (800X1600) | 65 | 16 | 1040 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR WOODEN PLANK (1200X200) | 600 | 10 | 6000 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES (1'X1') | 10 | 10 | 100 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES DEDO (1'X1') | 225 | 17 | 3825 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1702 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES FLOORING (1'X1') | 116 | 15 | 1740 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1601 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES DEDO (1'X1') | 225 | 17 | 3825 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1601 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES FLOORING (1'X1') | 116 | 15 | 1740 | 5 |  | Construction
Vikas Kumar B Prajapati | 139 | 0 | 04 Feb 2022 | GREENWOOD ASPIRE EXP | A 1601 FLOORING & DEDO WORK | LABOR FOR WOODEN PLANK (1200X200) | 700 | 10 | 7000 | 5 |  | Construction
Vikas Kumar B Prajapati | 193 | 0 | 17 Dec 2022 | NEPTUNE TRION EXP | TRION (I) FLOORING WORK | DEPART SALAT | 20 | 1100 | 22000 | 5 |  | Job Work
Vikas Kumar B Prajapati | 193 | 0 | 17 Dec 2022 | NEPTUNE TRION EXP | TRION (I) FLOORING WORK | DEPART SALAT HELPER | 20 | 500 | 10000 | 5 |  | Job Work
Vikas Kumar B Prajapati | 193 | 0 | 17 Dec 2022 | NEPTUNE TRION EXP | TRION (I) FLOORING WORK | LABOR FOR CHAMFER (RFT) | 72.32 | 20 | 1446.4 | 5 |  | Job Work
Vikas Kumar B Prajapati | 193 | 0 | 17 Dec 2022 | NEPTUNE TRION EXP | TRION (I) FLOORING WORK | LABOR FOR DHAR POLISH (RFT) | 108.48 | 17 | 1844.16 | 5 |  | Job Work
Vikas Kumar B Prajapati | 193 | 0 | 17 Dec 2022 | NEPTUNE TRION EXP | TRION (I) FLOORING WORK | LABOR FOR DOOR FRAME (RFT) | 72.32 | 40 | 2892.8 | 5 |  | Job Work