## Project_Work_Order6384799721457
Project Work Order
From 17 Mar 2005 To 07 Apr 2024
Page 1 of 1
Total Records: 243 Records 1 To 243
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C BASEMENT COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 19103 | 5.5 | 105066.5 | 18911.98 | 123978.48 | 5 | 7100 | 39050 | 211672.54 | 1387631.51 | 12003 | -1263653.03 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D BASEMENT COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 15995 | 5.5 | 87972.5 | 15835.06 | 103807.56 | 5 | 15815 | 86982.5 | 211672.54 | 1387631.51 | 180 | -1283823.95 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C BASEMENT COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D BASEMENT COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5029.26 | 42748.71 | 211672.54 | 1387631.51 | 25.0064 | -1336937.22 | ELECTRICAL SLAB CONDUIT WORK DONE FOR TOWER D 1ST FLOOR |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 0 | 0 | 0 | 0 | 5054.2664 | 0 | ELECTRICAL SLAB CONDUIT WORK DONE FOR TOWER D 2ND FLOOR |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 702 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 701 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1002 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1001 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 902 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 901 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 802 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 801 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 702 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 701 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 1 | 26000 | 26000 | 4680 | 30680 | 5 | 0.6 | 15600 | 211672.54 | 1387631.51 | 0.4 | -1356951.51 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1002 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1001 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 902 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 901 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 802 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 801 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | FLAT INTERNAL ELECTRICAL WORK WITH MATERIAL |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | FLAT | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 202 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 201 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 102 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 101 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 101 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 102 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 502 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 501 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 402 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 401 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 302 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 301 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 802 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 801 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 702 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 701 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 602 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 601 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1102 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1101 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1002 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1001 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 902 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 901 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1402 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1401 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1302 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1301 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1202 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1201 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 202 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 201 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1602 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1601 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1502 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1501 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 502 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 501 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 402 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 401 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 302 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 301 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 802 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 801 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 702 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 701 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 602 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 601 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 600 | 1200 | 216 | 1416 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1102 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1101 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1002 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1001 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 902 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 901 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1402 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1401 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1302 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1301 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1202 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1201 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1602 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1601 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1502 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1501 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 701 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1001 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 902 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 901 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 802 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 801 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 702 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1002 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 701 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1001 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 902 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 901 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 802 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 801 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 702 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1002 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 5TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 4TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 3RD FLOOR ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 102 ELECTRIC WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 24000 | 24000 | 4320 | 28320 | 5 | 1 | 24000 | 211672.54 | 1387631.51 | 0 | -1359311.51 | FLAT INTERNAL ELECTRIC WALL ZARI WORK WITH MATERIAL |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) | NOS | 0 | 2600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 8TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 7TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 6TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 5TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 4TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 6TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 9TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 8TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 7TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 9TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 4TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 6TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 5TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 4TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | LABOUR CHARGES FOR SLAB CONDUIT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 9TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 8TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 7TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 6TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 5TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 9TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 8TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 7TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | MISC LABOUR FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 3RD FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1ST FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 2ND FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 3RD FLOOR ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D GROUND FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C GROUND FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 10.8 | 54586.08 | 9825.5 | 64411.58 | 5 | 0 | 0 | 0 | 0 | 5054.2664 | 0 | ELECTRICAL SLAB CONDUIT WORK DONE FOR TOWER D GROUND FLOOR |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 1ST FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5029.26 | 42748.71 | 211672.54 | 1387631.51 | 25.0064 | -1336937.22 | ELECTRICAL SLAB CONDUIT WORK DONE FOR TOWER D 1ST FLOOR |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D 2ND FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 8.5 | 42961.26 | 7733.02 | 50694.28 | 5 | 5026.16 | 42722.36 | 211672.54 | 1387631.51 | 28.1064 | -1336937.22 | ELECTRICAL SLAB CONDUIT WORK DONE FOR TOWER D 2ND FLOOR |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER D GROUND FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5054.2664 | 10.8 | 54586.08 | 9825.5 | 64411.58 | 5 | 5029.26 | 54316.01 | 211672.54 | 1387631.51 | 25.0064 | -1323219.93 | ELECTRICAL SLAB CONDUIT WORK DONE FOR TOWER D GROUND FLOOR |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 1ST FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 211672.54 | 1387631.51 | 0 | -1384091.51 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 18 | 0 | 02 Aug 2021 | LAHUTE ELECTRIC CO. | TOWER C 2ND FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | MISC ELECTRIC WORK DONE FOR SLEEVE INSERT WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900