## Project_Work_Order6385189754356
Project Work Order
From 09 Apr 2009 To 22 May 2024
Page 1 of 1
Total Records: 164 Records 1 To 164
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
ANTICA GREENWOOD | 6 | 0 | 05 Jun 2020 | Bharat J. Makadia | VILLA 17 UP TO PLINTH RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 0 | 260 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | pur.nrpl1 |  | Construction | 05 Jun 2020
ANTICA GREENWOOD | 7 | 0 | 05 Jun 2020 | Bharat J. Makadia | VILLA 17 RCC WORK UP TO TERRACE FLOOR FOR SLAB | LABOUR FOR RCC | SQFT | 0 | 260 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | amish.patel | pur.nrpl1 | Amish.patel | Construction | 13 Jun 2020
ANTICA GREENWOOD | 9 | 0 | 17 Jun 2020 | Bharat J. Makadia | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | LABOUR FOR RCC | SQFT | 1667.38 | 260 | 433518.8 | 78033.38 | 511552.18 | 5 | 1667.38 | 433518.8 | 299446.88 | 1984280.68 | 0 | -1472728.5 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 9 | 0 | 17 Jun 2020 | Bharat J. Makadia | VILLA 17 RCC WORK UP TO FIRST FLOOR FOR SLAB | LABOUR FOR RCC | SQFT | 1667.38 | 260 | 433518.8 | 78033.38 | 511552.18 | 5 | 1667.38 | 433518.8 | 299446.88 | 1984280.68 | 0 | -1472728.5 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 9 | 0 | 17 Jun 2020 | Bharat J. Makadia | VILLA 17 RCC WORK UP TO TERRACE FLOOR FOR SLAB | LABOUR FOR RCC | SQFT | 985.27 | 260 | 256170.2 | 46110.64 | 302280.84 | 5 | 985.27 | 256170.2 | 299446.88 | 1984280.68 | 0 | -1681999.84 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 9 | 0 | 17 Jun 2020 | Bharat J. Makadia | VILLA 17 PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 2160.1 | 260 | 561626 | 101092.68 | 662718.68 | 5 | 2160.1 | 561626 | 299446.88 | 1984280.68 | 0 | -1321562 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 9 | 0 | 17 Jun 2020 | Bharat J. Makadia | VILLA 17 UP TO PLINTH RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 1098.95 | 260 | 285727 | 51430.86 | 337157.86 | 5 | 0 | 0 | 0 | 0 | 1098.95 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 59 | 1 | 11 Sep 2020 | Tycoon Earth Works | VILLA 17 EXCAVATION AND BACKFILLING WORK | LABOUR FOR TRIP OF SOIL | NOS | 1 | 1400 | 1400 | 252 | 1652 | 5 | 1 | 1400 | 126022.5 | 1111847.5 | 0 | -1110195.5 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 87 | 0 | 03 Nov 2020 | Jay B Makadiya | VILLA 17 CIVIL EXTRA WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 69 | 14 | 966 | 0 | 966 | 5 | 68.665 | 961.31 | 0 | 285581.4 | 0.335 | -284615.4 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 87 | 0 | 03 Nov 2020 | Jay B Makadiya | VILLA 17 CIVIL EXTRA WORK | LABOR FOR EXCAVATION (CFT) | CFT | 79 | 6 | 474 | 0 | 474 | 5 | 78.82 | 472.92 | 0 | 285581.4 | 0.18 | -285107.4 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 87 | 0 | 03 Nov 2020 | Jay B Makadiya | VILLA 17 CIVIL EXTRA WORK | LABOR FOR RCC COPING (RFT) | RFT | 19.5 | 35 | 682.5 | 0 | 682.5 | 5 | 19.16 | 670.6 | 0 | 285581.4 | 0.34 | -284898.9 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 87 | 0 | 03 Nov 2020 | Jay B Makadiya | VILLA 17 CIVIL EXTRA WORK | LABOR FOR GROUND BEAM (RFT) | RFT | 39.5 | 85 | 3357.5 | 0 | 3357.5 | 5 | 39.05 | 3319.25 | 0 | 285581.4 | 0.45 | -282223.9 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 178 | 0 | 02 Mar 2022 | Anant G Patel | VILLA 17 Electrical GF SLAB PIPING | LABOR FOR PROVIDING 20 & 25 SQMM PIPES & BOX IN SLAB | SQFT | 5500 | 11 | 60500 | 0 | 60500 | 5 | 5500 | 60500 | 0 | 60500 | 0 | 0 | Providing and making point with pipe and box in slab of ground floor of villa no. 17 |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 187 | 0 | 05 May 2022 | Tycoon Earth Works | VILLA 17 UP TO PLINTH LEVEL EXCAVATION & BACKFILLING WORK | CHARGES FOR HYWA (NOS) | NOS | 0 | 2550 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 187 | 0 | 05 May 2022 | Tycoon Earth Works | VILLA 17 UP TO PLINTH LEVEL EXCAVATION & BACKFILLING WORK | CHARGES FOR MINI DUMPER (DAY) | DAY | 5 | 6400 | 32000 | 5760 | 37760 | 5 | 1 | 6400 | 208284.8 | 1365422.3 | 4 | -1327662.3 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 187 | 0 | 05 May 2022 | Tycoon Earth Works | VILLA 17 UP TO PLINTH LEVEL EXCAVATION & BACKFILLING WORK | CHARGES FOR HYWA (NOS) | NOS | 100 | 2750 | 275000 | 49500 | 324500 | 5 | 48 | 132000 | 208284.8 | 1365422.3 | 52 | -1040922.3 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 187 | 0 | 05 May 2022 | Tycoon Earth Works | VILLA 17 EXCAVATION AND BACKFILLING WORK | CHARGES FOR MINI DUMPER (DAY) | DAY | 20 | 1700 | 34000 | 6120 | 40120 | 5 | 15 | 25500 | 208284.8 | 1365422.3 | 5 | -1325302.3 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 198 | 0 | 25 Jun 2022 | Isha Construction & New-Tech Demolition | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | LABOUR FOR 10 MM REBARING | NOS | 30 | 70 | 2100 | 378 | 2478 | 5 | 30 | 2100 | 4532.4 | 29712.4 | 0 | -27234.4 | DUE TO CHANGE IN DRAWING |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 198 | 0 | 25 Jun 2022 | Isha Construction & New-Tech Demolition | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | LABOR FOR REBARING 10MM (RE 10) | NOS | 0 | 75 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | MISC LABOR FOR REBARING 10MM (RE10) FOR VILLA 17 |  | deepak.p | pur.nrpl3 |  | Construction | 01 Jan 1900
ANTICA GREENWOOD | 198 | 0 | 25 Jun 2022 | Isha Construction & New-Tech Demolition | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | LABOR FOR REBARING 10MM (RE 10) | NOS | 60 | 90 | 5400 | 972 | 6372 | 5 | 20 | 1800 | 4532.4 | 29712.4 | 40 | -23340.4 | Misc 10mm RE 10 rebaring work at Villa 17 |  | T.Joshi | pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
ANTICA GREENWOOD | 198 | 0 | 25 Jun 2022 | Isha Construction & New-Tech Demolition | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | LABOR FOR REBARING 10MM (RE 10) | NOS | 0 | 70 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Rebaring work of 10mm with RE 10 done at Villa as per executions team&lsquo;s instructions. |  | deepak.p | pur.nrpl3 |  | Construction | 01 Jan 1900
ANTICA GREENWOOD | 204 | 0 | 12 Aug 2022 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR PLUMBING (NOS) | NOS | 1 | 70655 | 70655 | 0 | 70655 | 5 | 1 | 70655 | 0 | 141310 | 0 | -70655 | Misc. Plumbing work done at Villa 17 as per site execution team&lsquo;s instructions |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 230 | 0 | 27 May 2023 | A B PATEL | VILLA 17 FABRICATION WORK | LABOR FOR BALCONY RAILING (KG) | KG | 220 | 200 | 44000 | 7920 | 51920 | 5 | 185 | 37000 | 25380 | 166380 | 35 | -114460 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 232 | 0 | 10 Jun 2023 | Jay Corporation | VILLA 17 TERRACE WATERPROOFING WORK | LABOR FOR MEMBRANE BASED WATERPROOFING (SQFT) | SQFT | 5000 | 52 | 260000 | 46800 | 306800 | 5 | 3616 | 188032 | 33845.76 | 221877.76 | 1384 | 84922.24 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 235 | 0 | 26 Jul 2023 | Rathod Enterprise | VILLA 17 ELECTRICAL EARTHINGS | CHARGES FOR 25MM EARTHING WORK (SET) | SET | 1 | 5900 | 5900 | 1062 | 6962 | 5 | 1 | 5900 | 6372 | 41772 | 0 | -34810 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 235 | 0 | 26 Jul 2023 | Rathod Enterprise | VILLA 17 ELECTRICAL EARTHINGS | CHARGES FOR 25MM EARTHING WORK (SET) | SET | 4 | 5900 | 23600 | 4248 | 27848 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of advance maintenance free earthing system 1)25mm by 3 mtr long strip in pipe copper coated 250 micron 2) chemical bags: along with 25kg bags of premium ground improving compound as per IS 3043 duly modified premium quality for excellent electrical conductivity. |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 237 | 0 | 01 Aug 2023 | GOODEE ENTERPRISE | VILLA 17 TERRACE WATERPROOFING WORK | LABOR FOR CHEMICAL WATTA (RFT) | RFT | 300 | 30 | 9000 | 0 | 9000 | 5 | 275 | 8250 | 0 | 92435.2 | 25 | -83435.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 237 | 0 | 01 Aug 2023 | GOODEE ENTERPRISE | VILLA 17 TERRACE WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | SQFT | 1500 | 58.3 | 87450 | 0 | 87450 | 5 | 1444 | 84185.2 | 0 | 92435.2 | 56 | -4985.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 239 | 0 | 02 Aug 2023 | Ramanbhai Somjibhai Bhabhor | VILLA 17 FLOORING WORK CHAINA MOSAIC | LABOR FOR CHINA MOSAIC (SQFT) | SQFT | 3000 | 19 | 57000 | 0 | 57000 | 5 | 2921.46 | 55507.74 | 0 | 65007.74 | 78.54 | -8007.74 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 239 | 0 | 02 Aug 2023 | Ramanbhai Somjibhai Bhabhor | VILLA 17 FLOORING WORK CHAINA MOSAIC | LABOR FOR CHAINA MOSAIC VATA | RFT | 500 | 19 | 9500 | 0 | 9500 | 5 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 239 | 0 | 02 Aug 2023 | Ramanbhai Somjibhai Bhabhor | VILLA 17 FLOORING WORK CHAINA MOSAIC | LABOR FOR CHINA MOSAIC (SQFT) | SQFT | 500 | 19 | 9500 | 0 | 9500 | 5 | 500 | 9500 | 0 | 65007.74 | 0 | -55507.74 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 240 | 0 | 03 Aug 2023 | Alpesh kanubhai Patanwadia | VILLA 17 FABRICATION WORK | LABOR FOR RAILING WORK (LS) | LUMSUM | 1 | 900 | 900 | 0 | 900 | 5 | 1 | 900 | 0 | 2700 | 0 | -1800 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 247 | 0 | 06 Oct 2023 | Jairam S. Saini | VILLA 17 DOOR & WINDOW FRAME WORK | LABOR FOR CHAMFER (RFT) | RFT | 2500 | 20 | 50000 | 0 | 50000 | 5 | 2435.86 | 48717.2 | 0 | 161679.86 | 64.14 | -111679.86 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 247 | 0 | 06 Oct 2023 | Jairam S. Saini | VILLA 17 DOOR & WINDOW FRAME WORK | LABOUR FOR DOOR & WINDOW FRAME (RFT) | RFT | 1600 | 40 | 64000 | 0 | 64000 | 5 | 1528.42 | 61136.8 | 0 | 161679.86 | 71.58 | -97679.86 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 247 | 0 | 06 Oct 2023 | Jairam S. Saini | VILLA 17 DOOR & WINDOW FRAME WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 3100 | 17 | 52700 | 0 | 52700 | 5 | 3048.58 | 51825.86 | 0 | 161679.86 | 51.42 | -108979.86 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 254 | 0 | 04 Jan 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR SAND BEDDING | SQFT | 1800 | 7.5 | 13500 | 0 | 13500 | 5 | 1800 | 13500 | 0 | 160495.72 | 0 | -146995.72 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 254 | 0 | 04 Jan 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR VITRIFIED TILES FLOORING (800X1600) | SQFT | 4500 | 28 | 126000 | 0 | 126000 | 5 | 4285.2 | 119985.6 | 0 | 160495.72 | 214.8 | -34495.72 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 254 | 0 | 04 Jan 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR VITRIFIED TILES SKIRTING (800X1600) | RFT | 1000 | 28 | 28000 | 0 | 28000 | 5 | 805.24 | 22546.72 | 0 | 160495.72 | 194.76 | -132495.72 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 254 | 0 | 04 Jan 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR GROOVE (RFT) | RFT | 3000 | 2 | 6000 | 0 | 6000 | 5 | 2231.7 | 4463.4 | 0 | 160495.72 | 768.3 | -154495.72 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 255 | 0 | 18 Feb 2024 | SHREENATH ENGINEERING | VILLA 17 CIVIL EXTRA WORK | LABOR FOR 100 MM DIA CORE CUTTING (230 MM DEPTH) | NOS | 12 | 360 | 4320 | 777.6 | 5097.6 | 5 | 12 | 4320 | 1743.3 | 11428.3 | 0 | -6330.7 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 255 | 0 | 18 Feb 2024 | SHREENATH ENGINEERING | VILLA 17 CIVIL EXTRA WORK | LABOR FOR 100 MM DIA CORE CUTTING (700 MM DEPTH) | NOS | 2 | 1095 | 2190 | 394.2 | 2584.2 | 5 | 2 | 2190 | 1743.3 | 11428.3 | 0 | -8844.1 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 255 | 0 | 18 Feb 2024 | SHREENATH ENGINEERING | VILLA 17 CIVIL EXTRA WORK | LABOR FOR 125 MM DIA CORE CUTTING (150 MM DEPTH) | NOS | 3 | 360 | 1080 | 194.4 | 1274.4 | 5 | 3 | 1080 | 1743.3 | 11428.3 | 0 | -10153.9 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 255 | 0 | 18 Feb 2024 | SHREENATH ENGINEERING | VILLA 17 CIVIL EXTRA WORK | LABOR FOR 125 MM DIA CORE CUTTING (700 MM DEPTH) | NOS | 1 | 1095 | 1095 | 197.1 | 1292.1 | 5 | 1 | 1095 | 1743.3 | 11428.3 | 0 | -10136.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 255 | 0 | 18 Feb 2024 | SHREENATH ENGINEERING | VILLA 17 CIVIL EXTRA WORK | LABOR FOR 75 MM DIA CORE CUTTING (230 MM DEPTH) | NOS | 1 | 360 | 360 | 64.8 | 424.8 | 5 | 1 | 360 | 1743.3 | 11428.3 | 0 | -11003.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 255 | 0 | 18 Feb 2024 | SHREENATH ENGINEERING | VILLA 17 CIVIL EXTRA WORK | LABOR FOR 52 MM DIA CORE CUTTING (230 MM DEPTH) | NOS | 2 | 320 | 640 | 115.2 | 755.2 | 5 | 2 | 640 | 1743.3 | 11428.3 | 0 | -10673.1 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 256 | 0 | 18 Feb 2024 | KHARVA PRAGNESH | VILLA 17 RCC WORK UP TO GROUND FLOOR FOR SLAB | LABOR FOR GRINDING WORK (NOS) | NOS | 10 | 200 | 2000 | 0 | 2000 | 5 | 10 | 2000 | 0 | 7000 | 0 | -5000 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 258 | 0 | 22 Feb 2024 | GOODEE ENTERPRISE | VILLA 17 BATHROOMS WATERPROOFING WORK | LABOR FOR CHEMICAL WATTA (RFT) | RFT | 256 | 30 | 7680 | 0 | 7680 | 5 | 256 | 7680 | 0 | 139677.2 | 0 | -131997.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 258 | 0 | 22 Feb 2024 | GOODEE ENTERPRISE | VILLA 17 BATHROOMS WATERPROOFING WORK | LABOR FOR HOLE FILLING (NOS) | NOS | 10 | 500 | 5000 | 0 | 5000 | 5 | 10 | 5000 | 0 | 139677.2 | 0 | -134677.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 258 | 0 | 22 Feb 2024 | GOODEE ENTERPRISE | VILLA 17 BATHROOMS WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | SQFT | 3500 | 58.3 | 204050 | 0 | 204050 | 5 | 2084 | 121497.2 | 0 | 139677.2 | 1416 | 64372.8 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 258 | 0 | 22 Feb 2024 | GOODEE ENTERPRISE | VILLA 17 BATHROOMS WATERPROOFING WORK | LABOR FOR HOLE FILLING (NOS) | NOS | 5 | 500 | 2500 | 0 | 2500 | 5 | 5 | 2500 | 0 | 139677.2 | 0 | -137177.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 258 | 0 | 22 Feb 2024 | GOODEE ENTERPRISE | VILLA 17 BATHROOMS WATERPROOFING WORK | LABOR FOR CHEMICAL WATTA (RFT) | RFT | 100 | 30 | 3000 | 0 | 3000 | 5 | 100 | 3000 | 0 | 139677.2 | 0 | -136677.2 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | INSTALLATION CHARGES OF HI WALL MACHINE (TON 0.8 TO 1.8) | NOS | 9 | 1500 | 13500 | 2430 | 15930 | 5 | 9 | 13500 | 36935.46 | 242132.46 | 0 | -226202.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | CHARGES OF N2 TESTING | NOS | 9 | 850 | 7650 | 1377 | 9027 | 5 | 9 | 7650 | 36935.46 | 242132.46 | 0 | -233105.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | LABOR FOR COPPER PIPING (RMT) | RMT | 120 | 853 | 102360 | 18424.8 | 120784.8 | 5 | 120 | 102360 | 36935.46 | 242132.46 | 0 | -121347.66 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | CHARGES FOR PVC DRAIN PIPING (RMT) | RMT | 50 | 197 | 9850 | 1773 | 11623 | 5 | 50 | 9850 | 36935.46 | 242132.46 | 0 | -230509.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | LABOR FOR FLEXIBLE ELECTRIC CABLE (RMT) | RMT | 120 | 140 | 16800 | 3024 | 19824 | 5 | 120 | 16800 | 36935.46 | 242132.46 | 0 | -222308.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | LABOR FOR ZARI WORK (RMT) | RMT | 70 | 215 | 15050 | 2709 | 17759 | 5 | 67 | 14405 | 36935.46 | 242132.46 | 3 | -224373.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | LABOUR FOR INSTALLING L TYPE STAND FOR AC | NOS | 9 | 850 | 7650 | 1377 | 9027 | 5 | 9 | 7650 | 36935.46 | 242132.46 | 0 | -233105.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | CHARGES FOR GLASS CLOTH FOR EXPOSED PIPING | RMT | 40 | 200 | 8000 | 1440 | 9440 | 5 | 40 | 8000 | 36935.46 | 242132.46 | 0 | -232692.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | CHARGES FOR PVC DRAIN PIPING (RMT) | RMT | 26 | 197 | 5122 | 921.96 | 6043.96 | 5 | 26 | 5122 | 36935.46 | 242132.46 | 0 | -236088.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | LABOR FOR COPPER PIPING (RMT) | RMT | 20 | 853 | 17060 | 3070.8 | 20130.8 | 5 | 20 | 17060 | 36935.46 | 242132.46 | 0 | -222001.66 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 259 | 0 | 23 Feb 2024 | LYNX COMMUNICATION SYSTEM PVT LTD | VILLA 17 AC INSTALLATION WORK | LABOR FOR FLEXIBLE ELECTRIC CABLE (RMT) | RMT | 20 | 140 | 2800 | 504 | 3304 | 5 | 20 | 2800 | 36935.46 | 242132.46 | 0 | -238828.46 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 261 | 0 | 26 Feb 2024 | CHOTURAM SUTHAR | VILLA 17 CARPENTRY WORK | LABOUR FOR MAIN DOOR (SQFT) | SQFT | 48 | 150 | 7200 | 0 | 7200 | 5 | 48 | 7200 | 0 | 351217.5 | 0 | -344017.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 261 | 0 | 26 Feb 2024 | CHOTURAM SUTHAR | VILLA 17 CARPENTRY WORK | LABOUR FOR MDF FINISH (SQFT) | SQFT | 22 | 375 | 8250 | 0 | 8250 | 5 | 0 | 0 | 0 | 0 | 22 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 261 | 0 | 26 Feb 2024 | CHOTURAM SUTHAR | VILLA 17 CARPENTRY WORK | LABOUR FOR PALMET | SQFT | 100 | 475 | 47500 | 0 | 47500 | 5 | 89.38 | 42455.5 | 0 | 351217.5 | 10.62 | -303717.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 261 | 0 | 26 Feb 2024 | CHOTURAM SUTHAR | VILLA 17 CERA SHEET WORK | LABOUR FOR CEMENT SHEET (SQFT) | SQFT | 1200 | 70 | 84000 | 0 | 84000 | 5 | 1031 | 72170 | 0 | 351217.5 | 169 | -267217.5 | cement sheet fitting and fixing with (H frame/palak) |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 261 | 0 | 26 Feb 2024 | CHOTURAM SUTHAR | VILLA 17 CARPENTRY WORK | LABOR FOR WOODEN PATTI FINISHING WORK (RFT) | RFT | 80 | 130 | 10400 | 0 | 10400 | 5 | 76 | 9880 | 0 | 351217.5 | 4 | -340817.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 261 | 0 | 26 Feb 2024 | CHOTURAM SUTHAR | VILLA 17 CARPENTRY WORK | LABOUR FOR MAKING & FIXING FLUSH DOOR (SQFT) | SQFT | 400 | 575 | 230000 | 0 | 230000 | 5 | 381.76 | 219512 | 0 | 351217.5 | 18.24 | -121217.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR 4" SWR PIPE FITTING | RFT | 70 | 22 | 1540 | 0 | 1540 | 5 | 70 | 1540 | 0 | 50410 | 0 | -48870 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR CONCIL FLUSH TANK FIXING | NOS | 7 | 1100 | 7700 | 0 | 7700 | 5 | 6 | 6600 | 0 | 50410 | 1 | -42710 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR OVERHEAD SHOWER FITTING | NOS | 4 | 150 | 600 | 0 | 600 | 5 | 4 | 600 | 0 | 50410 | 0 | -49810 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR 1/2" BATH SPOUT FITTING | NOS | 4 | 150 | 600 | 0 | 600 | 5 | 4 | 600 | 0 | 50410 | 0 | -49810 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR WC FIXING - WALL HUNG (NOS) | NOS | 7 | 1200 | 8400 | 0 | 8400 | 5 | 6 | 7200 | 0 | 50410 | 1 | -42010 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR 6"*6" DRAIN JALI | NOS | 14 | 60 | 840 | 0 | 840 | 5 | 12 | 720 | 0 | 50410 | 2 | -49570 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR ANGLE COCK FITTING | NOS | 22 | 60 | 1320 | 0 | 1320 | 5 | 20 | 1200 | 0 | 50410 | 2 | -49090 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR BASIN MIXTURE PILLER COCK (OPEN) | NOS | 7 | 150 | 1050 | 0 | 1050 | 5 | 6 | 900 | 0 | 50410 | 1 | -49360 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR BOTTLE TRAP | NOS | 7 | 150 | 1050 | 0 | 1050 | 5 | 6 | 900 | 0 | 50410 | 1 | -49360 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR 1/2" FOUR WAY DIVERTER FITTING | NOS | 4 | 700 | 2800 | 0 | 2800 | 5 | 4 | 2800 | 0 | 50410 | 0 | -47610 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR 1/2" BATHROOM POINT | NOS | 45 | 350 | 15750 | 0 | 15750 | 5 | 45 | 15750 | 0 | 50410 | 0 | -34660 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR 4" P-TRAP FITTING | NOS | 12 | 300 | 3600 | 0 | 3600 | 5 | 12 | 3600 | 0 | 50410 | 0 | -46810 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 4 | 1100 | 4400 | 0 | 4400 | 5 | 4 | 4400 | 0 | 50410 | 0 | -46010 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 262 | 0 | 03 Mar 2024 | Bhimsinghbhai Punabhai Savaya | VILLA 17 PLUMBING WORK | LABOR FOR WASH BASIN FITTING | NOS | 7 | 600 | 4200 | 0 | 4200 | 5 | 6 | 3600 | 0 | 50410 | 1 | -46210 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 263 | 0 | 03 Mar 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | PROVIDING AND APPLYING APEX ULTIMA ON OUTSIDE AREA | SQFT | 0 | 7.9 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 263 | 0 | 03 Mar 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR MELAMINE POLISH (SQFT) | SQFT | 1200 | 25 | 30000 | 5400 | 35400 | 5 | 0 | 0 | 0 | 0 | 1200 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 263 | 0 | 03 Mar 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR ROLLER TEXTURE WORK | SQFT | 12500 | 18 | 225000 | 40500 | 265500 | 5 | 9485.6 | 170740.8 | 55334.96 | 362751.4 | 3014.4 | -97251.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 263 | 0 | 03 Mar 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR OIL PAINT (RFT) | RFT | 70 | 11.5 | 805 | 144.9 | 949.9 | 5 | 67.76 | 779.24 | 55334.96 | 362751.4 | 2.24 | -361801.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 263 | 0 | 03 Mar 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | PROVIDING AND APPLYING APEX ULTIMA ON OUTSIDE AREA | SQFT | 2200 | 12 | 26400 | 4752 | 31152 | 5 | 1713.6 | 20563.2 | 55334.96 | 362751.4 | 486.4 | -331599.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 264 | 0 | 03 Mar 2024 | Miran Decorators | VILLA 17 FALSE CEILING WORK | LABOR FOR WALL PUNNING (RFT) | RFT | 250 | 25 | 6250 | 1125 | 7375 | 5 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 264 | 0 | 03 Mar 2024 | Miran Decorators | VILLA 17 FALSE CEILING WORK | LABOR FOR GYPSUM CEILING (SQFT) | SQFT | 5000 | 55 | 275000 | 49500 | 324500 | 5 | 4583 | 252065 | 47266.26 | 309856.58 | 417 | 14643.42 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 264 | 0 | 03 Mar 2024 | Miran Decorators | VILLA 17 FALSE CEILING WORK | LABOR FOR GYPSUM VERTICAL (RFT) | RFT | 300 | 52 | 15600 | 2808 | 18408 | 5 | 202.41 | 10525.32 | 47266.26 | 309856.58 | 97.59 | -291448.58 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 264 | 0 | 03 Mar 2024 | Miran Decorators | VILLA 17 FALSE CEILING WORK | LABOR FOR LIGHT CUT OUT | NOS | 200 | 30 | 6000 | 1080 | 7080 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 265 | 0 | 03 Mar 2024 | CHOTURAM SUTHAR | VILLA 17 CARPENTRY WORK | LABOR FOR BALCONY RAILING (RFT) | RFT | 50 | 850 | 42500 | 0 | 42500 | 5 | 42 | 35700 | 0 | 73100 | 8 | -30600 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 10 SQMM MAINS (MTR) | RMT | 50 | 65 | 3250 | 0 | 3250 | 5 | 50 | 3250 | 0 | 107930 | 0 | -104680 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR LIGHT FITTING WORK (NOS) | NOS | 250 | 100 | 25000 | 0 | 25000 | 5 | 141 | 14100 | 0 | 107930 | 109 | -82930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR MCB POINT (NOS) | NOS | 90 | 100 | 9000 | 0 | 9000 | 5 | 63 | 6300 | 0 | 107930 | 27 | -98930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 16 AMP SOCKET POINT (NOS) | NOS | 30 | 200 | 6000 | 0 | 6000 | 5 | 7 | 1400 | 0 | 107930 | 23 | -101930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR FAN FITTING (NOS) | NOS | 15 | 100 | 1500 | 0 | 1500 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR CAT6 MAINS | RMT | 350 | 30 | 10500 | 0 | 10500 | 5 | 300 | 9000 | 0 | 107930 | 50 | -97430 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR DOOR VIDEO POINT (NOS) | NOS | 1 | 180 | 180 | 0 | 180 | 5 | 1 | 180 | 0 | 107930 | 0 | -107750 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR TELEPHONE POINT | NOS | 5 | 180 | 900 | 0 | 900 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR TV POINT | NOS | 7 | 180 | 1260 | 0 | 1260 | 5 | 7 | 1260 | 0 | 107930 | 0 | -106670 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR WIRING OF CEILING FAN POINT | POINT | 15 | 180 | 2700 | 0 | 2700 | 5 | 9 | 1620 | 0 | 107930 | 6 | -105230 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 1 SQMM WIRING (RMT) | RMT | 400 | 13 | 5200 | 0 | 5200 | 5 | 300 | 3900 | 0 | 107930 | 100 | -102730 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 1.5 SQMM WIRING (RMT) | RMT | 300 | 15 | 4500 | 0 | 4500 | 5 | 300 | 4500 | 0 | 107930 | 0 | -103430 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 2-WAY LIGHT POINT | NOS | 15 | 300 | 4500 | 0 | 4500 | 5 | 7 | 2100 | 0 | 107930 | 8 | -103430 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 4 SQMM WIRE (MTR) | RMT | 400 | 22 | 8800 | 0 | 8800 | 5 | 350 | 7700 | 0 | 107930 | 50 | -99130 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 6 AMP SOCKET POINT (NOS) | NOS | 100 | 60 | 6000 | 0 | 6000 | 5 | 70 | 4200 | 0 | 107930 | 30 | -101930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR AC POINT | NOS | 9 | 400 | 3600 | 0 | 3600 | 5 | 7 | 2800 | 0 | 107930 | 2 | -104330 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR EXHAUST FAN FITTING | NOS | 6 | 100 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 6 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR INTERNET POINT (NOS) | NOS | 1 | 180 | 180 | 0 | 180 | 5 | 1 | 180 | 0 | 107930 | 0 | -107750 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR RJ6 TV WIRING | RMT | 300 | 20 | 6000 | 0 | 6000 | 5 | 300 | 6000 | 0 | 107930 | 0 | -101930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR LIGHT POINT WIRING | NOS | 250 | 180 | 45000 | 0 | 45000 | 5 | 177 | 31860 | 0 | 107930 | 73 | -62930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR WIRING OF BELL POINT | POINT | 1 | 180 | 180 | 0 | 180 | 5 | 1 | 180 | 0 | 107930 | 0 | -107750 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 2.5 SQMM WIRE (MTR) | RMT | 700 | 18 | 12600 | 0 | 12600 | 5 | 300 | 5400 | 0 | 107930 | 400 | -95330 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 271 | 0 | 07 Mar 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR DB FITTING (NOS) | NOS | 2 | 1000 | 2000 | 0 | 2000 | 5 | 2 | 2000 | 0 | 107930 | 0 | -105930 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR ITALIAN MIRROR POLISH (SQFT) | SQFT | 1000 | 50 | 50000 | 0 | 50000 | 5 | 0 | 0 | 0 | 0 | 1000 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR ITALIAN MARBLE FLOORING (RFT) | RFT | 500 | 50 | 25000 | 0 | 25000 | 5 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR ITALIAN MARBLE FLOORING (SQFT) | SQFT | 1000 | 50 | 50000 | 0 | 50000 | 5 | 0 | 0 | 0 | 0 | 1000 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOUR FOR KOTA | SQFT | 900 | 35 | 31500 | 0 | 31500 | 5 | 0 | 0 | 0 | 0 | 900 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOUR FOR GRANITE PATTA (RFT) | RFT | 1000 | 40 | 40000 | 0 | 40000 | 5 | 0 | 0 | 0 | 0 | 1000 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOR FOR ITALIAN MIRROR POLISH (RFT) | RFT | 500 | 50 | 25000 | 0 | 25000 | 5 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 272 | 0 | 10 Mar 2024 | Jairam S. Saini | VILLA 17 FLOORING WORK | LABOUR FOR GRANITE (SQFT) | SQFT | 1500 | 40 | 60000 | 0 | 60000 | 5 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 274 | 0 | 19 Mar 2024 | B S Window Solution | VILLA 17 ALUMINUM DOOR AND WINDOW WORK | LABOUR FOR ALUMINUM WORK (SQFT) | SQFT | 1288.78 | 551.01 | 710130.67 | 127823.52 | 837954.19 | 5 | 0 | 0 | 0 | 0 | 1288.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 275 | 0 | 20 Mar 2024 | HD Infosys & Automation | VILLA 17 ELECTRICAL WORK | INSTALLATION CHARGES FOR RACK (NOS) | NOS | 1 | 500 | 500 | 90 | 590 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 275 | 0 | 20 Mar 2024 | HD Infosys & Automation | VILLA 17 ELECTRICAL WORK | CHARGES FOR NVR CONFIGURATION | NOS | 1 | 500 | 500 | 90 | 590 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 275 | 0 | 20 Mar 2024 | HD Infosys & Automation | VILLA 17 ELECTRICAL WORK | INSTALLATION CHARGES FOR CAMERA (NOS) | NOS | 5 | 300 | 1500 | 270 | 1770 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 276 | 0 | 20 Mar 2024 | AARYAN KITCHEN GALLERY | VILLA 17 CARPENTRY WORK | LABOUR FOR MODULAR KITCHEN | NOS | 1 | 500000 | 500000 | 0 | 500000 | 0 | 1 | 500000 | 0 | 500000 | 0 | 0 | Kitchen Type : MODULAR KITCHEN ELC ACRI GLASS Option ELC LUSTER MATT ACRI GLASS + HETTICH Carcass : WHITE Handles : TOP PROFILE Finish : ELC ACRI GLASS Glass : NA Profile : 4 S E B Hinges YES Skirting : MODULAR SKIRITING 4" Pelmet : NA DRAEWRS HETTICH ANTHERI BASE UNIT DESECRIPITION 1) BASE UNIT MAIN KITCHEN C TYPE (AREA (7032MM) Drawers:- Hettich Antherciate Drawers Drawers Manager:- PVC Cutlery, Thali Interl MATERAIL:- ELC ACRIGLASS WITH M.PLY 2) BASE UNIT MAIN KITCHEN L TYPE (Accessories) PVC Cutlery with 900mm /750MM THALI INTEL REHAU LEG and SKRITING, Cabinet:- M.ply with With Full Top Panel TWIN SWING CORNER UNIT (HETTICH) BLIND CONRER;- SHELF ONLY WALL CABINET WITH SHELF(MAIN KITCHEN) WALL CABINET WITH SHELF (AREA 4300*700) Cabinet:- M.ply with With Full Top Panel MATERAIL:- ELC ACRIGLASS WITH M.PLY TALL UNIT FOR BULIT IN OVEN 1) TALL UNIT WITH SHELF (600MM) Cabinet:- M.ply with With Full Top Panel 2) MATERAIL:- ELC ACRIGLASS WITH M.PLY FOR BULIT IN OVEN & MICROWAVE WALL CABINET WITH SHELF (DRY UNIT) 1) WALL CAIBNET WITH SHELF (1876*700) Cabinet:- M.ply with With Full Top Panel MATERAIL:- ELC ACRIGLASS WITH M.PLY DRY SERVICE BASE UNIT WITH SHELF 1) DRY BASE UNIT WITH SHELF (1800MM) Cabinet:- M.ply with With Full Top Panel MATERILA:- ELC AGRI GLASS DRY UNIT WALL CABINET WITH SHELF 1) DRY UNIT WALL CABINET WITH SHELF 1 NA Cabinet:- M.ply with With Full Top Panel Material:- ELC Series glass TAMBOOR UNIT WITH SHELF (600MM) 1) TAMBOOR UNIT WITH SHELF (600MM) Cabinet:- M.ply with With Full Top Panel REAHU ROLLER SHUTTER PVC 600MM |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 277 | 0 | 23 Mar 2024 | SWASTIK HOME DECOR | VILLA 17 INTERIOR WORK | CHARGES FOR CURTAIN FITTINGS | NOS | 1 | 351000 | 351000 | 0 | 351000 | 5 | 1 | 351000 | 0 | 351000 | 0 | 0 | LIVING BOOK-1555 SR-42 CURTAIN FABRIC MAIN 35.75 MTR BOOK-1831 SR-139 CURTAIN FABRIC SHEER 17.50 MTR BLACKOUT 80% CURTAIN LINING 35.75 MTR 3 PLATE 20.00 PCS M TRACK 34.00 RFT FITTING CHARGES 3.00 PCS FOYER BOOK-1774 SR-102 CURTAIN FABRIC 2.50 MTR BLACKOUT 80% CURTAIN LINING 2.50 MTR ROMAN 12.50 RQFT FITTING CHARGES 1.00 PCS DINING BOOK-1774 SR-102 CURTAIN FABRIC MAIN 16.75 MTR BOOK-1831 SR-139 CURTAIN FABRIC SHEER 14.25 MTR BLACKOUT 80% CURTAIN LINING 16.75 MTR ROMAN 11.00 SQFT I LET 10.00 PCS ROD 16.00 RFT NOB 2.00 PAIR DOUBLE BRACKET 3.00 PCS FITTING CHARGES 3.00 PCS G.F MASTERBEDROOM BOOK-1774 SR-102 CURTAIN FABRIC MAIN 19.75 MTR BOOK-1831SR-139 CURTAIN FABRIC SHEER 17.25 MTR BLACK OUT-603 CURTAIN LINING 19.75 MTR I LET 12.00 PCS ROMAN 25.50 SQFT ROD 21.00 RFT NOB 2.00 PAIR DOUBLE BRACKET 3.00 PCS FITTING CHARGES 3.00 PCS F.F BEDROOM-1 BOOK-1462 SR-123 CURTAIN FABRIC MAIN 19.00 MTR BOOK-1831SR-139 CURTAIN FABRIC SHEER 14.00 MTR BLACK OUT-603 CURTAIN LINING 19.00 MTR I LET 10.00 PCS ROMAN 37.00 SQFT ROD 15.00 R FT NOB 2.00 PAIR DOUBLE BRACKET 3.00 PCS FITTING CHARGES 3.00 PCS F.F HOME THETER BOOK-1555 SR-70 CURTAIN FABRIC MAIN 30.50 MTR BLACK OUT-603 CURTAIN LINING 30.50 MTR I LET 10.00 PCS ROMAN 24.00 SQFT ROD 17.00 R FT NOB 1.00 PAIR FITTING CHARGES 2.00 PCS F.F MASTERBEDROOM BOOK-2135 SR-518 CURTAIN FABRIC MAIN 22.00 MTR BOOK-1831SR-139 CURTAIN FABRIC SHEER 17.00 MTR BLACK OUT-603 CURTAIN LINING 22.00 MTR I LET 12.00 PCS ROMAN 45.00 SQFT ROD 21.00 R FT NOB 2.00 PAIR DOUBLE BRACKET 3.00 PCS FITTING CHARGES 4.00 PCS POOJA NI PACHAD B-1774 SR-102 /2135-SR-520 CURTAIN FABRIC 79.25 MTR BLACK OUT-603 CURTAIN LINING 79.25 MTR 3 PLATE 12.00 PCS CURTAIN MOTOR 2.00 PCS MOTORIZED TRACK 21.00 RFT REMOTE 2 CHANEL 1.00 PCS FITTING CHARGES 2.00 PCS |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 278 | 0 | 04 Apr 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR PRIMER (SQFT) | SQFT | 624 | 2.5 | 1560 | 280.8 | 1840.8 | 5 | 623.9 | 1559.75 | 59500.74 | 390060.2 | 0.1 | -388219.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 278 | 0 | 04 Apr 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR PUTTY & PRIMER (SQFT) | SQFT | 362 | 7.5 | 2715 | 488.7 | 3203.7 | 5 | 361 | 2707.5 | 59500.74 | 390060.2 | 1 | -386856.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 278 | 0 | 04 Apr 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | 2-3 COAT LAPI, 1 COAT PRIMER, 2-3 COAT ROYAL MATT (SQFT) | SQFT | 13315 | 21 | 279615 | 50330.7 | 329945.7 | 5 | 10257 | 215397 | 59500.74 | 390060.2 | 3058 | -60114.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 278 | 0 | 04 Apr 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR PRIMER (SQFT) | SQFT | 4413 | 2.5 | 11032.5 | 1985.86 | 13018.36 | 5 | 4413 | 11032.5 | 59500.74 | 390060.2 | 0 | -377041.84 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 278 | 0 | 04 Apr 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | LABOR FOR PUTTY & PRIMER (SQFT) | SQFT | 13315 | 7.5 | 99862.5 | 17975.26 | 117837.76 | 5 | 13315 | 99862.5 | 59500.74 | 390060.2 | 0 | -272222.44 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 278 | 0 | 04 Apr 2024 | Devarshi enterprise | VILLA 17 PAINT WORK | 2-3 COAT LAPI, 1 COAT PRIMER, 2-3 COAT ROYAL MATT (SQFT) | SQFT | 362 | 21 | 7602 | 1368.36 | 8970.36 | 5 | 0.01 | 0.21 | 59500.74 | 390060.2 | 361.99 | -381089.84 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 1.5 SQMM WIRING (RMT) | RMT | 300 | 15 | 4500 | 0 | 4500 | 5 | 300 | 4500 | 0 | 60895 | 0 | -56395 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 2 MODULE BOX | NOS | 17 | 45 | 765 | 0 | 765 | 5 | 17 | 765 | 0 | 60895 | 0 | -60130 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 3 MODULE BOX | NOS | 12 | 50 | 600 | 0 | 600 | 5 | 12 | 600 | 0 | 60895 | 0 | -60295 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 8 MODULE BOX | NOS | 31 | 100 | 3100 | 0 | 3100 | 5 | 31 | 3100 | 0 | 60895 | 0 | -57795 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR ROPE (RIVER) LIGHT FITTING (RMT) | RMT | 150 | 50 | 7500 | 0 | 7500 | 5 | 0 | 0 | 0 | 0 | 150 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 4 MODULE BOX | NOS | 15 | 60 | 900 | 0 | 900 | 5 | 15 | 900 | 0 | 60895 | 0 | -59995 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR 6 MODULE BOX | NOS | 22 | 85 | 1870 | 0 | 1870 | 5 | 22 | 1870 | 0 | 60895 | 0 | -59025 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOUR FOR CAT6 MAINS | RMT | 300 | 30 | 9000 | 0 | 9000 | 5 | 300 | 9000 | 0 | 60895 | 0 | -51895 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 25MM PIKA PIPE | RMT | 50 | 25 | 1250 | 0 | 1250 | 5 | 50 | 1250 | 0 | 60895 | 0 | -59645 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 9 | 100 | 900 | 0 | 900 | 5 | 9 | 900 | 0 | 60895 | 0 | -59995 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR CONDUIT PIPE 20MM (MTR) | RMT | 50 | 25 | 1250 | 0 | 1250 | 5 | 50 | 1250 | 0 | 60895 | 0 | -59645 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR CONDUIT PIPE 25MM (MTR) | RMT | 175 | 32 | 5600 | 0 | 5600 | 5 | 175 | 5600 | 0 | 60895 | 0 | -55295 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | CHARGES FOR 20MM BEND | NOS | 65 | 25 | 1625 | 0 | 1625 | 5 | 65 | 1625 | 0 | 60895 | 0 | -59270 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 15" FAN ROD | NOS | 9 | 220 | 1980 | 0 | 1980 | 5 | 9 | 1980 | 0 | 60895 | 0 | -58915 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR FAN HUKE (NOS) | NOS | 9 | 55 | 495 | 0 | 495 | 5 | 9 | 495 | 0 | 60895 | 0 | -60400 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR ZARI WORK (RFT) | RFT | 300 | 70 | 21000 | 0 | 21000 | 5 | 300 | 21000 | 0 | 60895 | 0 | -39895 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | CHARGES FOR 25MM BEND | NOS | 90 | 35 | 3150 | 0 | 3150 | 5 | 90 | 3150 | 0 | 60895 | 0 | -57745 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR 20MM PIKA PIPE | RMT | 50 | 15 | 750 | 0 | 750 | 5 | 50 | 750 | 0 | 60895 | 0 | -60145 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR FAN FASTNERS (NOS) | NOS | 9 | 120 | 1080 | 0 | 1080 | 5 | 9 | 1080 | 0 | 60895 | 0 | -59815 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 279 | 0 | 04 Apr 2024 | Ghanchi Imranbhai Gulamhusen | VILLA 17 ELECTRICAL WORK | LABOR FOR WIRING OF EXHAUST FAN POINT | POINT | 6 | 180 | 1080 | 0 | 1080 | 5 | 6 | 1080 | 0 | 60895 | 0 | -59815 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 280 | 0 | 22 Apr 2024 | HARI RADHE ENGINEERING WORKS | VILLA 17 FABRICATION WORK | LABOR FOR FABRICATION WORK (SQFT) | SQFT | 290 | 190 | 55100 | 9918 | 65018 | 5 | 289 | 54910 | 14968.8 | 98128.8 | 1 | -33110.8 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 280 | 0 | 22 Apr 2024 | HARI RADHE ENGINEERING WORKS | VILLA 17 FABRICATION WORK | LABOR FOR WATER CHANNEL FABRICATION WORK (RFT) | RFT | 20 | 90 | 1800 | 324 | 2124 | 5 | 15 | 1350 | 14968.8 | 98128.8 | 5 | -96004.8 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 281 | 0 | 23 Apr 2024 | Laxmi Steel Art | VILLA 17 S.S. RAILING AND GLASS WORK | CHARGES FOR HANDRAIL | RFT | 20 | 375 | 7500 | 1350 | 8850 | 5 | 0 | 0 | 0 | 0 | 20 | 0 | SS HAND RAIL 50 MM |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 281 | 0 | 23 Apr 2024 | Laxmi Steel Art | VILLA 17 S.S. RAILING AND GLASS WORK | CHARGES FOR GLASS RAILING WITH SS POST (RFT) |  | 20 | 2250 | 45000 | 8100 | 53100 | 5 | 0 | 0 | 0 | 0 | 20 | 0 | SS RAILLING 304 SS PIPE 50MM TOP SS BRAKET 12 MM TOUGHENED GLASS |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 282 | 0 | 23 Apr 2024 | Namo narayan Gas sales and services | VILLA 17 GAS LINE WORK | CHARGES FOR GASLINE BUSHING FIXING | NOS | 3 | 310 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 282 | 0 | 23 Apr 2024 | Namo narayan Gas sales and services | VILLA 17 GAS LINE WORK | CHARGES FOR GASLINE WORK | RFT | 30 | 380 | 11400 | 0 | 11400 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 282 | 0 | 23 Apr 2024 | Namo narayan Gas sales and services | VILLA 17 GAS LINE WORK | CHARGES FOR REGULATOR FIXING | NOS | 2 | 250 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 282 | 0 | 23 Apr 2024 | Namo narayan Gas sales and services | VILLA 17 GAS LINE WORK | CHARGES FOR RUBBER PIPE FIXING | RMT | 3 | 150 | 450 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 283 | 0 | 30 Apr 2024 | New Real Fabrication | VILLA 17 FABRICATION WORK | LABOR FOR SLOTTED ANGLE RACK 42X92X16 | NOS | 2 | 2700 | 5400 | 972 | 6372 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
ANTICA GREENWOOD | 283 | 0 | 30 Apr 2024 | New Real Fabrication | VILLA 17 FABRICATION WORK | LABOR FOR SLOTTED ANGLE RACK 45X92X16 | NOS | 1 | 3000 | 3000 | 540 | 3540 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900