## Project_Work_Order6385240433102
Project Work Order
From 13 Apr 2006 To 28 May 2024
Page 1 of 1
Total Records: 43 Records 1 To 43
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1201 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1202 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1301 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1302 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1401 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1402 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1501 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1502 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1601 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1602 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1701 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1702 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1801 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1802 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1901 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1902 Duct PLATFORM Febrication | LABOR FOR FABRICATION WORK (KG) | KG | 455 | 134 | 60970 | 10974.6 | 71944.6 | 5 | 400.79 | 53705.86 | 187293.24 | 1227810.82 | 54.21 | -1155866.22 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1201 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 55 | 6600 | 187293.24 | 1227810.82 | 0 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1202 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 55 | 6600 | 187293.24 | 1227810.82 | 0 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1301 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 55 | 6600 | 187293.24 | 1227810.82 | 0 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1302 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 54 | 6480 | 187293.24 | 1227810.82 | 1 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1401 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 20 | 120 | 2400 | 432 | 2832 | 5 | 14 | 1680 | 187293.24 | 1227810.82 | 6 | -1224978.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1402 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 20 | 120 | 2400 | 432 | 2832 | 5 | 20 | 2400 | 187293.24 | 1227810.82 | 0 | -1224978.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1501 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 20 | 120 | 2400 | 432 | 2832 | 5 | 14 | 1680 | 187293.24 | 1227810.82 | 6 | -1224978.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1502 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 20 | 120 | 2400 | 432 | 2832 | 5 | 20 | 2400 | 187293.24 | 1227810.82 | 0 | -1224978.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1601 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 20 | 120 | 2400 | 432 | 2832 | 5 | 14 | 1680 | 187293.24 | 1227810.82 | 6 | -1224978.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1602 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 20 | 120 | 2400 | 432 | 2832 | 5 | 20 | 2400 | 187293.24 | 1227810.82 | 0 | -1224978.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1701 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 49 | 5880 | 187293.24 | 1227810.82 | 6 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1702 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 49 | 5880 | 187293.24 | 1227810.82 | 6 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1801 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 49 | 5880 | 187293.24 | 1227810.82 | 6 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1802 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 49 | 5880 | 187293.24 | 1227810.82 | 6 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1901 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 49 | 5880 | 187293.24 | 1227810.82 | 6 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1902 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 55 | 120 | 6600 | 1188 | 7788 | 5 | 49 | 5880 | 187293.24 | 1227810.82 | 6 | -1220022.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1401 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 35 | 120 | 4200 | 756 | 4956 | 5 | 35 | 4200 | 187293.24 | 1227810.82 | 0 | -1222854.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1402 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 35 | 120 | 4200 | 756 | 4956 | 5 | 29 | 3480 | 187293.24 | 1227810.82 | 6 | -1222854.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1501 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 35 | 120 | 4200 | 756 | 4956 | 5 | 35 | 4200 | 187293.24 | 1227810.82 | 0 | -1222854.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1502 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 35 | 120 | 4200 | 756 | 4956 | 5 | 29 | 3480 | 187293.24 | 1227810.82 | 6 | -1222854.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1601 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 35 | 120 | 4200 | 756 | 4956 | 5 | 35 | 4200 | 187293.24 | 1227810.82 | 0 | -1222854.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | B 1602 Duct PLATFORM Febrication | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 35 | 120 | 4200 | 756 | 4956 | 5 | 29 | 3480 | 187293.24 | 1227810.82 | 6 | -1222854.82 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | TOWER B TERRACE FABRICATION WORK | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 45 | 120 | 5400 | 972 | 6372 | 5 | 45 | 5400 | 187293.24 | 1227810.82 | 0 | -1221438.82 | Monkey ladder, ODU Railing & Terrace to OHWT Stair |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | TOWER B TERRACE FABRICATION WORK | CHARGES FOR MS RAILING WORK | KG | 550 | 134 | 73700 | 13266 | 86966 | 5 | 529.73 | 70983.82 | 187293.24 | 1227810.82 | 20.27 | -1140844.82 | Monkey ladder, ODU Railing & Terrace to OHWT Stair |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 340 | 0 | 23 Aug 2023 | SARVODAYA FABRICATION WORKS | COMMON MISCELLANEOUS LIFT WORK | LABOR FOR FABRICATED LIFT DOOR REMOVING & INSTALLATION (NOS) | NOS | 2 | 4000 | 8000 | 1440 | 9440 | 5 | 2 | 8000 | 187293.24 | 1227810.82 | 0 | -1218370.82 | Agency : SARVODAYA FABRICATION WORKS Labour Name in Kanix : 1) LABOR FOR FABRICATED GATE (LS) Tower & Floor : B 18th & 19th floor Qty : Each Floor Qty as below 1) LABOR FOR FABRICATED GATE (LS) = 1 nos. Rate (Basic rate): 1) LABOR FOR FABRICATED GATE (LS) = 4000 per Nos. Unit of Measurement : Nos Purpose of Work : Passenger Lift Safety Gate at 18th and 19th Floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 362 | 0 | 02 Oct 2023 | SARVODAYA FABRICATION WORKS | TOWER B TERRACE FABRICATION WORK | LABOR FOR ANCHOR FASTNERS (NOS) | NOS | 76 | 120 | 9120 | 1641.6 | 10761.6 | 5 | 76 | 9120 | 31309.2 | 205249.2 | 0 | -194487.6 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 362 | 0 | 02 Oct 2023 | SARVODAYA FABRICATION WORKS | TOWER B TERRACE FABRICATION WORK | CHARGES FOR MS RAILING WORK | KG | 1230 | 134 | 164820 | 29667.6 | 194487.6 | 5 | 1230 | 164820 | 31309.2 | 205249.2 | 0 | -10761.6 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900