## Project_Work_Order6385267872850
Project Work Order
From 13 Apr 2006 To 31 May 2024
Page 1 of 1
Total Records: 30 Records 1 To 30
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER C 8TH FLOOR CIVIL EXTRA WORK | LABOR FOR COLUMN CASTING & DEBRISH CLEANING | NOS | 1 | 15750 | 15750 | 2835 | 18585 | 5 | 1 | 15750 | 96307.62 | 631349.92 | 0 | -612764.92 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER C 8TH FLOOR CIVIL EXTRA WORK | LABOR FOR SHUTTERING WORK (LS) | LUMSUM | 1 | 75000 | 75000 | 13500 | 88500 | 5 | 1 | 75000 | 96307.62 | 631349.92 | 0 | -542849.92 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER C 8TH FLOOR CIVIL EXTRA WORK | LABOR FOR STEEL BINDING & REPAIRNING WORK | NOS | 1 | 18000 | 18000 | 3240 | 21240 | 5 | 1 | 18000 | 96307.62 | 631349.92 | 0 | -610109.92 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT CIVIL EXTRA WORK CIVIL EXTRA WORK | LABOR FOR RCC WALL RECASTING (LS) | LUMSUM | 1 | 6000 | 6000 | 1080 | 7080 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT CIVIL EXTRA WORK CIVIL EXTRA WORK | LABOR FOR SHUTTERING WORK (LS) | LUMSUM | 1 | 25000 | 25000 | 4500 | 29500 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT CIVIL EXTRA WORK CIVIL EXTRA WORK | LABOR FOR STEEL BINDING & REPAIRNING WORK | NOS | 1 | 6000 | 6000 | 1080 | 7080 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT EXTRA CIVIL WORK | LABOR FOR R.C.C PARDI (STEEL BINDING + SHUTTERING + CASTING) | SQFT | 487.5 | 110 | 53625 | 9652.5 | 63277.5 | 5 | 487.5 | 53625 | 96307.62 | 631349.92 | 0 | -568072.42 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT EXTRA CIVIL WORK | LABOR FOR SLAB(STEEL BINDING + SHUTTERING + CASTING) | SQFT | 125.75 | 110 | 13832.5 | 2489.86 | 16322.36 | 5 | 125.75 | 13832.5 | 96307.62 | 631349.92 | 0 | -615027.56 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT EXTRA CIVIL WORK | LABORFOR FOOTING BASE RAFT(STEEL BINDING+SHUTTERING+CASTING) | SQFT | 220.75 | 125 | 27593.75 | 4966.88 | 32560.63 | 5 | 220.75 | 27593.75 | 96307.62 | 631349.92 | 0 | -598789.29 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | COMMON CIVIL EXTRA WORK | LABOR FOR RCC & PLASTER | LTR | 385544.61 | 4.5 | 1734950.75 | 312291.14 | 2047241.89 | 5 | 0 | 0 | 0 | 0 | 385544.61 | 0 | 1) STP TANK (R.C.C AND PLASTER):349584.61LIT 2) RAINWATER TANK (R.C.C AND PLASTER):35960 LIT |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | COMMON CIVIL EXTRA WORK | LABOR FOR RETAINING WALL (SQFT) | SQFT | 3875.48 | 140 | 542567.2 | 97662.1 | 640229.3 | 5 | 0 | 0 | 0 | 0 | 3875.48 | 0 | R.C.C.COMMON RETAINING WALL EXTRA DEPTH: 3875.48 SQ FT |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | COMMON CIVIL EXTRA WORK | LABOR FOR RETAINING WALL (SQFT) | SQFT | 200 | 140 | 28000 | 5040 | 33040 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 2ND FLOOR CIVIL EXTRA WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 290 | 18 | 5220 | 939.6 | 6159.6 | 5 | 285 | 5130 | 96307.62 | 631349.92 | 5 | -625190.32 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 3RD FLOOR CIVIL EXTRA WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 290 | 18 | 5220 | 939.6 | 6159.6 | 5 | 285 | 5130 | 96307.62 | 631349.92 | 5 | -625190.32 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 4TH FLOOR CIVIL EXTRA WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 290 | 18 | 5220 | 939.6 | 6159.6 | 5 | 285 | 5130 | 96307.62 | 631349.92 | 5 | -625190.32 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 5TH FLOOR CIVIL EXTRA WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 290 | 18 | 5220 | 939.6 | 6159.6 | 5 | 285 | 5130 | 96307.62 | 631349.92 | 5 | -625190.32 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT EXTRA CIVIL WORK | LABOR FOR DRESSING & PCC WORK (SQFT) | SQFT | 331.25 | 10 | 3312.5 | 596.26 | 3908.76 | 5 | 331.25 | 3312.5 | 96307.62 | 631349.92 | 0 | -627441.16 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT EXTRA CIVIL WORK | LABOR FOR METAL SOILING | SQFT | 331.25 | 10 | 3312.5 | 596.26 | 3908.76 | 5 | 331.25 | 3312.5 | 96307.62 | 631349.92 | 0 | -627441.16 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER C 1ST FLOOR EXTRA CIVIL WOK MASONRY WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 365 | 20 | 7300 | 1314 | 8614 | 5 | 234.08 | 4681.6 | 96307.62 | 631349.92 | 130.92 | -622735.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER C 2ND FLOOR EXTRA CIVIL WOK MASONRY WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 365 | 20 | 7300 | 1314 | 8614 | 5 | 234.08 | 4681.6 | 96307.62 | 631349.92 | 130.92 | -622735.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER C 3RD FLOOR EXTRA CIVIL WOK MASONRY WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 365 | 20 | 7300 | 1314 | 8614 | 5 | 234.08 | 4681.6 | 96307.62 | 631349.92 | 130.92 | -622735.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | SITE OFFICE CIVIL WORK | LABOR FOR 9" MASONRY WORK (SQFT) | SQFT | 1600 | 25 | 40000 | 7200 | 47200 | 5 | 1579.25 | 39481.25 | 96307.62 | 631349.92 | 20.75 | -584149.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | SITE OFFICE CIVIL WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7420 | 18 | 133560 | 24040.8 | 157600.8 | 5 | 7230 | 130140 | 96307.62 | 631349.92 | 190 | -473749.12 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 1ST FLOOR CIVIL EXTRA WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 290 | 18 | 5220 | 939.6 | 6159.6 | 5 | 285 | 5130 | 96307.62 | 631349.92 | 5 | -625190.32 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | SITE OFFICE CIVIL WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 2300 | 20 | 46000 | 8280 | 54280 | 5 | 2265 | 45300 | 96307.62 | 631349.92 | 35 | -577069.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 1ST FLOOR CIVIL EXTRA WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 700 | 20 | 14000 | 2520 | 16520 | 5 | 700 | 14000 | 96307.62 | 631349.92 | 0 | -614829.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 2ND FLOOR CIVIL EXTRA WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 700 | 20 | 14000 | 2520 | 16520 | 5 | 700 | 14000 | 96307.62 | 631349.92 | 0 | -614829.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 3RD FLOOR CIVIL EXTRA WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 700 | 20 | 14000 | 2520 | 16520 | 5 | 700 | 14000 | 96307.62 | 631349.92 | 0 | -614829.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 4TH FLOOR CIVIL EXTRA WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 700 | 20 | 14000 | 2520 | 16520 | 5 | 700 | 14000 | 96307.62 | 631349.92 | 0 | -614829.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 74 | 0 | 27 Apr 2023 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER D 5TH FLOOR CIVIL EXTRA WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 700 | 20 | 14000 | 2520 | 16520 | 5 | 700 | 14000 | 96307.62 | 631349.92 | 0 | -614829.92 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900