## Project_Work_Order6385275462426
Project Work Order
From 22 May 2008 To 01 Jun 2024
Page 1 of 1
Total Records: 199 Records 1 To 199
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 5829.18 | 5.25 | 30603.2 | 5508.58 | 36111.78 | 5 | 0 | 0 | 0 | 0 | 5829.18 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 24077.712 | 10.5 | 252815.98 | 45506.88 | 298322.86 | 5 | 0 | 0 | 0 | 0 | 24077.712 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 24077.712 | 24.5 | 589903.94 | 106182.7 | 696086.64 | 5 | 0 | 0 | 0 | 0 | 24077.712 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 2129.644 | 5.25 | 11180.63 | 2012.52 | 13193.15 | 5 | 0 | 0 | 0 | 0 | 2129.644 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 0 | 19.25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | deepak.p | Pur.nrpl3 |  | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 11624.78 | 19.25 | 223777.02 | 40279.86 | 264056.88 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 9775.012 | 19.25 | 188168.98 | 33870.42 | 222039.4 | 5 | 0 | 0 | 0 | 0 | 9775.012 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 0 | 5.25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | deepak.p | Pur.nrpl3 |  | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 5795.6 | 5.25 | 30426.9 | 5476.84 | 35903.74 | 5 | 0 | 0 | 0 | 0 | 5795.6 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 7645.368 | 5.25 | 40138.18 | 7224.88 | 47363.06 | 5 | 0 | 0 | 0 | 0 | 7645.368 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 11624.78 | 5.25 | 61030.1 | 10985.42 | 72015.52 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 9775.012 | 5.25 | 51318.81 | 9237.38 | 60556.19 | 5 | 0 | 0 | 0 | 0 | 9775.012 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 18TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 11624.78 | 5.25 | 61030.1 | 10985.42 | 72015.52 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9775.012 | 5.25 | 51318.81 | 9237.38 | 60556.19 | 5 | 0 | 0 | 0 | 0 | 9775.012 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 18TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 552.26 | 28.5 | 15739.41 | 2833.1 | 18572.51 | 5 | 0 | 0 | 0 | 0 | 552.26 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 1064.822 | 28.5 | 30347.43 | 5462.54 | 35809.97 | 5 | 190.81 | 5438.09 | 9828014.58 | 64428093.6 | 874.012 | -64392283.64 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 552.26 | 28.5 | 15739.41 | 2833.1 | 18572.51 | 5 | 0 | 0 | 0 | 0 | 552.26 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 552.26 | 104.5 | 57711.17 | 10388.02 | 68099.19 | 5 | 552.26 | 57711.17 | 9828014.58 | 64428093.6 | 0 | -64359994.41 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 1064.822 | 104.5 | 111273.9 | 20029.3 | 131303.2 | 5 | 664.81 | 69472.65 | 9828014.58 | 64428093.6 | 400.012 | -64296790.4 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 24077.712 | 133 | 3202335.7 | 576420.42 | 3778756.12 | 5 | 24077.2 | 3202267.6 | 9828014.58 | 64428093.6 | 0.512 | -60649337.49 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 11072.52 | 104.5 | 1157078.34 | 208274.1 | 1365352.44 | 5 | 11072.52 | 1157078.34 | 9828014.58 | 64428093.6 | 0 | -63062741.16 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 24077.712 | 57 | 1372429.58 | 247037.32 | 1619466.9 | 5 | 0 | 0 | 0 | 0 | 24077.712 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 1064.822 | 28.5 | 30347.43 | 5462.54 | 35809.97 | 5 | 0 | 0 | 0 | 0 | 1064.822 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 552.26 | 28.5 | 15739.41 | 2833.1 | 18572.51 | 5 | 0 | 0 | 0 | 0 | 552.26 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 1064.822 | 28.5 | 30347.43 | 5462.54 | 35809.97 | 5 | 0 | 0 | 0 | 0 | 1064.822 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710.19 | 910214.86 | 9828014.58 | 64428093.6 | 0 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 8710 | 248235 | 9828014.58 | 64428093.6 | 0.19 | -64135169.91 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 8710.19 | 248240.42 | 9828014.58 | 64428093.6 | 0 | -64135169.91 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 11072.52 | 28.5 | 315566.82 | 56802.02 | 372368.84 | 5 | 0 | 0 | 0 | 0 | 11072.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 11072.52 | 28.5 | 315566.82 | 56802.02 | 372368.84 | 5 | 0 | 0 | 0 | 0 | 11072.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 15TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B GROUND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 11072.52 | 28.5 | 315566.82 | 56802.02 | 372368.84 | 5 | 0 | 0 | 0 | 0 | 11072.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 10TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 11TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 12TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 13TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 14TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 5TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 6TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 7TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 8TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 9TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 0 | 28.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 16TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 17TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 7031.26 | 200390.91 | 9828014.58 | 64428093.6 | 1678.93 | -64135169.91 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 2ND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 3RD FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER B 4TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900