## Project_Work_Order6385292776695
Project Work Order
From 09 May 2007 To 03 Jun 2024
Page 1 of 1
Total Records: 196 Records 1 To 196
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 0 | 19.25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | deepak.p | Pur.nrpl3 |  | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 11624.78 | 19.25 | 223777.02 | 40279.86 | 264056.88 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 32633.1821 | 24.5 | 799512.96 | 143912.34 | 943425.3 | 5 | 0 | 0 | 0 | 0 | 32633.1821 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 32633.1821 | 10.5 | 342648.41 | 61676.72 | 404325.13 | 5 | 0 | 0 | 0 | 0 | 32633.1821 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 8710 | 167667.5 | 9828014.58 | 64428093.6 | 0.19 | -64230241.65 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 11624.78 | 5.25 | 61030.1 | 10985.42 | 72015.52 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8901.384 | 19.25 | 171351.64 | 30843.3 | 202194.94 | 5 | 0 | 0 | 0 | 0 | 8901.384 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 19.25 | 167671.16 | 30180.8 | 197851.96 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 0 | 5.25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | deepak.p | Pur.nrpl3 |  | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8901.384 | 5.25 | 46732.27 | 8411.8 | 55144.07 | 5 | 0 | 0 | 0 | 0 | 8901.384 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 11624.78 | 5.25 | 61030.1 | 10985.42 | 72015.52 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8901.384 | 5.25 | 46732.27 | 8411.8 | 55144.07 | 5 | 0 | 0 | 0 | 0 | 8901.384 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 11624.78 | 5.25 | 61030.1 | 10985.42 | 72015.52 | 5 | 0 | 0 | 0 | 0 | 11624.78 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8901.384 | 5.25 | 46732.27 | 8411.8 | 55144.07 | 5 | 0 | 0 | 0 | 0 | 8901.384 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 5.25 | 45728.5 | 8231.14 | 53959.64 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 18TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 18TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR ZARI WORK (NOS) | NOS | 1 | 1600 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 191.194 | 28.5 | 5449.03 | 980.82 | 6429.85 | 5 | 190.81 | 5438.09 | 9828014.58 | 64428093.6 | 0.384 | -64421663.75 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 552.26 | 28.5 | 15739.41 | 2833.1 | 18572.51 | 5 | 0 | 0 | 0 | 0 | 552.26 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 191.194 | 104.5 | 19979.77 | 3596.36 | 23576.13 | 5 | 190.81 | 19939.65 | 9828014.58 | 64428093.6 | 0.384 | -64404517.47 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 552.26 | 104.5 | 57711.17 | 10388.02 | 68099.19 | 5 | 552.26 | 57711.17 | 9828014.58 | 64428093.6 | 0 | -64359994.41 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR RCC WORK FOR SLAB | LABOR FOR SLEEVE INSERT | NOS | 1 | 4000 | 4000 | 720 | 4720 | 5 | 1 | 4000 | 9828014.58 | 64428093.6 | 0 | -64423373.6 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 32633.1779 | 133 | 4340212.66 | 781238.28 | 5121450.94 | 5 | 30928 | 4113424 | 9828014.58 | 64428093.6 | 1705.1779 | -59306642.66 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 11072.52 | 104.5 | 1157078.34 | 208274.1 | 1365352.44 | 5 | 11072.5 | 1157076.25 | 9828014.58 | 64428093.6 | 0.02 | -63062741.16 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 191.194 | 28.5 | 5449.03 | 980.82 | 6429.85 | 5 | 0 | 0 | 0 | 0 | 191.194 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 552.26 | 28.5 | 15739.41 | 2833.1 | 18572.51 | 5 | 0 | 0 | 0 | 0 | 552.26 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 191.194 | 28.5 | 5449.03 | 980.82 | 6429.85 | 5 | 0 | 0 | 0 | 0 | 191.194 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 552.26 | 28.5 | 15739.41 | 2833.1 | 18572.51 | 5 | 0 | 0 | 0 | 0 | 552.26 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710.19 | 910214.86 | 9828014.58 | 64428093.6 | 0 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 8710 | 910195 | 9828014.58 | 64428093.6 | 0.19 | -63354040.07 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 11072.52 | 28.5 | 315566.82 | 56802.02 | 372368.84 | 5 | 0 | 0 | 0 | 0 | 11072.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 8710.19 | 104.5 | 910214.86 | 163838.68 | 1074053.54 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 8710.19 | 248240.42 | 9828014.58 | 64428093.6 | 0 | -64135169.91 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 11072.52 | 28.5 | 315566.82 | 56802.02 | 372368.84 | 5 | 0 | 0 | 0 | 0 | 11072.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR MASONRY WORK | LABOR FOR MASONRY WORK (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 15TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A GROUND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 11072.52 | 28.5 | 315566.82 | 56802.02 | 372368.84 | 5 | 0 | 0 | 0 | 0 | 11072.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 10TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 11TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 12TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 13TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 14TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 5TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 6TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 7TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 8TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 9TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A BASEMENT PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 32633.1779 | 57 | 1860091.14 | 334816.4 | 2194907.54 | 5 | 0 | 0 | 0 | 0 | 32633.1779 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 16TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 17TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 2ND FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 3RD FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS AARANYA | 10 | 0 | 25 May 2021 | SHREYPATH INFRASTRUCTURE PVT LTD | TOWER A 4TH FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 8710.19 | 28.5 | 248240.42 | 44683.28 | 292923.7 | 5 | 0 | 0 | 0 | 0 | 8710.19 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900