## Project_Work_Order6385309380925
Project Work Order
From 05 May 2005 To 05 Jun 2024
Page 1 of 1
Total Records: 11 Records 1 To 11
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER A 5TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 229.22 | 72 | 16503.84 | 2970.7 | 19474.54 | 5 | 229.22 | 16503.84 | 56135.98 | 368002.3 | 0 | -348527.76 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER A 6TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 125.54 | 96 | 12051.84 | 2169.34 | 14221.18 | 5 | 125.54 | 12051.84 | 56135.98 | 368002.3 | 0 | -353781.12 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER A 7TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 125.6 | 120 | 15072 | 2712.96 | 17784.96 | 5 | 125.6 | 15072 | 56135.98 | 368002.3 | 0 | -350217.34 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER A 8TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 125.57 | 144 | 18082.08 | 3254.78 | 21336.86 | 5 | 125.57 | 18082.08 | 56135.98 | 368002.3 | 0 | -346665.44 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER B 5TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 602.47 | 72 | 43377.84 | 7808.02 | 51185.86 | 5 | 602.47 | 43377.84 | 56135.98 | 368002.3 | 0 | -316816.44 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER B 6TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 468.1 | 96 | 44937.6 | 8088.76 | 53026.36 | 5 | 468.1 | 44937.6 | 56135.98 | 368002.3 | 0 | -314975.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER B 7TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 507.46 | 120 | 60895.2 | 10961.14 | 71856.34 | 5 | 507.46 | 60895.2 | 56135.98 | 368002.3 | 0 | -296145.96 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER C 5TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 167.22 | 72 | 12039.84 | 2167.18 | 14207.02 | 5 | 167.22 | 12039.84 | 56135.98 | 368002.3 | 0 | -353795.28 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER C 6TH FLOOR DRY WALL WORK | LEAD CHARGES (SQMT) | SQMT | 146.78 | 96 | 14090.88 | 2536.36 | 16627.24 | 5 | 146.78 | 14090.88 | 56135.98 | 368002.3 | 0 | -351375.06 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER B 8TH FLOOR MASONRY WORK REBARING WORK | LEAD CHARGES (SQMT) | SQMT | 262.3 | 144 | 37771.2 | 6798.82 | 44570.02 | 5 | 262.3 | 37771.2 | 56135.98 | 368002.3 | 0 | -323432.28 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 308 | 0 | 13 Jan 2024 | Smart- Gyptech, | TOWER B 9TH FLOOR MASONRY WORK REBARING WORK | LEAD CHARGES (SQMT) | SQMT | 220.5 | 168 | 37044 | 6667.92 | 43711.92 | 5 | 220.5 | 37044 | 56135.98 | 368002.3 | 0 | -324290.38 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900