## Project_Work_Order6385309386832
Project Work Order
From 05 May 2005 To 05 Jun 2024
Page 1 of 1
Total Records: 124 Records 1 To 124
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 12TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 4.67 | 2218.25 | 403476.16 | 2645009.71 | 4.73 | -2639741.01 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 13TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.75 | 475 | 4156.25 | 748.12 | 4904.37 | 10 | 4.67 | 2218.25 | 403476.16 | 2645009.71 | 4.08 | -2640105.34 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 1ST FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 21.84 | 475 | 10374 | 1867.32 | 12241.32 | 10 | 16.588 | 7879.3 | 403476.16 | 2645009.71 | 5.252 | -2632768.39 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 2ND FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 21.89 | 475 | 10397.75 | 1871.6 | 12269.35 | 10 | 0 | 0 | 0 | 0 | 21.89 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 11TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 12TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 13TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 812.96 | 475 | 386156 | 69508.08 | 455664.08 | 10 | 0 | 0 | 0 | 0 | 812.96 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 1ST FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 821.38 | 475 | 390155.5 | 70228 | 460383.5 | 10 | 133.61 | 63464.75 | 403476.16 | 2645009.71 | 687.77 | -2184626.21 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 2ND FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 722.02 | 475 | 342959.5 | 61732.72 | 404692.22 | 10 | 0 | 0 | 0 | 0 | 722.02 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 3RD FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 181.51 | 475 | 86217.25 | 15519.1 | 101736.35 | 10 | 0 | 0 | 0 | 0 | 181.51 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 5TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 275.292 | 130763.7 | 403476.16 | 2645009.71 | 49.468 | -2462981.73 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 6TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 274.95 | 475 | 130601.25 | 23508.22 | 154109.47 | 10 | 259.558 | 123290.05 | 403476.16 | 2645009.71 | 15.392 | -2490900.24 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 7TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 275.569 | 130895.28 | 403476.16 | 2645009.71 | 49.191 | -2462981.73 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 8TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 266.672 | 126669.2 | 403476.16 | 2645009.71 | 58.088 | -2462981.73 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 9TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 35.5 | 16862.5 | 403476.16 | 2645009.71 | 289.26 | -2462981.73 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 10TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 170.54 | 475 | 81006.5 | 14581.18 | 95587.68 | 10 | 0 | 0 | 0 | 0 | 170.54 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 12TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 70.81 | 33634.75 | 403476.16 | 2645009.71 | 253.95 | -2462981.73 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 13TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 302.5 | 475 | 143687.5 | 25863.76 | 169551.26 | 10 | 70.81 | 33634.75 | 403476.16 | 2645009.71 | 231.69 | -2475458.45 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 1ST FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 754.83 | 475 | 358544.25 | 64537.96 | 423082.21 | 10 | 372.47 | 176923.25 | 403476.16 | 2645009.71 | 382.36 | -2221927.5 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 2ND FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 756.6 | 475 | 359385 | 64689.3 | 424074.3 | 10 | 0 | 0 | 0 | 0 | 756.6 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 3RD FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 147.9 | 475 | 70252.5 | 12645.46 | 82897.96 | 10 | 0 | 0 | 0 | 0 | 147.9 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 4TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 0 | 0 | 0 | 0 | 324.76 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 10TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 63.52 | 475 | 30172 | 5430.96 | 35602.96 | 10 | 0 | 0 | 0 | 0 | 63.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 11TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 475 | 138277.25 | 24889.9 | 163167.15 | 10 | 142.16 | 67526 | 403476.16 | 2645009.71 | 148.95 | -2481842.56 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 12TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 475 | 138277.25 | 24889.9 | 163167.15 | 10 | 142.16 | 67526 | 403476.16 | 2645009.71 | 148.95 | -2481842.56 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 13TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 322.9 | 475 | 153377.5 | 27607.96 | 180985.46 | 10 | 37.06 | 17603.5 | 403476.16 | 2645009.71 | 285.84 | -2464024.25 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 10TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 63.52 | 475 | 30172 | 5430.96 | 35602.96 | 10 | 0 | 0 | 0 | 0 | 63.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 11TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 324.76 | 475 | 154261 | 27766.98 | 182027.98 | 10 | 70.81 | 33634.75 | 403476.16 | 2645009.71 | 253.95 | -2462981.73 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 4TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 5TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 447.09 | 212367.75 | 403476.16 | 2645009.71 | 434.76 | -2150732.78 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 6TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 772.31 | 475 | 366847.25 | 66032.5 | 432879.75 | 10 | 270.77 | 128615.75 | 403476.16 | 2645009.71 | 501.54 | -2212129.96 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 7TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 277.22 | 131679.5 | 403476.16 | 2645009.71 | 604.63 | -2150732.78 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 8TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 9TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 475 | 418878.75 | 75398.18 | 494276.93 | 10 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 5TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 38.89 | 475 | 18472.75 | 3325.1 | 21797.85 | 5 | 0 | 0 | 0 | 0 | 38.89 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 6TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 34.65 | 475 | 16458.75 | 2962.58 | 19421.33 | 5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 10TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 266.48 | 475 | 126578 | 22784.04 | 149362.04 | 5 | 0 | 0 | 0 | 0 | 266.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 13TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 7.1 | 475 | 3372.5 | 607.06 | 3979.56 | 5 | 0 | 0 | 0 | 0 | 7.1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 11TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 0 | 0 | 0 | 0 | 5.24 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 12TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 0 | 0 | 0 | 0 | 5.24 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 13TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 27.5 | 475 | 13062.5 | 2351.26 | 15413.76 | 5 | 0 | 0 | 0 | 0 | 27.5 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 4TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 821.38 | 475 | 390155.5 | 70228 | 460383.5 | 5 | 0 | 0 | 0 | 0 | 821.38 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 6TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 77.69 | 475 | 36902.75 | 6642.5 | 43545.25 | 5 | 0 | 0 | 0 | 0 | 77.69 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 13TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 37.04 | 475 | 17594 | 3166.92 | 20760.92 | 5 | 0 | 0 | 0 | 0 | 37.04 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 5TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 0 | 0 | 0 | 0 | 5.24 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 6TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 55.05 | 475 | 26148.75 | 4706.78 | 30855.53 | 5 | 0 | 0 | 0 | 0 | 55.05 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 7TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 0 | 0 | 0 | 0 | 5.24 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 8TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 0 | 0 | 0 | 0 | 5.24 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 9TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 1.125 | 534.38 | 403476.16 | 2645009.71 | 4.115 | -2642072.69 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 10TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 266.48 | 475 | 126578 | 22784.04 | 149362.04 | 5 | 0 | 0 | 0 | 0 | 266.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 9TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.58 | 475 | 3125.5 | 562.6 | 3688.1 | 5 | 0 | 0 | 0 | 0 | 6.58 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 10TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 13.76 | 475 | 6536 | 1176.48 | 7712.48 | 5 | 0 | 0 | 0 | 0 | 13.76 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 11TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.58 | 475 | 3125.5 | 562.6 | 3688.1 | 5 | 0 | 0 | 0 | 0 | 6.58 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 12TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.58 | 475 | 3125.5 | 562.6 | 3688.1 | 5 | 0 | 0 | 0 | 0 | 6.58 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 13TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.66 | 475 | 3163.5 | 569.44 | 3732.94 | 5 | 0 | 0 | 0 | 0 | 6.66 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 4TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 5.24 | 475 | 2489 | 448.02 | 2937.02 | 5 | 0 | 0 | 0 | 0 | 5.24 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 13TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 16.48 | 475 | 7828 | 1409.04 | 9237.04 | 5 | 0 | 0 | 0 | 0 | 16.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 4TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.29 | 475 | 2987.75 | 537.8 | 3525.55 | 5 | 0 | 0 | 0 | 0 | 6.29 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 5TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.58 | 475 | 3125.5 | 562.6 | 3688.1 | 5 | 0 | 0 | 0 | 0 | 6.58 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 6TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 7.45 | 475 | 3538.75 | 636.98 | 4175.73 | 5 | 0 | 0 | 0 | 0 | 7.45 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 7TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.58 | 475 | 3125.5 | 562.6 | 3688.1 | 5 | 2.189 | 1039.78 | 403476.16 | 2645009.71 | 4.391 | -2641321.61 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 8TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.58 | 475 | 3125.5 | 562.6 | 3688.1 | 5 | 0 | 0 | 0 | 0 | 6.58 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 6TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 17.65 | 475 | 8383.75 | 1509.08 | 9892.83 | 5 | 0 | 0 | 0 | 0 | 17.65 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 7TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 0 | 0 | 0 | 0 | 14.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 8TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 0 | 0 | 0 | 0 | 14.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 9TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 0 | 0 | 0 | 0 | 14.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 11TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 0 | 0 | 0 | 0 | 14.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 12TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 0 | 0 | 0 | 0 | 14.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 9TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 0 | 0 | 0 | 0 | 6.6 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 10TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 13.76 | 475 | 6536 | 1176.48 | 7712.48 | 5 | 0 | 0 | 0 | 0 | 13.76 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 11TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 0 | 0 | 0 | 0 | 6.6 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 12TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 0 | 0 | 0 | 0 | 6.6 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 13TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 7.25 | 475 | 3443.75 | 619.88 | 4063.63 | 5 | 0 | 0 | 0 | 0 | 7.25 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 4TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 0 | 0 | 0 | 0 | 14.48 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 5TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 14.48 | 475 | 6878 | 1238.04 | 8116.04 | 5 | 4.18 | 1985.5 | 403476.16 | 2645009.71 | 10.3 | -2636893.67 | HAVE DONE WORK DUE TO CHANGES IN OFFICE. INSTEAD OF BLOCK MASONRY WORK. |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 4TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 0 | 0 | 0 | 0 | 6.6 | 0 | AS PER ATTACHED SHEET. |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 5TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 0 | 0 | 0 | 0 | 6.6 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 6TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.04 | 475 | 3819 | 687.42 | 4506.42 | 5 | 0 | 0 | 0 | 0 | 8.04 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 7TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 0 | 0 | 0 | 0 | 6.6 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 8TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.6 | 475 | 3135 | 564.3 | 3699.3 | 5 | 3.75 | 1781.25 | 403476.16 | 2645009.71 | 2.85 | -2641310.41 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 5TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 475 | 138277.25 | 24889.9 | 163167.15 | 10 | 175.79 | 83500.25 | 403476.16 | 2645009.71 | 115.32 | -2481842.56 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 6TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 295.35 | 475 | 140291.25 | 25252.42 | 165543.67 | 10 | 235.37 | 111800.75 | 403476.16 | 2645009.71 | 59.98 | -2479466.04 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 7TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 475 | 138277.25 | 24889.9 | 163167.15 | 10 | 291.11 | 138277.25 | 403476.16 | 2645009.71 | 0 | -2481842.56 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 8TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 475 | 138277.25 | 24889.9 | 163167.15 | 10 | 0 | 0 | 0 | 0 | 291.11 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 9TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 475 | 138277.25 | 24889.9 | 163167.15 | 10 | 139.61 | 66314.75 | 403476.16 | 2645009.71 | 151.5 | -2481842.56 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 1ST FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 712.75 | 475 | 338556.25 | 60940.12 | 399496.37 | 10 | 268.804 | 127681.9 | 403476.16 | 2645009.71 | 443.946 | -2245513.34 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 7TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.42 | 475 | 3999.5 | 719.92 | 4719.42 | 10 | 8.16 | 3876 | 403476.16 | 2645009.71 | 0.26 | -2640290.29 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 8TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.42 | 475 | 3999.5 | 719.92 | 4719.42 | 10 | 0 | 0 | 0 | 0 | 8.42 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 9TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.42 | 475 | 3999.5 | 719.92 | 4719.42 | 10 | 6.702 | 3183.45 | 403476.16 | 2645009.71 | 1.718 | -2640290.29 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 2ND FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 726 | 475 | 344850 | 62073 | 406923 | 10 | 246.225 | 116956.88 | 403476.16 | 2645009.71 | 479.775 | -2238086.71 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 3RD FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 189.57 | 475 | 90045.75 | 16208.24 | 106253.99 | 10 | 0 | 0 | 0 | 0 | 189.57 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 4TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 335.62 | 475 | 159419.5 | 28695.52 | 188115.02 | 10 | 0 | 0 | 0 | 0 | 335.62 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 1ST FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 20.63 | 475 | 9799.25 | 1763.86 | 11563.11 | 10 | 9.44 | 4484 | 403476.16 | 2645009.71 | 11.19 | -2633446.6 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 2ND FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 21.01 | 475 | 9979.75 | 1796.36 | 11776.11 | 10 | 21.01 | 9979.75 | 403476.16 | 2645009.71 | 0 | -2633233.6 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 3RD FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 4.32 | 475 | 2052 | 369.36 | 2421.36 | 10 | 0 | 0 | 0 | 0 | 4.32 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 4TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.71 | 475 | 4612.25 | 830.2 | 5442.45 | 10 | 0 | 0 | 0 | 0 | 9.71 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 5TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.42 | 475 | 3999.5 | 719.92 | 4719.42 | 10 | 8.42 | 3999.5 | 403476.16 | 2645009.71 | 0 | -2640290.29 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 6TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.55 | 475 | 4061.25 | 731.02 | 4792.27 | 10 | 8.55 | 4061.25 | 403476.16 | 2645009.71 | 0 | -2640217.44 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 8TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 0 | 0 | 0 | 0 | 25.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 9TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 0 | 0 | 0 | 0 | 25.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 10TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 2.24 | 475 | 1064 | 191.52 | 1255.52 | 10 | 0 | 0 | 0 | 0 | 2.24 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 11TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.42 | 475 | 3999.5 | 719.92 | 4719.42 | 10 | 6.77 | 3215.75 | 403476.16 | 2645009.71 | 1.65 | -2640290.29 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 12TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 8.42 | 475 | 3999.5 | 719.92 | 4719.42 | 10 | 6.77 | 3215.75 | 403476.16 | 2645009.71 | 1.65 | -2640290.29 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER C 13TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.34 | 475 | 4436.5 | 798.58 | 5235.08 | 10 | 3.53 | 1676.75 | 403476.16 | 2645009.71 | 5.81 | -2639774.63 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 2ND FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 20.89 | 475 | 9922.75 | 1786.1 | 11708.85 | 10 | 0 | 0 | 0 | 0 | 20.89 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 3RD FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 4.14 | 475 | 1966.5 | 353.98 | 2320.48 | 10 | 0 | 0 | 0 | 0 | 4.14 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 4TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 0 | 0 | 0 | 0 | 25.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 5TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 25.52 | 12122 | 403476.16 | 2645009.71 | 0 | -2630705.75 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 6TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 22.35 | 475 | 10616.25 | 1910.92 | 12527.17 | 10 | 20.75 | 9856.25 | 403476.16 | 2645009.71 | 1.6 | -2632482.54 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 7TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 20.985 | 9967.88 | 403476.16 | 2645009.71 | 4.535 | -2630705.75 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 9TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 0 | 0 | 0 | 0 | 9.4 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 10TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 6.01 | 475 | 2854.75 | 513.86 | 3368.61 | 10 | 0 | 0 | 0 | 0 | 6.01 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 11TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 0 | 0 | 0 | 0 | 25.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 12TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 25.52 | 475 | 12122 | 2181.96 | 14303.96 | 10 | 0 | 0 | 0 | 0 | 25.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 13TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 23.52 | 475 | 11172 | 2010.96 | 13182.96 | 10 | 0 | 0 | 0 | 0 | 23.52 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER B 1ST FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 23.77 | 475 | 11290.75 | 2032.34 | 13323.09 | 10 | 4.332 | 2057.7 | 403476.16 | 2645009.71 | 19.438 | -2631686.62 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 3RD FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 3.37 | 475 | 1600.75 | 288.14 | 1888.89 | 10 | 0 | 0 | 0 | 0 | 3.37 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 4TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 0 | 0 | 0 | 0 | 9.4 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 5TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 4.119 | 1956.53 | 403476.16 | 2645009.71 | 5.281 | -2639741.01 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 6TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 7.96 | 475 | 3781 | 680.58 | 4461.58 | 10 | 4.22 | 2004.5 | 403476.16 | 2645009.71 | 3.74 | -2640548.13 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 7TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 4.468 | 2122.3 | 403476.16 | 2645009.71 | 4.932 | -2639741.01 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 8TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 8.96 | 4256 | 403476.16 | 2645009.71 | 0.44 | -2639741.01 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 10TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 2.24 | 475 | 1064 | 191.52 | 1255.52 | 10 | 0 | 0 | 0 | 0 | 2.24 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
NEPTUNE TRION EXP | 117 | 0 | 05 May 2021 | Smart- Gyptech, | TOWER A 11TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 9.4 | 475 | 4465 | 803.7 | 5268.7 | 10 | 4.67 | 2218.25 | 403476.16 | 2645009.71 | 4.73 | -2639741.01 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900