## Project_Work_Order6385309632976
Project Work Order
From 01 May 2008 To 05 Jun 2024
Page 1 of 1
Total Records: 24 Records 1 To 24
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 14TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 16 | 585 | 9360 | 1684.8 | 11044.8 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 15TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 16 | 585 | 9360 | 1684.8 | 11044.8 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 16TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 16 | 585 | 9360 | 1684.8 | 11044.8 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 17TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 16 | 585 | 9360 | 1684.8 | 11044.8 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 14TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 40 | 585 | 23400 | 4212 | 27612 | 5 | 0 | 0 | 0 | 0 | 40 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 15TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 40 | 585 | 23400 | 4212 | 27612 | 5 | 0 | 0 | 0 | 0 | 40 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 16TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 585 | 515882.25 | 92858.8 | 608741.05 | 5 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 17TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 585 | 515882.25 | 92858.8 | 608741.05 | 5 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 14TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 585 | 170299.35 | 30653.88 | 200953.23 | 5 | 143.45 | 83918.25 | 15737.08 | 103165.33 | 147.66 | 97787.9 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 15TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 585 | 170299.35 | 30653.88 | 200953.23 | 5 | 0 | 0 | 0 | 0 | 291.11 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 16TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 585 | 170299.35 | 30653.88 | 200953.23 | 5 | 0 | 0 | 0 | 0 | 291.11 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 17TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 291.11 | 585 | 170299.35 | 30653.88 | 200953.23 | 5 | 0 | 0 | 0 | 0 | 291.11 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 14TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 330 | 585 | 193050 | 34749 | 227799 | 5 | 0 | 0 | 0 | 0 | 330 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 15TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 330 | 585 | 193050 | 34749 | 227799 | 5 | 0 | 0 | 0 | 0 | 330 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 16TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 330 | 585 | 193050 | 34749 | 227799 | 5 | 0 | 0 | 0 | 0 | 330 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER A 17TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 330 | 585 | 193050 | 34749 | 227799 | 5 | 0 | 0 | 0 | 0 | 330 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 14TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 585 | 515882.25 | 92858.8 | 608741.05 | 5 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 15TH FLOOR DRY WALL WORK | LABOR FOR DRY WALL (SQMT) | SQMT | 881.85 | 585 | 515882.25 | 92858.8 | 608741.05 | 5 | 0 | 0 | 0 | 0 | 881.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 16TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 40 | 585 | 23400 | 4212 | 27612 | 5 | 0 | 0 | 0 | 0 | 40 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER B 17TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 40 | 585 | 23400 | 4212 | 27612 | 5 | 0 | 0 | 0 | 0 | 40 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 14TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 15 | 585 | 8775 | 1579.5 | 10354.5 | 5 | 6 | 3510 | 15737.08 | 103165.33 | 9 | -92810.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 15TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 15 | 585 | 8775 | 1579.5 | 10354.5 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 16TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 15 | 585 | 8775 | 1579.5 | 10354.5 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
NEPTUNE TRION EXP | 302 | 0 | 01 Jan 2024 | UNITECH WORKS | TOWER C 17TH FLOOR DRY WALL WORK | LABOR FOR DPC (SQMT) | SQMT | 15 | 585 | 8775 | 1579.5 | 10354.5 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900