## Project_Work_Order6385326655475
Project Work Order
From 19 May 2005 To 07 Jun 2024
Page 1 of 1
Total Records: 175 Records 1 To 175
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE | SQFT | 5029.26 | 8.5 | 42748.71 | 0 | 42748.71 | 5 | 5029.26 | 42748.71 | 57832.56 | 379124.82 | 0 | -336376.11 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT | NOS | 1 | 3000 | 3000 | 0 | 3000 | 5 | 1 | 3000 | 57832.56 | 379124.82 | 0 | -376124.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 5029.26 | 8.5 | 42748.71 | 7694.76 | 50443.47 | 5 | 5029.26 | 42748.71 | 57832.56 | 379124.82 | 0 | -328681.35 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 5029.26 | 8.5 | 42748.71 | 7694.76 | 50443.47 | 5 | 5029.26 | 42748.71 | 57832.56 | 379124.82 | 0 | -328681.35 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 5029.26 | 8.5 | 42748.71 | 7694.76 | 50443.47 | 5 | 5029.26 | 42748.71 | 57832.56 | 379124.82 | 0 | -328681.35 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 5029.26 | 8.5 | 42748.71 | 7694.76 | 50443.47 | 5 | 5029.26 | 42748.71 | 57832.56 | 379124.82 | 0 | -328681.35 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 12TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 5029.26 | 8.5 | 42748.71 | 7694.76 | 50443.47 | 5 | 5029.26 | 42748.71 | 57832.56 | 379124.82 | 0 | -328681.35 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 13TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 14TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 15TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 16TH FLOOR COMMON ELECTRIC WORK | LABOUR FOR SLAB CONDUITE |  | 0 | 8.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 57832.56 | 379124.82 | 0 | -375584.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 10TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 57832.56 | 379124.82 | 0 | -375584.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 11TH FLOOR COMMON ELECTRIC WORK ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 57832.56 | 379124.82 | 0 | -375584.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 12TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 57832.56 | 379124.82 | 0 | -375584.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 13TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 14TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 15TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 16TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 12TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 1 | 3000 | 3000 | 540 | 3540 | 5 | 1 | 3000 | 57832.56 | 379124.82 | 0 | -375584.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 13TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 14TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 15TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 16TH FLOOR COMMON ELECTRIC WORK | LABOR FOR SLEEVE INSERT |  | 0 | 3000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 701 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 702 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 801 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 802 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 901 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 902 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1001 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1002 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1101 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1102 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1201 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1202 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1301 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1302 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1401 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1402 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1501 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1502 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1601 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1602 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 801 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 802 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 901 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 902 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1001 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1002 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1101 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1102 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1201 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1202 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1301 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1302 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1401 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1402 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1501 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1502 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1601 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1602 ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 0 | 600 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 701 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0.6 | 26000 | 15600 | 2808 | 18408 | 5 | 0.6 | 15600 | 57832.56 | 379124.82 | 0 | -360716.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 702 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0.6 | 26000 | 15600 | 2808 | 18408 | 5 | 0.6 | 15600 | 57832.56 | 379124.82 | 0 | -360716.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 801 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 802 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 901 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 902 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1001 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1002 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1301 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1302 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1401 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1402 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1501 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1502 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1601 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER C 1602 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 801 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 802 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0.6 | 26000 | 15600 | 2808 | 18408 | 5 | 0.6 | 15600 | 57832.56 | 379124.82 | 0 | -360716.82 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 901 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 902 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1001 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1002 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1101 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1102 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1201 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 95 | 0 | 06 Sep 2023 | Ambika Electricals | TOWER D 1202 ELECTRIC WORK | LABOR FOR ELECTRIC BOX FITTING (NOS) |  | 0 | 26000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 102 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 60.5 | 1150 | 69575 | 12523.5 | 82098.5 | 5 | 0 | 0 | 0 | 0 | 60.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 101 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 102 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 201 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 202 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 301 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 302 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 401 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 402 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 501 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 502 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 601 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 602 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 701 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 702 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 801 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 802 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 901 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 902 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1001 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1002 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1101 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1102 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1201 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1202 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1301 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 22 | 25300 | 27324 | 179124 | 88 | -29854 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1302 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 22 | 25300 | 27324 | 179124 | 88 | -29854 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1401 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1402 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1501 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1502 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1601 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1602 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 201 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 202 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 301 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 302 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 401 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 402 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 501 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 502 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 601 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 602 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 701 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 702 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 801 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 802 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 71.5 | 1150 | 82225 | 14800.5 | 97025.5 | 5 | 0 | 0 | 0 | 0 | 71.5 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 901 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 902 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1001 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1002 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1101 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1102 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1201 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1202 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 88 | 1150 | 101200 | 18216 | 119416 | 5 | 0 | 0 | 0 | 0 | 88 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1301 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 22 | 25300 | 27324 | 179124 | 88 | -29854 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1302 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 22 | 25300 | 27324 | 179124 | 88 | -29854 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1401 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 22 | 25300 | 27324 | 179124 | 88 | -29854 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1402 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 22 | 25300 | 27324 | 179124 | 88 | -29854 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1501 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1502 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1601 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1602 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1701 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1702 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1801 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER C 1802 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1701 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1702 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1801 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 135 | 0 | 09 Apr 2024 | Ambika Electricals | TOWER D 1802 ELECTRIC WORK | LABOUR FOR ELECTRIC POINT (NOS) | NOS | 110 | 1150 | 126500 | 22770 | 149270 | 5 | 0 | 0 | 0 | 0 | 110 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900