## Project_Work_Order6385421911896
Project Work Order
From 19 May 2005 To 18 Jun 2024
Page 1 of 1
Total Records: 44 Records 1 To 44
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR ITALIAN MARBLE (UMRA) | RFT | 30 | 35 | 1050 | 0 | 1050 | 5 | 15.76 | 551.6 | 10180.16 | 4103437.41 | 14.24 | -4102387.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES (1'X1') | RFT | 10 | 10 | 100 | 0 | 100 | 5 | 0 | 0 | 0 | 0 | 10 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES DEDO (1200X600) | SQFT | 1590 | 28 | 44520 | 0 | 44520 | 5 | 1530.98 | 42867.44 | 10180.16 | 4103437.41 | 59.02 | -4058917.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (800X1600) | RFT | 15 | 16 | 240 | 0 | 240 | 5 | 10.32 | 165.12 | 10180.16 | 4103437.41 | 4.68 | -4103197.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR WOODEN PLANK (1200X200) | RFT | 500 | 10 | 5000 | 0 | 5000 | 5 | 399.37 | 3993.7 | 10180.16 | 4103437.41 | 100.63 | -4098437.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR DHAR POLISH (RFT) | RFT | 127 | 17 | 2159 | 0 | 2159 | 5 | 45.94 | 780.98 | 10180.16 | 4103437.41 | 81.06 | -4101278.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR MARBLE FIXING AT LEDGE WALL TOP (SQFT) | SQFT | 16 | 40 | 640 | 0 | 640 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR SINK HOLE IN KOTA | NOS | 2 | 500 | 1000 | 0 | 1000 | 5 | 1 | 500 | 10180.16 | 4103437.41 | 1 | -4102437.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOUR FOR KOTA | SQFT | 100 | 35 | 3500 | 0 | 3500 | 5 | 50.5975 | 1770.91 | 10180.16 | 4103437.41 | 49.4025 | -4099937.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR ITALIAN MARBLE SKIRTING | RFT | 240 | 35 | 8400 | 0 | 8400 | 5 | 102.83 | 3599.05 | 10180.16 | 4103437.41 | 137.17 | -4095037.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (1200X600) | SQFT | 555 | 22 | 12210 | 0 | 12210 | 5 | 500.29 | 11006.38 | 10180.16 | 4103437.41 | 54.71 | -4091227.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR CHAMFER (RFT) | RFT | 165 | 20 | 3300 | 0 | 3300 | 5 | 51.76 | 1035.2 | 10180.16 | 4103437.41 | 113.24 | -4100137.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR MS ANGLE SUPPORT FOR BASIN KOTA | NOS | 14 | 250 | 3500 | 0 | 3500 | 5 | 6 | 1500 | 10180.16 | 4103437.41 | 8 | -4099937.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR SINK HOLE IN GRANITE | NOS | 2 | 500 | 1000 | 0 | 1000 | 5 | 1 | 500 | 10180.16 | 4103437.41 | 1 | -4102437.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR HOLE IN KOTA (NOS) | NOS | 6 | 600 | 3600 | 0 | 3600 | 5 | 6 | 3600 | 10180.16 | 4103437.41 | 0 | -4099837.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR MARBLE FIXING AT LEDGE WALL TOP (RFT) | RFT | 10 | 40 | 400 | 0 | 400 | 5 | 0 | 0 | 0 | 0 | 10 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR TABLE TOP (SQFT) | SQFT | 167 | 40 | 6680 | 0 | 6680 | 5 | 59.85 | 2394 | 10180.16 | 4103437.41 | 107.15 | -4096757.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOUR FOR BOTTOM PATTI | RFT | 100 | 40 | 4000 | 0 | 4000 | 5 | 38.93 | 1557.2 | 10180.16 | 4103437.41 | 61.07 | -4099437.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (800X1600) | SQFT | 1030 | 28 | 28840 | 0 | 28840 | 5 | 982.9 | 27521.2 | 10180.16 | 4103437.41 | 47.1 | -4074597.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (600X600) | RFT | 9 | 16 | 144 | 0 | 144 | 5 | 7.33 | 117.28 | 10180.16 | 4103437.41 | 1.67 | -4103293.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR BASIN HOLE IN MARBLE | NOS | 6 | 600 | 3600 | 0 | 3600 | 5 | 6 | 3600 | 10180.16 | 4103437.41 | 0 | -4099837.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR BASIN MIXTURE PILLER COCK (OPEN) | NOS | 14 | 100 | 1400 | 0 | 1400 | 5 | 12 | 1200 | 10180.16 | 4103437.41 | 2 | -4102037.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 KITCHEN & BASIN PLATFORM | LABOR FOR DOUBLE DHAR POLISH | RFT | 100 | 25 | 2500 | 0 | 2500 | 5 | 38.93 | 973.25 | 10180.16 | 4103437.41 | 61.07 | -4100937.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | PROVIDING & FIXING 3MM SPACER WITH REQUIRED TOOLS & TACKLES | SQFT | 1070 | 2 | 2140 | 0 | 2140 | 5 | 819.3 | 1638.6 | 10180.16 | 4103437.41 | 250.7 | -4101297.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR ITALIAN MARBLE FLOORING (SQFT) | SQFT | 1000 | 50 | 50000 | 0 | 50000 | 5 | 956.35 | 47817.5 | 10180.16 | 4103437.41 | 43.65 | -4053437.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES DEDO (1'X1') | SQFT | 225 | 17 | 3825 | 0 | 3825 | 5 | 207 | 3519 | 10180.16 | 4103437.41 | 18 | -4099612.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (600X600) | SQFT | 90 | 17 | 1530 | 0 | 1530 | 5 | 69.22 | 1176.74 | 10180.16 | 4103437.41 | 20.78 | -4101907.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES SKIRTING (600X600) | RFT | 45 | 16 | 720 | 0 | 720 | 5 | 25.42 | 406.72 | 10180.16 | 4103437.41 | 19.58 | -4102717.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES FLOORING (1'X1') | SQFT | 116 | 15 | 1740 | 0 | 1740 | 5 | 95.41 | 1431.15 | 10180.16 | 4103437.41 | 20.59 | -4101697.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES SKIRTING (800X1600) | RFT | 280 | 27 | 7560 | 0 | 7560 | 5 | 254.08 | 6860.16 | 10180.16 | 4103437.41 | 25.92 | -4095877.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES UMRA (1200X600) | RFT | 18 | 16 | 288 | 0 | 288 | 5 | 13.08 | 209.28 | 10180.16 | 4103437.41 | 4.92 | -4103149.41 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 139 | 0 | 04 Feb 2022 | Vikas Kumar B Prajapati | A 1101 FLOORING & DEDO WORK | LEAD CHARGES (LS) | LUMSUM | 1 | 15000 | 15000 | 0 | 15000 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction | 01 Jan 1900
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1101 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 19215 | 1000965 | 0 | -959665 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy | 01 Jan 1900
GREENWOOD ASPIRE EXP | 180 | 0 | 11 Jul 2022 | BAIDYANATH PASWAN | A 1101 FLOORING & DEDO WORK | LABOR FOR ITALIAN MIRROR POLISH (RFT) | RFT | 230 | 48 | 11040 | 1987.2 | 13027.2 | 5 | 182 | 8736 | 387443.52 | 2539907.52 | 48 | -2526880.32 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 180 | 0 | 11 Jul 2022 | BAIDYANATH PASWAN | A 1101 FLOORING & DEDO WORK | LABOR FOR ITALIAN MIRROR POLISH (SQFT) | SQFT | 1200 | 48 | 57600 | 10368 | 67968 | 5 | 958 | 45984 | 387443.52 | 2539907.52 | 242 | -2471939.52 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 193 | 0 | 09 Aug 2022 | Govind R. Makwana | A 1101 GROUT FILLING WORK GROUTING WORK | LABOR FOR EPOXY GROUT WITH SPACER (SQFT) | SQFT | 710 | 11 | 7810 | 0 | 7810 | 5 | 674 | 7414 | 0 | 409397.83 | 36 | -401587.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 193 | 0 | 09 Aug 2022 | Govind R. Makwana | A 1101 GROUT FILLING WORK GROUTING WORK | LABOR FOR CEMENT BASE GROUT WITH SPACER (SQFT) | SQFT | 150 | 4.75 | 712.5 | 0 | 712.5 | 5 | 0 | 0 | 0 | 0 | 150 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 193 | 0 | 09 Aug 2022 | Govind R. Makwana | A 1101 GROUT FILLING WORK GROUTING WORK | LABOR FOR CLEANING WORK | NOS | 2 | 500 | 1000 | 0 | 1000 | 5 | 2 | 1000 | 0 | 409397.83 | 0 | -408397.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 193 | 0 | 09 Aug 2022 | Govind R. Makwana | A 1101 GROUT FILLING WORK GROUTING WORK | LABOR FOR EPOXY GROUT WITHOUT SPACER (SQFT) | SQFT | 2200 | 5.5 | 12100 | 0 | 12100 | 5 | 1853 | 10191.5 | 0 | 409397.83 | 347 | -397297.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 193 | 0 | 09 Aug 2022 | Govind R. Makwana | A 1101 GROUT FILLING WORK GROUTING WORK | LABOR FOR EPOXY GROUT WITH SPACER (SQFT) | SQFT | 0 | 7.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 193 | 0 | 09 Aug 2022 | Govind R. Makwana | A 1101 GROUT FILLING WORK GROUTING WORK | LABOR FOR CEMENT BASE GROUT WITHOUT SPACER (SQFT) | SQFT | 1150 | 2.5 | 2875 | 0 | 2875 | 5 | 1140 | 2850 | 0 | 409397.83 | 10 | -406522.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 194 | 0 | 12 Aug 2022 | Vikas Kumar B Prajapati | A 1101 FIXING OF MARBLE FOR DOOR & WINDOW | LABOR FOR CHAMFER (RFT) | RFT | 1500 | 20 | 30000 | 0 | 30000 | 5 | 1144.964 | 22899.28 | 0 | 1398696.47 | 355.036 | -1368696.47 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 194 | 0 | 12 Aug 2022 | Vikas Kumar B Prajapati | A 1101 FIXING OF MARBLE FOR DOOR & WINDOW | LABOR FOR DHAR POLISH (RFT) | RFT | 1800 | 17 | 30600 | 0 | 30600 | 5 | 1491.604 | 25357.27 | 0 | 1398696.47 | 308.396 | -1368096.47 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900
GREENWOOD ASPIRE EXP | 194 | 0 | 12 Aug 2022 | Vikas Kumar B Prajapati | A 1101 FIXING OF MARBLE FOR DOOR & WINDOW | LABOUR FOR DOOR & WINDOW FRAME (RFT) | RFT | 1050 | 40 | 42000 | 0 | 42000 | 5 | 894.042 | 35761.68 | 0 | 1398696.47 | 155.958 | -1356696.47 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work | 01 Jan 1900