## Project_Work_Order6385438633480
Project Work Order
From 20 May 2014 To 20 Jun 2024
Page 1 of 1
Total Records: 6 Records 1 To 6
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS SERENITY | 204 | 0 | 13 Jun 2024 | PARJAPATI SUNILKUMAR HARIBHAI | CLUB HOUSE FLOORING AND DEDO WORK | LABOR FOR DOOR FRAME (RFT) | RFT | 16 | 40 | 640 | 0 | 640 | 5 | 0 | 0 | 0 | 0 | 16 | 0 | DOOR FRAME (RFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS SERENITY | 204 | 0 | 13 Jun 2024 | PARJAPATI SUNILKUMAR HARIBHAI | CLUB HOUSE FLOORING AND DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 10 | 17 | 170 | 0 | 170 | 5 | 0 | 0 | 0 | 0 | 10 | 0 | DHAR POLISH (RFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS SERENITY | 204 | 0 | 13 Jun 2024 | PARJAPATI SUNILKUMAR HARIBHAI | CLUB HOUSE FLOORING AND DEDO WORK | LABOR FOR ITALIAN DEDO (SQFT) | SQFT | 293.76 | 60 | 17625.6 | 0 | 17625.6 | 5 | 0 | 0 | 0 | 0 | 293.76 | 0 | ITALIAN DEDO (SQFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS SERENITY | 204 | 0 | 13 Jun 2024 | PARJAPATI SUNILKUMAR HARIBHAI | CLUB HOUSE FLOORING AND DEDO WORK | LABOR FOR ITALIAN MARBLE (UMRA) | RFT | 4.75 | 35 | 166.25 | 0 | 166.25 | 5 | 0 | 0 | 0 | 0 | 4.75 | 0 | ITALIAN MARBLE (UMRA) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS SERENITY | 204 | 0 | 13 Jun 2024 | PARJAPATI SUNILKUMAR HARIBHAI | CLUB HOUSE FLOORING AND DEDO WORK | LABOR FOR ITALIAN MARBLE FLOORING (SQFT) | SQFT | 275.61 | 50 | 13780.5 | 0 | 13780.5 | 5 | 0 | 0 | 0 | 0 | 275.61 | 0 | ITALIAN MARBLE FLOORING (SQFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900
GREENWOODS SERENITY | 204 | 0 | 13 Jun 2024 | PARJAPATI SUNILKUMAR HARIBHAI | CLUB HOUSE FLOORING AND DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 20 | 17 | 340 | 0 | 340 | 5 | 0 | 0 | 0 | 0 | 20 | 0 | DHAR POLISH (RFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction | 01 Jan 1900