## Project_Work_Order6385856467408
Project Work Order
From 10 Jul 1986 To 07 Aug 2024
Page 1 of 1
Total Records: 111 Records 1 To 111
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS AARANYA | 77 | 0 | 31 May 2023 | CIVIL ART ENTERPRISE | TOWER D 101 SH CONSULTANCY CHARGES | CHARGES FOR PROVIDING PROJECT MANAGEMENT CONSULTANCY (LS) | LUMSUM | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 0.5 | 100000 | 18000 | 118000 | 0.5 | 118000 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 50 | 28 | 1400 | 252 | 1652 | 5 | 0 | 0 | 0 | 0 | 50 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 200 | 22 | 4400 | 792 | 5192 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR GROOVE (RFT) | RFT | 500 | 20 | 10000 | 1800 | 11800 | 5 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR GYPSUM CEILING (SQFT) | SQFT | 2000 | 55 | 110000 | 19800 | 129800 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR GYPSUM VERTICAL (RFT) | RFT | 500 | 52 | 26000 | 4680 | 30680 | 5 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR LIGHT CUT OUT | NOS | 50 | 30 | 1500 | 270 | 1770 | 5 | 0 | 0 | 0 | 0 | 50 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR MOLDING (RFT) | RFT | 200 | 55 | 11000 | 1980 | 12980 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR PUNNING | SQFT | 4000 | 25 | 100000 | 18000 | 118000 | 5 | 0 | 0 | 0 | 0 | 4000 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 78 | 0 | 09 Jun 2023 | Miran Decorators | TOWER D 101 SH PUNNING WORK | LABOR FOR WALL GROOVE | RFT | 1000 | 18 | 18000 | 3240 | 21240 | 5 | 0 | 0 | 0 | 0 | 1000 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 79 | 0 | 15 Jun 2023 | TransCube Engineers Pvt Ltd | TOWER D 101 SH ELECTRIC WORK | LABOUR FOR ELECTRIC WORK (NOS) | NOS | 1 | 79790 | 79790 | 14362.2 | 94152.2 | 5 | 1 | 79790 | 14362.2 | 94152.2 | 0 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 81 | 0 | 03 Jul 2023 | HYGIENE PEST MANAGEMENT | TOWER D 101 SH ANTI TERMITE TREATMENT | ANTI TERMITE TREATMENT (SQFT) | SQFT | 1960 | 5.25 | 10290 | 1852.2 | 12142.2 | 5 | 0 | 0 | 0 | 0 | 1960 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 83 | 0 | 07 Jul 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | TOWER D 101 SH HVAC WORK | CHARGES FOR 300 x 50 GI PERFORATED CABLE TRAY (RMT) | RMT | 6 | 150 | 900 | 162 | 1062 | 5 | 0 | 0 | 0 | 0 | 6 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 83 | 0 | 07 Jul 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | TOWER D 101 SH HVAC WORK | CHARGES FOR M.S. STRUCTURAL WORK (KG) | KG | 30 | 25 | 750 | 135 | 885 | 5 | 0 | 0 | 0 | 0 | 30 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 83 | 0 | 07 Jul 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | TOWER D 101 SH HVAC WORK | LABOR FOR 1.5 SQMM 2 CORE SHIELDED CONTROL CABLE | RMT | 100 | 50 | 5000 | 900 | 5900 | 5 | 82 | 4100 | 2539.8 | 16649.8 | 18 | -10749.8 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 83 | 0 | 07 Jul 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | TOWER D 101 SH HVAC WORK | LABOR FOR AC DRAIN PIPE (RMT) | RMT | 50 | 65 | 3250 | 585 | 3835 | 5 | 34 | 2210 | 2539.8 | 16649.8 | 16 | -12814.8 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 83 | 0 | 07 Jul 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | TOWER D 101 SH HVAC WORK | LABOR FOR GI PERFORATED CABLE TRAY | RMT | 80 | 150 | 12000 | 2160 | 14160 | 5 | 52 | 7800 | 2539.8 | 16649.8 | 28 | -2489.8 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 83 | 0 | 07 Jul 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | TOWER D 101 SH HVAC WORK | LABOR FOR VRF SYSTEM (NOS) | NOS | 1 | 1000 | 1000 | 180 | 1180 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 84 | 0 | 10 Jul 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH FURNITURE WORK | LABOUR FOR PALMET | SQFT | 150 | 325 | 48750 | 8775 | 57525 | 5 | 150 | 48750 | 32279.4 | 211609.4 | 0 | -154084.4 | Wooden Palmet 19mm ply + 4mm MDF |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 84 | 0 | 10 Jul 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH FURNITURE WORK | LABOR FOR WOODEN CEILING WORK | SQFT | 275 | 470 | 129250 | 23265 | 152515 | 5 | 264 | 124080 | 32279.4 | 211609.4 | 11 | -59094.4 | Wooden ceiling in Oak wood and veener as per drawing/reference photo |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 84 | 0 | 10 Jul 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH FURNITURE WORK | LABOUR FOR CEMENT SHEET (SQFT) | SQFT | 275 | 300 | 82500 | 14850 | 97350 | 5 | 0 | 0 | 0 | 0 | 275 | 0 | cement sheet ceiling finished in 12mm ply + 6mm cement sheet |  | T.Joshi | pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 84 | 0 | 10 Jul 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH FURNITURE WORK | LABOUR FOR PALMET | SQFT | 20 | 325 | 6500 | 1170 | 7670 | 5 | 20 | 6500 | 32279.4 | 211609.4 | 0 | -203939.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | DEPART LABOR | NOS | 6 | 1100 | 6600 | 0 | 6600 | 5 | 2.73 | 3003 | 0 | 100239.89 | 3.27 | -93639.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | DEPART MASON | NOS | 3 | 1100 | 3300 | 0 | 3300 | 5 | 3 | 3300 | 0 | 100239.89 | 0 | -96939.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR CHAMFER (RFT) | RFT | 920 | 20 | 18400 | 0 | 18400 | 5 | 913.9 | 18278 | 0 | 100239.89 | 6.1 | -81839.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR DOOR & WINDOW FRAME (SQFT) | SQFT | 650 | 40 | 26000 | 0 | 26000 | 5 | 643.26 | 25730.4 | 0 | 100239.89 | 6.74 | -74239.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (1200X600) | SQFT | 1290 | 22 | 28380 | 0 | 28380 | 5 | 1288.16 | 28339.52 | 0 | 100239.89 | 1.84 | -71859.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (300X300) | SQFT | 160 | 15 | 2400 | 0 | 2400 | 5 | 150.54 | 2258.1 | 0 | 100239.89 | 9.46 | -97839.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 87 | 0 | 04 Aug 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 1150 | 17 | 19550 | 0 | 19550 | 5 | 1137.11 | 19330.87 | 0 | 100239.89 | 12.89 | -80689.89 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 88 | 0 | 08 Aug 2023 | Jaydutt Contractors and Engineers | TOWER D 101 SH DRILLING WORK | LABOR FOR 30 MM DIA DRILLING (230 MM DEPTH) | NOS | 7 | 90 | 630 | 113.4 | 743.4 | 5 | 0 | 0 | 0 | 0 | 7 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 89 | 0 | 12 Aug 2023 | Uniqas Private Limited | TOWER D 101 SH AUTOMATION WORK | CHARGES FOR SUPPLY & INSTALLATION OF AUTOMATION | NOS | 0 | 196244 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | LOBBY Doorbell Smart touch switch (2M) SB-1 FOYER 2 Switch smart wifi touch panel (2M) SB-2 LIVING/HALL/PASSAGE 6 Switch 1 Fan Smart Wifi touch panel (8M) SB-03 Curtain-40 kg Motor, 7-14 ft. fully built track, Remote LR IR blaster tv/ac TV/AC BALCONY "4 Switch + 1 fan + 1 socket + 1 RJ11 + 1 RJ45 smart touch panel (8M)" SB-10 KITCHEN 6 Switch 1 Fan Smart Wifi touch panel (8M) SB-11 COMMON BATHROOM RF Motion Sensor SB-24 2 Switch smart wifi touch panel (2M) SB-24 STUDY/GUEST ROOM 6 Switch 1 Fan Smart Wifi touch panel (8M) SB-27 Smart IR blaster SB-29 BEDROOM 2 2 Switch smart wifi touch panel (2M) SB-31 4 Switch + 1 fan + 1 socket + 1 RJ11 + 1 RJ45 smart touch panel (8M) SB-32 "2 Switch+1 socket smart wifi touch panel (4M)" SB-33 IR Blaster for tv/ac SB-34 Att.Toilet PIR Sensors for Bathroom SB-36 1 node smart retro module (gyser) SB-36 MASTER BEDROOM 2 Switch smart wifi touch panel (2M) SB-39 "4 Switch + 1 fan + 1 socket + 1 RJ11 + 1 RJ45 smart touch panel (8M)" SB-40 2 Switch + 1 Socket touch panel (4M) SB-41 Curtain-40 kg Motor, 7-14 ft. fully built track, Remote MB IR Blaster for tv/ac AC/TV Att.Toilet RF motion sensor (Bathroom) SB-44 1 node smart retro module (gyser) SB-44 BEDROOM 1 2 Switch smart wifi touch panel (2M) SB-48 2 Switch smart wifi touch panel (2M) SB-49 4 Switch + 1 fan + 1 socket + 1 RJ11 + 1 RJ45 smart touch panel (8M) SB-50 IR Blaster for tv/ac SB-51 Att.Toilet RF motion sensor (Bathroom) SB-54 1 node smart retro module (gyser) SB-54 |  |  | Pur.nrpl3 |  | Job Work | 12 Aug 2023
GREENWOODS AARANYA | 90 | 0 | 12 Aug 2023 | Uniqas Private Limited | TOWER D 101 SH AUTOMATION WORK | CHARGES FOR SUPPLY & INSTALLATION OF AUTOMATION | NOS | 0 | 196244 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 25 Aug 2023
GREENWOODS AARANYA | 91 | 0 | 25 Aug 2023 | Uniqas Private Limited | TOWER D 101 SH AUTOMATION WORK | CHARGES FOR SUPPLY & INSTALLATION OF AUTOMATION | NOS | 1 | 206728 | 206728 | 37211.04 | 243939.04 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 91 | 0 | 25 Aug 2023 | Uniqas Private Limited | TOWER D 101 SH AUTOMATION WORK | CHARGES FOR WIFI TOUCH PANEL (NOS) | NOS | 1 | 16912 | 16912 | 3044.16 | 19956.16 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | WIFI TOUCH PANEL - 2 SWITCH 1 SOCKET 4M - 2 nos x 4100 rs = 8200 rs WIFI TOUCH PANEL - 4 SWITCH(4-HV) 1 SOCKET 16A-6M - 1 NO X 8712 rS |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 93 | 0 | 01 Sep 2023 | MANORATH ENTERPRISE | TOWER D 101 SH WATERPROOFING WORK | LABOUR FOR WATERPROOFING (SQFT) | SQFT | 1573 | 46 | 72358 | 13024.44 | 85382.44 | 5 | 1573 | 72358 | 28888.92 | 189382.92 | 0 | -104000.48 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 99 | 0 | 29 Sep 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH FURNITURE WORK | LABOUR FOR CARPENTRY WORK (NOS) | NOS | 1 | 2233201 | 2233201 | 401976.18 | 2635177.18 | 5 | 0.7 | 1563240.7 | 281383.34 | 1844624.04 | 0.3 | 790553.14 | Work order for fixed furniture , loose/movable furniture and modular kitchen. materials to be used as per approved qtn sheet. work to be executed as per BOQ provided. |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 103 | 0 | 25 Oct 2023 | Jairam S. Saini | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (CMT) | CMT | 13 | 2000 | 26000 | 0 | 26000 | 5 | 13 | 26000 | 0 | 26000 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 104 | 0 | 26 Oct 2023 | Heli Floors | TOWER D 101 SH FLOORING & DEDO WORK | CHARGES FOR LAMINATE FLOORING (SQFT) | SQFT | 542.49 | 140 | 75948.6 | 13670.74 | 89619.34 | 5 | 542.49 | 75948.6 | 16601.14 | 108829.74 | 0 | -19210.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 104 | 0 | 26 Oct 2023 | Heli Floors | TOWER D 101 SH FLOORING & DEDO WORK | CHARGES FOR REDUCER (RFT) | RFT | 24 | 85 | 2040 | 367.2 | 2407.2 | 5 | 24 | 2040 | 16601.14 | 108829.74 | 0 | -106422.54 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 104 | 0 | 26 Oct 2023 | Heli Floors | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR SKIRTING (RFT) | RFT | 128 | 85 | 10880 | 1958.4 | 12838.4 | 5 | 128 | 10880 | 16601.14 | 108829.74 | 0 | -95991.34 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 104 | 0 | 26 Oct 2023 | Heli Floors | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR DOOR BIDDING PATTI (RFT) | RFT | 56 | 60 | 3360 | 604.8 | 3964.8 | 5 | 56 | 3360 | 16601.14 | 108829.74 | 0 | -104864.94 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | CHARGES FOR TILE PATTA CUTTING (SQFT) | SQFT | 226 | 10 | 2260 | 0 | 2260 | 5 | 224.7 | 2247 | 0 | 157464.01 | 1.3 | -155204.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR KOTA PLATFORM | SQFT | 44 | 35 | 1540 | 0 | 1540 | 5 | 43.94 | 1537.9 | 0 | 157464.01 | 0.06 | -155924.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR SINK HOLE IN GRANITE | NOS | 2 | 600 | 1200 | 0 | 1200 | 5 | 2 | 1200 | 0 | 157464.01 | 0 | -156264.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES DEDO (1200X600) | SQFT | 146 | 28 | 4088 | 0 | 4088 | 5 | 145.38 | 4070.64 | 0 | 157464.01 | 0.62 | -153376.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES DEDO (600X600) | SQFT | 214 | 17 | 3638 | 0 | 3638 | 5 | 213.5 | 3629.5 | 0 | 157464.01 | 0.5 | -153826.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (1200X600) | SQFT | 55 | 22 | 1210 | 0 | 1210 | 5 | 54.86 | 1206.92 | 0 | 157464.01 | 0.14 | -156254.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR COUNTER TOP (SQFT) | SQFT | 44 | 40 | 1760 | 0 | 1760 | 5 | 43.94 | 1757.6 | 0 | 157464.01 | 0.06 | -155704.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR ITALIAN MARBLE PLATFORM | SQFT | 26 | 45 | 1170 | 0 | 1170 | 5 | 25.35 | 1140.75 | 0 | 157464.01 | 0.65 | -156294.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR ITALIAN DEDO (SQFT) | SQFT | 247 | 60 | 14820 | 0 | 14820 | 5 | 246.05 | 14763 | 0 | 157464.01 | 0.95 | -142644.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | DEPART LABOR | NOS | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0.454 | 499.4 | 0 | 157464.01 | 0.546 | -156364.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | DEPART MASON | NOS | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0.91 | 1001 | 0 | 157464.01 | 0.09 | -156364.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR CHAMFER (RFT) | RFT | 200 | 20 | 4000 | 0 | 4000 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR DOOR & WINDOW SILL | SQFT | 100 | 40 | 4000 | 0 | 4000 | 5 | 0 | 0 | 0 | 0 | 100 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES DEDO (1200X600) | SQFT | 503 | 28 | 14084 | 0 | 14084 | 5 | 501.33 | 14037.24 | 0 | 157464.01 | 1.67 | -143380.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR VITRIFIED TILES FLOORING (1200X600) | SQFT | 110 | 22 | 2420 | 0 | 2420 | 5 | 108.7 | 2391.4 | 0 | 157464.01 | 1.3 | -155044.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR WOODEN PLANK (1200X200) | RFT | 283 | 10 | 2830 | 0 | 2830 | 5 | 283 | 2830 | 0 | 157464.01 | 0 | -154634.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR COUNTER TOP (SQFT) | SQFT | 23 | 40 | 920 | 0 | 920 | 5 | 22.36 | 894.4 | 0 | 157464.01 | 0.64 | -156544.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR ITALIAN MARBLE FLOORING WITH CUTTING (SQFT) | SQFT | 42 | 50 | 2100 | 0 | 2100 | 5 | 41.25 | 2062.5 | 0 | 157464.01 | 0.75 | -155364.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR VITRIFIED FLOORING - 45° (RFT) | RFT | 92 | 25 | 2300 | 0 | 2300 | 5 | 91.64 | 2291 | 0 | 157464.01 | 0.36 | -155164.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR ITALIAN MARBLE PLATFORM | SQFT | 56 | 45 | 2520 | 0 | 2520 | 5 | 55.98 | 2519.1 | 0 | 157464.01 | 0.02 | -154944.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR ITALIAN DEDO (SQFT) | SQFT | 106 | 60 | 6360 | 0 | 6360 | 5 | 105.23 | 6313.8 | 0 | 157464.01 | 0.77 | -151104.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR KOTA PLATFORM | SQFT | 33 | 35 | 1155 | 0 | 1155 | 5 | 32.81 | 1148.35 | 0 | 157464.01 | 0.19 | -156309.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR SINK HOLE IN GRANITE | NOS | 1 | 600 | 600 | 0 | 600 | 5 | 1 | 600 | 0 | 157464.01 | 0 | -156864.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES DEDO (1'X1') | SQFT | 196 | 17 | 3332 | 0 | 3332 | 5 | 195.03 | 3315.51 | 0 | 157464.01 | 0.97 | -154132.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR SPARTEK TILES FLOORING (1'X1') | SQFT | 143 | 15 | 2145 | 0 | 2145 | 5 | 141.52 | 2122.8 | 0 | 157464.01 | 1.48 | -155319.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | DEPART MASON | NOS | 10 | 1100 | 11000 | 0 | 11000 | 5 | 8 | 8800 | 0 | 157464.01 | 2 | -146464.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR AUSTRALIAN MARBLE FITTING | SQFT | 956 | 65 | 62140 | 0 | 62140 | 5 | 955.28 | 62093.2 | 0 | 157464.01 | 0.72 | -95324.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR CHAMFER (RFT) | RFT | 179 | 20 | 3580 | 0 | 3580 | 5 | 178.94 | 3578.8 | 0 | 157464.01 | 0.06 | -153884.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 164 | 17 | 2788 | 0 | 2788 | 5 | 163.1 | 2772.7 | 0 | 157464.01 | 0.9 | -154676.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR DOOR & WINDOW SILL | SQFT | 120 | 40 | 4800 | 0 | 4800 | 5 | 119.8 | 4792 | 0 | 157464.01 | 0.2 | -152664.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR HOLE 1" DIA (NOS) | NOS | 4 | 100 | 400 | 0 | 400 | 5 | 4 | 400 | 0 | 157464.01 | 0 | -157064.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR VITRIFIED FLOORING - 45° (RFT) | RFT | 25 | 25 | 625 | 0 | 625 | 5 | 24.82 | 620.5 | 0 | 157464.01 | 0.18 | -156839.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 105 | 0 | 26 Oct 2023 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | PROVIDING & FIXING 3MM SPACER WITH REQUIRED TOOLS & TACKLES | SQFT | 415 | 2 | 830 | 0 | 830 | 5 | 413.5 | 827 | 0 | 157464.01 | 1.5 | -156634.01 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 111 | 0 | 05 Dec 2023 | Shree Ram Fabrication | TOWER D 101 SH RAILING WORK | LABOR FOR BALCONY RAILING (RFT) | RFT | 92 | 1210 | 111320 | 20037.6 | 131357.6 | 5 | 51.3 | 62073 | 22346.28 | 146492.28 | 40.7 | -15134.68 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | DEPART LABOR | NOS | 15 | 700 | 10500 | 1890 | 12390 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | LABOR FOR MONOCOAT POLISH WORK (RFT) | RFT | 500 | 90 | 45000 | 8100 | 53100 | 5 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | LABOR FOR MONOCOAT POLISH WORK (SQFT) | SQFT | 700 | 180 | 126000 | 22680 | 148680 | 5 | 0 | 0 | 0 | 0 | 700 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | LABOR FOR OIL PAINT (RFT) | RFT | 200 | 8 | 1600 | 288 | 1888 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | LABOR FOR OIL PAINT (SQFT) | SQFT | 200 | 11.5 | 2300 | 414 | 2714 | 5 | 0 | 0 | 0 | 0 | 200 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | LABOR FOR PUTTY & PRIMER (SQFT) | SQFT | 4500 | 7.5 | 33750 | 6075 | 39825 | 5 | 0 | 0 | 0 | 0 | 4500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 114 | 0 | 11 Dec 2023 | MAA ASHAPURA IMPERIAL | TOWER D 101 SH PAINT WORK | PROVIDING & APPLYING ROYALE MATT | SQFT | 4500 | 18 | 81000 | 14580 | 95580 | 5 | 0 | 0 | 0 | 0 | 4500 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 122 | 0 | 02 Jan 2024 | Star Engineering | TOWER D 101 SH FABRICATION WORK | LABOR FOR ANCHOR FASTNER 12MM | NOS | 12 | 120 | 1440 | 0 | 1440 | 5 | 0 | 0 | 0 | 0 | 12 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 122 | 0 | 02 Jan 2024 | Star Engineering | TOWER D 101 SH FABRICATION WORK | LABOR FOR FABRICATED DUCT PLATFORM | KG | 240 | 135 | 32400 | 0 | 32400 | 5 | 0 | 0 | 0 | 0 | 240 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 122 | 0 | 02 Jan 2024 | Star Engineering | TOWER D 101 SH FABRICATION WORK | LABOR FOR ANCHOR FASTNERS M 12 (NOS) | NOS | 40 | 120 | 4800 | 0 | 4800 | 5 | 0 | 0 | 0 | 0 | 40 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 122 | 0 | 02 Jan 2024 | Star Engineering | TOWER D 101 SH FABRICATION WORK | LABOR FOR FABRICATED DUCT PLATFORM | KG | 112 | 135 | 15120 | 0 | 15120 | 5 | 0 | 0 | 0 | 0 | 112 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 134 | 0 | 08 Apr 2024 | B S Window Solution | TOWER D 101 SH ALUMINIUM WORK | LABOR FOR ALUMINUM WINDOW (SQFT) | SQFT | 540 | 558.82 | 301762.8 | 54317.3 | 356080.1 | 5 | 540 | 301762.8 | 150277.86 | 985154.94 | 0 | -629074.84 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CARTING CHARGES (NOS) | NOS | 1 | 650 | 650 | 117 | 767 | 5 | 1 | 650 | 5498.64 | 36046.64 | 0 | -35279.64 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CHARGES FOR HOLE IN GLASS | NOS | 12 | 45 | 540 | 97.2 | 637.2 | 5 | 12 | 540 | 5498.64 | 36046.64 | 0 | -35409.44 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CHARGES FOR MAGNETEIC SEAL (NOS) | NOS | 8 | 145 | 1160 | 208.8 | 1368.8 | 5 | 8 | 1160 | 5498.64 | 36046.64 | 0 | -34677.84 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CHARGES FOR SILICON | NOS | 3 | 178 | 534 | 96.12 | 630.12 | 5 | 3 | 534 | 5498.64 | 36046.64 | 0 | -35416.52 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | LABOR FOR 10 MM TUFFEN GLASS (SQFT) | SQFT | 100.25 | 155 | 15538.75 | 2796.98 | 18335.73 | 5 | 100.25 | 15538.75 | 5498.64 | 36046.64 | 0 | -17710.91 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | LABOR FOR BIG CUT (NOS) | NOS | 3 | 450 | 1350 | 243 | 1593 | 5 | 3 | 1350 | 5498.64 | 36046.64 | 0 | -34453.64 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | LABOR FOR GLASS FIXING (SQFT) | SQFT | 100.25 | 45 | 4511.25 | 812.02 | 5323.27 | 5 | 100.25 | 4511.25 | 5498.64 | 36046.64 | 0 | -30723.37 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 149 | 0 | 03 Jun 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | LABOR FOR MS BRACKET (NOS) | NOS | 12 | 522 | 6264 | 1127.52 | 7391.52 | 5 | 12 | 6264 | 5498.64 | 36046.64 | 0 | -28655.12 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 157 | 0 | 09 Jul 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CARTING CHARGES (NOS) | NOS | 1 | 600 | 600 | 108 | 708 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 157 | 0 | 09 Jul 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CHARGES FOR 5MM MIRROR GLASS | SQFT | 55.75 | 105 | 5853.75 | 1053.68 | 6907.43 | 5 | 0 | 0 | 0 | 0 | 55.75 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 157 | 0 | 09 Jul 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | CHARGES FOR SILICON | NOS | 6 | 178 | 1068 | 192.24 | 1260.24 | 5 | 0 | 0 | 0 | 0 | 6 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 157 | 0 | 09 Jul 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | LABOR FOR GLASS FIXING (SQFT) | SQFT | 55.75 | 50 | 2787.5 | 501.76 | 3289.26 | 5 | 0 | 0 | 0 | 0 | 55.75 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 157 | 0 | 09 Jul 2024 | Meet Glass Designing Works | TOWER D 101 SH GLASS WORK | LABOR FOR MIRROR MOUNTED TAPE | NOS | 3 | 385 | 1155 | 207.9 | 1362.9 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 158 | 0 | 09 Jul 2024 | Caras Realty | TOWER D 101 SH CIVIL WORK | DEPART LABOR | NOS | 4 | 1400 | 5600 | 0 | 5600 | 0 | 4 | 5600 | 0 | 11200 | 0 | -5600 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 158 | 0 | 09 Jul 2024 | Caras Realty | TOWER D 101 SH CIVIL WORK | DEPART MASON | NOS | 4 | 1400 | 5600 | 0 | 5600 | 0 | 4 | 5600 | 0 | 11200 | 0 | -5600 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 165 | 0 | 15 Jul 2024 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | DEPART LABOR | NOS | 3 | 500 | 1500 | 0 | 1500 | 5 | 3 | 1500 | 0 | 21350.85 | 0 | -19850.85 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 165 | 0 | 15 Jul 2024 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | DEPART MASON | NOS | 3 | 1100 | 3300 | 0 | 3300 | 5 | 3 | 3300 | 0 | 21350.85 | 0 | -18050.85 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 165 | 0 | 15 Jul 2024 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR CHAMFER (RFT) | RFT | 250.49 | 20 | 5009.8 | 0 | 5009.8 | 5 | 250 | 5000 | 0 | 21350.85 | 0.49 | -16341.05 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 165 | 0 | 15 Jul 2024 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 250.49 | 17 | 4258.33 | 0 | 4258.33 | 5 | 250.05 | 4250.85 | 0 | 21350.85 | 0.44 | -17092.52 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 165 | 0 | 15 Jul 2024 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOR FOR HOLE (NOS) | NOS | 3 | 500 | 1500 | 0 | 1500 | 5 | 3 | 1500 | 0 | 21350.85 | 0 | -19850.85 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 165 | 0 | 15 Jul 2024 | Kailash Sharma | TOWER D 101 SH FLOORING & DEDO WORK | LABOUR FOR GRANITE PATTA (RFT) | RFT | 145.93 | 40 | 5837.2 | 0 | 5837.2 | 5 | 145 | 5800 | 0 | 21350.85 | 0.93 | -15513.65 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 166 | 0 | 15 Jul 2024 | PIYUSHBHAI DUBEY & ANKUSH DUBEY | TOWER D 101 SH PLANTATION WORK | CHARGES FOR PLANTATION WORK | LUMSUM | 1 | 32940 | 32940 | 0 | 32940 | 5 | 1 | 32940 | 0 | 32940 | 0 | 0 | Price includes below materials 1) rectangular rcc pot 2)arica palm 3) round RCC pot 4)arica palm big size 5)table palm 6)Sepotia Palm 7)monstera big 8) soil 9) labour 10) vermi compost 11) freight |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 167 | 0 | 15 Jul 2024 | Kalaben T Yadav | TOWER D 101 SH CIVIL WORK | LABOR FOR NANO TOPPING OVER PLASTER WORK | SQFT | 438.75 | 70 | 30712.5 | 0 | 30712.5 | 5 | 323.16 | 22621.2 | 0 | 22621.2 | 115.59 | 8091.3 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS AARANYA | 172 | 0 | 30 Jul 2024 | KHANDELWAL DRAPE SHOP | TOWER D 101 SH CURTAIN & MATTRESSES | CHARGES FOR ARABIAN PATTERN STITCHING | PART | 33 | 350 | 11550 | 0 | 11550 | 0 | 0 | 0 | 0 | 0 | 33 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900