## Project_Work_Order6385890427203
Project Work Order
From 01 Jan 2024 To 11 Aug 2024
Page 1 of 1
Total Records: 55 Records 1 To 55
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A30 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B43 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B46 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B41 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A20 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A34 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B44 FLOORING WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A40 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 21-22 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B45 FLOORING WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B42 FLOORING WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | GW SERENITY VILLA CARPENTRY WORKS | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 85 | 4350 | 369750 | 66555 | 436305 | 5 | 0 | 0 | 0 | 0 | 85 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 38 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B43 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B46 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B41 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A20 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A34 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B4 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B45 FLOORING WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B42 FLOORING WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | GW SERENITY VILLA CARPENTRY WORKS | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 1283.2 | 1225 | 1571920 | 282945.6 | 1854865.6 | 5 | 0 | 0 | 0 | 0 | 1283.2 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 38 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B44 FLOORING WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A30 FLOORING & DEDO WORK | LABOUR FOR DOOR CLOSER FITTING (NOS) | NOS | 4 | 4350 | 17400 | 3132 | 20532 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | DOOR CLOSER FITTING |  |  | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B41 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A20 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A34 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B4 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A40 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 21-22 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | GW SERENITY VILLA CARPENTRY WORKS | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 1283.2 | 320 | 410624 | 73912.32 | 484536.32 | 5 | 0 | 0 | 0 | 0 | 1283.2 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 38 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B44 FLOORING WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A30 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B43 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B46 FLOORING & DEDO WORK | LABOUR FOR MAIN DOOR VEENER (SQFT) | SQFT | 64.16 | 1225 | 78596 | 14147.28 | 92743.28 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | 35MM FLUSH DOOR, 4MM VENEER, WOODEN PATTI, HANDLE, EUROPA CYLINDER LOCK, OUTSIDE VENEER FINISH PANELING - ALL WORK IS INCLUSIVE OF MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A34 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B4 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A40 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 21-22 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B45 FLOORING WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B42 FLOORING WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B44 FLOORING WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A30 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B43 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B46 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B41 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A20 FLOORING & DEDO WORK | LABOUR FOR DOOR FRAME (SQFT) | SQFT | 64.16 | 320 | 20531.2 | 3695.62 | 24226.82 | 5 | 0 | 0 | 0 | 0 | 64.16 | 0 | MAIN DOOR WOODEN FRAME AND PATTA |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B4 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A40 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 21-22 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B45 FLOORING WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA B42 FLOORING WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900
GREENWOODS SERENITY | 226 | 0 | 08 Aug 2024 | SHREE HARI ASSOCIATES | VILLA A 38 FLOORING & DEDO WORK | LABOR FOR INSTALLING INTERNAL DOOR (SQFT) | SQFT | 117.5 | 510 | 59925 | 10786.5 | 70711.5 | 5 | 0 | 0 | 0 | 0 | 117.5 | 0 | 35MM FLUSH DOOR, 0.9MM LAMINATE, WOODEN PATTI, EUROPA MOTORISED LOCK, SS STOPERS, - ALL WORK IS INCLUDING MATERIAL, LABOUR, ALL NECESSARY TOOLS AND TACKLES ETC. COMPLETE. |  | deepak.p | pur.nrpl4 |  | Construction | 01 Jan 1900