## Project_Work_Order6385890992722
Project Work Order
From 11 Jul 2014 To 11 Aug 2024
Page 1 of 1
Total Records: 3 Records 1 To 3
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2
GREENWOODS SERENITY | 152 | 0 | 29 Aug 2023 | NARSI SUTHAR | VILLA A1 CARPENTERY WORK FURNITURE WORK | LABOR FOR HANDLE (NOS) | NOS | 1 | 14445 | 14445 | 0 | 14445 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | SUPPLY AND INSTALLATION OF MAIN DOOR LOCK AT SERENITY VILLA 1 AS PER DETAILS. MADE OUT OF DRY TEAK WOOD AND 3D CNC WORK AS PER DETAILS. |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS SERENITY | 152 | 0 | 29 Aug 2023 | NARSI SUTHAR | INFRA CLUB HOUSE CARPENTRY WORK | LABOR FOR FURNITURE WORK | NOS | 1 | 1023390 | 1023390 | 0 | 1023390 | 5 | 0.95 | 972220.5 | 0 | 1291457.5 | 0.05 | -268067.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900
GREENWOODS SERENITY | 152 | 0 | 29 Aug 2023 | NARSI SUTHAR | INFRA CLUB HOUSE CARPENTRY WORK | LABOR FOR FURNITURE WORK | NOS | 1 | 319237 | 319237 | 0 | 319237 | 5 | 1 | 319237 | 0 | 1291457.5 | 0 | -972220.5 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work | 01 Jan 1900