## Project_Work_Order6386070544056
Project Work Order
From 14 Aug 1986 To 01 Sep 2024
Page 3 of 3
Total Records: 10111 Records 10001 To 10111
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
NEPTUNE TRION EXP | 347 | 0 | 06 Jul 2024 | Shree Ram Fabrication | TOWER A TERRACE FABRICATION WORK | SUPPLY & INSTALLATION CHARGES OF ACP SHEET FIXING (SQFT) | SQFT | 180 | 260 | 46800 | 8424 | 55224 | 5 | 0 | 0 | 0 | 0 | 180 | 0 | Site : Neptune Trion Agency : SHREE RAM FABRICATION Tower & Floor : As Mentioned Below Tower A ( Terrace Floor ) Tower B ( Terrace Floor ) Tower C ( Terrace Floor ) Labour Name in Kanix : As Mentioned Below SUPPLY AND INSTALLATION CHARGES OF ACP SHEET FIXING Qty : As Mentioned Below Tower A - 180 Sq Ft Tower B - 360 Sq Ft Tower C - 180 Sq Ft Rate (Basic rate) : As Mentioned Below SUPPLY AND INSTALLATION CHARGES OF ACP SHEET FIXING - 260 Rs/Sqft Unit of Measurement : Sqft Purpose of Work : Duct Covering Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 347 | 0 | 06 Jul 2024 | Shree Ram Fabrication | TOWER C TERRACE FABRICATION WORK | SUPPLY & INSTALLATION CHARGES OF ACP SHEET FIXING (SQFT) | SQFT | 180 | 260 | 46800 | 8424 | 55224 | 5 | 0 | 0 | 0 | 0 | 180 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 347 | 0 | 06 Jul 2024 | Shree Ram Fabrication | TOWER B TERRACE FABRICATION WORK | SUPPLY & INSTALLATION CHARGES OF ACP SHEET FIXING (SQFT) | SQFT | 360 | 260 | 93600 | 16848 | 110448 | 5 | 0 | 0 | 0 | 0 | 360 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 1ST FLOOR ELECTRICAL WORK | LABOR FOR WIRING OF 15A SWITCH SOCKET | POINT | 2 | 200 | 400 | 0 | 400 | 5 | 2 | 400 | 0 | 400 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 2ND FLOOR ELECTRIC WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 45 | 180 | 8100 | 0 | 8100 | 5 | 45 | 8100 | 0 | 8100 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER A 1ST FLOOR ELECTRICAL WORK | LABOR FOR WIRING OF 15A SWITCH SOCKET | POINT | 2 | 200 | 400 | 0 | 400 | 5 | 2 | 400 | 0 | 400 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C GROUND FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 10 | 180 | 1800 | 0 | 1800 | 5 | 0 | 0 | 0 | 0 | 10 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 2ND FLOOR ELECTRIC WORK | LABOR FOR 1.5SQ MM CIRCUIT | RMT | 60 | 15 | 900 | 0 | 900 | 5 | 60 | 900 | 0 | 900 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER A 1ST FLOOR ELECTRICAL WORK | LABOR FOR 1.5SQ MM CIRCUIT | RMT | 60 | 15 | 900 | 0 | 900 | 5 | 60 | 900 | 0 | 900 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER A 1ST FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 40 | 180 | 7200 | 0 | 7200 | 5 | 40 | 7200 | 0 | 7200 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER B GROUND FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 10 | 180 | 1800 | 0 | 1800 | 5 | 10 | 1800 | 0 | 1800 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER B 2ND FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 3 | 180 | 540 | 0 | 540 | 5 | 3 | 540 | 0 | 540 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER A GROUND FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 10 | 180 | 1800 | 0 | 1800 | 5 | 10 | 1800 | 0 | 1800 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 1ST FLOOR ELECTRICAL WORK | LABOR FOR 1.5SQ MM CIRCUIT | RMT | 60 | 15 | 900 | 0 | 900 | 5 | 60 | 900 | 0 | 900 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 1ST FLOOR ELECTRICAL WORK | LABOUR FOR 2.5SQ MM CIRCUIT | RMT | 40 | 18 | 720 | 0 | 720 | 5 | 40 | 720 | 0 | 720 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 2ND FLOOR ELECTRIC WORK | LABOUR FOR 2.5SQ MM CIRCUIT | RMT | 40 | 18 | 720 | 0 | 720 | 5 | 40 | 720 | 0 | 720 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 1ST FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 45 | 180 | 8100 | 0 | 8100 | 5 | 39 | 7020 | 0 | 7020 | 6 | 1080 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 86.6667
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER B 1ST FLOOR ELECTRICAL WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 3 | 180 | 540 | 0 | 540 | 5 | 3 | 540 | 0 | 540 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER A 2ND FLOOR ELECTRIC WORK | LABOUR FOR LIGHT POINT (NOS) | NOS | 3 | 180 | 540 | 0 | 540 | 5 | 3 | 540 | 0 | 540 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER C 2ND FLOOR ELECTRIC WORK | LABOR FOR WIRING OF 15A SWITCH SOCKET | POINT | 2 | 200 | 400 | 0 | 400 | 5 | 2 | 400 | 0 | 400 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 348 | 0 | 11 Jul 2024 | Ghanchi Imranbhai Gulamhusen | TOWER A 1ST FLOOR ELECTRICAL WORK | LABOUR FOR 2.5SQ MM CIRCUIT | RMT | 40 | 18 | 720 | 0 | 720 | 5 | 40 | 720 | 0 | 720 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 349 | 0 | 16 Jul 2024 | S R PRAJAPATI | TOWER B 5TH FLOOR PLUMBING WORK | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 5 | 1200 | 6000 | 0 | 6000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 349 | 0 | 16 Jul 2024 | S R PRAJAPATI | TOWER B 6TH FLOOR PLUMBING WORK | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 16 | 1200 | 19200 | 0 | 19200 | 5 | 12 | 14400 | 0 | 14400 | 4 | 4800 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 75
NEPTUNE TRION EXP | 349 | 0 | 16 Jul 2024 | S R PRAJAPATI | TOWER B 8TH FLOOR PLUMBING WORK | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 16 | 1200 | 19200 | 0 | 19200 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 349 | 0 | 16 Jul 2024 | S R PRAJAPATI | TOWER B 9TH FLOOR PLUMBING WORK | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 16 | 1200 | 19200 | 0 | 19200 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 349 | 0 | 16 Jul 2024 | S R PRAJAPATI | TOWER B 7TH FLOOR PLUMBING WORK | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 16 | 1200 | 19200 | 0 | 19200 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 350 | 0 | 16 Jul 2024 | Goud Arbaz Rizwanmiya | TOWER B TERRACE WATERPROOFING WORK | LABOR FOR BBCC (SQFT) | SQFT | 13000 | 40 | 520000 | 0 | 520000 | 5 | 0 | 0 | 0 | 0 | 13000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 351 | 0 | 20 Jul 2024 | MAA ASHAPURA IMPERIAL | TOWER C 3RD FLOOR CARPENTRY WORK | LABOR FOR PELMET (SQFT) | SQFT | 310 | 575 | 178250 | 32085 | 210335 | 5 | 282 | 162150 | 29187 | 191337 | 28 | 18998 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 90.9677
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 13 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 10 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 2 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 7 & 8 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 22 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2nd FLOOR SHOP NO 7 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 2 | 450 | 900 | 162 | 1062 | 5 | 0 | 0 | 0 | 0 | 2 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2ND FLOOR SHOP NO 4 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 2 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 22 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2ND FLOOR SHOP NO 2 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 18 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 25 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2nd FLOOR SHOP NO 6 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2ND FLOOR SHOP NO 3 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 14 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2ND FLOOR SHOP NO 1 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 9 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 20 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 23 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOWROOM B ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 11 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 15 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 3 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 21 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 7 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 15 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 16 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOWROOM B ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 21 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 8 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 10 & 11 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 16 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOWROOM C ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOWROOM C ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 24 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 2nd FLOOR SHOP NO 5 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 12 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 4 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 19 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 23 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 18 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 9 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 4 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 1 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 17 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 14 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B 1ST FLOOR SHOP NO 12 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 3 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 5 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOP NO 17 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 5 & 6 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER B GROUND FLOOR SHOP NO 13 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C 1ST FLOOR SHOP NO 6 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOWROOM A ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A 1ST FLOOR SHOWROOM A ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER A GROUND FLOOR SHOP NO 19 & 20 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 352 | 0 | 29 Jul 2024 | Laxmi Steel Art | TOWER C GROUND FLOOR SHOP NO 1 ROLLING SHUTTER WORK | LABOR FOR SS BRACKET (NOS) | NOS | 1 | 450 | 450 | 81 | 531 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Tower and Floor : Tower/A,B,C G.F,1st & 2nd Floor Qty : As Mentioned Below Tower/A GROUND FLOOR : - 9nos 1st Floor :- 8nos 2nd Floor :- 2nos Tower/B GROUND FLOOR : - 10nos 1st Floor :- 10nos 2nd Floor :- 2nos Tower/C GROUND FLOOR : - 5nos 1st Floor :- 6nos 2nd Floor :- 2nos Rate (Basic rate) : Rs.450/- Per nos Unit of Measurement : nos Purpose of Work : As Per Architect Drawing |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | SITC OF 125 AMP 4 POLE MCCB (NOS) | NOS | 2 | 1530 | 3060 | 550.8 | 3610.8 | 3 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | 3.5C x 50 SQMM ALU. ARMOURED XLPE LT CABLE TERMINATIONS | NOS | 4 | 162 | 648 | 116.64 | 764.64 | 3 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | CHARGES FOR 3.5Cx 120 SQMM XLPE LT CABLE TERMINATION (NOS) | NOS | 4 | 215 | 860 | 154.8 | 1014.8 | 3 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | CHARGES FOR PCC PANEL (NOS) | NOS | 1 | 10800 | 10800 | 1944 | 12744 | 3 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | SITC OF 32AMP x 4 Pole MCB | NOS | 2 | 900 | 1800 | 324 | 2124 | 3 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | LABOR FOR 25X3MM COPPER FLAT (RFT) | RFT | 300 | 17.66 | 5298 | 953.64 | 6251.64 | 3 | 0 | 0 | 0 | 0 | 300 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | CHARGES FOR 5C x 16 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 1963 | 22 | 43186 | 7773.48 | 50959.48 | 3 | 0 | 0 | 0 | 0 | 1963 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | CHARGES FOR 3.5Cx120 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 232 | 38 | 8816 | 1586.88 | 10402.88 | 3 | 0 | 0 | 0 | 0 | 232 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | LABOR FOR 1C x 16 SQMM ALU. PVC INSULATED CABLE TERMINATION | NOS | 8 | 54 | 432 | 77.76 | 509.76 | 3 | 0 | 0 | 0 | 0 | 8 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | SITC OF 63 AMP 4 POLE MCB (NOS) | NOS | 1 | 900 | 900 | 162 | 1062 | 3 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | CHARGES FOR 1C x 16 SQMM ALU. PVC INSULATED CABLE (RMT) | RMT | 449 | 10 | 4490 | 808.2 | 5298.2 | 3 | 0 | 0 | 0 | 0 | 449 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | SITC OF 200 AMP 4 POLE MCCB (NOS) | NOS | 2 | 1530 | 3060 | 550.8 | 3610.8 | 3 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | LABOR FOR 5Cx16SQMM ALU. ARMOURED XLPE LT CABLE TERMINATIONS | NOS | 36 | 75 | 2700 | 486 | 3186 | 3 | 0 | 0 | 0 | 0 | 36 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 353 | 0 | 07 Aug 2024 | CHIRAG ELECTRICALS | COMMON ELECTRIC WORK | CHARGES FOR 3.5C x 50 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 217 | 32 | 6944 | 1249.92 | 8193.92 | 3 | 0 | 0 | 0 | 0 | 217 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 354 | 0 | 07 Aug 2024 | MAA ASHAPURA IMPERIAL | TOWER A GROUND FLOOR CARPENTRY WORK | LABOR FOR LIFT CABIN COVER WITH MDF SHEET | NOS | 1 | 6500 | 6500 | 1170 | 7670 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Site : Neptune Trion Agency : Maa Ashapura Imperial Tower and Floor : As Mentioned Below Tower - A/C -- GF (Front Side Lift) Labour Name in Kanix : As Mentioned Below LABOR FOR LIFT CABIN COVER WITH MDF SHEET (NOS) Qty : As Mentioned Below Tower =A (Front Side Lift) LABOR FOR LIFT CABIN COVER WITH MDF SHEET (NOS) = 1 NOS Tower =C (Front Side Lift) LABOR FOR LIFT CABIN COVER WITH MDF SHEET (NOS)) = 1 NOS Rate (Basic rate) : As Mentioned Below LABOR FOR LIFT CABIN COVER WITH MDF SHEET (NOS) = 6500 RS/NOS Unit of Measurement : NOS Purpose of Work : FOR WOODEN WORK New Work order / Revision : NEW |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 354 | 0 | 07 Aug 2024 | MAA ASHAPURA IMPERIAL | TOWER C GROUND FLOOR CARPENTRY WORK | LABOR FOR LIFT CABIN COVER WITH MDF SHEET | NOS | 1 | 6500 | 6500 | 1170 | 7670 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 355 | 0 | 12 Aug 2024 | URBAN JUNGGLE PVT LTD | TRION (I) MISC WORK | ANTI TERMITE TREATMENT (SQFT) | SQFT | 8325 | 1.9 | 15817.5 | 2847.16 | 18664.66 | 0 | 0 | 0 | 0 | 0 | 8325 | 0 | Chemical to be used Imidacloprid (Premise) 30.5% -Manufactured by Bayer Germany. This will be used in internal wall and floor junction. Chemical concentration will be 1-liter Water with 2.1 ml chemical. Chemical Concentration- 1-liter water with 2.1 ml chemical |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 356 | 0 | 12 Aug 2024 | Shameshwar infratech | TRION (I) PLUMBING WORK | LABOR FOR PLUMBING (NOS) | NOS | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 357 | 0 | 14 Aug 2024 | Bhimsinghbhai Punabhai Savaya | GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | LABOR FOR 1/2" POINT FITTING | NOS | 18 | 350 | 6300 | 1134 | 7434 | 5 | 18 | 6300 | 1134 | 7434 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 357 | 0 | 14 Aug 2024 | Bhimsinghbhai Punabhai Savaya | GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | LABOR FOR MAKING LEDGE WALL (NOS) | NOS | 4 | 1100 | 4400 | 0 | 4400 | 5 | 4 | 4400 | 0 | 4400 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 357 | 0 | 14 Aug 2024 | Bhimsinghbhai Punabhai Savaya | GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | LABOR FOR 3" SWR PIPE FITTING | RFT | 23 | 20 | 460 | 0 | 460 | 5 | 23 | 460 | 0 | 460 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 357 | 0 | 14 Aug 2024 | Bhimsinghbhai Punabhai Savaya | GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | LABOR FOR 4" SWR PIPE FITTING | RFT | 42 | 22 | 924 | 0 | 924 | 5 | 42 | 924 | 0 | 924 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 357 | 0 | 14 Aug 2024 | Bhimsinghbhai Punabhai Savaya | GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | LABOR FOR CONCIL FLUSH TANK FIXING | NOS | 4 | 1200 | 4800 | 0 | 4800 | 5 | 4 | 4800 | 0 | 4800 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 357 | 0 | 14 Aug 2024 | Bhimsinghbhai Punabhai Savaya | GF 9-13 & FF 5-20 PLUMBING WORK TEKIT | LABOR FOR 3" NAHNI-TRAP FITTING | NOS | 7 | 300 | 2100 | 378 | 2478 | 5 | 7 | 2100 | 378 | 2478 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 358 | 0 | 14 Aug 2024 | HYGIENE PEST MANAGEMENT | TRION (I) MISC WORK | LABOR FOR PIGEON NET (SQFT) | SQFT | 1125 | 20 | 22500 | 4050 | 26550 | 5 | 0 | 0 | 0 | 0 | 1125 | 0 | All Balcony and gallery area 3 years warranty |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 359 | 0 | 23 Aug 2024 | Sanjaybhai Vichhiyabhai Bhuriya | TOWER C TERRACE WATERPROOFING WORK | LABOR FOR BBCC (SQFT) | SQFT | 10000 | 37 | 370000 | 0 | 370000 | 5 | 0 | 0 | 0 | 0 | 10000 | 0 | Site : Neptune Trion Agency : Bhuriya Sanjaybhai Vichhiyabhai Labour Name in Kanix : As Mentioned Below 1) LABOR FOR BBCC (SQFT) (Misc Work -> Terrace Waterproofing) Tower and Floor : Tower C Terrace Qty : As Mentioned Below Tower C (Terrace) 1) LABOR FOR BBCC (SQFT) = 10000 Sq Ft Rate (Basic rate) : As Mentioned Below 1) LABOR FOR BBCC (SQFT) = 37 Rs / Sqft Unit of Measurement : Sqft Purpose of Work : WATER PROOFING WORK |  |  | pur.nrpl2 |  | Job Work |  |  |  | Token |  |  | 0