## Project_Work_Order6386106942555
Project Work Order
From 11 Aug 2005 To 05 Sep 2024
Page 1 of 1
Total Records: 41 Records 1 To 41
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 10TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 11TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 12TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9294.83 | 25 | 232370.75 | 41826.74 | 274197.49 | 5 | 0 | 0 | 0 | 0 | 9294.83 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 13TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 14TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 15TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9294.83 | 25 | 232370.75 | 41826.74 | 274197.49 | 5 | 0 | 0 | 0 | 0 | 9294.83 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 16TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 17TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 18TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 2ND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9294.83 | 25 | 232370.75 | 41826.74 | 274197.49 | 5 | 0 | 0 | 0 | 0 | 9294.83 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 3RD FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 4TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 5TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 6TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9294.83 | 25 | 232370.75 | 41826.74 | 274197.49 | 5 | 0 | 0 | 0 | 0 | 9294.83 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 7TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 8TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 9TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9294.83 | 25 | 232370.75 | 41826.74 | 274197.49 | 5 | 0 | 0 | 0 | 0 | 9294.83 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Floor wise external plaster work |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl4 | 19 Jul 2021 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | LOWER BASEMENT PLASTER WORK PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Lower basement o/s plaster work |  | deepak.p | pur.nrpl2 |  | Construction |  |  |  | Cancelled | pur.nrpl4 | 19 Jul 2021 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | UPPER BASEMENT PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 25 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Upper basement o/s plaster work |  | deepak.p | pur.nrpl2 |  | Construction |  |  |  | Cancelled | pur.nrpl4 | 19 Jul 2021 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 0 | 37.5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Cancelled | pur.nrpl2 | 21 Mar 2022 | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 2ND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 388.71 | 25 | 9717.75 | 1749.2 | 11466.95 | 5 | 0 | 0 | 0 | 0 | 388.71 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 6TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 388.71 | 25 | 9717.75 | 1749.2 | 11466.95 | 5 | 0 | 0 | 0 | 0 | 388.71 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 9TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 388.71 | 25 | 9717.75 | 1749.2 | 11466.95 | 5 | 0 | 0 | 0 | 0 | 388.71 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 12TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 388.71 | 25 | 9717.75 | 1749.2 | 11466.95 | 5 | 0 | 0 | 0 | 0 | 388.71 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 15TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 388.71 | 25 | 9717.75 | 1749.2 | 11466.95 | 5 | 0 | 0 | 0 | 0 | 388.71 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | GROUND FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9268.14 | 37.5 | 347555.25 | 62559.94 | 410115.19 | 5 | 0 | 0 | 0 | 0 | 9268.14 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 1ST FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9268.14 | 25 | 231703.5 | 41706.64 | 273410.14 | 5 | 0 | 0 | 0 | 0 | 9268.14 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 3RD FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 4TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 5TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 7TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 8TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 10TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 11TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 13TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 14TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 16TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 17TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 21 | 0 | 03 Mar 2021 | K K CONSTRUCTION | 18TH FLOOR PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 9160.85 | 25 | 229021.25 | 41223.82 | 270245.07 | 5 | 0 | 0 | 0 | 0 | 9160.85 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0