## Project_Work_Order6386112882096
Project Work Order
From 11 Aug 2005 To 06 Sep 2024
Page 1 of 1
Total Records: 9 Records 1 To 9
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR CIVIL WORK | DEPART LABOR | NOS | 30 | 400 | 12000 | 2160 | 14160 | 5 | 0 | 0 | 0 | 0 | 30 | 0 | DEPART LABOUR |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR CIVIL WORK | DEPART MASON | NOS | 10 | 700 | 7000 | 1260 | 8260 | 5 | 0 | 0 | 0 | 0 | 10 | 0 | DEPART MASON |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 6000 | 20 | 120000 | 21600 | 141600 | 5 | 0 | 0 | 0 | 0 | 6000 | 0 | 4.5" MASONRY WORK (SQFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 20.7105
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR 6" MASONRY WORK (SQFT) | SQFT | 1600 | 23 | 36800 | 6624 | 43424 | 5 | 0 | 0 | 0 | 0 | 1600 | 0 | 6" MASONRY WORK (SQFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 25.7494
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR 9" MASONRY WORK (SQFT) | SQFT | 4700 | 25 | 117500 | 21150 | 138650 | 5 | 0 | 0 | 0 | 0 | 4700 | 0 | 9" MASONRY WORK (SQFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 24.7432
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 27000 | 23 | 621000 | 111780 | 732780 | 5 | 0 | 0 | 0 | 0 | 27000 | 0 | INTERNAL PLASTER (SQFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR RCC COPING (RFT) | RFT | 1400 | 50 | 70000 | 12600 | 82600 | 5 | 0 | 0 | 0 | 0 | 1400 | 0 | RCC COPING (RFT) |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 60.8886
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR MASONRY WORK | LABOR FOR RCC LINTEL | RFT | 1200 | 75 | 90000 | 16200 | 106200 | 5 | 0 | 0 | 0 | 0 | 1200 | 0 | RCC LINTEL |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 6.2175
GREENWOODS ABODE | 64 | 0 | 15 Jun 2024 | DEEP CONSTRUCTION | TOWER B 1ST FLOOR CIVIL WORK | DEPART LABOR | NOS | 40 | 400 | 16000 | 2880 | 18880 | 5 | 0 | 0 | 0 | 0 | 40 | 0 | For misc. works |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0