## Project_Work_Order6386124482782
Project Work Order
From 29 Aug 2018 To 07 Sep 2024
Page 1 of 1
Total Records: 66 Records 1 To 66
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1702 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 54.42 | 1800 | 97956 | 17632.08 | 115588.08 | 5 | 23.874 | 42973.2 | 7735.18 | 50708.38 | 30.546 | 64879.7 | SS GLASS RAILING 304-BALCONY -AS PER DRAWINGLOW HEIGHT (600MM)- BEDROOM -AS PER DRAWING OPTION -1(1)S.S.BLUSTER 80MMX8 MM (2) 12MM TOUGHENED GLASS (3) 50MM PIPE TOP (4) BASE PLATE 100X150X10MM |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 43.8699
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1701 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 54.42 | 1800 | 97956 | 17632.08 | 115588.08 | 5 | 23.928 | 43070.4 | 7752.68 | 50823.08 | 30.492 | 64765 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 43.9691
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1602 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 52.25 | 1800 | 94050 | 16929 | 110979 | 5 | 31.35 | 56430 | 10157.4 | 66587.4 | 20.9 | 44391.6 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 60
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1601 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 52.25 | 1800 | 94050 | 16929 | 110979 | 5 | 31.35 | 56430 | 10157.4 | 66587.4 | 20.9 | 44391.6 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 60
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1502 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 50.42 | 1800 | 90756 | 16336.08 | 107092.08 | 5 | 30.246 | 54442.8 | 9799.7 | 64242.5 | 20.174 | 42849.58 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 59.9881
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1501 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 50.42 | 1800 | 90756 | 16336.08 | 107092.08 | 5 | 30.246 | 54442.8 | 9799.7 | 64242.5 | 20.174 | 42849.58 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 59.9881
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1402 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 47.92 | 1800 | 86256 | 15526.08 | 101782.08 | 5 | 28.398 | 51116.4 | 9200.96 | 60317.36 | 19.522 | 41464.72 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 59.2613
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1401 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 47.92 | 1800 | 86256 | 15526.08 | 101782.08 | 5 | 28.249 | 50848.2 | 9152.68 | 60000.88 | 19.671 | 41781.2 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 58.9503
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1302 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 62.92 | 1800 | 113256 | 20386.08 | 133642.08 | 5 | 28.5 | 51300 | 9234 | 60534 | 34.42 | 73108.08 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 45.2956
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1301 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 62.92 | 1800 | 113256 | 20386.08 | 133642.08 | 5 | 28.608 | 51494.4 | 9269 | 60763.4 | 34.312 | 72878.68 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 45.4673
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1202 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 39.42 | 1800 | 70956 | 12772.08 | 83728.08 | 5 | 39.42 | 70956 | 12772.08 | 83728.08 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1201 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 39.42 | 1800 | 70956 | 12772.08 | 83728.08 | 5 | 39.42 | 70956 | 12772.08 | 83728.08 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1102 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 38.58 | 1800 | 69444 | 12499.92 | 81943.92 | 5 | 0 | 0 | 0 | 0 | 38.58 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1101 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 38.58 | 1800 | 69444 | 12499.92 | 81943.92 | 5 | 0 | 0 | 0 | 0 | 38.58 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1002 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 22.548 | 40586.4 | 7305.56 | 47891.96 | 15.032 | 31927.96 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 60
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1001 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.578 | 67640.4 | 12175.28 | 79815.68 | 0.002 | 4.24 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.9947
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 902 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 22.5 | 40500 | 7290 | 47790 | 15.08 | 32029.92 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 59.8723
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 901 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 13.698 | 24656.4 | 4438.16 | 29094.56 | 23.882 | 50725.36 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 36.4502
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 802 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 22.548 | 40586.4 | 7305.56 | 47891.96 | 15.032 | 31927.96 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 60
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 801 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 34.07 | 61326 | 11038.68 | 72364.68 | 3.51 | 7455.24 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 90.6599
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 702 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 62.92 | 1800 | 113256 | 20386.08 | 133642.08 | 5 | 62.918 | 113252.4 | 20385.44 | 133637.84 | 0.002 | 4.24 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.9968
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 701 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 62.92 | 1800 | 113256 | 20386.08 | 133642.08 | 5 | 62.92 | 113256 | 20386.08 | 133642.08 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 602 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 601 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 502 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 501 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 402 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 23.7 | 42660 | 7678.8 | 50338.8 | 13.88 | 29481.12 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 63.0655
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 401 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 302 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 23.7 | 42660 | 7678.8 | 50338.8 | 13.88 | 29481.12 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 63.0655
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 301 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 23.7 | 42660 | 7678.8 | 50338.8 | 13.88 | 29481.12 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 63.0655
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 202 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 201 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 37.58 | 1800 | 67644 | 12175.92 | 79819.92 | 5 | 37.58 | 67644 | 12175.92 | 79819.92 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 102 RAILING WORK | LABOR FOR BALCONY AND KITCHEN RAILING | RFT | 0 | 1800 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Cancelled | pur.nrpl2 | 16 Dec 2023 | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1702 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1701 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1602 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1601 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1502 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1501 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1402 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1401 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1302 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1301 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1202 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1201 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1102 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1101 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1002 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 1001 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 902 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 901 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 802 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 801 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 702 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 701 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 0 | 0 | 0 | 0 | 43 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 602 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 601 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 502 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 501 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 402 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 401 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 302 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 41.5 | 34652.5 | 6237.46 | 40889.96 | 1.5 | 1477.94 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.5116
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 301 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 202 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42.7 | 35654.5 | 6417.82 | 42072.32 | 0.3 | 295.58 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.3023
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 201 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 43 | 835 | 35905 | 6462.9 | 42367.9 | 5 | 42 | 35070 | 6312.6 | 41382.6 | 1 | 985.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.6744
GREENWOOD ASPIRE EXP | 235 | 0 | 03 Dec 2022 | KHUSHI ENTERPRISE | B 102 RAILING WORK | LABOR FOR BEDROOM RAILING | RFT | 0 | 835 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Cancelled | pur.nrpl2 | 16 Dec 2023 | 0