## Project_Work_Order6386277845316
Project Work Order
From 18 Aug 2005 To 25 Sep 2024
Page 1 of 1
Total Records: 66 Records 1 To 66
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 77 | 0 | 20 Feb 2021 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 38958.5 | 4.75 | 185052.88 | 33309.52 | 218362.4 | 5 | 38958.5 | 185052.88 | 33309.52 | 218362.4 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 77 | 0 | 20 Feb 2021 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 33564.5 | 2 | 67129 | 12083.22 | 79212.22 | 5 | 33564.5 | 67129 | 12083.22 | 79212.22 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 77 | 0 | 20 Feb 2021 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 33564.5 | 17.5 | 587378.75 | 105728.18 | 693106.93 | 5 | 33564.5 | 587378.75 | 105728.18 | 693106.93 | 0 | 0 | Layer I |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 77 | 0 | 20 Feb 2021 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 33564.5 | 17.5 | 587378.75 | 105728.18 | 693106.93 | 5 | 33564.5 | 587378.75 | 105728.18 | 693106.93 | 0 | 0 | Layer II |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 77 | 0 | 20 Feb 2021 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOR FOR PCC (SQFT) | SQFT | 5641.86 | 7 | 39493.02 | 7108.74 | 46601.76 | 5 | 5641.86 | 39493.02 | 7108.74 | 46601.76 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 413 | 0 | 21 Mar 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON CIVIL WORK TRIMIX SMOOTH FINISH | LABOR FOR PCC (SQFT) | SQFT | 550 | 4 | 2200 | 396 | 2596 | 5 | 501.915 | 2007.66 | 361.38 | 2369.04 | 48.085 | 226.96 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 91.2573
GREENWOOD ASPIRE EXP | 413 | 0 | 21 Mar 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON CIVIL WORK TRIMIX SMOOTH FINISH | LABOUR FOR DRESSING WORK (SQFT) | SQFT | 2000 | 2.5 | 5000 | 900 | 5900 | 5 | 1954.047 | 4885.12 | 879.32 | 5764.44 | 45.953 | 135.56 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 97.7024
GREENWOOD ASPIRE EXP | 413 | 0 | 21 Mar 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON CIVIL WORK TRIMIX SMOOTH FINISH | LABOUR FOR TRIMIX (SQFT) | SQFT | 2000 | 9 | 18000 | 3240 | 21240 | 5 | 1928.28 | 17354.52 | 3123.82 | 20478.34 | 71.72 | 761.66 | Basement TRIMIX Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.414
GREENWOOD ASPIRE EXP | 413 | 0 | 21 Mar 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON CIVIL WORK TRIMIX SMOOTH FINISH | LABOR FOR STEEL BINDING (SQFT) | SQFT | 2000 | 2.1 | 4200 | 756 | 4956 | 5 | 1928.28 | 4049.39 | 728.9 | 4778.29 | 71.72 | 177.71 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.414
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 2000 | 2.1 | 4200 | 756 | 4956 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 2760 | 2.1 | 5796 | 1043.28 | 6839.28 | 5 | 0 | 0 | 0 | 0 | 2760 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 2000 | 2.1 | 4200 | 756 | 4956 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 3809.2 | 9 | 34282.8 | 6170.9 | 40453.7 | 5 | 3016.56 | 27149.04 | 4886.82 | 32035.86 | 792.64 | 8417.84 | RCC/PCC 125 mm thick with SYSTEM 'TRIMIX' RMC free supply by customer Fixing ISMC Channels in required line and level for side shuttering and guide for double beam surface vibrator to construct 125 mm thick PCC floor on prepared and fairly leveled sub-base in required levels. Laying PCC for floor concrete in a thickness of 125 mm and level precisely by using double beam surface (screed) vibrator. The leveled concrete shall be finished by using 'TRIMIX' system of power floating and power trowelling, making palas for clients to cure for 07 days.etc. Labour name LABOUR FOR TRIMIX (SQFT) |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 79.1914
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 3619.98 | 9 | 32579.82 | 5864.36 | 38444.18 | 5 | 1756.189 | 15805.7 | 2845.02 | 18650.72 | 1863.791 | 19793.46 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 48.5138
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 1308.32 | 9 | 11774.88 | 2119.48 | 13894.36 | 5 | 1156.189 | 10405.7 | 1873.02 | 12278.72 | 152.131 | 1615.64 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 88.372
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 4100.86 | 9 | 36907.74 | 6643.4 | 43551.14 | 5 | 2185.559 | 19670.03 | 3540.6 | 23210.63 | 1915.301 | 20340.51 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 53.2951
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 4547.12 | 9 | 40924.08 | 7366.34 | 48290.42 | 5 | 0 | 0 | 0 | 0 | 4547.12 | 0 | As per Latest new revised duly signed new drawings Add WMM & Trimix Quantity in WO No. 417 Sahas Road & Infrastructure |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 5597.41 | 9 | 50376.69 | 9067.8 | 59444.49 | 5 | 0 | 0 | 0 | 0 | 5597.41 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 3657.8 | 9 | 32920.2 | 5925.64 | 38845.84 | 5 | 0 | 0 | 0 | 0 | 3657.8 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 2000 | 9 | 18000 | 3240 | 21240 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 2760 | 9 | 24840 | 4471.2 | 29311.2 | 5 | 0 | 0 | 0 | 0 | 2760 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOUR FOR TRIMIX (SQFT) | SQFT | 2000 | 9 | 18000 | 3240 | 21240 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOR FOR PCC (SQFT) | SQFT | 3809.2 | 4 | 15236.8 | 2742.62 | 17979.42 | 5 | 3016.019 | 12064.08 | 2171.54 | 14235.62 | 793.181 | 3743.8 | PCC 100mm with free supply of RMC at site LABOR FOR PCC (SQFT) |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 79.1772
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOR FOR PCC (SQFT) | SQFT | 3619.98 | 4 | 14479.92 | 2606.38 | 17086.3 | 5 | 3016.019 | 12064.08 | 2171.54 | 14235.62 | 603.961 | 2850.68 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 83.3159
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOR FOR PCC (SQFT) | SQFT | 1308.32 | 4 | 5233.28 | 942 | 6175.28 | 5 | 0 | 0 | 0 | 0 | 1308.32 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOR FOR PCC (SQFT) | SQFT | 4100.86 | 4 | 16403.44 | 2952.62 | 19356.06 | 5 | 3016.019 | 12064.08 | 2171.54 | 14235.62 | 1084.841 | 5120.44 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 73.546
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 3809.2 | 2.1 | 7999.32 | 1439.88 | 9439.2 | 5 | 3809.2 | 7999.32 | 1439.88 | 9439.2 | 0 | 0 | Reinforcement of 8mm steel 300mm c/c with free steel supplied by customer Labour name LABOR FOR STEEL BINDING |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 3619.98 | 2.1 | 7601.96 | 1368.36 | 8970.32 | 5 | 859.367 | 1804.67 | 324.84 | 2129.51 | 2760.613 | 6840.81 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 23.7396
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 1308.32 | 2.1 | 2747.47 | 494.54 | 3242.01 | 5 | 0 | 0 | 0 | 0 | 1308.32 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 4100.86 | 2.1 | 8611.81 | 1550.12 | 10161.93 | 5 | 3016.56 | 6334.78 | 1140.26 | 7475.04 | 1084.3 | 2686.89 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 73.5592
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 4547.12 | 2.1 | 9548.95 | 1718.82 | 11267.77 | 5 | 0 | 0 | 0 | 0 | 4547.12 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 5597.41 | 2.1 | 11754.56 | 2115.82 | 13870.38 | 5 | 0 | 0 | 0 | 0 | 5597.41 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOR FOR STEEL BINDING (SQFT) | SQFT | 3657.8 | 2.1 | 7681.38 | 1382.64 | 9064.02 | 5 | 429.37 | 901.68 | 162.3 | 1063.98 | 3228.43 | 8000.04 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 11.7385
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 4547.12 | 6 | 27282.72 | 4910.88 | 32193.6 | 5 | 4547.12 | 27282.72 | 4910.88 | 32193.6 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 5597.41 | 6 | 33584.46 | 6045.2 | 39629.66 | 5 | 5597.41 | 33584.46 | 6045.2 | 39629.66 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 3657.8 | 6 | 21946.8 | 3950.42 | 25897.22 | 5 | 3657.8 | 21946.8 | 3950.42 | 25897.22 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 3809.2 | 6 | 22855.2 | 4113.94 | 26969.14 | 5 | 0 | 0 | 0 | 0 | 3809.2 | 0 | Earthwork - Excavation, Mobilisation and Filling work with Jcb, tractors at site upto 150mm thickness. (excess thickness shall be charged proportionately). Dressing & Levelling of Earth with Labour or required means Labour name LABOR FOR EXCAVATION (SQFT) |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 3619.98 | 6 | 21719.88 | 3909.58 | 25629.46 | 5 | 0 | 0 | 0 | 0 | 3619.98 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 1308.32 | 6 | 7849.92 | 1412.98 | 9262.9 | 5 | 759.34 | 4556.04 | 820.08 | 5376.12 | 548.98 | 3886.78 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 58.0393
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOR FOR EXCAVATION (SQFT) | SQFT | 4100.86 | 6 | 24605.16 | 4428.92 | 29034.08 | 5 | 0 | 0 | 0 | 0 | 4100.86 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 7618.4 | 18 | 137131.2 | 24683.62 | 161814.82 | 5 | 7618.4 | 137131.2 | 24683.62 | 161814.82 | 0 | 0 | WMM : Layer-1. Big Metal WMM (WET MIX MACADAM) 100 mm thick(compacted) 'VIBRO-COMPACTED' Layer. Shall be done on existing ready laye without any change if gradient Laying WMM in a thickness of 125 mm in proper line, level, grade and camber, compacting the same with vibro-roller etc. complete. Labour name LABOUR FOR WMM WMM : Layer-2. Laying WMM in a thickness of 125 mm in proper line, level, grade and camber, compacting the same with vibro-roller etc. complete. INFRA Labour name LABOUR FOR WMM |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 9094.24 | 18 | 163696.32 | 29465.34 | 193161.66 | 5 | 9094.24 | 163696.32 | 29465.34 | 193161.66 | 0 | 0 | As per Latest new revised duly signed new drawings Add WMM & Trimix Quantity in WO No. 417 Sahas Road & Infrastructure |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 11194.82 | 18 | 201506.76 | 36271.22 | 237777.98 | 5 | 11194.82 | 201506.76 | 36271.22 | 237777.98 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 7315.6 | 18 | 131680.8 | 23702.54 | 155383.34 | 5 | 5678.632 | 102215.38 | 18398.76 | 120614.14 | 1636.968 | 34769.2 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 77.6236
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 3000 | 18 | 54000 | 9720 | 63720 | 5 | 1840.644 | 33131.59 | 5963.68 | 39095.27 | 1159.356 | 24624.73 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.3548
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOUR FOR WMM (SQFT) | SQFT | 2000 | 18 | 36000 | 6480 | 42480 | 5 | 1840.64 | 33131.52 | 5963.68 | 39095.2 | 159.36 | 3384.8 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 92.032
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 4547.12 | 2.25 | 10231.02 | 1841.58 | 12072.6 | 5 | 1723.31 | 3877.45 | 697.94 | 4575.39 | 2823.81 | 7497.21 | As per Latest new revised duly signed new drawings Add WMM & Trimix Quantity in WO No. 417 Sahas Road & Infrastructure |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 37.8989
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 5597.41 | 2.25 | 12594.17 | 2266.96 | 14861.13 | 5 | 0 | 0 | 0 | 0 | 5597.41 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 3657.8 | 2.25 | 8230.05 | 1481.4 | 9711.45 | 5 | 0 | 0 | 0 | 0 | 3657.8 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 3809.2 | 2.25 | 8570.7 | 1542.72 | 10113.42 | 5 | 3809.2 | 8570.7 | 1542.72 | 10113.42 | 0 | 0 | Laying Quarry Dust in proper line, level, grade and camber, compacting the same with vibro-roller etc. Labour name LABOUR FOR QUARRY DUST |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 3619.98 | 2.25 | 8144.96 | 1466.1 | 9611.06 | 5 | 3619.98 | 8144.96 | 1466.1 | 9611.06 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 1308.32 | 2.25 | 2943.72 | 529.86 | 3473.58 | 5 | 1308.32 | 2943.72 | 529.86 | 3473.58 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOUR FOR QUARRY DUST (SQFT) | SQFT | 4100.86 | 2.25 | 9226.94 | 1660.84 | 10887.78 | 5 | 4100.86 | 9226.94 | 1660.84 | 10887.78 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | COMMON ROAD WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 3809.2 | 1.75 | 6666.1 | 1199.9 | 7866 | 5 | 0 | 0 | 0 | 0 | 3809.2 | 0 | Groove Cutting with 'Diamond-Blade Cutter' for controlling effect of temperature stresses on concrete road with bitumen filling Labour name LABOR FOR GROOVE CUTTING WITH SQFT |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 3619.98 | 1.75 | 6334.97 | 1140.3 | 7475.27 | 5 | 0 | 0 | 0 | 0 | 3619.98 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 1308.32 | 1.75 | 2289.56 | 412.12 | 2701.68 | 5 | 0 | 0 | 0 | 0 | 1308.32 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 4100.86 | 1.75 | 7176.51 | 1291.78 | 8468.29 | 5 | 3016.56 | 5278.98 | 950.22 | 6229.2 | 1084.3 | 2239.09 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 73.5592
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 4547.12 | 1.75 | 7957.46 | 1432.34 | 9389.8 | 5 | 429.37 | 751.4 | 135.26 | 886.66 | 4117.75 | 8503.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 9.4427
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 5597.41 | 1.75 | 9795.47 | 1763.18 | 11558.65 | 5 | 0 | 0 | 0 | 0 | 5597.41 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 3657.8 | 1.75 | 6401.15 | 1152.2 | 7553.35 | 5 | 0 | 0 | 0 | 0 | 3657.8 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR TRIMIX WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 2000 | 1.75 | 3500 | 630 | 4130 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR TRIMIX WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 2760 | 1.75 | 4830 | 869.4 | 5699.4 | 5 | 0 | 0 | 0 | 0 | 2760 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR TRIMIX WORK | LABOR FOR GROOVE CUTTING WITH BITUMEN FILLING (SQFT) | SQFT | 2000 | 1.75 | 3500 | 630 | 4130 | 5 | 0 | 0 | 0 | 0 | 2000 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER A GROUND FLOOR ROAD WORK | LABOR FOR PCC (SQFT) | SQFT | 4547.12 | 4 | 18188.48 | 3273.92 | 21462.4 | 5 | 0 | 0 | 0 | 0 | 4547.12 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER B GROUND FLOOR ROAD WORK | LABOR FOR PCC (SQFT) | SQFT | 5597.41 | 4 | 22389.64 | 4030.14 | 26419.78 | 5 | 0 | 0 | 0 | 0 | 5597.41 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 417 | 0 | 04 Apr 2024 | Sahas Roads & Infrastructure Pvt.Ltd | TOWER C GROUND FLOOR ROAD WORK | LABOR FOR PCC (SQFT) | SQFT | 3657.8 | 4 | 14631.2 | 2633.62 | 17264.82 | 5 | 0 | 0 | 0 | 0 | 3657.8 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0