## Project_Work_Order6386346438002
Project Work Order
From 27 Sep 2013 To 03 Oct 2024
Page 1 of 1
Total Records: 19 Records 1 To 19
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR 2.6 TR CEILING MOUNTED 4 WAY CASSETTE UNIT | NOS | 18 | 4000 | 72000 | 12960 | 84960 | 5 | 0 | 0 | 0 | 0 | 18 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR 3.3 TR CEILING MOUNTED 4 WAY CASSETTE UNIT | NOS | 23 | 4000 | 92000 | 16560 | 108560 | 5 | 0 | 0 | 0 | 0 | 23 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR 4.13 TR CEILING MOUNTED 4 WAY CASSETTE UNIT | NOS | 28 | 4000 | 112000 | 20160 | 132160 | 5 | 0 | 0 | 0 | 0 | 28 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR OUTDOOR CONDENSING OF 14 HP CAPACITY WITH R 410 | NOS | 1 | 15400 | 15400 | 2772 | 18172 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR OUTDOOR CONDENSING OF 20 HP CAPACITY WITH R 410 | NOS | 3 | 22000 | 66000 | 11880 | 77880 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR OUTDOOR CONDENSING OF 40 HP CAPACITY WITH R 410 | NOS | 1 | 44000 | 44000 | 7920 | 51920 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR OUTDOOR CONDENSING OF 60 HP CAPACITY WITH R 410 | NOS | 2 | 66000 | 132000 | 23760 | 155760 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR OUTDOOR UNIT BRANCH KIT (NOS) | NOS | 4 | 1000 | 4000 | 720 | 4720 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | INSTALLATION CHARGES OF REFNET (NOS) | NOS | 64 | 750 | 48000 | 8640 | 56640 | 5 | 64 | 48000 | 8640 | 56640 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR M.S. STRUCTURAL WORK (KG) | KG | 1000 | 25 | 25000 | 4500 | 29500 | 5 | 965.88 | 24147 | 4346.46 | 28493.46 | 34.12 | 1006.54 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 96.588
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR PIPING WORK FOR AC (RMT) | RMT | 990 | 150 | 148500 | 26730 | 175230 | 5 | 990 | 148500 | 26730 | 175230 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR UPVC DRAIN PIPE WITH INSULATION (RMT) | RMT | 700 | 25 | 17500 | 3150 | 20650 | 5 | 700 | 17500 | 3150 | 20650 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | LABOR FOR 1.5 SQMM 2 CORE SHIELDED CONTROL CABLE | RMT | 1500 | 25 | 37500 | 6750 | 44250 | 5 | 1500 | 37500 | 6750 | 44250 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | TESTING & COMMISSIONING CHARGES OF 14HP VRF SYSTEM | NOS | 1 | 2000 | 2000 | 360 | 2360 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | TESTING & COMMISSIONING CHARGES OF 20HP VRF SYSTEM | NOS | 11 | 727.27 | 7999.97 | 1440 | 9439.97 | 5 | 0 | 0 | 0 | 0 | 11 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR 90° ODU EXHAUST AIR COWL (NOS) | NOS | 0 | 1000 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | pur.nrpl1 |  | Construction |  |  |  | Cancelled | pur.nrpl1 | 28 Dec 2023 | 0
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | LABOR FOR RE-WORK OF EXISTING WORK | LOT | 1 | 70000 | 70000 | 12600 | 82600 | 5 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR 300 x 50 GI PERFORATED CABLE TRAY (RMT) | RMT | 700 | 110 | 77000 | 13860 | 90860 | 5 | 700 | 77000 | 13860 | 90860 | 0 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
NEPTUNE TRION EXP | 296 | 0 | 28 Dec 2023 | LYNX COMMUNICATION SYSTEM PVT LTD | GF 9-13 & FF 5-20 AC WORK TEKIT | CHARGES FOR 90° ODU EXHAUST AIR COWL (NOS) | NOS | 12 | 1000 | 12000 | 2160 | 14160 | 5 | 0 | 0 | 0 | 0 | 12 | 0 |  |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0