## Project_Work_Order6386423778770
Project Work Order
From 07 Sep 2006 To 12 Oct 2024
Page 1 of 1
Total Records: 159 Records 1 To 159
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR FLOORING WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 140 | 17 | 2380 | 0 | 2380 | 5 | 127.89 | 2174.13 | 0 | 2174.13 | 12.11 | 205.87 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 91.35
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 4TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 5TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | GROUND FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | GROUND FLOOR SHOP NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | GROUND FLOOR SHOP NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | GROUND FLOOR SHOP NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | GROUND FLOOR SHOP NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 1ST FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 2ND FLOOR FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 1ST FLOOR SHOP NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 1ST FLOOR SHOP NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 1ST FLOOR SHOP NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 1ST FLOOR SHOP NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 2ND FLOOR SHOP NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 2ND FLOOR SHOP NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 2ND FLOOR SHOP NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 2ND FLOOR SHOP NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 34.51 | 586.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.992
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 35.51 | 603.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.3236
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 35.51 | 603.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.3236
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 34.51 | 586.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.992
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 34.51 | 586.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.992
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 35.51 | 603.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.3236
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 35.51 | 603.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.3236
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 3RD FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.74 | 998.58 | 0 | 998.58 | 34.51 | 586.67 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.992
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR FLOORING WORK FLOORING & DEDO | LABOR FOR DHAR POLISH (RFT) | RFT | 25.03 | 17 | 425.51 | 0 | 425.51 | 5 | 0 | 0 | 0 | 0 | 25.03 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 15TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 01 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 02 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 03 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 05 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 06 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 35.99 | 611.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 61.8143
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 07 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 94.25 | 17 | 1602.25 | 0 | 1602.25 | 5 | 0 | 0 | 0 | 0 | 94.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 7TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 8TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 9TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 10TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 11TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 12TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 13TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 14TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 16TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 17TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 18TH FLOOR OFFICE NO 08 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 0 | 0 | 0 | 0 | 93.25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
NEPTUNE OBELISK EXP | 62 | 0 | 05 Jan 2024 | Vikas Kumar B Prajapati | 6TH FLOOR OFFICE NO 04 FLOORING & DEDO WORK | LABOR FOR DHAR POLISH (RFT) | RFT | 93.25 | 17 | 1585.25 | 0 | 1585.25 | 5 | 58.26 | 990.42 | 0 | 990.42 | 34.99 | 594.83 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 62.4772