## Project_Work_Order6386467775621
Project Work Order
From 16 Sep 2014 To 17 Oct 2024
Page 1 of 1
Total Records: 2 Records 1 To 2
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOODS SERENITY | 220 | 0 | 30 Jul 2024 | Devarshi enterprise | VILLA A34 PAINT WORK | LABOR FOR PAINT WORK (LS) | LUMSUM | 1 | 325000 | 325000 | 58500 | 383500 | 5 | 0.9 | 292500 | 52650 | 345150 | 0.1 | 38350 | PAINT WORK (LS) - 325000/- FOR STANDARD WORK, OTHER THAN STANDARD WORK SHALL BE BILLED AS PER ATTACHED RATES. |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 90
GREENWOODS SERENITY | 220 | 0 | 30 Jul 2024 | Devarshi enterprise | VILLA A21-A22 PAINT WORK | LABOR FOR PAINT WORK (LS) | LUMSUM | 1 | 325000 | 325000 | 58500 | 383500 | 5 | 0.4 | 130000 | 23400 | 153400 | 0.6 | 230100 | PAINT WORK (LS) - 325000/- FOR STANDARD WORK, OTHER THAN STANDARD WORK SHALL BE BILLED AS PER ATTACHED RATES. |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 40