## Project_Work_Order6386495061049
Project Work Order
From 03 Sep 2020 To 20 Oct 2024
Page 1 of 1
Total Records: 60 Records 1 To 60
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4149.45 | 25 | 103736.25 | 18672.52 | 122408.77 | 5 | 3099.245 | 77481.13 | 13946.6 | 91427.73 | 1050.205 | 30981.05 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6905
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 2ND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 1ST FLOOR COMMON PAINT & COLOR REWORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 1526.08 | 38152 | 6867.36 | 45019.36 | 1448.96 | 42744.32 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3022.35 | 25 | 75558.75 | 13600.58 | 89159.33 | 5 | 2538.995 | 63474.88 | 11425.48 | 74900.36 | 483.355 | 14258.98 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.0073
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2408.195 | 60204.88 | 10836.88 | 71041.76 | 352.555 | 10400.38 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 87.2297
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2408.195 | 60204.88 | 10836.88 | 71041.76 | 352.555 | 10400.38 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 87.2297
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 2ND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2657.105 | 66427.63 | 11956.98 | 78384.61 | 103.645 | 3057.53 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.2458
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2975.04 | 25 | 74376 | 13387.68 | 87763.68 | 5 | 2515.34 | 62883.5 | 11319.04 | 74202.54 | 459.7 | 13561.14 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.5481
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3022.35 | 25 | 75558.75 | 13600.58 | 89159.33 | 5 | 2538.995 | 63474.88 | 11425.48 | 74900.36 | 483.355 | 14258.98 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 84.0073
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2408.195 | 60204.88 | 10836.88 | 71041.76 | 352.555 | 10400.38 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 87.2297
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2408.195 | 60204.88 | 10836.88 | 71041.76 | 352.555 | 10400.38 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 87.2297
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2408.195 | 60204.88 | 10836.88 | 71041.76 | 352.555 | 10400.38 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 87.2297
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4149.45 | 25 | 103736.25 | 18672.52 | 122408.77 | 5 | 4148.894 | 103722.35 | 18670.02 | 122392.37 | 0.556 | 16.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.9866
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 4160.93 | 104023.25 | 18724.2 | 122747.45 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4149.45 | 25 | 103736.25 | 18672.52 | 122408.77 | 5 | 4148.894 | 103722.35 | 18670.02 | 122392.37 | 0.556 | 16.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.9866
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 2ND FLOORCOMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4149.45 | 25 | 103736.25 | 18672.52 | 122408.77 | 5 | 3099.245 | 77481.13 | 13946.6 | 91427.73 | 1050.205 | 30981.05 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6905
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 1ST FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.75 | 25 | 93218.75 | 16779.38 | 109998.13 | 5 | 3728.264 | 93206.6 | 16777.2 | 109983.8 | 0.486 | 14.33 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 99.987
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 1ST FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 2760.75 | 25 | 69018.75 | 12423.38 | 81442.13 | 5 | 2446.755 | 61168.88 | 11010.4 | 72179.28 | 313.995 | 9262.86 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 88.6265
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A TERRACE COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3133.5 | 25 | 78337.5 | 14100.76 | 92438.26 | 5 | 2594.14 | 64853.5 | 11673.64 | 76527.14 | 539.36 | 15911.12 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 82.7873
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B TERRACE COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 1917.17 | 25 | 47929.25 | 8627.26 | 56556.51 | 5 | 1917.17 | 47929.25 | 8627.28 | 56556.53 | 0 | -0.02 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C TERRACE COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3133.5 | 25 | 78337.5 | 14100.76 | 92438.26 | 5 | 3133.5 | 78337.5 | 14100.76 | 92438.26 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 4160.93 | 25 | 104023.25 | 18724.18 | 122747.43 | 5 | 3107.855 | 77696.38 | 13985.36 | 91681.74 | 1053.075 | 31065.7 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6914
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR 1 BASE COAT & 1 SPRAY COAT | SQFT | 3728.55 | 25 | 93213.75 | 16778.48 | 109992.23 | 5 | 2783.565 | 69589.13 | 12526.04 | 82115.17 | 944.985 | 27877.07 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 74.6554