## Project_Work_Order6386504366586
Project Work Order
From 08 Sep 2005 To 21 Oct 2024
Page 1 of 1
Total Records: 62 Records 1 To 62
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 2ND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A GROUND FLOOR COMMON PAINT & COLOR REWORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 0 | 0 | 0 | 0 | 1600 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 1ST FLOOR COMMON PAINT & COLOR REWORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 1ST FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A TERRACE COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 0 | 0 | 0 | 0 | 1600 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B TERRACE COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 0 | 0 | 0 | 0 | 1200 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C TERRACE COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER A 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1543.54 | 27783.72 | 5001.06 | 32784.78 | 56.46 | 1199.22 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 96.4713
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 1ST FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 1028.54 | 18513.72 | 3332.46 | 21846.18 | 571.46 | 12137.82 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 64.2838
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 2ND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 1200 | 21600 | 3888 | 25488 | 0 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER B GROUND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1200 | 18 | 21600 | 3888 | 25488 | 5 | 0 | 0 | 0 | 0 | 1200 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 295 | 0 | 01 May 2023 | Devarshi enterprise | TOWER C GROUND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR APEX ULTIMA PROTECT | SQFT | 1600 | 18 | 28800 | 5184 | 33984 | 5 | 0 | 0 | 0 | 0 | 1600 | 0 | Purpose of Work : Plumbing Duct Area Paint Work |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0