## Project_Work_Order6386520702201
Project Work Order
From 22 Sep 2014 To 23 Oct 2024
Page 1 of 1
Total Records: 4 Records 1 To 4
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOODS SERENITY | 219 | 0 | 25 Jul 2024 | JASHBHAI A. PARMAR | VILLA B45 CIVIL WORK PLASTER WORK | LABOR FOR EXTERNAL PLASTER (SQFT) | SQFT | 8100 | 24 | 194400 | 0 | 194400 | 5 | 8100 | 194400 | 0 | 194400 | 0 | 0 | EXTERNAL PLASTER |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOODS SERENITY | 219 | 0 | 25 Jul 2024 | JASHBHAI A. PARMAR | VILLA B45 CIVIL WORK PLASTER WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 11700 | 18 | 210600 | 0 | 210600 | 5 | 9941.31 | 178943.58 | 0 | 178943.58 | 1758.69 | 31656.42 | INTERNAL PLASTER |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 89.6693
GREENWOODS SERENITY | 219 | 0 | 25 Jul 2024 | JASHBHAI A. PARMAR | VILLA B45 DEPARTMENT WORK | DEPART LABOR | NOS | 69 | 500 | 34500 | 0 | 34500 | 5 | 69 | 34500 | 0 | 34500 | 0 | 0 | DEPART LABOR |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOODS SERENITY | 219 | 0 | 25 Jul 2024 | JASHBHAI A. PARMAR | VILLA B45 DEPARTMENT WORK | DEPART MASON | NOS | 25 | 800 | 20000 | 0 | 20000 | 5 | 25 | 20000 | 0 | 20000 | 0 | 0 | DEPART MASON |  | T.Joshi | pur.nrpl4 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100