## Project_Work_Order6386676526647
Project Work Order
From 06 Oct 2005 To 10 Nov 2024
Page 1 of 1
Total Records: 255 Records 1 To 255
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 10TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7527.84 | 220 | 1656124.8 | 298102.46 | 1954227.26 | 5 | 7527.84 | 1656124.8 | 298102.46 | 1954227.26 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 11TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7555.67 | 220 | 1662247.4 | 299204.54 | 1961451.94 | 5 | 7555.67 | 1662247.4 | 299204.54 | 1961451.94 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 12TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7580.81 | 220 | 1667778.2 | 300200.08 | 1967978.28 | 5 | 7580.81 | 1667778.2 | 300200.08 | 1967978.28 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 2ND FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7024.48 | 220 | 1545385.6 | 278169.4 | 1823555 | 5 | 0 | 0 | 0 | 0 | 7024.48 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 3RD FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 0 | 0 | 0 | 0 | 7576.62 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 4TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 5TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 6TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7574.49 | 220 | 1666387.8 | 299949.8 | 1966337.6 | 5 | 7574.49 | 1666387.8 | 299949.8 | 1966337.6 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 7TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7024.48 | 220 | 1545385.6 | 278169.4 | 1823555 | 5 | 7024.48 | 1545385.6 | 278169.4 | 1823555 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 12TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7655.49 | 220 | 1684207.8 | 303157.4 | 1987365.2 | 5 | 7655.49 | 1684207.8 | 303157.4 | 1987365.2 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 13TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7219.48 | 220 | 1588285.6 | 285891.4 | 1874177 | 5 | 7219.48 | 1588285.6 | 285891.4 | 1874177 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 14TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7270.36 | 220 | 1599479.2 | 287906.26 | 1887385.46 | 5 | 7270.36 | 1599479.2 | 287906.26 | 1887385.46 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 15TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7738.62 | 220 | 1702496.4 | 306449.36 | 2008945.76 | 5 | 7738.62 | 1702496.4 | 306449.36 | 2008945.76 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 16TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7764.64 | 220 | 1708220.8 | 307479.74 | 2015700.54 | 5 | 7764.64 | 1708220.8 | 307479.74 | 2015700.54 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 1ST FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7024.48 | 220 | 1545385.6 | 278169.4 | 1823555 | 5 | 0 | 0 | 0 | 0 | 7024.48 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A UP TO PLINTH RCC WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 13256.76 | 257 | 3406987.32 | 613257.72 | 4020245.04 | 5 | 0 | 0 | 0 | 0 | 13256.76 | 0 | BASEMENT RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B UP TO PLINTH RCC WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 11553.47 | 257 | 2969241.79 | 534463.52 | 3503705.31 | 5 | 0 | 0 | 0 | 0 | 11553.47 | 0 | BASEMENT RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C UP TO PLINTH RCC WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 13292.16 | 257 | 3416085.12 | 614895.32 | 4030980.44 | 5 | 0 | 0 | 0 | 0 | 13292.16 | 0 | BASEMENT RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 2ND FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 6958.37 | 220 | 1530841.4 | 275551.46 | 1806392.86 | 5 | 0 | 0 | 0 | 0 | 6958.37 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 10TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7602.64 | 220 | 1672580.8 | 301064.54 | 1973645.34 | 5 | 7602.64 | 1672580.8 | 301064.54 | 1973645.34 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 11TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7630.62 | 220 | 1678736.4 | 302172.56 | 1980908.96 | 5 | 7630.62 | 1678736.4 | 302172.56 | 1980908.96 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 177.15 | 95 | 16829.25 | 3029.26 | 19858.51 | 5 | 0 | 0 | 0 | 0 | 177.15 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOUR FOR RCC COLUMN (CFT) | CFT | 251.31 | 130 | 32670.3 | 5880.66 | 38550.96 | 5 | 0 | 0 | 0 | 0 | 251.31 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOR FOR BEAM (CFT) | CFT | 138.37 | 130 | 17988.1 | 3237.86 | 21225.96 | 5 | 0 | 0 | 0 | 0 | 138.37 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE SQUASH COURT CIVIL WORK | LABOR FOR MASONRY/PLASTER WORK (SQFT) | SQFT | 1353 | 110 | 148830 | 26789.4 | 175619.4 | 5 | 0 | 0 | 0 | 0 | 1353 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | UG TANK RCC WORK FOR SLAB | LABOR FOR RCC SLAB (SQFT) | SQFT | 2905.46 | 150 | 435819 | 78447.42 | 514266.42 | 5 | 0 | 0 | 0 | 0 | 2905.46 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 385.75 | 15 | 5786.25 | 1041.52 | 6827.77 | 5 | 0 | 0 | 0 | 0 | 385.75 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOR FOR 6" MASONRY WORK (SQFT) | SQFT | 78 | 15 | 1170 | 210.6 | 1380.6 | 5 | 0 | 0 | 0 | 0 | 78 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOR FOR 9" MASONRY WORK (SQFT) | SQFT | 875.38 | 20 | 17507.6 | 3151.36 | 20658.96 | 5 | 0 | 0 | 0 | 0 | 875.38 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | COMMON CIVIL WORK | LABOR FOR INTERNAL PLASTER (SQFT) | SQFT | 2683.29 | 15 | 40249.35 | 7244.88 | 47494.23 | 5 | 0 | 0 | 0 | 0 | 2683.29 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE SWIMMING POOL RCC WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 1300 | 250 | 325000 | 58500 | 383500 | 5 | 0 | 0 | 0 | 0 | 1300 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE BASEMENT CIVIL RCC WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 4184.9 | 257 | 1075519.3 | 193593.48 | 1269112.78 | 5 | 0 | 0 | 0 | 0 | 4184.9 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE GROUND FLOOR CIVIL RCC WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 3239.68 | 257 | 832597.76 | 149867.6 | 982465.36 | 5 | 0 | 0 | 0 | 0 | 3239.68 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE SQUASH COURT CIVIL WORK | LABOR FOR RCC SLAB (SQFT) | SQFT | 1353 | 257 | 347721 | 62589.78 | 410310.78 | 5 | 0 | 0 | 0 | 0 | 1353 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE BASEMENT CIVIL MASONRY WORK | LABOR FOR MASONRY/PLASTER WORK (SQFT) | SQFT | 4184.9 | 110 | 460339 | 82861.02 | 543200.02 | 5 | 0 | 0 | 0 | 0 | 4184.9 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | CLUB HOUSE GROUND FLOOR CIVIL MASONRY WORK | LABOR FOR MASONRY/PLASTER WORK (SQFT) | SQFT | 3239.68 | 110 | 356364.8 | 64145.66 | 420510.46 | 5 | 0 | 0 | 0 | 0 | 3239.68 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 19TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 5811.86 | 42 | 244098.12 | 43937.66 | 288035.78 | 5 | 5811.86 | 244098.12 | 43937.66 | 288035.78 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 19TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 5811.86 | 54 | 313840.44 | 56491.28 | 370331.72 | 5 | 0 | 0 | 0 | 0 | 5811.86 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 18TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7684.82 | 42 | 322762.44 | 58097.24 | 380859.68 | 5 | 7684.82 | 322762.44 | 58097.24 | 380859.68 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 18TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7684.82 | 54 | 414980.28 | 74696.46 | 489676.74 | 5 | 6000 | 324000 | 58320 | 382320 | 1684.82 | 107356.74 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 78.076
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 17TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7675.92 | 42 | 322388.64 | 58029.96 | 380418.6 | 5 | 7675.92 | 322388.64 | 58029.96 | 380418.6 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 17TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7675.92 | 54 | 414499.68 | 74609.94 | 489109.62 | 5 | 6900 | 372600 | 67068 | 439668 | 775.92 | 49441.62 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 89.8915
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 19TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 5729.51 | 42 | 240639.42 | 43315.1 | 283954.52 | 5 | 5729.51 | 240639.42 | 43315.1 | 283954.52 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 19TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 5729.51 | 54 | 309393.54 | 55690.84 | 365084.38 | 5 | 0 | 0 | 0 | 0 | 5729.51 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 18TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7568.7 | 42 | 317885.4 | 57219.38 | 375104.78 | 5 | 7568.7 | 317885.4 | 57219.38 | 375104.78 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 18TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7568.7 | 54 | 408709.8 | 73567.76 | 482277.56 | 5 | 2500 | 135000 | 24300 | 159300 | 5068.7 | 322977.56 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 33.0308
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 17TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7541.7 | 42 | 316751.4 | 57015.26 | 373766.66 | 5 | 7541.7 | 316751.4 | 57015.26 | 373766.66 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 17TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7541.7 | 54 | 407251.8 | 73305.32 | 480557.12 | 5 | 7541.7 | 407251.8 | 73305.32 | 480557.12 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 17TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7675.92 | 51 | 391471.92 | 70464.94 | 461936.86 | 5 | 7675.92 | 391471.92 | 70464.94 | 461936.86 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 19TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 5811.86 | 42 | 244098.12 | 43937.66 | 288035.78 | 5 | 5811.86 | 244098.12 | 43937.66 | 288035.78 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 18TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7685.14 | 42 | 322775.88 | 58099.66 | 380875.54 | 5 | 7685.14 | 322775.88 | 58099.66 | 380875.54 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 18TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7685.14 | 54 | 414997.56 | 74699.56 | 489697.12 | 5 | 3000 | 162000 | 29160 | 191160 | 4685.14 | 298537.12 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 39.0364
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 17TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7657.82 | 42 | 321628.44 | 57893.12 | 379521.56 | 5 | 7657.82 | 321628.44 | 57893.12 | 379521.56 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 17TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7657.82 | 54 | 413522.28 | 74434.02 | 487956.3 | 5 | 7657.82 | 413522.28 | 74434.02 | 487956.3 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 17TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7657.82 | 51 | 390548.82 | 70298.78 | 460847.6 | 5 | 0 | 0 | 0 | 0 | 7657.82 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 19TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 5729.51 | 51 | 292205.01 | 52596.9 | 344801.91 | 5 | 0 | 0 | 0 | 0 | 5729.51 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 18TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7568.7 | 51 | 386003.7 | 69480.66 | 455484.36 | 5 | 0 | 0 | 0 | 0 | 7568.7 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 17TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7541.7 | 51 | 384626.7 | 69232.8 | 453859.5 | 5 | 7541.7 | 384626.7 | 69232.8 | 453859.5 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 19TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 5811.86 | 51 | 296404.86 | 53352.88 | 349757.74 | 5 | 0 | 0 | 0 | 0 | 5811.86 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 18TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7684.82 | 51 | 391925.82 | 70546.64 | 462472.46 | 5 | 7684.82 | 391925.82 | 70546.64 | 462472.46 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 17TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7541.7 | 220 | 1659174 | 298651.32 | 1957825.32 | 5 | 7541.7 | 1659174 | 298651.32 | 1957825.32 | 0 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 19TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 5811.86 | 220 | 1278609.2 | 230149.66 | 1508758.86 | 5 | 5811.86 | 1278609.2 | 230149.66 | 1508758.86 | 0 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 18TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7684.82 | 220 | 1690660.4 | 304318.88 | 1994979.28 | 5 | 7684.82 | 1690660.4 | 304318.86 | 1994979.26 | 0 | 0.02 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 17TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7675.92 | 220 | 1688702.4 | 303966.44 | 1992668.84 | 5 | 7675.92 | 1688702.4 | 303966.44 | 1992668.84 | 0 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 19TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 5811.86 | 51 | 296404.86 | 53352.88 | 349757.74 | 5 | 0 | 0 | 0 | 0 | 5811.86 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 18TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7685.14 | 51 | 391942.14 | 70549.58 | 462491.72 | 5 | 0 | 0 | 0 | 0 | 7685.14 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 9TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 76.62 | 51 | 3907.62 | 703.38 | 4611 | 5 | 0 | 0 | 0 | 0 | 76.62 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 19TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 5811.86 | 220 | 1278609.2 | 230149.66 | 1508758.86 | 5 | 5811.86 | 1278609.2 | 230149.66 | 1508758.86 | 0 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 18TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7685.14 | 220 | 1690730.8 | 304331.54 | 1995062.34 | 5 | 1598.19 | 351601.8 | 63288.32 | 414890.12 | 6086.95 | 1580172.22 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 20.7958
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 17TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7657.82 | 220 | 1684720.4 | 303249.68 | 1987970.08 | 5 | 7657.82 | 1684720.4 | 303249.68 | 1987970.08 | 0 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 19TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 5729.51 | 220 | 1260492.2 | 226888.6 | 1487380.8 | 5 | 4550 | 1001000 | 180180 | 1181180 | 1179.51 | 306200.8 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 79.4134
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 18TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7568.7 | 220 | 1665114 | 299720.52 | 1964834.52 | 5 | 7568.7 | 1665114 | 299720.52 | 1964834.52 | 0 | 0 | Civil work up to plaster from 17th floor to 19th floor |  | T.Joshi | pur.nrpl2 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 4TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7576.62 | 386407.62 | 69553.38 | 455961 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 5TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7576.62 | 386407.62 | 69553.38 | 455961 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 6TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7574.49 | 51 | 386298.99 | 69533.82 | 455832.81 | 5 | 7574.49 | 386298.99 | 69533.82 | 455832.81 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 7TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7024.48 | 51 | 358248.48 | 64484.72 | 422733.2 | 5 | 7024.43 | 358245.93 | 64484.26 | 422730.19 | 0.05 | 3.01 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 99.9993
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 8TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7026.61 | 51 | 358357.11 | 64504.28 | 422861.39 | 5 | 7026.61 | 358357.11 | 64504.28 | 422861.39 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 9TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7576.62 | 386407.62 | 69553.38 | 455961 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 14TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7270.36 | 51 | 370788.36 | 66741.9 | 437530.26 | 5 | 7270.36 | 370788.36 | 66741.9 | 437530.26 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 15TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7738.62 | 51 | 394669.62 | 71040.54 | 465710.16 | 5 | 7738.62 | 394669.62 | 71040.54 | 465710.16 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 16TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7764.64 | 51 | 395996.64 | 71279.4 | 467276.04 | 5 | 320 | 16320 | 2937.6 | 19257.6 | 7444.64 | 448018.44 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 4.1212
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 1ST FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7024.48 | 51 | 358248.48 | 64484.72 | 422733.2 | 5 | 7023.69 | 358208.19 | 64477.48 | 422685.67 | 0.79 | 47.53 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 99.9888
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 2ND FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7024.48 | 51 | 358248.48 | 64484.72 | 422733.2 | 5 | 7024.48 | 358248.48 | 64484.72 | 422733.2 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 3RD FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7026.61 | 358357.11 | 64504.28 | 422861.39 | 550.01 | 33099.61 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 92.7407
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 9TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7502.63 | 51 | 382634.13 | 68874.14 | 451508.27 | 5 | 7502.63 | 382634.13 | 68874.14 | 451508.27 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 6TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7499.81 | 51 | 382490.31 | 68848.26 | 451338.57 | 5 | 7499.81 | 382490.31 | 68848.26 | 451338.57 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 10TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7602.64 | 51 | 387734.64 | 69792.24 | 457526.88 | 5 | 7602.64 | 387734.64 | 69792.24 | 457526.88 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 11TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7630.62 | 51 | 389161.62 | 70049.1 | 459210.72 | 5 | 7630.62 | 389161.62 | 70049.1 | 459210.72 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 12TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7655.49 | 51 | 390429.99 | 70277.4 | 460707.39 | 5 | 7655.49 | 390429.99 | 70277.4 | 460707.39 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 13TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7219.48 | 51 | 368193.48 | 66274.82 | 434468.3 | 5 | 7219.48 | 368193.48 | 66274.82 | 434468.3 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 2ND FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 6958.37 | 51 | 354876.87 | 63877.84 | 418754.71 | 5 | 6958.37 | 354876.87 | 63879.82 | 418756.69 | 0 | -1.98 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 3RD FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7501.67 | 51 | 382585.17 | 68865.34 | 451450.51 | 5 | 7501.67 | 382585.17 | 68865.34 | 451450.51 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 4TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7501.67 | 51 | 382585.17 | 68865.34 | 451450.51 | 5 | 0 | 0 | 0 | 0 | 7501.67 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 5TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7501.67 | 51 | 382585.17 | 68865.34 | 451450.51 | 5 | 7501.67 | 382585.17 | 68865.34 | 451450.51 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 7TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 6958.37 | 51 | 354876.87 | 63877.84 | 418754.71 | 5 | 6958.37 | 354876.87 | 63877.84 | 418754.71 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 8TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7134.7 | 51 | 363869.7 | 65496.54 | 429366.24 | 5 | 7134.7 | 363869.7 | 65496.54 | 429366.24 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 12TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7580.81 | 51 | 386621.31 | 69591.84 | 456213.15 | 5 | 7580.81 | 386621.31 | 69591.84 | 456213.15 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 13TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7154.15 | 51 | 364861.65 | 65675.1 | 430536.75 | 5 | 7154.15 | 364861.65 | 65675.1 | 430536.75 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 14TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7204.94 | 51 | 367451.94 | 66141.34 | 433593.28 | 5 | 7204.94 | 367451.94 | 66141.34 | 433593.28 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 15TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7664.63 | 51 | 390896.13 | 70361.3 | 461257.43 | 5 | 7664.63 | 390896.13 | 70361.3 | 461257.43 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 16TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7691.63 | 51 | 392273.13 | 70609.16 | 462882.29 | 5 | 7691.63 | 392273.13 | 70609.16 | 462882.29 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 1ST FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 6958.37 | 51 | 354876.87 | 63877.84 | 418754.71 | 5 | 6958.37 | 354876.87 | 63877.84 | 418754.71 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 9TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 9TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 0 | 0 | 0 | 0 | 7576.62 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C GROUND FLOOR PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7108.79 | 110 | 781966.9 | 140754.04 | 922720.94 | 5 | 0 | 0 | 0 | 0 | 7108.79 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C UP TO PLINTH PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 13292.16 | 110 | 1462137.6 | 263184.76 | 1725322.36 | 5 | 0 | 0 | 0 | 0 | 13292.16 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 10TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7527.84 | 51 | 383919.84 | 69105.58 | 453025.42 | 5 | 7527.84 | 383919.84 | 69105.58 | 453025.42 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 11TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7555.67 | 51 | 385339.17 | 69361.06 | 454700.23 | 5 | 7555.67 | 385339.17 | 69361.06 | 454700.23 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 6TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7574.49 | 42 | 318128.58 | 57263.14 | 375391.72 | 5 | 7574.49 | 318128.58 | 57263.14 | 375391.72 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 6TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7574.49 | 54 | 409022.46 | 73624.04 | 482646.5 | 5 | 0 | 0 | 0 | 0 | 7574.49 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 7TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 42 | 295028.16 | 53105.06 | 348133.22 | 5 | 7024.48 | 295028.16 | 53105.08 | 348133.24 | 0 | -0.02 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 7TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 54 | 379321.92 | 68277.94 | 447599.86 | 5 | 0 | 0 | 0 | 0 | 7024.48 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 8TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7026.61 | 42 | 295117.62 | 53121.18 | 348238.8 | 5 | 7026.61 | 295117.62 | 53121.18 | 348238.8 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 8TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7026.61 | 54 | 379436.94 | 68298.64 | 447735.58 | 5 | 0 | 0 | 0 | 0 | 7026.61 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 3RD FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 3RD FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 3788.31 | 204568.74 | 36822.38 | 241391.12 | 3788.31 | 241391.1 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 50
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 4TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 4TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 0 | 0 | 0 | 0 | 7576.62 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 5TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 5TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 0 | 0 | 0 | 0 | 7576.62 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 16TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7764.64 | 42 | 326114.88 | 58700.68 | 384815.56 | 5 | 7764.64 | 326114.88 | 58700.68 | 384815.56 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 16TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7764.64 | 54 | 419290.56 | 75472.3 | 494762.86 | 5 | 7764.64 | 419290.56 | 75472.3 | 494762.86 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 1ST FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 42 | 295028.16 | 53105.06 | 348133.22 | 5 | 7024.48 | 295028.16 | 53105.06 | 348133.22 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 1ST FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 54 | 379321.92 | 68277.94 | 447599.86 | 5 | 7024.48 | 379321.92 | 68277.94 | 447599.86 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 42 | 295028.16 | 53105.06 | 348133.22 | 5 | 7024.48 | 295028.16 | 53105.06 | 348133.22 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 2ND FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 54 | 379321.92 | 68277.94 | 447599.86 | 5 | 7024.48 | 379321.92 | 68277.94 | 447599.86 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 13TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7219.48 | 42 | 303218.16 | 54579.26 | 357797.42 | 5 | 7219.48 | 303218.16 | 54579.26 | 357797.42 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 13TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7219.48 | 54 | 389851.92 | 70173.34 | 460025.26 | 5 | 7219.48 | 389851.92 | 70173.34 | 460025.26 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 14TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7270.36 | 42 | 305355.12 | 54963.92 | 360319.04 | 5 | 7270.36 | 305355.12 | 54963.92 | 360319.04 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 14TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7270.36 | 54 | 392599.44 | 70667.9 | 463267.34 | 5 | 7270.36 | 392599.44 | 70667.9 | 463267.34 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 15TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7738.62 | 42 | 325022.04 | 58503.96 | 383526 | 5 | 7738.62 | 325022.04 | 58503.96 | 383526 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 15TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7738.62 | 54 | 417885.48 | 75219.38 | 493104.86 | 5 | 7738.62 | 417885.48 | 75219.38 | 493104.86 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 10TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7602.64 | 42 | 319310.88 | 57475.96 | 376786.84 | 5 | 7602.64 | 319310.88 | 57475.96 | 376786.84 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 10TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7602.64 | 54 | 410542.56 | 73897.66 | 484440.22 | 5 | 0 | 0 | 0 | 0 | 7602.64 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 11TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7630.62 | 42 | 320486.04 | 57687.48 | 378173.52 | 5 | 7630.62 | 320486.04 | 57687.48 | 378173.52 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 11TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7630.62 | 54 | 412053.48 | 74169.62 | 486223.1 | 5 | 7630.62 | 412053.48 | 74169.62 | 486223.1 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 12TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7655.49 | 42 | 321530.58 | 57875.5 | 379406.08 | 5 | 7655.49 | 321530.58 | 57875.5 | 379406.08 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 12TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7655.49 | 54 | 413396.46 | 74411.36 | 487807.82 | 5 | 7655.49 | 413396.46 | 74411.36 | 487807.82 | 0 | 0 | TOWER C PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 4TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7576.62 | 386407.62 | 69553.38 | 455961 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 5TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7576.62 | 386407.62 | 69553.38 | 455961 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 6TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7574.49 | 51 | 386298.99 | 69533.82 | 455832.81 | 5 | 7574.49 | 386298.99 | 69533.82 | 455832.81 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 7TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7024.48 | 51 | 358248.48 | 64484.72 | 422733.2 | 5 | 7024.48 | 358248.48 | 64484.72 | 422733.2 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 8TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7026.61 | 51 | 358357.11 | 64504.28 | 422861.39 | 5 | 7026.61 | 358357.11 | 64504.28 | 422861.39 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 9TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7500 | 51 | 382500 | 68850 | 451350 | 5 | 7500 | 382500 | 68850 | 451350 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 14TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7270.36 | 51 | 370788.36 | 66741.9 | 437530.26 | 5 | 7270.36 | 370788.36 | 66741.9 | 437530.26 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 15TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7738.62 | 51 | 394669.62 | 71040.54 | 465710.16 | 5 | 7738.62 | 394669.62 | 71040.54 | 465710.16 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 16TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7764.64 | 51 | 395996.64 | 71279.4 | 467276.04 | 5 | 7764.64 | 395996.64 | 71279.4 | 467276.04 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 1ST FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7024.48 | 51 | 358248.48 | 64484.72 | 422733.2 | 5 | 0 | 0 | 0 | 0 | 7024.48 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 2ND FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7024.48 | 51 | 358248.48 | 64484.72 | 422733.2 | 5 | 7024.48 | 358248.48 | 64484.72 | 422733.2 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 3RD FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7576.62 | 51 | 386407.62 | 69553.38 | 455961 | 5 | 7576.62 | 386407.62 | 69553.38 | 455961 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B GROUND FLOOR PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6962.57 | 110 | 765882.7 | 137858.88 | 903741.58 | 5 | 0 | 0 | 0 | 0 | 6962.57 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B UP TO PLINTH PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 11553.47 | 110 | 1270881.7 | 228758.7 | 1499640.4 | 5 | 0 | 0 | 0 | 0 | 11553.47 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 10TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7602.64 | 51 | 387734.64 | 69792.24 | 457526.88 | 5 | 7602.64 | 387734.64 | 69792.24 | 457526.88 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 11TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7630.62 | 51 | 389161.62 | 70049.1 | 459210.72 | 5 | 7630.62 | 389161.62 | 70049.1 | 459210.72 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 12TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7655.49 | 51 | 390429.99 | 70277.4 | 460707.39 | 5 | 7655.49 | 390429.99 | 70277.4 | 460707.39 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 13TH FLOOR MASONRY WORK | LABOUR FOR BLOCK WORK (SQFT) | SQFT | 7219.48 | 51 | 368193.48 | 66274.82 | 434468.3 | 5 | 7219.48 | 368193.48 | 66274.82 | 434468.3 | 0 | 0 |  |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 7TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6958.37 | 42 | 292251.54 | 52605.28 | 344856.82 | 5 | 5218.78 | 219188.76 | 39453.98 | 258642.74 | 1739.59 | 86214.08 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 7TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6958.37 | 54 | 375751.98 | 67635.36 | 443387.34 | 5 | 6958.37 | 375751.98 | 67635.36 | 443387.34 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 8TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7134.7 | 42 | 299657.4 | 53938.34 | 353595.74 | 5 | 5351.03 | 224743.26 | 40453.78 | 265197.04 | 1783.67 | 88398.7 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75.0001
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 8TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7134.7 | 54 | 385273.8 | 69349.28 | 454623.08 | 5 | 7134.7 | 385273.8 | 69349.28 | 454623.08 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 9TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7502.63 | 42 | 315110.46 | 56719.88 | 371830.34 | 5 | 2682.76 | 112675.92 | 20281.68 | 132957.6 | 4819.87 | 238872.74 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 35.7576
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 9TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7502.63 | 54 | 405142.02 | 72925.56 | 478067.58 | 5 | 7502.63 | 405142.02 | 72925.56 | 478067.58 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 4TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7501.67 | 42 | 315070.14 | 56712.62 | 371782.76 | 5 | 5626.25 | 236302.5 | 42534.46 | 278836.96 | 1875.42 | 92945.8 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 4TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7501.67 | 54 | 405090.18 | 72916.24 | 478006.42 | 5 | 7501.67 | 405090.18 | 72916.24 | 478006.42 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 5TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7501.67 | 42 | 315070.14 | 56712.62 | 371782.76 | 5 | 5626.25 | 236302.5 | 42534.46 | 278836.96 | 1875.42 | 92945.8 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 5TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7501.67 | 54 | 405090.18 | 72916.24 | 478006.42 | 5 | 7501.67 | 405090.18 | 72916.24 | 478006.42 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 6TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7499.81 | 42 | 314992.02 | 56698.56 | 371690.58 | 5 | 5624.86 | 236244.12 | 42523.94 | 278768.06 | 1874.95 | 92922.52 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 6TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7499.81 | 54 | 404989.74 | 72898.16 | 477887.9 | 5 | 7499.81 | 404989.74 | 72898.16 | 477887.9 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 1ST FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6958.37 | 42 | 292251.54 | 52605.28 | 344856.82 | 5 | 5218.78 | 219188.76 | 39453.98 | 258642.74 | 1739.59 | 86214.08 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 1ST FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6958.37 | 54 | 375751.98 | 67635.36 | 443387.34 | 5 | 3788 | 204552 | 36819.36 | 241371.36 | 3170.37 | 202015.98 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6958.37 | 42 | 292251.54 | 52605.28 | 344856.82 | 5 | 5218.78 | 219188.76 | 39453.98 | 258642.74 | 1739.59 | 86214.08 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 2ND FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 6958.37 | 54 | 375751.98 | 67635.36 | 443387.34 | 5 | 6958.37 | 375751.98 | 67635.36 | 443387.34 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 3RD FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7501.67 | 42 | 315070.14 | 56712.62 | 371782.76 | 5 | 5626.25 | 236302.5 | 42534.46 | 278836.96 | 1875.42 | 92945.8 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 75
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 3RD FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7501.67 | 54 | 405090.18 | 72916.24 | 478006.42 | 5 | 7501.67 | 405090.18 | 72916.24 | 478006.42 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 14TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7204.94 | 42 | 302607.48 | 54469.34 | 357076.82 | 5 | 7204.94 | 302607.48 | 54469.34 | 357076.82 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 14TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7204.94 | 54 | 389066.76 | 70032.02 | 459098.78 | 5 | 7204.94 | 389066.76 | 70032.02 | 459098.78 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 15TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7664.63 | 42 | 321914.46 | 57944.6 | 379859.06 | 5 | 7664.63 | 321914.46 | 57944.6 | 379859.06 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 15TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7664.63 | 54 | 413890.02 | 74500.2 | 488390.22 | 5 | 3832.32 | 206945.28 | 37250.16 | 244195.44 | 3832.31 | 244194.78 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 50.0001
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 16TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7691.63 | 42 | 323048.46 | 58148.72 | 381197.18 | 5 | 7691.63 | 323048.46 | 58148.72 | 381197.18 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 16TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7691.63 | 54 | 415348.02 | 74762.64 | 490110.66 | 5 | 7691.63 | 415348.02 | 74762.64 | 490110.66 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 11TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7555.67 | 42 | 317338.14 | 57120.86 | 374459 | 5 | 7555.67 | 317338.14 | 57120.86 | 374459 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 11TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7555.67 | 54 | 408006.18 | 73441.12 | 481447.3 | 5 | 3777.84 | 204003.36 | 36720.6 | 240723.96 | 3777.83 | 240723.34 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 50.0001
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 12TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7580.81 | 42 | 318394.02 | 57310.92 | 375704.94 | 5 | 7580.81 | 318394.02 | 57310.92 | 375704.94 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 12TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7580.81 | 54 | 409363.74 | 73685.48 | 483049.22 | 5 | 7580.81 | 409363.74 | 73685.48 | 483049.22 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 13TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7154.15 | 42 | 300474.3 | 54085.38 | 354559.68 | 5 | 7154.15 | 300474.3 | 54085.38 | 354559.68 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 13TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7154.15 | 54 | 386324.1 | 69538.34 | 455862.44 | 5 | 7154.15 | 386324.1 | 69538.34 | 455862.44 | 0 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 9TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 9TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 7576.62 | 409137.48 | 73644.74 | 482782.22 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A GROUND FLOOR PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7108.79 | 110 | 781966.9 | 140754.04 | 922720.94 | 5 | 7108.79 | 781966.9 | 53742.46 | 835709.36 | 0 | 87011.58 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A UP TO PLINTH PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 13256.76 | 110 | 1458243.6 | 262483.84 | 1720727.44 | 5 | 0 | 0 | 0 | 0 | 13256.76 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 10TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7527.84 | 42 | 316169.28 | 56910.48 | 373079.76 | 5 | 1881.96 | 79042.32 | 14227.62 | 93269.94 | 5645.88 | 279809.82 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 10TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7527.84 | 54 | 406503.36 | 73170.6 | 479673.96 | 5 | 0 | 0 | 0 | 0 | 7527.84 | 0 | TOWER B PLASTER WORK |  | T.Joshi | Estimation | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 6TH FLOOR EXTERNAL DOUBLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7574.49 | 42 | 318128.58 | 57263.14 | 375391.72 | 5 | 7574.49 | 318128.58 | 57263.14 | 375391.72 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 6TH FLOOR INTERNAL SINGLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7574.49 | 54 | 409022.46 | 73624.04 | 482646.5 | 5 | 7574.49 | 409022.46 | 73624.04 | 482646.5 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 7TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 42 | 295028.16 | 53105.06 | 348133.22 | 5 | 7024.48 | 295028.16 | 53105.06 | 348133.22 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 7TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 54 | 379321.92 | 68277.94 | 447599.86 | 5 | 3512.24 | 189660.96 | 34138.98 | 223799.94 | 3512.24 | 223799.92 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 50
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 8TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7026.61 | 42 | 295117.62 | 53121.18 | 348238.8 | 5 | 7026.61 | 295117.62 | 53121.18 | 348238.8 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 8TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7026.61 | 54 | 379436.94 | 68298.64 | 447735.58 | 5 | 7026.61 | 379436.94 | 68298.64 | 447735.58 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 3RD FLOOR EXTERNAL DOUBLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 3RD FLOOR INTERNAL SINGLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 5682.46 | 306852.84 | 55233.52 | 362086.36 | 1894.16 | 120695.86 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 99.9999
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 4TH FLOOR EXTERNAL DOUBLE COAT PLASTER - SQ FT | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 4TH FLOOR INTERNAL SINGLE COAT PLASTER - SQ FT | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 0 | 0 | 0 | 0 | 7576.62 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 5TH FLOOR EXTERNAL DOUBLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 42 | 318218.04 | 57279.24 | 375497.28 | 5 | 7576.62 | 318218.04 | 57279.24 | 375497.28 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 5TH FLOOR INTERNAL SINGLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7576.62 | 54 | 409137.48 | 73644.74 | 482782.22 | 5 | 0 | 0 | 0 | 0 | 7576.62 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 16TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7764.64 | 42 | 326114.88 | 58700.68 | 384815.56 | 5 | 7764.64 | 326114.88 | 58700.68 | 384815.56 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 16TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7764.64 | 54 | 419290.56 | 75472.3 | 494762.86 | 5 | 7764.64 | 419290.56 | 75472.3 | 494762.86 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 1ST FLOOR EXTERNAL DOUBLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 42 | 295028.16 | 53105.06 | 348133.22 | 5 | 7024.48 | 295028.16 | 53105.06 | 348133.22 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 1ST FLOOR INTERNAL SINGLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 54 | 379321.92 | 68277.94 | 447599.86 | 5 | 7024.48 | 379321.92 | 68277.94 | 447599.86 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 2ND FLOOR EXTERNAL DOUBLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 42 | 295028.16 | 53105.06 | 348133.22 | 5 | 7024.48 | 295028.16 | 53105.06 | 348133.22 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 2ND FLOOR INTERNAL SINGLE COAT PLASTER | LABOUR FOR PLASTER (SQFT) | SQFT | 7024.48 | 54 | 379321.92 | 68277.94 | 447599.86 | 5 | 7024.48 | 379321.92 | 68277.94 | 447599.86 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 13TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7219.48 | 42 | 303218.16 | 54579.26 | 357797.42 | 5 | 7219.48 | 303218.16 | 54579.26 | 357797.42 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 13TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7219.48 | 54 | 389851.92 | 70173.34 | 460025.26 | 5 | 7219.48 | 389851.92 | 70173.34 | 460025.26 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 14TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7270.36 | 42 | 305355.12 | 54963.92 | 360319.04 | 5 | 7270.36 | 305355.12 | 54963.94 | 360319.06 | 0 | -0.02 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 14TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7270.36 | 54 | 392599.44 | 70667.9 | 463267.34 | 5 | 7270.36 | 392599.44 | 70667.9 | 463267.34 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 15TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7738.62 | 42 | 325022.04 | 58503.96 | 383526 | 5 | 7738.62 | 325022.04 | 58503.96 | 383526 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 15TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7738.62 | 54 | 417885.48 | 75219.38 | 493104.86 | 5 | 7738.62 | 417885.48 | 75219.38 | 493104.86 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 10TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7602.64 | 42 | 319310.88 | 57475.96 | 376786.84 | 5 | 7602.64 | 319310.88 | 57475.96 | 376786.84 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 10TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7602.64 | 54 | 410542.56 | 73897.66 | 484440.22 | 5 | 7602.64 | 410542.56 | 73897.66 | 484440.22 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 11TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7630.62 | 42 | 320486.04 | 57687.48 | 378173.52 | 5 | 7630.62 | 320486.04 | 57687.48 | 378173.52 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 11TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7630.62 | 54 | 412053.48 | 74169.62 | 486223.1 | 5 | 3815.31 | 206026.74 | 37084.82 | 243111.56 | 3815.31 | 243111.54 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 50
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 12TH FLOOR EXTERNAL DOUBLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7655.49 | 42 | 321530.58 | 57875.5 | 379406.08 | 5 | 7655.49 | 321530.58 | 57875.5 | 379406.08 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 12TH FLOOR INTERNAL SINGLE COAT PLASTER WORK | LABOUR FOR PLASTER (SQFT) | SQFT | 7655.49 | 54 | 413396.46 | 74411.36 | 487807.82 | 5 | 7655.49 | 413396.46 | 74411.36 | 487807.82 | 0 | 0 | TOWER A PLASTER WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 5TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 6TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7574.49 | 220 | 1666387.8 | 299949.8 | 1966337.6 | 5 | 7574.49 | 1666387.8 | 299949.8 | 1966337.6 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 7TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7024.48 | 220 | 1545385.6 | 278169.4 | 1823555 | 5 | 7024.48 | 1545385.6 | 278169.4 | 1823555 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 8TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7026.61 | 220 | 1545854.2 | 278253.76 | 1824107.96 | 5 | 7026.61 | 1545854.2 | 278253.76 | 1824107.96 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 9TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C GROUND FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7108.79 | 257 | 1826959.03 | 328852.62 | 2155811.65 | 5 | 0 | 0 | 0 | 0 | 7108.79 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 15TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7738.62 | 220 | 1702496.4 | 306449.36 | 2008945.76 | 5 | 7738.62 | 1702496.4 | 306449.36 | 2008945.76 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 16TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7764.64 | 220 | 1708220.8 | 307479.74 | 2015700.54 | 5 | 7764.64 | 1708220.8 | 307479.74 | 2015700.54 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 1ST FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7024.48 | 220 | 1545385.6 | 278169.4 | 1823555 | 5 | 0 | 0 | 0 | 0 | 7024.48 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 2ND FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7024.48 | 220 | 1545385.6 | 278169.4 | 1823555 | 5 | 0 | 0 | 0 | 0 | 7024.48 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 3RD FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 4TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B GROUND FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 6962.57 | 257 | 1789380.49 | 322088.48 | 2111468.97 | 5 | 0 | 0 | 0 | 0 | 6962.57 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 10TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7602.64 | 220 | 1672580.8 | 301064.54 | 1973645.34 | 5 | 7602.64 | 1672580.8 | 301064.54 | 1973645.34 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 11TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7630.62 | 220 | 1678736.4 | 302172.56 | 1980908.96 | 5 | 7602.64 | 1672580.8 | 301064.56 | 1973645.36 | 27.98 | 7263.6 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 99.6333
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 12TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7655.49 | 220 | 1684207.8 | 303157.4 | 1987365.2 | 5 | 7655.49 | 1684207.8 | 303157.4 | 1987365.2 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 13TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7219.48 | 220 | 1588285.6 | 285891.4 | 1874177 | 5 | 7219.48 | 1588285.6 | 285891.4 | 1874177 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER C 14TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7270.36 | 220 | 1599479.2 | 287906.26 | 1887385.46 | 5 | 7270.36 | 1599479.2 | 287906.26 | 1887385.46 | 0 | 0 | TOWER C RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 4TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7501.67 | 220 | 1650367.4 | 297066.14 | 1947433.54 | 5 | 7501.67 | 1650367.4 | 297066.14 | 1947433.54 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 5TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7501.67 | 220 | 1650367.4 | 297066.14 | 1947433.54 | 5 | 7501.67 | 1650367.4 | 297066.14 | 1947433.54 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 6TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7499.81 | 220 | 1649958.2 | 296992.48 | 1946950.68 | 5 | 7499.81 | 1649958.2 | 296992.48 | 1946950.68 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 7TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 6958.37 | 220 | 1530841.4 | 275551.46 | 1806392.86 | 5 | 6958.37 | 1530841.4 | 275551.46 | 1806392.86 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 8TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7134.7 | 220 | 1569634 | 282534.12 | 1852168.12 | 5 | 7134.7 | 1569634 | 282534.12 | 1852168.12 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 9TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7502.63 | 220 | 1650578.6 | 297104.14 | 1947682.74 | 5 | 7502.63 | 1650578.6 | 297104.14 | 1947682.74 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 13TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7154.15 | 220 | 1573913 | 283304.34 | 1857217.34 | 5 | 7154.15 | 1573913 | 283304.34 | 1857217.34 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 14TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7204.94 | 220 | 1585086.8 | 285315.62 | 1870402.42 | 5 | 7204.94 | 1585086.8 | 285315.62 | 1870402.42 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 15TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7664.63 | 220 | 1686218.6 | 303519.34 | 1989737.94 | 5 | 7664.63 | 1686218.6 | 303519.34 | 1989737.94 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 16TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7691.63 | 220 | 1692158.6 | 304588.54 | 1996747.14 | 5 | 7691.63 | 1692158.6 | 304588.54 | 1996747.14 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 1ST FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 6958.37 | 220 | 1530841.4 | 275551.46 | 1806392.86 | 5 | 0 | 0 | 0 | 0 | 6958.37 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER B 3RD FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7501.67 | 220 | 1650367.4 | 297066.14 | 1947433.54 | 5 | 7501.67 | 1650367.4 | 297066.14 | 1947433.54 | 0 | 0 | TOWER B RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 8TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7026.61 | 220 | 1545854.2 | 278253.76 | 1824107.96 | 5 | 7026.61 | 1545854.2 | 278253.76 | 1824107.96 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A 9TH FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7576.62 | 220 | 1666856.4 | 300034.16 | 1966890.56 | 5 | 7576.62 | 1666856.4 | 300034.16 | 1966890.56 | 0 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 63 | 0 | 22 Dec 2020 | Krishna Associates | TOWER A GROUND FLOOR RCC WORK FOR SLAB | LABOUR FOR RCC | SQFT | 7108.79 | 257 | 1826959.03 | 328852.62 | 2155811.65 | 5 | 0 | 0 | 0 | 0 | 7108.79 | 0 | TOWER A RCC WORK |  | T.Joshi | pur.nrpl1 | T.Joshi | Construction |  |  |  | Approved | T.Joshi |  | 0