## Project_Work_Order6386736666305
Project Work Order
From 01 Oct 2017 To 17 Nov 2024
Page 1 of 1
Total Records: 44 Records 1 To 44
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | 100MM DIA 3 MTR 13MM THK CENTRIFUGAL CAST IRON PIPE | NOS | 16 | 850 | 13600 | 2448 | 16048 | 5 | 0 | 0 | 0 | 0 | 16 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 75MM DIA, 2.9/3 MTR CENTRIFUGAL CAST IRON PIPE | NOS | 62 | 850 | 52700 | 9486 | 62186 | 5 | 34 | 28900 | 5202 | 34102 | 28 | 28084 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 54.8387
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 8 SWG GI EARTH WIRE | RMT | 780 | 15 | 11700 | 2106 | 13806 | 5 | 0 | 0 | 0 | 0 | 780 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | INSTALLATION CHARGES FOR 250 KVA TRANSFORMER (NOS) | NOS | 2 | 2500 | 5000 | 900 | 5900 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | INSTALLATION CHARGES FOR 500 KVA TRANSFORMER (NOS) | NOS | 6 | 2500 | 15000 | 2700 | 17700 | 5 | 0 | 0 | 0 | 0 | 6 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | INSTALLATION CHARGES FOR EARTH TERMINAL STATION (NOS) | NOS | 19 | 100 | 1900 | 342 | 2242 | 5 | 0 | 0 | 0 | 0 | 19 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | 3 C x 185 SQMM ALU. ARMOURED XLPE HT CABLE TERMINATION | NOS | 24 | 2500 | 60000 | 10800 | 70800 | 5 | 24 | 60000 | 10800 | 70800 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3 C x 185 SQMM ALU. ARMOURED XLPE HT CABLE (RMT) | RMT | 205 | 90 | 18450 | 3321 | 21771 | 5 | 205 | 18450 | 3321 | 21771 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3.5C x 25 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 25 | 35 | 875 | 157.5 | 1032.5 | 5 | 0 | 0 | 0 | 0 | 25 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR M.S. STRUCTURAL WORK (KG) | KG | 614.05 | 25 | 15351.25 | 2763.22 | 18114.47 | 5 | 614.05 | 15351.25 | 2763.22 | 18114.47 | 0 | 0 | As per Site , Cable tray MS Support fabrication work JMR SR NO. 9xed Supply & Installation of cable tray 9.17 In Case of MS Fabricated supports from 35x35x5 mm MS Angle duly painted and fixed with Anchor fasteners on ceiling /wall JMR Quantity 2995 kg. So please revise existing Quantity in WO No. 392 Transcube Engineer Pvt Ltd. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 300 x 50/75 x 1.6 GI LADDER TYPE CABLE TRAY | RMT | 120 | 130 | 15600 | 2808 | 18408 | 5 | 120 | 15600 | 2808 | 18408 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 400 x 50/75 x 1.6 GI LADDER TYPE CABLE TRAY | RMT | 8 | 130 | 1040 | 187.2 | 1227.2 | 5 | 8 | 1040 | 187.2 | 1227.2 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 1C x 400 SQMM XLPE LT CABLE TERMINATION (NOS) | NOS | 250 | 490 | 122500 | 22050 | 144550 | 5 | 250 | 122500 | 22050 | 144550 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3 C x 185 SQMM ALU. ARMOURED XLPE HT CABLE (RMT) | RMT | 15 | 90 | 1350 | 243 | 1593 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 1 | 2500 | 2500 | 450 | 2950 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOR FOR MAIN DB (NOS) | NOS | 2 | 2500 | 5000 | 900 | 5900 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOUR FOR DB FITTING (NOS) | NOS | 3 | 1550 | 4650 | 837 | 5487 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 1 C x 400 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 5080 | 45 | 228600 | 41148 | 269748 | 5 | 5080 | 228600 | 41148 | 269748 | 0 | 0 | COMMON ELECTRIC CABLE WORK |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3 C x 185 SQMM ALU. ARMOURED XLPE HT CABLE (RMT) | RMT | 204 | 90 | 18360 | 3304.8 | 21664.8 | 5 | 204 | 18360 | 3304.8 | 21664.8 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3 C x 70 SQMM ALU. ARMOURED XLPE HT CABLE (RMT) | RMT | 14 | 70 | 980 | 176.4 | 1156.4 | 5 | 0 | 0 | 0 | 0 | 14 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 600 x 50/75 x 1.6 GI LADDER TYPE CABLE TRAY | RMT | 252 | 155 | 39060 | 7030.8 | 46090.8 | 5 | 235 | 36425 | 6556.5 | 42981.5 | 17 | 3109.3 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 93.254
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 200 x 50/75 x 1.6 GI LADDER TYPE CABLE TRAY | RMT | 155 | 120 | 18600 | 3348 | 21948 | 5 | 62.5 | 7500 | 1350 | 8850 | 92.5 | 13098 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 40.3226
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 300 x 50/75 x 1.6 GI LADDER TYPE CABLE TRAY | RMT | 25 | 130 | 3250 | 585 | 3835 | 5 | 25 | 3250 | 585 | 3835 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR LOAD BREAKE SWITCH (NOS) | NOS | 2 | 5500 | 11000 | 1980 | 12980 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR M.S. STRUCTURAL WORK (KG) | KG | 2380.95 | 25 | 59523.75 | 10714.28 | 70238.03 | 5 | 2380.95 | 59523.75 | 10714.28 | 70238.03 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR RMU (NOS) | NOS | 1 | 6500 | 6500 | 1170 | 7670 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 1C x 400 SQMM XLPE LT CABLE TERMINATION (NOS) | NOS | 10 | 490 | 4900 | 882 | 5782 | 5 | 10 | 4900 | 882 | 5782 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3.5Cx 120 SQMM XLPE LT CABLE TERMINATION (NOS) | NOS | 4 | 500 | 2000 | 360 | 2360 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3.5Cx 25 SQMM XLPE LT CABLE TERMINATION (NOS) | NOS | 6 | 370 | 2220 | 399.6 | 2619.6 | 5 | 0 | 0 | 0 | 0 | 6 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3C x 240 SQMM XLPE HT CABLE TERMINATION (NOS) | NOS | 28 | 2500 | 70000 | 12600 | 82600 | 5 | 4 | 10000 | 1800 | 11800 | 24 | 70800 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 14.2857
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3C x 70 SQMM XLPE HT CABLE TERMINATION (NOS) | NOS | 8 | 2000 | 16000 | 2880 | 18880 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 400 x 50/75 x 1.6 GI LADDER TYPE CABLE TRAY | RMT | 25 | 130 | 3250 | 585 | 3835 | 5 | 25 | 3250 | 585 | 3835 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3 C x 240 SQMM ALU. ARMOURED XLPE HT CABLE (RMT) | RMT | 440 | 90 | 39600 | 7128 | 46728 | 5 | 250 | 22500 | 4050 | 26550 | 190 | 20178 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3 C x 70 SQMM ALU. ARMOURED XLPE HT CABLE (RMT) | RMT | 216 | 70 | 15120 | 2721.6 | 17841.6 | 5 | 0 | 0 | 0 | 0 | 216 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3.5Cx 120 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 198 | 50 | 9900 | 1782 | 11682 | 5 | 0 | 0 | 0 | 0 | 198 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOR FOR 25MM PVC PIPE (MTR) | RMT | 470 | 15 | 7050 | 1269 | 8319 | 5 | 0 | 0 | 0 | 0 | 470 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 3.5C x 25 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 170 | 35 | 5950 | 1071 | 7021 | 5 | 0 | 0 | 0 | 0 | 170 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 1C x 300 SQMM XLPE LT CABLE TERMINATION (NOS) | NOS | 240 | 350 | 84000 | 15120 | 99120 | 5 | 0 | 0 | 0 | 0 | 240 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOR FOR 25X3MM COPPER FLAT (RMT) | RMT | 1560 | 35 | 54600 | 9828 | 64428 | 5 | 0 | 0 | 0 | 0 | 1560 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOR FOR DWC 180/150 MM DIA PIPE WITH COUPLER (RMT) | RMT | 435 | 20 | 8700 | 1566 | 10266 | 5 | 0 | 0 | 0 | 0 | 435 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOR FOR DWC 90/75 MM DIA PIPE WITH COUPLER (RMT) | RMT | 890 | 20 | 17800 | 3204 | 21004 | 5 | 700 | 14000 | 2520 | 16520 | 190 | 4484 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 78.6517
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | LABOR FOR EXCAVATION (CMT) | CMT | 369 | 90 | 33210 | 5977.8 | 39187.8 | 5 | 221 | 19890 | 3580.2 | 23470.2 | 148 | 15717.6 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 59.8916
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 1 C x 300 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 3670 | 36 | 132120 | 23781.6 | 155901.6 | 5 | 0 | 0 | 0 | 0 | 3670 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 392 | 0 | 28 Dec 2023 | TransCube Engineers Pvt Ltd | INFRA ELECTRIC WORK | CHARGES FOR 1 C x 400 SQMM ALU. ARMOURED XLPE LT CABLE (RMT) | RMT | 132 | 45 | 5940 | 1069.2 | 7009.2 | 5 | 132 | 5940 | 1069.2 | 7009.2 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100