## Project_Work_Order6386771512219
Project Work Order
From 20 Oct 2011 To 21 Nov 2024
Page 1 of 1
Total Records: 13 Records 1 To 13
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | DEPART LABOR | NOS | 200 | 350 | 70000 | 12600 | 82600 | 5 | 200 | 70000 | 12600 | 82600 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR 9" MASONRY WORK (SQFT) | SQFT | 25000 | 18 | 450000 | 81000 | 531000 | 5 | 10666.27 | 191992.86 | 34558.74 | 226551.6 | 14333.73 | 304448.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 42.6651
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR BEAM & COLUMN CASTING (RFT) | RFT | 10000 | 120 | 1200000 | 216000 | 1416000 | 5 | 5221 | 626520 | 112773.6 | 739293.6 | 4779 | 676706.4 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 52.21
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR DESIGN WALL PLASTER (SQFT) | SQFT | 20000 | 25 | 500000 | 90000 | 590000 | 5 | 14230.95 | 355773.75 | 64039.28 | 419813.03 | 5769.05 | 170186.97 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 71.1548
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR PCC (SQFT) | SQFT | 6000 | 10 | 60000 | 10800 | 70800 | 5 | 3606.02 | 36060.2 | 6490.84 | 42551.04 | 2393.98 | 28248.96 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 60.1003
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR RCC COPING (RFT) | RFT | 5000 | 50 | 250000 | 45000 | 295000 | 5 | 1802.04 | 90102 | 16218.38 | 106320.38 | 3197.96 | 188679.62 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 36.0408
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOUR FOR RCC FOOTING (CFT) | CFT | 3500 | 130 | 455000 | 81900 | 536900 | 5 | 1151.5 | 149695 | 26945.1 | 176640.1 | 2348.5 | 360259.9 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 32.9
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR SINGLE COAT PLASTER WORK (SQFT) | SQFT | 10017.9944 | 15 | 150269.92 | 27048.58 | 177318.5 | 5 | 10017.9944 | 150269.92 | 27048.58 | 177318.5 | 0 | 0 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOUR FOR BREAKER (DAY) | DAY | 54 | 1200 | 64800 | 11664 | 76464 | 5 | 14 | 16800 | 3024 | 19824 | 40 | 56640 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 25.9259
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOUR FOR DRESSING WORK (SQFT) | SQFT | 5000 | 5 | 25000 | 4500 | 29500 | 5 | 3526.25 | 17631.25 | 3173.64 | 20804.89 | 1473.75 | 8695.11 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 70.525
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | DEPART LABOR |  | 200 | 350 | 70000 | 12600 | 82600 | 5 | 200 | 70000 | 8694 | 78694 | 0 | 3906 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | Pur.nrpl3 | 03 Apr 2024 | 100
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL CIVIL WORK | LABOR FOR 4.5" MASONRY WORK (SQFT) | SQFT | 10000 | 18 | 180000 | 32400 | 212400 | 5 | 2142.6 | 38566.8 | 6942.02 | 45508.82 | 7857.4 | 166891.18 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | Pur.nrpl3 | 03 Apr 2024 | 32.936
GREENWOODS SERENITY | 158 | 0 | 22 Sep 2023 | MANGLAM CONSTRUCTIONS | INFRA COMPOUND WALL PLASTER WORK | LABOR FOR SINGLE COAT PLASTER WORK (SQFT) | SQFT | 20000 | 15 | 300000 | 54000 | 354000 | 5 | 8067.1356 | 121007.03 | 21781.26 | 142788.29 | 11932.8644 | 211211.71 |  |  | T.Joshi | Pur.nrpl3 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 40.3357