## Project_Work_Order6386865604372
Project Work Order
From 11 Nov 2020 To 02 Dec 2024
Page 1 of 1
Total Records: 35 Records 1 To 35
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1002 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 1890 | 36890 | 0 | 4410 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 902 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 702 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 6300 | 41300 | 0 | 0 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 802 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 602 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 502 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 402 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 501 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 901 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1001 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 6300 | 41300 | 0 | 0 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 801 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 701 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 11 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 601 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 0 | 35000 | 5 | 1 | 35000 | 0 | 35000 | 0 | 0 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 12 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 401 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 0 | 35000 | 5 | 1 | 35000 | 0 | 35000 | 0 | 0 | Labour Name in Kanix : LABOR FOR SUNK FILLING WITH SCREEDING \nFloring work \nPurpose of Work : Toilet & Flower bed Sunk filling work with top Screeding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 12 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 302 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 0 | 35000 | 5 | 1 | 35000 | 0 | 35000 | 0 | 0 | Purpose of Work : Toilet & Flower bed Sunk filling work with top Scree ding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 12 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 201 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 0 | 35000 | 5 | 1 | 35000 | 0 | 35000 | 0 | 0 | Purpose of Work : Toilet & Flower bed Sunk filling work with top Scree ding |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 12 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1602 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 | Please generate a work order for LABOR FOR SUNK FILLING WITH SCREED. Site :- Aspire Agency :- Manglam Construction Labour Name in Kanix :- LABOR FOR SUNK FILLING WITH SCREEDING Tower & Floor :- A (1101,1102,1201,1202,1301,1302,1401,1402,1501,1502,1601,1602,1701,1702) Rate (Basic rate):- 35000/- PER APARTMENT. Unit of Measurement :- NOS (PER APARTMENT) Purpose of Work :- Toilet & Flower bed Sunk filling work with top Screeding. New Work order / Revision :- 163 |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1502 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1402 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 0.4 | 14000 | 2520 | 16520 | 0.6 | 24780 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 40
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1302 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1102 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1202 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 3465 | 38465 | 0 | 2835 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1601 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1501 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1401 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 1890 | 36890 | 0 | 4410 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1301 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1201 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1101 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1702 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 0.4 | 14000 | 2520 | 16520 | 0.6 | 24780 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 40
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1701 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 1575 | 36575 | 0 | 4725 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 03 Oct 2023 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1801 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 6300 | 41300 | 0 | 0 | Unit of Measurement :- NOS. Purpose of Work :- Penthouse Sunk Filling Work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 28 Feb 2024 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1802 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 1 | 35000 | 6300 | 41300 | 0 | 0 | Unit of Measurement :- NOS. Purpose of Work :- Penthouse Sunk Filling Work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 28 Feb 2024 | 100
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1901 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Unit of Measurement :- NOS. Purpose of Work :- Penthouse Sunk Filling Work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 28 Feb 2024 | 0
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | A 1902 FLOORING & DEDO WORK | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 1 | 35000 | 35000 | 6300 | 41300 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | Unit of Measurement :- NOS. Purpose of Work :- Penthouse Sunk Filling Work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | pur.nrpl2 | 28 Feb 2024 | 0
GREENWOOD ASPIRE EXP | 163 | 0 | 30 Apr 2022 | MANGLAM CONSTRUCTIONS | TOWER A TERRACE COMMON FLOORING & DEDO | LABOR FOR SUNK FILLING WITH SCREED (NOS) | NOS | 2 | 35000 | 70000 | 12600 | 82600 | 5 | 0.7714 | 26999 | 4859.82 | 31858.82 | 1.2286 | 50741.18 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Consultancy |  |  |  | Approved | T.Joshi |  | 38.57