## RABillBrowse_Contwise6385951271
Contractor RA Bill
ANTICA GREENWOOD
Page 1 of 1
Total Records: 9 Records 1 To 9
Contractor | WO NO | RA Bill | RA Bill Date | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | DEPART LABOR | INFRA CIVIL EXTRA WORK | 0 | 5 | NOS | 500 | 100% Completion | 100 | 125 | 3860.53 | 2500 | C + SGST 18% I/P URD | 0 | 2500 | 2375 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOR FOR 9" MASONRY WORK (SQFT) | INFRA CIVIL EXTRA WORK | 0 | 671.48 | SQFT | 18 | 100% Completion | 100 | 604.332 | 3860.53 | 12086.64 | C + SGST 18% I/P URD | 0 | 12086.64 | 11482.308 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOR FOR BEAM & COLUMN CASTING (RFT) | INFRA CIVIL EXTRA WORK | 0 | 181 | RFT | 120 | 100% Completion | 100 | 1086 | 3860.53 | 21720 | C + SGST 18% I/P URD | 0 | 21720 | 20634 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOR FOR EXCAVATION (CFT) | INFRA CIVIL EXTRA WORK | 0 | 736 | CFT | 12 | 100% Completion | 100 | 441.6 | 3860.53 | 8832 | C + SGST 18% I/P URD | 0 | 8832 | 8390.4 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOR FOR PCC (SQFT) | INFRA CIVIL EXTRA WORK | 0 | 276 | SQFT | 10 | 100% Completion | 100 | 138 | 3860.53 | 2760 | C + SGST 18% I/P URD | 0 | 2760 | 2622 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOR FOR RCC COPING (RFT) | INFRA CIVIL EXTRA WORK | 0 | 194 | RFT | 50 | 100% Completion | 100 | 485 | 3860.53 | 9700 | C + SGST 18% I/P URD | 0 | 9700 | 9215 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOR FOR SINGLE COAT PLASTER WORK (SQFT) | INFRA CIVIL EXTRA WORK | 0 | 801 | SQFT | 17 | 100% Completion | 100 | 680.85 | 3860.53 | 13617 | C + SGST 18% I/P URD | 0 | 13617 | 12936.15 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | DEPART MASON | INFRA CIVIL EXTRA WORK | 0 | 5 | NOS | 800 | 100% Completion | 100 | 200 | 3860.53 | 4000 | C + SGST 18% I/P URD | 0 | 4000 | 3800 | Approved
DEVANGBHAI H BHARVAD | 260 | 614 | 2024-03-10 | ANTICA GREENWOOD | LABOUR FOR DRESSING WORK (SQFT) | INFRA CIVIL EXTRA WORK | 0 | 399 | SQFT | 5 | 100% Completion | 100 | 99.75 | 3860.53 | 1995 | C + SGST 18% I/P URD | 0 | 1995 | 1895.25 | Approved